## Sheet1
Name | ID | Description | Requestor | Manager | Type | Program | Program Name | Sub Portfolio | Manager Used for Reporting | Tag | W | IT Project Manager | Project Manager (not IT or Eng) | Initiative Owner | IT Business Partner | ITLT Responsible | Executive Sponsor | Type of Project | Accountable Workstream | Interdependencies | WAVE Stage | WAVE Status | WAVE # | L | Dashboard Link | Finance Dashboard Link | Overall % Complete | Start Date | Finish Date | Duration PRT | High Level Status | Accomplishments | Upcoming | Support Needed | PM Assessed Health | Status Trend | Overall Health | Project Plan Health | Schedule Health | Risk Health | Quality Health | Budget Health | Open Risks | Open Issues | Red | Yellow | Green | Blue | Past Due | Start Delay | Incomplete Data | Unassigned | Total Tasks | Pending Tasks | Not Started | In Progress | Overall total budget | Total budget CapEx | Total Budget OpEx | Total actuals | Total CapEx actuals | Total OpEx actuals | Total Addback actuals | Total forecast | Total CapEx forecast | Total OpEx forecast | Total Addback forecast | Total EAC | CapEx EAC | OpEx EAC | Addback EAC | Total Budget vs EAC | CapEx Budget vs EAC | OpEx Budget vs EAC | Total Budget vs EAC variance | CapEx Budget vs EAC variance | OpEx Budget vs EAC variance | Last Financials Update | Baseline Start | Baseline Finish | Variance From Baseline | Baseline Duration | Last Plan Update | Last Status Update | Project Support Needed | Total Open RAID | RAID Support Needed | Change Support Needed | L/L Risk | L/M Risk | L/H Risk | M/L Risk | M/M Risk | M/H Risk | H/L Risk | H/M Risk | H/H Risk | L/L Issue | L/M Issue | L/H Issue | M/L Issue | M/M Issue | M/H Issue | H/L Issue | H/M Issue | H/H Issue | EUR | EUR Overall total budget | EUR Total budget CapEx | EUR Total Budget OpEx | EUR Total actuals | EUR Total CapEx actuals | EUR Total OpEx actuals | EUR Total Addback actuals | EUR Total forecast | EUR Total CapEx forecast | EUR Total OpEx forecast | EUR Total Addback forecast | EUR Total EAC | EUR CapEx EAC | EUR OpEx EAC | EUR Addback EAC | EUR Total Budget vs EAC | EUR CapEx Budget vs EAC | EUR OpEx Budget vs EAC | EUR Total Budget vs EAC variance | EUR CapEx Budget vs EAC variance | EUR OpEx Budget vs EAC variance | Extra | Status | Currency | PMO Selection | Product Category | Project Type | Region | Phase | Strategic Alignment | Primary Benefit | Status (Last Week) | Approval Status | Portfolio | 5 Yr Rev Impact | 5 Yr Cost Savings | Project Duration | Payback Period | Estimated Project Expense | Benefit Description | Benefit Quantification | Benefit Realization Timing | Benefit Manager | Net recurring benefits | One-time benefits | Implementation costs | L3 latest estimated date | L4 latest estimated date | Planning summary | NDA | Wave # Assigned | Smartsheet Status | Elapsed | Plan Update Aging | Status Update Aging | % Red | % Yellow | % Green | % Blue | % Incomplete | % Complete | Year | Project In Intake | Display order | Override Auto-ID | Custom ID | Missing Information | Type Helper | Project Number | Provisioned | Move to Intake | Ready for Intake | Needs Update | Business Project Manager | B | PMO Start Date | PMO Finish Date | PMO Project Interdependencies | PMO Gate 0 Date | PMO Gate 1 Date | PMO Gate 2 Date | PMO Gate 3 Date | PMO Gate IT Launch Date | PMO Gate 4 Date | PMO Gate 5 Date | PMO Duration | PMO Start Variance | Start Variance % | PMO Finish Variance | Finish Variance % | PMO Duration Variance | Duration Variance % | Actual Gate 0 Date | Actual Gate 1 Date | Actual Gate 2 Date | Actual Gate 3 Date | Actual IT Launch Date | Actual Gate 4 Date | Actual Gate 5 Date | Original Gate 0 Date | Original Gate 1 Date | Original Gate 2 Date | Original Gate 3 Date | Original IT Launch Date | Original Gate 4 Date | Original Gate 5 Date | Gate 1 Variance | Gate 2 Variance | Gate 3 Variance | Gate 4 Variance | Gate 5 Variance | Gate 1 % Variance | Gate 2 % Variance | Gate 3 % Variance | Gate 4 % Variance | Gate 5 % Variance | E | Budget | Delivery Organization | Work Type | Strategic Goal | Project Score | Priority | Project Interdependencies | WorkApp Link | Scope | Approval Status Update Date | One-time benefits | Created Date | Created in Current Week | Phase | In JELD-WEN Intake | Functional Evaluators | Prioritization Score | col 1 | col 2 | Send to approver | Start Date_to_Interdependencies_days | budget_variance_absolute | budget_variance_pct | pct_complete_normalized
site services model consolidated | 23229 | implementation of field service module of salesforce. campgemini are implementation partners. us and can teams are impacted. | garrett farmer | garrett farmer | project | standalone project | standalone project | bus-na/corp/it | jorge eleta | it na it na/corporate | not specified | garrett farmer | not specified | brad nelson | sheri schrier | mike schipper | not specified | manufacturing | na - ops: customer service | hr; it; legal | l5 (realised) | on track | 23229.0 | not specified | project dashboard | financial dashboard | 1.0 | 2024-02-12 | 2024-08-29 | 144d | project system integrator has rolled off as of yesterday. the support team has performed the handoff and own support moving forward. all new issues/defects will follow normal ams support process. business kpi evaluations and calculations are underway. | completion of all defects in go-live tracker. | kpi details to be provided to team. | not specified | blue | on track | green | blue | green | green | green | green | 0 | 0 | 0.0 | 0.0 | 0.0 | 113.0 | 0.0 | 0.0 | 0.0 | 0.0 | 113.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | 69291.0 | 15755.0 | 53536.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 69291.0 | 15755.0 | 53536.0 | not specified | -69291.0 | -15755.0 | -53536.0 | 0.0 | 0.0 | 0 | 2024-09-16 | 2024-02-12 | 2024-08-29 | -2d | 144d | 2024-09-04 | 2025-09-18 | not specified | 1 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | completed | not specified | it | not specified | not specified | not specified | realize value / close / care period | not specified | not specified | on track | pending archive | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 2.026 | not specified | 0.038003 | 2023-12-10 | 2024-03-07 | on plan | not specified | not specified | on track | 1.0 | 420.0 | 41.0 | 0.0 | 0.0 | 0.0 | 1.0 | 0.0 | 1.0 | previous year | not specified | 3 | not specified | not specified | 1.0 | p | 2 | not specified | 1.0 | 1.0 | not specified | not specified | not specified | 2024-01-02 | 2024-08-30 | 1847.0 | not specified | 2024-01-09 | 2024-02-09 | 2024-03-07 |  | 2024-04-18 | 2024-06-27 | 174d | -41.0 | -0.235632183908046 | 1.0 | 0.00574712643678161 | 30.0 | 0.172413793103448 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified | 2024-10-02 | not specified | not specified | false | stage 5 - care period | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 1
na titan standard cost | 13069 | implement standard cost model and create financial transaction for all inventory movements (shipments, purchases, inventory adjustments, scrap, returns, etc.) in all titan na plants. we are unable to optimize our profitability because titan lacks the transactional detail required to analyze our costs. adding standard cost accounting will improve data-driven decision making at the plant level, leading to improving profitability. approved and in the works, will provide better visibility to costs for improved decision making. eligible for titan systems, which covers 70% of global sales. | cyndi maples | cyndi maples | project | standalone project | standalone project | bus-na/corp/it | jorge eleta | it na/corporate | not specified | cyndi maples | florence kennedy ward | florence kennedy ward | mike crawford (r2r) | kirk kroft | not specified | other | support functions: finance | it | l3 (planned) | on hold | 13069.0 | not specified | project dashboard | finance dashboard | 0.46 | 2022-09-21 | 2027-10-28 | 1332d | pilot uat complete. basware regression complete. formal pilot uat approvals from initiative owner, business team and basware team. project team planning for parallel testing production migration complete. parallel production testing in progress, start 3/10/2025. | not specified | continue parallel production testing | not specified | green | on track | red | green | green | red | green | green | 7 | 5 | 0.0 | 0.0 | 40.0 | 104.0 | 33.0 | 33.0 | 0.0 | 0.0 | 144.0 | 40.0 | 39.0 | 1.0 | 1443404.78 | 742058.84 | 701345.94 | 651715.07 | 439265.74 | 212449.33 | not specified | 494150.0 | 233775.0 | 260375.0 | not specified | 1145865.07 | 673040.74 | 472824.33 | not specified | 297539.71 | 69018.1 | 228521.61 | 0.206137401041446 | 0.0930089317445501 | 0.325832940588492 | 2025-10-27 | 2022-09-21 | 2027-10-28 | 0 | 1332d | 2025-03-12 | 2025-09-18 | not specified | 16 | 1.0 | not specified | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 4.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | canceled | not specified | it | not specified | not specified | not specified | implementation / execution | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 2.926682 | not specified | 1.35154313 | 2024-05-30 |  | due soon for l2 | not specified | not specified | portfolio | 0.608858858858859 | 231.0 | 41.0 | 0.0 | 0.0 | 0.277777777777778 | 0.722222222222222 | 0.0 | 1.0 | 2027 | not specified | 3 | not specified | not specified | 1.0 | p | 6 | 1.0 | 1.0 | not specified | not specified | not specified | not specified | 2024-02-02 | 2024-07-31 | not specified | not specified | [6 empty] | 129d | 499.0 | 3.86821705426357 | -1184.0 | -9.17829457364341 | -1203.0 | -9.32558139534884 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | stage 3 - implementation | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.46
pricing program development | pg-0011 | not specified | jessi beamer | amy phillips | program | pg-0011 | pg-0011: pricing program development | bus-na/corp/it | amanda jones | not specified | not specified | amy phillips | not specified | not specified | not specified | tyce deal | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | program dashboard | finance dashboard | 0.412374491180461 | 2023-09-27 | 2026-10-30 | 808d | add the high level status of the program in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | on track | red | red | red | red | yellow | red | 0 | 1 | 28.0 | 52.0 | 6.0 | 12.0 | 29.0 | 23.0 | 55.0 | 54.0 | 98.0 | 86.0 | 67.0 | 19.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 |  | 2024-02-01 | 2024-07-29 | 0 | 128d | 2025-09-18 | 2025-10-29 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | active | not specified | it | not specified | not specified | not specified | see project details | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.675742574257426 | 41.0 | 0.0 | 0.285714285714286 | 0.530612244897959 | 0.0612244897959184 | 0.122448979591837 | 0.561224489795918 | 0.438775510204082 | 2026 | not specified | 2 | not specified | not specified | not specified | pg | 11 | not specified | not specified | not specified | not specified | not specified | not specified | 2023-09-27 | 2026-10-30 | not specified | not specified | [6 empty] | 808d | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.41237
doors pricing simplification | 22676 | not specified | jessi beamer | amy phillips | project | pg-0011 | pg-0011: pricing program development | bus-na/corp/it | amanda jones | na it | not specified | amy phillips | not specified | harmony lee | jon gies | tyce deal | not specified | pricing | na - doors & dist: commercial - product & pricing | it | l5 (realised) | on track | 22676.0 | not specified | project dashboard | financial dashboard | 0.44 | 2023-09-27 | 2026-04-30 | 677d | it portion of project on hold until nov 2024. pricing team is working on their process and price refresh | pricing team: roll out to cohort 1 complete | pricing team: roll out to cohort 2 & 3 pricing platform anticipated start nov 2024 | not specified | green | on track | red | red | red | red | green | red | 0 | 0 | 5.0 | 1.0 | 4.0 | 5.0 | 6.0 | 7.0 | 0.0 | 0.0 | 15.0 | 10.0 | 9.0 | 1.0 | 4700000.0 | 2000000.0 | 2700000.0 | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 4700000.0 | 2000000.0 | 2700000.0 | 1.0 | 1.0 | 1 | 2025-10-27 | 2024-02-01 | 2024-07-29 | -458d | 128d | 2025-02-20 | 2024-11-05 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | active | not specified | it | not specified | not specified | not specified | realize value / close / care period | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 22.184 | 0.0 | 5.06616 | 2023-10-20 | 2024-04-06 | on plan | not specified | not specified | on track | 0.806499261447563 | 251.0 | 358.0 | 0.333333333333333 | 0.0666666666666667 | 0.266666666666667 | 0.333333333333333 | 0.0 | 1.0 | 2026 | not specified | 3 | not specified | not specified | 1.0 | p | 8 | not specified | 1.0 | 1.0 | not specified | not specified | not specified | 2023-09-27 | 2026-01-06 | not specified | not specified | [6 empty] | 595d | 0.0 | 0.0 | -114.0 | -0.191596638655462 | -82.0 | -0.13781512605042 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | stage 5 - care period | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.44
windows pricing program refresh | 22677 | not specified | jessi beamer | amy phillips | project | pg-0011 | pg-0011: pricing program development | bus-na/corp/it | amanda jones | na it | not specified | amy phillips | not specified | harmony lee | jon gies | tyce deal | not specified | pricing | na - windows: commercial - product & pricing | it | l5 (realised) | on track | 22677.0 | not specified | project dashboard | financial dashboard | 0.94 | 2023-10-17 | 2026-01-01 | 578d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | not specified | decision on go-no go for customer tiering / cohorts - need from john m. | yellow | on track | red | yellow | red | red | yellow | red | 0 | 1 | 4.0 | 46.0 | 1.0 | 5.0 | 4.0 | 4.0 | 51.0 | 51.0 | 56.0 | 51.0 | 45.0 | 6.0 | 4978000.0 | 3252000.0 | 1726000.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 4978000.0 | 3252000.0 | 1726000.0 | 1.0 | 1.0 | 1 | 2025-10-27 | 2024-02-01 | 2024-07-29 | -372d | 128d | 2025-02-20 | 2024-11-05 | true | 3 | 1.0 | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | active | not specified | it | not specified | not specified | not specified | realize value / close / care period | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 19.12 | not specified | 4.297 | 2023-10-20 | 2024-02-20 | on plan | not specified | not specified | on track | 0.920415224913495 | 251.0 | 358.0 | 0.0714285714285714 | 0.821428571428571 | 0.0178571428571429 | 0.0892857142857143 | 0.910714285714286 | 0.089285714285714 | 2026 | not specified | 3 | not specified | not specified | 1.0 | p | 9 | not specified | 1.0 | not specified | not specified | not specified | not specified | 2023-10-17 | 2026-01-01 | not specified | not specified | [6 empty] | 578d | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | stage 5 - care period | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.94
distribution pricing restructuring | 22678 | not specified | jessi beamer | amy phillips | project | pg-0011 | pg-0011: pricing program development | bus-na/corp/it | amanda jones | na it | not specified | amy phillips | not specified | not specified | jon gies | tyce deal | not specified | not specified | not specified | not specified | not specified | on track | 22678.0 | not specified | project dashboard | financial dashboard | 0.36 | 2023-10-01 | 2024-07-01 | 196d | project cancelled in wave | cancelled on 4.22.25 by charlie drain after a discussion with brent | not specified | not specified | on track | on track | red | red | green | green | yellow | green | 0 | 0 | 16.0 | 4.0 | 0.0 | 2.0 | 16.0 | 7.0 | 4.0 | 3.0 | 22.0 | 20.0 | 8.0 | 12.0 | 2963000.0 | 1613000.0 | 1350000.0 | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 2025-10-27 | 2024-02-01 | 2024-07-29 | 20d | 128d | 2024-08-26 | 2025-05-20 | not specified | 1 | 1.0 | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | canceled | not specified | it | not specified | not specified | not specified | realize value / close / care period | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 17.92 | not specified | 4.077 | 2023-10-20 | 2024-02-20 | on plan | not specified | not specified | on track | 1.0 | 429.0 | 162.0 | 0.727272727272727 | 0.181818181818182 | 0.0 | 0.0909090909090909 | 0.181818181818182 | 0.818181818181818 | previous year | not specified | 3 | not specified | not specified | 1.0 | p | 10 | not specified | 1.0 | not specified | not specified | not specified | not specified | 2023-10-01 | 2024-07-01 | not specified | not specified | [6 empty] | 196d | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | stage 5 - care period | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.36
pricing platform implementation | p-0012 | not specified | jessi beamer | amy phillips | project | pg-0011 | pg-0011: pricing program development | bus-na/corp/it | amanda jones | not specified | not specified | amy phillips | not specified | not specified | terry davis | tyce deal | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | financial dashboard | 0.0 | 2023-12-04 | 2026-10-30 | 760d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | on track | red | red | red | green | green | green | 0 | 0 | 3.0 | 1.0 | 1.0 | 0.0 | 3.0 | 5.0 | 0.0 | 0.0 | 5.0 | 5.0 | 5.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2024-02-01 | 2024-07-29 | -589d | 128d | 2025-09-18 | 2024-11-05 | true | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | active | not specified | it | not specified | not specified | not specified | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.655263157894737 | 41.0 | 358.0 | 0.6 | 0.2 | 0.2 | 0.0 | 0.0 | 1.0 | 2026 | not specified | 3 | not specified | not specified | 1.0 | p | 12 | not specified | not specified | not specified | not specified | not specified | not specified | 2023-12-04 | 2026-10-30 | not specified | not specified | [6 empty] | 760d | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0
source-to-pay (s2p) phase 2 (indirect procurement) | 23231 | implementation of an end-to-end, comprehensive solution that will, enable improved indirect sourcing and supplier management capability and effiency, reduce maverick spend and provide greater visibility to indirect spending. | tamara johnson | tamara johnson | project | standalone project | standalone project | bus-na/corp/it | amanda jones | it mfg. & supply chain na it na/corporate | not specified | tamara johnson | rachael gabbard | andrea schnieders | christian suarez | kirk kroft | not specified | sourcing | na - ops sourcing | it | l4 (executed) | on track | 23231.0 | not specified | project dashboard | financial dashboard | 0.76 | 2024-05-01 | 2026-09-30 | 631d | lacantina go live postponed to align with cfin go live q1 2026 | not specified | go live of lacantina | no support needed | green | on track | red | green | red | green | green | green | 1 | 0 | 1.0 | 0.0 | 3.0 | 60.0 | 1.0 | 2.0 | 0.0 | 0.0 | 64.0 | 4.0 | 3.0 | 1.0 | 6200000.0 | 2500000.0 | 3700000.0 | 4843840.5 | 2216137.0 | 2627703.5 | 686922.0 | 1047340.0 | 0.0 | 1047340.0 | 0.0 | 5891180.5 | 2216137.0 | 3675043.5 | 686922.0 | 308819.5 | 283863.0 | 24956.5 | 0.0498095967741936 | 0.1135452 | 0.006745 | 2025-10-27 | 2024-05-01 | 2025-11-06 | -235d | 397d | 2025-10-28 | 2025-10-27 | not specified | 3 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | active | not specified | it | not specified | not specified | not specified | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 10.52262345 | not specified | 5.285744 | 2023-12-10 | 2024-01-10 | on plan | not specified | 1.0 | on track | 0.619651347068146 | 1.0 | 2.0 | 0.015625 | 0.0 | 0.046875 | 0.9375 | 0.0 | 1.0 | 2026 | not specified | 3 | not specified | not specified | not specified | p | 13 | 1.0 | 1.0 | 1.0 | not specified | not specified | not specified | 2024-02-02 | 2025-07-10 | not specified | not specified | [6 empty] | 375d | -89.0 | -0.237333333333333 | -447.0 | -1.192 | -256.0 | -0.682666666666667 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.76
managed printer/copier support | 32878 | not specified | jamal mebane | jamal mebane | project | standalone project | standalone project | it-infra/service | jorge eleta | not specified | not specified | jamal mebane | not specified | gordon greenland | mike schipper | m.j. vaidya | not specified | sg&a | support functions: global it - infrastructure / service desk | it | l5 (realised) | on track | 32878.0 | not specified | project dashboard | financial dashboard | 0.46 | 2023-09-15 | 2024-12-30 | 337d | all work complete | all work complete | prep for project closeout | not specified | green | on track | red | green | red | green | yellow | red | 0 | 0 | 5.0 | 0.0 | 0.0 | 30.0 | 5.0 | 5.0 | 2.0 | 2.0 | 35.0 | 5.0 | 5.0 | 0.0 | 30000.0 | 0.0 | 30000.0 | 43616.0 | 0.0 | 43616.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 43616.0 | 0.0 | 43616.0 | not specified | -13616.0 | 0.0 | -13616.0 | -0.453866666666667 | 0.0 | -0.453866666666667 | 2025-10-27 |  |  | 0 | 0 | 2025-03-10 | 2025-03-10 | not specified | 1 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | active | not specified | it | not specified | not specified | not specified | realize value / close / care period | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0.0 | not specified | 0.0 | 2023-10-16 | 2024-06-24 | on plan | not specified | 1.0 | on track | 1.0 | 233.0 | 233.0 | 0.142857142857143 | 0.0 | 0.0 | 0.857142857142857 | 0.0571428571428571 | 0.942857142857143 | previous year | not specified | 3 | not specified | not specified | 1.0 | p | 14 | not specified | 1.0 | 1.0 | not specified | not specified | not specified | 2024-02-02 | 2024-07-31 | not specified | not specified | [6 empty] | 129d | 140.0 | 1.08527131782946 | -152.0 | -1.17829457364341 | -208.0 | -1.61240310077519 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | stage 5 - care period | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.46
critical event management: mass notifications phase i | 16298 | not specified | meridith fix | meridith fix | project | standalone project | standalone project | bus-na/corp/it | amanda jones, jorge eleta | it na/corporate | not specified | meridith fix | jeff benson | rocco procopio | mike crawford (r2r) | m.j. vaidya | not specified | other | support functions: eh&s | hr; legal; it | l3 (planned) | on track | 16298.0 | not specified | project dashboard | financial dashboard | 0.92 | 2024-03-04 | 2025-09-05 | 395d | on hold | on hold | on hold | on hold | yellow | sideways | yellow | green | yellow | green | green | green | 0 | 0 | 5.0 | 1.0 | 6.0 | 89.0 | 12.0 | 10.0 | 0.0 | 0.0 | 101.0 | 12.0 | 10.0 | 2.0 | 723249.0 | 53560.0 | 669689.0 | 405363.333333334 | 36367.5 | 368995.833333334 | 0.0 | 23119.6666666667 | 0.0 | 23119.6666666667 | 0.0 | 428483.000000001 | 36367.5 | 392115.500000001 | 0.0 | 294765.999999999 | 17192.5 | 277573.499999999 | 0.407558116222766 | 0.320995145631068 | 0.414481199482146 | 2025-10-28 | 2024-03-04 | 2025-07-31 | -26d | 369d | 2025-07-10 | 2025-09-18 | not specified | 1 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on-hold | not specified | it | not specified | not specified | global | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | -0.179 | not specified | 0.1346 | 2024-12-03 | 2024-06-15 | past due for l3 | not specified | 1.0 | on track | 1.0 | 111.0 | 41.0 | 0.0495049504950495 | 0.0099009900990099 | 0.0594059405940594 | 0.881188118811881 | 0.0 | 1.0 | current year | n | 3 | not specified | not specified | 1.0 | p | 15 | not specified | 1.0 | not specified | not specified | not specified | not specified | 2024-03-04 | 2024-12-13 | not specified | not specified | [6 empty] | 205d | 0.0 | 0.0 | -266.0 | -1.29756097560976 | -190.0 | -0.926829268292683 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.92
uk exterior door | 13203 | not specified | abasic@jeldwen.com | amer basic | project | standalone project | standalone project | not specified | not specified | not specified | not specified | amer basic | thomas howard | tony pell | adam painter | rachael horton-farmer | not specified | growth | uk: commercial | it; engineering; hr; legal | l3 (planned) | on hold | 13203.0 | not specified | project dashboard | financial dashboard | 0.15 | 2024-04-01 | 2024-11-08 | 160d | w38: project confirmed cancelled by io. it will be moved to cancelled projects in smartsheet | not specified | not specified | not specified | blue | on track | red | red | red | red | yellow | red | 4 | 0 | 23.0 | 28.0 | 0.0 | 11.0 | 35.0 | 29.0 | 16.0 | 1.0 | 62.0 | 51.0 | 45.0 | 6.0 | 729500.0 | 376000.0 | 353500.0 | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 729500.0 | 376000.0 | 353500.0 | 1.0 | 1.0 | 1 | 2025-02-25 | 2024-02-02 | 2024-07-31 | -72d | 129d | 2024-09-30 | 2024-11-01 | not specified | 24 | not specified | not specified | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | canceled | not specified | it | not specified | not specified | eu | implementation / execution | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 1.2987315 | not specified | 3.124 | 2023-10-17 | 2025-10-03 | on plan | not specified | 1.0 | on track | 1.0 | 394.0 | 362.0 | 0.370967741935484 | 0.451612903225806 | 0.0 | 0.17741935483871 | 0.258064516129032 | 0.741935483870968 | previous year | n | 3 | not specified | not specified | 1.0 | p | 18 | not specified | 1.0 | 1.0 | not specified | not specified | not specified | 2024-04-01 | 2025-12-09 | not specified | not specified | [6 empty] | 442d | 0.0 | 0.0 | 396.0 | 0.895927601809955 | 282.0 | 0.638009049773756 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | stage 3 - implementation | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.15
espresso glass & slab | 32435 | “inspired door design for every budget” a product line of fiberglass doors that combine true-to-life wood graining with enhanced security features, fire resistance, and a more sustainable manufacturing model to create an upscale fiberglass entry door without the luxury price tag. | jim copeland | jim copeland | project | standalone project | standalone project | eng-it | amanda jones | automation na it | not specified | not specified | jim copeland | matt goodman | not specified | not specified | jennifer matson | npi / npd | na - doors & dist: commercial - product & pricing | hr; legal; engineering | l3 (planned) | on track | 32435.0 | not specified | project dashboard | financial dashboard | 0.46 | 2022-03-09 | 2026-11-04 | 1216d | key focus areas: 1.0 • staining process improvement: follow up with ken and mike to finalize and implement a solution for improving the staining process to better bring out the graining in grinnell. (@ken hull, @mike lotko) • thd samples 1.5 • die redundancy and enhancement: initiate the process to get a second die made for the two panel arch top, ensuring redundancy and more pronounced graining for finishing. (@ken hull, @mike lotko) • traditional channel die change process: establish a working team and develop a plan to shorten the die changeover time for supporting seven skus in the traditional channel, moving from shifts to minutes. (@jim copeland, @mike lotko adam, justin) • assessment of dies: assess the dies produced for acceptability, decide on replacement for any cracked dies, and initiate the supply chain process for ordering replacements if needed. (@mike lotko @ken hull) • glazed units die timeline: follow up with larry after tomorrow’s meeting to obtain and communicate a timeline for the die required to confirm the glazed unit design. (@mike lotko) • design lock for glazed business focus • market pricing research: complete research with sales and marketing to establish market pricing for the traditional channel and communicate findings to the team. (@matt goodman) • base coat application costing: determine the cost and margin impact of applying a base coat to all doors before entering the traditional channel and decide on the number of colors to offer. (paul, ken, matt) | key focus areas: 1.0 • staining process improvement: follow up with ken and mike to finalize and implement a solution for improving the staining process to better bring out the graining in grinnell. (@ken hull, @mike lotko) • thd samples 1.5 • die redundancy and enhancement: initiate the process to get a second die made for the two panel arch top, ensuring redundancy and more pronounced graining for finishing. (@ken hull, @mike lotko) • traditional channel die change process: establish a working team and develop a plan to shorten the die changeover time for supporting seven skus in the traditional channel, moving from shifts to minutes. (@jim copeland, @mike lotko adam, justin) • assessment of dies: assess the dies produced for acceptability, decide on replacement for any cracked dies, and initiate the supply chain process for ordering replacements if needed. (@mike lotko @ken hull) • glazed units die timeline: follow up with larry after tomorrow’s meeting to obtain and communicate a timeline for the die required to confirm the glazed unit design. (@mike lotko) • design lock for glazed business focus • market pricing research: complete research with sales and marketing to establish market pricing for the traditional channel and communicate findings to the team. (@matt goodman) • base coat application costing: determine the cost and margin impact of applying a base coat to all doors before entering the traditional channel and decide on the number of colors to offer. (paul, ken, matt) | not specified | not specified | yellow | on track | red | green | red | red | yellow | red | 6 | 0 | 33.0 | 12.0 | 316.0 | 559.0 | 36.0 | 42.0 | 8.0 | 8.0 | 920.0 | 361.0 | 318.0 | 43.0 | 6696925.0 | 6696925.0 | not specified | 7015365.6 | 6957815.71 | 57549.89 | 0.0 | 823025.0 | 823025.0 | 0.0 | 0.0 | 7838390.6 | 7780840.71 | 57549.89 | 0.0 | -1141465.6 | -1083915.71 | -57549.89 | -0.170446227186358 | -0.161852747342997 | 0 | 2025-10-27 | 2022-03-09 | 2026-01-02 | 0 | 998d | 2025-10-28 | 2025-10-02 | not specified | 29 | 1.0 | not specified | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | engineering | not specified | not specified | not specified | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 3.968 | not specified | 6.8 | 2024-01-26 | 2024-02-10 | on plan | not specified | 1.0 | on track | 0.782072368421053 | 1.0 | 27.0 | 0.0358695652173913 | 0.0130434782608696 | 0.343478260869565 | 0.607608695652174 | 0.00869565217391304 | 0.991304347826087 | 2026 | not specified | 3 | not specified | not specified | 1.0 | p | 1 | not specified | not specified | not specified | not specified | jim copeland | not specified | 2022-03-09 | 2025-06-24 | not specified | not specified | [6 empty] | 860d | 0.0 | 0.0 | -498.0 | -0.579069767441861 | -356.0 | -0.413953488372093 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.46
cybersecurity - ot vulnerability scanning | 32869 | not specified | brad duffey | brad duffey | project | standalone project | standalone project | it-cyber | jorge eleta | cybersecurity it | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | 32869.0 | not specified | project dashboard | financial dashboard | 0.38 | 2024-02-20 | 2025-05-01 | 313d | project cancelled. | na scanning completed, digesting information | report findings to itlt, determine a path forward for the project scope before continuing in gate meetings. | no support needed. | green | on track | red | red | yellow | red | green | green | 1 | 0 | 2.0 | 1.0 | 4.0 | 1.0 | 7.0 | 5.0 | 0.0 | 0.0 | 8.0 | 7.0 | 5.0 | 2.0 | 250000.0 | 226000.0 | 24000.0 | 246068.0 | 223106.0 | 22962.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 246068.0 | 223106.0 | 22962.0 | not specified | 3932.0 | 2894.0 | 1038.0 | 0.015728 | 0.0128053097345133 | 0.04325 | 2025-10-27 | 2024-02-20 | 2025-04-18 | -8d | 304d | 2025-03-27 | 2025-09-19 | not specified | 1 | not specified | not specified | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | canceled | not specified | it | not specified | not specified | not specified | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0.6753 | 2023-10-17 | 2024-12-20 | on plan | not specified | 1.0 | on track | 1.0 | 216.0 | 40.0 | 0.25 | 0.125 | 0.5 | 0.125 | 0.0 | 1.0 | current year | n | 3 | not specified | not specified | 1.0 | p | 19 | not specified | 1.0 | 1.0 | not specified | not specified | not specified | 2024-02-02 | 2024-07-31 | not specified | not specified | [6 empty] | 129d | -18.0 | -0.13953488372093 | -274.0 | -2.12403100775194 | -184.0 | -1.42635658914729 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.38
cybersecurity - removable media restriction | 37802 | not specified | brad duffey | brad duffey | project | standalone project | standalone project | it-cyber | jorge eleta | not specified | not specified | brad duffey | not specified | brad duffey | ravi ramaraj | m.j. vaidya | not specified | sg&a | support functions: global it - cyber | it | l1 (identified) | on hold | 37802.0 | not specified | project dashboard | financial dashboard | 0.5 | 2024-06-18 | 2024-12-06 | 124d | in holding pattern | drafts finalized, submitted to legal for review | awaiting committee approval for created policy | no support needed at this time. | green | on track | red | red | green | green | green | green | 0 | 0 | 4.0 | 0.0 | 4.0 | 0.0 | 8.0 | 7.0 | 0.0 | 0.0 | 8.0 | 8.0 | 7.0 | 1.0 | 0.0 | 0.0 | 0.0 | 8201.0 | 0.0 | 8201.0 | not specified | not specified | 0.0 | 0.0 | not specified | 8201.0 | 0.0 | 8201.0 | not specified | -8201.0 | 0.0 | -8201.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2024-06-18 | 2024-12-06 | 0 | 124d | 2024-11-21 | 2025-02-26 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on-hold | not specified | it | not specified | not specified | not specified | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 2024-06-22 | 2024-07-12 | on plan | not specified | 1.0 | on track | 1.0 | 342.0 | 245.0 | 0.5 | 0.0 | 0.5 | 0.0 | 0.0 | 1.0 | previous year | n | 3 | not specified | not specified | 1.0 | p | 20 | not specified | 1.0 | not specified | not specified | not specified | not specified | 2024-02-02 | 2024-07-31 | not specified | not specified | [6 empty] | 129d | -137.0 | -1.06201550387597 | -128.0 | -0.992248062015504 | 5.0 | 0.0387596899224806 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.5
it accountable – na & corporate projects | it-na/corp | not specified | not specified | not specified | sub portfolio | not specified | standalone project | it-na/corp | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | sub portfolio dashboard | finance dashboard | 0.85338249754179 | 2023-01-13 | 2024-12-13 | 501d | on track | not specified | not specified | not specified | on track | on track | on track | on track | on track | on track | on track | on track | 0 | 0 | 24.0 | 0.0 | 0.0 | 81.0 | 24.0 | 24.0 | 40.0 | 40.0 | 105.0 | 24.0 | 24.0 | 0.0 | 350000.0 | 0.0 | 350000.0 | 1486502.75 | 1124131.25 | 362371.5 | not specified | 0.0 | 0.0 | 0.0 | not specified | 1486502.75 | 1124131.25 | 362371.5 | not specified | -1136502.75 | -1124131.25 | -12371.5 | -3.24715071428571 | 0.0 | -0.0353471428571429 |  | 2023-01-13 | 2024-10-03 | 0 | 450d | 2025-01-23 | 2025-10-16 | not specified | not specified | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 1.0 | 279.0 | 13.0 | 0.228571428571429 | 0.0 | 0.0 | 0.771428571428572 | 0.380952380952381 | 0.619047619047619 | previous year | not specified | 1 | 1.0 | it-na/corp | not specified | sprt | 22 | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | [6 empty] | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.85338
it accountable – eu projects | it-eu | not specified | not specified | not specified | sub portfolio | not specified | standalone project | it-eu | not specified | it it-eu | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | sub portfolio dashboard | finance dashboard | 0.710824455322008 | 2022-06-03 | 2028-02-25 | 1496d | on track | not specified | not specified | not specified | on track | on track | on track | on track | on track | on track | on track | on track | 0 | 0 | 128.0 | 117.0 | 336.0 | 890.0 | 176.0 | 159.0 | 306.0 | 306.0 | 1471.0 | 581.0 | 533.0 | 48.0 | 2201013.14117646 | 1107840.78823529 | 1093172.35294117 | 1388544.24882353 | 797358.094117645 | 591186.15470588 | not specified | 356108.62352941 | 18470.5882352941 | 337638.035294116 | not specified | 1744652.87235294 | 815828.682352939 | 928824.189999997 | not specified | 456360.26882352 | 292012.105882351 | 164348.162941173 | 0.207341001417007 | 0.263586707569691 | 0.15034057758504 |  | 2022-06-03 | 2029-05-09 | 0 | 1809d | 2025-10-28 | 2025-10-24 | not specified | not specified | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.594251336898396 | 1.0 | 5.0 | 0.0870156356220258 | 0.079537729435758 | 0.228416043507818 | 0.605030591434398 | 0.208021753908906 | 0.791978246091094 | 2028 | not specified | 1 | 1.0 | it-na/eu | not specified | sprt | 23 | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | [6 empty] | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.71082
it accountable – cybersecurity projects | it-cyber | not specified | not specified | not specified | sub portfolio | not specified | standalone project | it-cyber | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | sub portfolio dashboard | finance dashboard | 0.651595411887383 | 2023-09-23 | 2026-04-16 | 669d | on track | not specified | not specified | not specified | on track | on track | on track | on track | on track | on track | on track | on track | 0 | 0 | 4.0 | 1.0 | 1.0 | 0.0 | 17.0 | 17.0 | 0.0 | 0.0 | 140.0 | 140.0 | 46.0 | 21.0 | 3019254.0 | 2639584.0 | 379670.0 | 2931954.4 | 2555832.17 | 376122.23 | not specified | 137367.83 | 75721.54 | 61646.29 | not specified | 3069322.23 | 2631553.71 | 437768.52 | not specified | -50068.23 | 8030.29000000004 | -58098.52 | -0.0165829804315901 | 0.00304225590092986 | -0.153023731134933 |  | 2023-09-23 | 2025-08-28 | 0 | 504d | 2025-10-10 | 2025-10-13 | not specified | not specified | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.819133034379671 | 19.0 | 16.0 | 0.0285714285714286 | 0.00714285714285714 | 0.00714285714285714 | 0.0 | 0.0 | 1.0 | 2026 | not specified | 1 | 1.0 | it-cyber | not specified | sprt | 24 | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | [6 empty] | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.6516
it accountable – infrastructure & service desk projects | it-infra/service | not specified | not specified | not specified | sub portfolio | not specified | standalone project | it-infra/service | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | sub portfolio dashboard | finance dashboard | 0.812432809773124 | 2023-09-01 | 2025-12-12 | 596d | on track | not specified | not specified | not specified | on track | on track | on track | on track | on track | on track | on track | on track | 0 | 0 | 58.0 | 13.0 | 15.0 | 340.0 | 60.0 | 59.0 | 93.0 | 83.0 | 426.0 | 86.0 | 80.0 | 6.0 | 3783501.0 | 3500451.0 | 283050.0 | 3212904.290534 | 2861860.420534 | 351043.87 | not specified | 260665.0 | 0.0 | 260665.0 | not specified | 3473569.290534 | 2861860.420534 | 611708.87 | not specified | 309931.709466 | 638590.579466 | -328658.87 | 0.0819166453150138 | 0.18243094374582 | -1.16113361596891 |  | 2023-09-01 | 2025-09-26 | 0 | 541d | 2025-10-28 | 2025-10-27 | not specified | not specified | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.946308724832215 | 1.0 | 2.0 | 0.136150234741784 | 0.0305164319248826 | 0.0352112676056338 | 0.7981220657277 | 0.21830985915493 | 0.78169014084507 | current year | not specified | 1 | 1.0 | it-infra/service | not specified | sprt | 25 | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | [6 empty] | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.81243
business accountable – na & corporate with it dependencies | bus-na/corp/it | not specified | not specified | not specified | sub portfolio | not specified | standalone project | bus-na/corp/it | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | sub portfolio dashboard | finance dashboard | 0.613900805810918 | 2022-01-01 | 2027-10-28 | 1519d | on track | not specified | not specified | not specified | on track | on track | on track | on track | on track | on track | on track | on track | 0 | 0 | 583.0 | 265.0 | 286.0 | 2425.0 | 585.0 | 721.0 | 1148.0 | 1126.0 | 3559.0 | 1134.0 | 706.0 | 428.0 | 80504933.78 | 48646269.84 | 34699764.94 | 39068773.55 | 19630408.8666667 | 19438364.6833333 | not specified | 9668385.61666667 | 1371315.8 | 8297069.81666667 | not specified | 48737159.1666667 | 21001724.6666667 | 27735434.5 | not specified | 31767774.6133333 | 27644545.1733333 | 6964330.44 | 0.394606555421147 | 0.568276771564553 | 0.200702524989496 |  | 2022-01-01 | 2027-10-28 | 0 | 1519d | 2025-10-28 | 2025-10-27 | not specified | not specified | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.657011191573404 | 1.0 | 2.0 | 0.163810059005339 | 0.0744591177296994 | 0.0803596515875246 | 0.681371171677437 | 0.322562517561113 | 0.677437482438887 | 2027 | not specified | 1 | 1.0 | bus-na/corp/it | not specified | sprt | 26 | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | [6 empty] | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.6139
business accountable – eu with it dependencies | bus-eu/it | not specified | not specified | not specified | sub portfolio | not specified | standalone project | it-eu | not specified | it it-eu | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | sub portfolio dashboard | finance dashboard | 0.714924731182796 | 2023-09-12 | 2026-04-20 | 680d | on track | not specified | not specified | not specified | on track | on track | on track | on track | on track | on track | on track | on track | 0 | 0 | 27.0 | 56.0 | 167.0 | 779.0 | 54.0 | 42.0 | 75.0 | 75.0 | 1029.0 | 250.0 | 220.0 | 30.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 |  | 2023-09-12 | 2026-01-01 | 0 | 603d | 2025-10-27 | 2025-10-27 | not specified | not specified | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.819117647058824 | 2.0 | 2.0 | 0.0262390670553936 | 0.054421768707483 | 0.162293488824101 | 0.757045675413022 | 0.0728862973760933 | 0.927113702623907 | 2026 | not specified | 1 | 1.0 | bus-eu/it | not specified | sprt | 27 | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | [6 empty] | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.71492
doorlite frame project - optic | 32453 | not specified | ryan russel | greg hughes | project | standalone project | standalone project | eng-it | amanda jones | automation | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | 32453.0 | not specified | project dashboard | finance dashboard | 0.38 | 2022-06-17 | 2026-06-22 | 1047d | 7/26 pkg: foam sample are good. p.o just needs to be placed. sending 3d frame to jacob to review foam fitment. met with texas instr to request packaging specs. waiting on meeting with jr auto to clear up confusion on 40x51 pallet. | not specified | not specified | we need help | yellow | on track | red | green | red | red | yellow | green | 9 | 0 | 207.0 | 13.0 | 117.0 | 146.0 | 227.0 | 212.0 | 211.0 | 210.0 | 483.0 | 337.0 | 311.0 | 26.0 | 9620061.0 | 9095061.0 | 525000.0 | 7705880.82 | 7672357.78 | 33523.04 | not specified | 923792.0 | 923792.0 | 0.0 | not specified | 8629672.82 | 8596149.78 | 33523.04 | not specified | 990388.18 | 498911.220000001 | 491476.96 | 0.102950301458587 | 0.0548551812901531 | 0.936146590476191 | 2025-10-27 | 2024-02-02 | 2024-07-31 | 0 | 129d | 2025-06-04 | 2024-11-05 | not specified | 117 | 1.0 | not specified | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | active | not specified | engineering | not specified | not specified | eu | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | 1.0 | on track | 0.839541547277937 | 147.0 | 358.0 | 0.428571428571429 | 0.0269151138716356 | 0.242236024844721 | 0.302277432712215 | 0.436853002070393 | 0.563146997929607 | 2026 | not specified | 3 | not specified | not specified | 1.0 | p | 31 | not specified | not specified | not specified | not specified | not specified | not specified | 2024-02-02 | 2024-07-31 | not specified | not specified | [6 empty] | 129d | 595.0 | 4.61240310077519 | -691.0 | -5.35658914728682 | -918.0 | -7.11627906976744 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.38
mes sql upgrade & consolidation spital | 39267 | migration of 15+ mes databases from various virtual servers into the virtual cluster austria (reducing replications) consolidation of various databases | karolin koch | karolin koch | project | standalone project | standalone project | it-eu | not specified | it it central eu it-eu | not specified | karolin koch | not specified | j�rgen kocher | markus ellinger | rachael horton-farmer | not specified | sg&a | support functions: global it - europe | it | l5 (realised) | on track | 39267.0 | not specified | project dashboard | finance dashboard | 1.0 | 2022-06-03 | 2024-12-31 | 673d | w49: project ready for closure | w49: wave stage l5 approved | w50: project closed | impact: n/a p2g: n/a | blue | on track | yellow | blue | yellow | green | green | green | 0 | 0 | 0.0 | 0.0 | 0.0 | 28.0 | 0.0 | 0.0 | 0.0 | 0.0 | 28.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 43483.79 | 27326.0 | 16157.79 | not specified | 0.0 | 0.0 | 0.0 | not specified | 43483.79 | 27326.0 | 16157.79 | not specified | -43483.79 | -27326.0 | -16157.79 | 0.0 | 0.0 | 0 | 2025-10-27 | 2022-06-03 | 2025-02-06 | 0 | 700d | 2024-12-09 | 2024-12-09 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | completed | not specified | it | not specified | not specified | central eu | realize value / close / care period | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0.0823262 | 2023-11-10 | 2024-12-31 | on plan | not specified | 1.0 | on track | 1.0 | 324.0 | 324.0 | 0.0 | 0.0 | 0.0 | 1.0 | 0.0 | 1.0 | previous year | n | 3 | not specified | not specified | not specified | p | 32 | not specified | 1.0 | 1.0 | not specified | not specified | not specified | 2024-02-02 | 2024-07-31 | not specified | not specified | [6 empty] | 129d | 609.0 | 4.72093023255814 | -153.0 | -1.18604651162791 | -544.0 | -4.21705426356589 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | stage 5 - care period | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 1
special order program rebuild including catalog and retail commercial actions- doors portion | 22630 | not specified | emily bartlett | emily bartlett | program | 22630 | 22630: special order program rebuild including catalog and retail commercial actions- doors portion | bus-na/corp/it | amanda jones | na it | not specified | it pm not required | emily bartlett | neely cousar | mike crawford (brm) | tyce deal | not specified | growth | na - doors & dist: commercial - product & pricing | engineering; it; hr | l4 (executed) | on track | not specified | not specified | program dashboard | finance dashboard | 0.525743944636678 | 2023-11-06 | 2025-06-26 | 429d | add the high level status of the program in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | on track | yellow | on track | green | red | yellow | green | 0 | 0 | 22.0 | 86.0 | 1.0 | 161.0 | 6.0 | 18.0 | 113.0 | 87.0 | 270.0 | 109.0 | 56.0 | 53.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 |  | 2023-11-06 | 2025-06-26 | 0 | 429d | 2025-05-21 | 2025-10-29 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | usd | it | not specified | not specified | not specified | see project details | not specified | not specified | on track | on track | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 1.0 | 161.0 | 0.0 | 0.0814814814814815 | 0.318518518518519 | 0.0037037037037037 | 0.596296296296296 | 0.418518518518519 | 0.581481481481481 | current year | not specified | 2 | not specified | not specified | not specified | not specified | 252 | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | [6 empty] | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.52574
special order catalog - doors | p-0323 | special order catalog - doors project is designed to update the special order door catalog to improve pricing and customer experience in 2 phases. phase 1 will update a large portion of the exterior door offering and phase 2 will be a grand launch of the door offering including revised pricing and the remainder of the door revisions not included in rev 1. | emily bartlett | emily bartlett | project | 22630 | 22630: special order program rebuild including catalog and retail commercial actions- doors portion | bus-na/corp/it | amanda jones | na it | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | 22630.0 | not specified | project dashboard | finance dashboard | 1.0 | 2023-11-06 | 2024-10-31 | 259d | exterior rev 1 and interior/exterior rev 2 catalogs are on track for delivery. steering committee meeting on 5/23/2024. | steering committee meeting held 5/23/2024 transitioned project plan from teamguru to smartsheets certified lowe's release for 6/4 exterior rev 1 | need confirmation on tami's budget for commercialization for august launch materials. certify thd exterior rev 1 release for 6/10 in-store date | not specified | green | on track | red | blue | red | green | yellow | green | 0 | 0 | 0.0 | 5.0 | 0.0 | 124.0 | 0.0 | 0.0 | 18.0 | 18.0 | 129.0 | 5.0 | 0.0 | 5.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2023-11-06 | 2024-08-20 | 0 | 207d | 2024-11-25 | 2024-11-01 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | active | usd | other | not specified | not specified | not specified | realize value / close / care period | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 26.53211834 | not specified | 1.66366 | 2023-10-18 | 2024-09-09 | on plan | not specified | 1.0 | on track | 1.0 | 338.0 | 362.0 | 0.0 | 0.0387596899224806 | 0.0 | 0.961240310077519 | 0.13953488372093 | 0.86046511627907 | previous year | n | 3 | not specified | not specified | not specified | p | 33 | not specified | 1.0 | 1.0 | not specified | not specified | not specified | 2023-11-06 | 2024-08-20 | not specified | not specified | [6 empty] | 207d | 0.0 | 0.0 | -72.0 | -0.347826086956522 | -52.0 | -0.251207729468599 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | stage 5 - care period | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 1
thd in-store display revamp | p-0324 | not specified | emily bartlett | emily bartlett | project | 22630 | 22630: special order program rebuild including catalog and retail commercial actions- doors portion | bus-na/corp/it | amanda jones | na it | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.0 | 2025-01-01 | 2025-06-26 | 127d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | sideways | red | green | green | red | yellow | green | 0 | 1 | 18.0 | 25.0 | 0.0 | 13.0 | 3.0 | 15.0 | 37.0 | 37.0 | 56.0 | 43.0 | 0.0 | 43.0 | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-01-29 | 2024-11-25 | not specified | 1 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | usd | other | not specified | not specified | not specified | realize value / close / care period | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 1.0 | 273.0 | 338.0 | 0.321428571428571 | 0.446428571428571 | 0.0 | 0.232142857142857 | 0.660714285714286 | 0.339285714285714 | current year | not specified | 3 | not specified | not specified | 1.0 | p | 253 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | 0.0 | not specified | -127.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | in-store display revamp | not specified |  | not specified | not specified | false | stage 5 - care period | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0
jw lowe’s in-store display revamp | p-0331 | not specified | emily bartlett | emily bartlett | project | 22630 | 22630: special order program rebuild including catalog and retail commercial actions- doors portion | not specified | amanda jones | na it | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.66 | 2025-01-01 | 2025-04-04 | 68d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | sideways | red | yellow | red | green | yellow | green | 0 | 0 | 4.0 | 56.0 | 0.0 | 24.0 | 2.0 | 2.0 | 57.0 | 31.0 | 84.0 | 60.0 | 55.0 | 5.0 | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-03-07 | 0 | 48d | 2025-05-21 | 2024-12-03 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | usd | other | not specified | not specified | not specified | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 1.0 | 161.0 | 330.0 | 0.0476190476190476 | 0.666666666666667 | 0.0 | 0.285714285714286 | 0.678571428571429 | 0.321428571428571 | current year | not specified | 3 | not specified | not specified | 1.0 | p | 265 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-03-07 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | -28.0 | not specified | -68.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | jw lowe’s in-store display revamp | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.66
abs lowe’s in-store display revamp | p-0332 | not specified | emily bartlett | emily bartlett | project | 22630 | 22630: special order program rebuild including catalog and retail commercial actions- doors portion | not specified | amanda jones | na it | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.0 | 2024-12-09 | 2025-05-29 | 124d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | sideways | green | green | green | green | yellow | green | 0 | 0 | 0.0 | 0.0 | 1.0 | 0.0 | 1.0 | 1.0 | 1.0 | 1.0 | 1.0 | 1.0 | 1.0 | 0.0 | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-28 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2024-12-10 | 2024-12-03 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | usd | other | not specified | not specified | not specified | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 1.0 | 323.0 | 330.0 | 0.0 | 0.0 | 1.0 | 0.0 | 1.0 | 0.0 | current year | not specified | 3 | not specified | not specified | 1.0 | p | 266 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | 23.0 | not specified | 28.0 | not specified | -124.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | abs lowe’s in-store display revamp | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0
special order program rebuild including catalog and retail commercial actions- windows portion | 22578 | special order catalog - windos project is designed to improve the customer experience and product offerings for windows. | emily bartlett | emily bartlett | project | standalone project | standalone project | bus-na/corp/it | amanda jones | na it | not specified | mike crawford (brm) | emily bartlett | divya kapoor | mike crawford (brm) | tyce deal | not specified | growth | na - windows: commercial - product & pricing | it | l3 (planned) | on track | 22578.0 | not specified | project dashboard | finance dashboard | 0.99 | 2024-05-06 | 2024-10-29 | 127d | vinyl windows: on 9/6 stopped development because we need merchant approval for the pricing changes. mike sent email to dave van eck to escalate the fact that we are still awaiting on approval to publish and each day we wait is a risk for the october 2024 menards catalog publication. dave responded to mike to continue with development while he works with menards on the pricing approval. | not specified | vinyl: next week we expect that marketing provide requested help me choose documentation. expecting merchant approval for pricing increase. updated release dates are as follows: thd vinyl and wood publish 10/7/24 lowe's wood publish 10/1/24 and vinyl publish10/8/24 menards 10/21/24 | not specified | yellow | on track | red | green | red | green | yellow | green | 0 | 1 | 2.0 | 10.0 | 0.0 | 48.0 | 2.0 | 0.0 | 13.0 | 13.0 | 60.0 | 12.0 | 0.0 | 12.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2024-05-06 | 2024-10-10 | 0 | 114d | 2025-02-21 | 2024-11-01 | not specified | 1 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | active | not specified | it | not specified | not specified | not specified | realize value / close / care period | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 4.621 | not specified | 0.15 | 2023-10-11 | 2024-01-07 | on plan | not specified | 1.0 | on track | 1.0 | 250.0 | 362.0 | 0.0333333333333333 | 0.166666666666667 | 0.0 | 0.8 | 0.216666666666667 | 0.783333333333333 | previous year | n | 3 | not specified | not specified | 1.0 | p | 34 | not specified | 1.0 | 1.0 | not specified | not specified | not specified | 2024-05-06 | 2024-06-21 | not specified | not specified | [6 empty] | 35d | 0.0 | 0.0 | -130.0 | -3.71428571428571 | -92.0 | -2.62857142857143 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | stage 5 - care period | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.99
standard it project management processes and tools | 38468 | revisit our it project management processes and tools and look for reductions in administrative overhead. even though our it stage get process was very robust in many aspects it was at the same time very heavy in administration (excel, ppts...). there are also gaps in different areas such as project financial management, resource management, etc. the pmo team believes that there are opportunities to use existing tools (smartsheet being one of them...) to address some of those gaps. preliminary thinking of some of our most senior pms is that we could easily generate 10% of efficiencies from every pm that could be better used. quality of the work and project controls should also see important improvements. | garrett farmer | cyndi maples | project | standalone project | standalone project | it-na/corp | not specified | it na/corporate | not specified | cyndi maples | not specified | jorge eleta gomez de segura | mike schipper | rachael horton-farmer | not specified | sg&a | support functions: global it - north america | it | l5 (realised) | on track | 38468.0 | not specified | project dashboard | finance dashboard | 1.0 | 2023-10-16 | 2024-10-03 | 254d | itlt - l4/l5 approved, 10/3/2024. project officially closed. | not specified | not specified | not specified | blue | on track | green | blue | green | green | green | green | 0 | 0 | 0.0 | 0.0 | 0.0 | 58.0 | 0.0 | 0.0 | 0.0 | 0.0 | 58.0 | 0.0 | 0.0 | 0.0 | 350000.0 | not specified | 350000.0 | 273920.25 | 105518.25 | 168402.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 273920.25 | 105518.25 | 168402.0 | 0.0 | 76079.75 | -105518.25 | 181598.0 | 0.217370714285714 | 0.0 | 0.518851428571429 | 2025-10-27 | 2023-10-16 | 2024-10-03 | 0 | 254d | 2024-10-04 | 2024-11-12 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | completed | not specified | it | not specified | not specified | not specified | realize value / close / care period | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | -0.012 | not specified | 0.104 | 2023-10-16 | 2024-05-31 | on plan | not specified | 1.0 | on track | 1.0 | 390.0 | 351.0 | 0.0 | 0.0 | 0.0 | 1.0 | 0.0 | 1.0 | previous year | n | 3 | not specified | not specified | not specified | p | 35 | not specified | 1.0 | 1.0 | not specified | not specified | not specified | 2023-10-16 | 2024-09-19 | not specified | not specified | [6 empty] | 244d | 0.0 | 0.0 | -14.0 | -0.0573770491803279 | -10.0 | -0.040983606557377 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | stage 5 - care period | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 1
special order catalog: thd gcc design builder launch | 13664 | thd is moving away from paradigm as the host for the special order catalog. thd is building their own gcc platform to support special order catalog orders from jeld-wen. jeld-wen will be supporting thd gcc team in creating the jeld-wen catalog in thd gcc platform. | emily bartlett | emily bartlett | project | standalone project | standalone project | bus-na/corp/it | amanda jones | na it | not specified | not specified | emily bartlett | colleen creese | mike crawford (brm) | tyce deal | not specified | footprint | na - doors & dist: commercial - sales | it | submitted for l2 approval | on track | 13664.0 | not specified | project dashboard | finance dashboard | 0.62 | 2024-09-02 | 2025-07-31 | 239d | we continue with the simple rules testing now. on 12/9 we asked gcc team for details on how to test orders for regionality and certifications. that will come more with the complex testing. there is no current end date on testing established. | not specified | continue testing and jason will reach to mike with requests for the layered visualization needs for the project such that we can get those image requirements in place. | not specified | yellow | on track | red | red | red | green | yellow | green | 0 | 0 | 11.0 | 52.0 | 0.0 | 11.0 | 4.0 | 7.0 | 71.0 | 68.0 | 74.0 | 63.0 | 0.0 | 63.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2024-02-02 | 2024-07-31 | 0 | 129d | 2025-08-08 | 2025-02-27 | not specified | 1 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | active | not specified | it | not specified | not specified | not specified | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | -0.33 | not specified | not specified |  |  | not planned (l2 to l4) | not specified | 1.0 | on track | 1.0 | 82.0 | 244.0 | 0.148648648648649 | 0.702702702702703 | 0.0 | 0.148648648648649 | 0.959459459459459 | 0.040540540540541 | current year | n | 3 | not specified | not specified | 1.0 | p | 48 | not specified | 1.0 | not specified | not specified | not specified | not specified | 2024-02-02 | 2024-08-02 | not specified | not specified | [6 empty] | 131d | -213.0 | -1.62595419847328 | -363.0 | -2.77099236641221 | -108.0 | -0.824427480916031 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.62
interior prehung retail packaging program | pg-0049 | not specified | greg hughes | ryan russel | program | pg-0049 | pg-0049: interior prehung retail packaging program | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | kirk kroft | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | program dashboard | finance dashboard | 0.320561622464899 | 2023-12-20 | 2025-08-01 | 423d | add the high level status of the program in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | on track | red | on track | red | red | yellow | green | 0 | 0 | 50.0 | 0.0 | 0.0 | 86.0 | 50.0 | 46.0 | 22.0 | 22.0 | 136.0 | 50.0 | 46.0 | 4.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 |  | 2023-12-20 | 2024-11-05 | 0 | 230d | 2025-09-18 | 2025-10-29 | not specified | 0 | not specified | not specified | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | active | not specified | it | not specified | not specified | not specified | see project details | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 1.0 | 41.0 | 0.0 | 0.367647058823529 | 0.0 | 0.0 | 0.632352941176471 | 0.161764705882353 | 0.838235294117647 | current year | not specified | 2 | not specified | not specified | not specified | pg | 49 | not specified | not specified | not specified | not specified | not specified | not specified | 2024-01-05 | 2024-11-05 | not specified | not specified | [6 empty] | 218d | 16.0 | 0.073394495412844 | -269.0 | -1.23394495412844 | -205.0 | -0.940366972477064 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.32056
interior prehung retail packaging engineering | p-0050 | not specified | greg hughes | ryan russel | project | pg-0049 | pg-0049: interior prehung retail packaging program | eng-it | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | finance dashboard | 0.05 | 2024-01-05 | 2024-11-05 | 218d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | on track | red | red | green | green | yellow | green | 0 | 0 | 43.0 | 0.0 | 0.0 | 2.0 | 43.0 | 43.0 | 1.0 | 1.0 | 45.0 | 43.0 | 43.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2024-01-05 | 2024-11-05 | 0 | 218d | 2025-09-18 | 2024-11-05 | not specified | 1 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | active | not specified | engineering | not specified | not specified | not specified | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 1.0 | 41.0 | 358.0 | 0.955555555555556 | 0.0 | 0.0 | 0.0444444444444444 | 0.0222222222222222 | 0.977777777777778 | previous year | not specified | 3 | not specified | not specified | 1.0 | p | 50 | not specified | not specified | not specified | not specified | not specified | not specified | 2024-01-05 | 2024-11-05 | not specified | not specified | [6 empty] | 218d | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.05
interior prehung retail packaging standardization | 23071 | not specified | ryan russel | ryan russel | project | pg-0049 | pg-0049: interior prehung retail packaging program | bus-na/corp/it | not specified | it mfg. & supply chain na it na/corporate | not specified | ryan russel | not specified | greg hughes | christian suarez | kirk kroft | not specified | manufacturing | na - doors & dist: commercial - product & pricing | it; engineering | l3 (planned) | on track | 23071.0 | not specified | project dashboard | finance dashboard | 0.46 | 2023-12-20 | 2025-08-01 | 423d | integration test file has been updated now need to change import and label to support exterior prehang label changes requested | export file development drafted | change loftware automation, change loftware label, change loftware solution, test and validate changes | no support required | green | on track | red | green | red | red | yellow | green | 1 | 1 | 7.0 | 0.0 | 0.0 | 84.0 | 7.0 | 3.0 | 21.0 | 21.0 | 91.0 | 7.0 | 3.0 | 4.0 | 96050.0 | 52022.0 | 44028.0 | 79284.78 | 37790.28 | 41494.5 | not specified | 0.0 | 0.0 | 0.0 | not specified | 79284.78 | 37790.28 | 41494.5 | not specified | 16765.22 | 14231.72 | 2533.5 | 0.174546798542426 | 0.273571181423244 | 0.0575429272281276 | 2025-10-27 | 2023-12-20 | 2024-09-30 | -2d | 204d | 2025-09-18 | 2025-09-10 | not specified | 14 | not specified | not specified | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | active | not specified | it | not specified | not specified | not specified | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 1.003 | not specified | 0.206275 | 2023-10-25 | 2024-01-12 | on plan | not specified | not specified | on track | 1.0 | 41.0 | 49.0 | 0.0769230769230769 | 0.0 | 0.0 | 0.923076923076923 | 0.230769230769231 | 0.769230769230769 | current year | not specified | 3 | not specified | not specified | 1.0 | p | 4 | not specified | 1.0 | 1.0 | not specified | not specified | not specified | 2024-02-02 | 2024-07-31 | not specified | not specified | [6 empty] | 129d | 44.0 | 0.341085271317829 | -366.0 | -2.83720930232558 | -294.0 | -2.27906976744186 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.46
canada controls | 1846 | toronto o2c controls automation unable to satisfy internal control requirements (sox) in current manual operating environment. inability to put effective and efficient system controls in place to validate / monitor pricing, discount changes, and order entry / invoicing accuracy. systems tools not designed, configured / integrated to leverage system controls and automation for this channel. pricing errors lead to overstatement or understatement of income; cm related to pricing errors of $1.0m in 2022. unable to leverage systems processes for growth opportunities across na. | jorge eleta | cyndi maples | project | standalone project | standalone project | bus-na/corp/it | not specified | it na it na/corporate | not specified | cyndi maples | not specified | richard chin | sheri schrier | kirk kroft | not specified | pricing | na - windows: manufacturing - canada | it | l3 (planned) | on hold | 1846.0 | not specified | project dashboard | finance dashboard | 1.0 | 2024-01-08 | 2025-07-04 | 390d | project cancelled/status remains 'on hold' wave and smartsheet per mike schipper. requirements will be implemented as part of cpq project start q3 2025. | wave and smartsheet financials updated through november 2024. | not specified | not specified | blue | on track | red | blue | green | green | green | red | 0 | 0 | 0.0 | 0.0 | 0.0 | 97.0 | 0.0 | 0.0 | 0.0 | 0.0 | 97.0 | 0.0 | 0.0 | 0.0 | 340560.0 | 300000.0 | 40560.0 | 38522.5 | 27351.5 | 11171.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 38522.5 | 27351.5 | 11171.0 | not specified | 302037.5 | 272648.5 | 29389.0 | 0.886884836739488 | 0.908828333333333 | 0.724580867850099 | 2025-10-27 | 2024-01-08 | 2025-07-04 | 0 | 390d | 2025-02-19 | 2024-12-03 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | canceled | not specified | it | not specified | not specified | not specified | realize value / close / care period | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0.0 | not specified | 0.3456 | 2023-10-19 | 2024-11-20 | on plan | not specified | 1.0 | on track | 1.0 | 252.0 | 330.0 | 0.0 | 0.0 | 0.0 | 1.0 | 0.0 | 1.0 | current year | n | 3 | not specified | not specified | 1.0 | p | 51 | not specified | 1.0 | 1.0 | not specified | not specified | not specified | 2024-02-02 | 2024-08-02 | not specified | not specified | [6 empty] | 131d | 25.0 | 0.190839694656489 | -336.0 | -2.56488549618321 | -259.0 | -1.97709923664122 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | stage 5 - care period | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 1
segment insights | 13067 | implementation of an end-to-end, comprehensive solution that will enable consolidation of north america's orders, sales, and profitability data into an institutional platform | jorge eleta | tamara johnson | project | standalone project | standalone project | bus-na/corp/it | not specified | it na/corporate | not specified | tamara johnson | not specified | jeremy russell | mike crawford (r2r) | m.j. vaidya | not specified | sg&a | support functions: finance | it | l5 (realised) | on track | 13067.0 | not specified | project dashboard | finance dashboard | 0.73 | 2023-09-05 | 2025-05-09 | 439d | team continues work on additional business requirements | deployment of pbi model update | enhancements and bug fixes | no support needed | green | on track | red | green | red | green | green | green | 0 | 0 | 2.0 | 0.0 | 0.0 | 57.0 | 2.0 | 1.0 | 0.0 | 0.0 | 59.0 | 2.0 | 1.0 | 1.0 | 4448000.0 | 3455000.0 | 993000.0 | 4046622.95 | 3155826.98 | 890795.97 | 806147.47 | 108700.0 | 89200.0 | 19500.0 | 17500.0 | 4155322.95 | 3245026.98 | 910295.97 | 823647.47 | 292677.05 | 209973.02 | 82704.03 | 0.0657996964928058 | 0.0607736671490593 | 0.0832870392749245 | 2025-10-27 | 2024-01-15 | 2025-01-17 | 0 | 265d | 2025-05-12 | 2025-10-13 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | active | not specified | it | not specified | not specified | not specified | realize value / close / care period | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | -0.14 | not specified | 3.506999 | 2023-12-10 | 2024-11-30 | on plan | not specified | 1.0 | on track | 1.0 | 170.0 | 16.0 | 0.0338983050847458 | 0.0 | 0.0 | 0.966101694915254 | 0.0 | 1.0 | current year | n | 3 | not specified | not specified | 1.0 | p | 53 | not specified | 1.0 | 1.0 | not specified | not specified | not specified | 2024-02-02 | 2024-08-02 | not specified | not specified | [6 empty] | 131d | 150.0 | 1.14503816793893 | -280.0 | -2.13740458015267 | -308.0 | -2.35114503816794 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | stage 5 - care period | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.73
buyer workbench | 13751 | not specified | jorge eleta | chad alterio | project | standalone project | standalone project | bus-na/corp/it | not specified | mfg. & supply chain na it | not specified | fabio rivera | not specified | emily cochrane | christian suarez | kirk kroft | not specified | supply chain | na - ops: supply chain | it | l3 (planned) | on hold | 13751.0 | not specified | project dashboard | finance dashboard | 0.45 | 2024-02-02 | 2024-08-02 | 131d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | on track | red | red | yellow | green | yellow | green | 0 | 0 | 11.0 | 0.0 | 0.0 | 9.0 | 11.0 | 11.0 | 20.0 | 20.0 | 20.0 | 11.0 | 11.0 | 0.0 | 300000.0 | 240000.0 | 60000.0 | 7654.0 | 178.0 | 7476.0 | not specified | 292346.0 | 239822.0 | 52524.0 | not specified | 300000.0 | 240000.0 | 60000.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2024-02-02 | 2024-07-31 | 0 | 129d | 2024-08-14 | 2024-11-01 | not specified | 1 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | active | not specified | it | not specified | not specified | not specified | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | -0.175 | 15.0 | 4.90089 | 2023-10-19 | 2025-10-03 | on plan | not specified | 1.0 | on track | 1.0 | 441.0 | 362.0 | 0.55 | 0.0 | 0.0 | 0.45 | 1.0 | 0.0 | previous year | n | 3 | not specified | not specified | 1.0 | p | 54 | not specified | 1.0 | 1.0 | not specified | not specified | not specified | 2024-02-02 | 2024-08-02 | not specified | not specified | [6 empty] | 131d | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.45
ach payments - canada cash management and a/p ach conversion | 22375 | not specified | jorge eleta | mike crawford (r2r) | project | standalone project | standalone project | bus-na/corp/it | not specified | not specified | not specified | mike crawford (r2r) | not specified | amy jackson | mike crawford (r2r) | m.j. vaidya | not specified | working capital | support functions: working capital | it | l4 (executed) | on track | 22375.0 | not specified | project dashboard | finance dashboard | 0.45 | 2024-02-02 | 2024-08-02 | 131d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | on track | red | red | yellow | green | yellow | green | 0 | 0 | 11.0 | 0.0 | 0.0 | 9.0 | 11.0 | 11.0 | 20.0 | 20.0 | 20.0 | 11.0 | 11.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2024-02-02 | 2024-07-31 | 0 | 129d | 2024-08-14 | 2024-11-01 | not specified | 1 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | active | not specified | it | not specified | not specified | not specified | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0.2 | 0.75 | 0.046 | 2024-04-03 | 2024-06-28 | on plan | not specified | 1.0 | on track | 1.0 | 441.0 | 362.0 | 0.55 | 0.0 | 0.0 | 0.45 | 1.0 | 0.0 | previous year | n | 3 | not specified | not specified | 1.0 | p | 56 | not specified | 1.0 | 1.0 | not specified | not specified | not specified | 2024-02-02 | 2024-08-02 | not specified | not specified | [6 empty] | 131d | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.45
rise: improve sales training | 22679 | not specified | jorge eleta | sheri schrier | project | standalone project | standalone project | bus-na/corp/it | not specified | it na it na/corporate | not specified | sheri schrier | not specified | nancy poradish | sheri schrier | tyce deal | not specified | other | na - ops: customer service | hr; it | l5 (realised) | on track | 22679.0 | not specified | project dashboard | finance dashboard | 0.45 | 2024-02-02 | 2024-08-02 | 131d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | blue | on track | red | red | yellow | green | yellow | green | 0 | 0 | 11.0 | 0.0 | 0.0 | 9.0 | 11.0 | 11.0 | 20.0 | 20.0 | 20.0 | 11.0 | 11.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2024-02-02 | 2024-07-31 | 0 | 129d | 2024-08-14 | 2025-09-18 | not specified | 1 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | completed | not specified | it | not specified | not specified | not specified | realize value / close / care period | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | -0.616 | not specified | 0.07 | 2023-12-10 | 2025-01-31 | on plan | not specified | 1.0 | on track | 1.0 | 441.0 | 41.0 | 0.55 | 0.0 | 0.0 | 0.45 | 1.0 | 0.0 | previous year | n | 3 | not specified | not specified | 1.0 | p | 57 | not specified | 1.0 | 1.0 | not specified | not specified | not specified | 2024-02-02 | 2024-08-02 | not specified | not specified | [6 empty] | 131d | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | stage 5 - care period | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.45
quality assurance tracking (qat) program | 22723 | not specified | jorge eleta | sheri schrier | project | standalone project | standalone project | bus-na/corp/it | not specified | na it | not specified | sheri schrier | not specified | dave miller | shannon messing | shannon messing | not specified | manufacturing | na - ops: customer service | it | l5 (realised) | on track | 22723.0 | not specified | project dashboard | finance dashboard | 0.45 | 2024-02-02 | 2024-08-02 | 131d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | on track | red | red | yellow | green | yellow | green | 0 | 0 | 11.0 | 0.0 | 0.0 | 9.0 | 11.0 | 11.0 | 20.0 | 20.0 | 20.0 | 11.0 | 11.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-04 | 2024-02-02 | 2024-07-31 | 0 | 129d | 2024-08-14 | 2024-11-01 | not specified | 1 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | active | not specified | it | not specified | not specified | not specified | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0.54722 | not specified | 0.05 | 2023-02-11 | 2024-05-31 | past due for l4 | not specified | 1.0 | on track | 1.0 | 441.0 | 362.0 | 0.55 | 0.0 | 0.0 | 0.45 | 1.0 | 0.0 | previous year | n | 3 | not specified | not specified | 1.0 | p | 58 | not specified | 1.0 | 1.0 | not specified | not specified | not specified | 2024-02-02 | 2024-08-02 | not specified | not specified | [6 empty] | 131d | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.45
complete talon 1.5 | 23724 | not specified | jorge eleta | jon gies | project | standalone project | standalone project | bus-na/corp/it | not specified | mfg. & supply chain na it | not specified | jon gies | not specified | adam rummler | mike doescher | kirk kroft | not specified | manufacturing | na - doors & dist.: manufacturing - west | it | l4 (executed) | on hold | 23724.0 | not specified | project dashboard | finance dashboard | 0.45 | 2024-02-02 | 2024-08-02 | 131d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | on track | red | red | yellow | green | yellow | green | 0 | 0 | 11.0 | 0.0 | 0.0 | 9.0 | 11.0 | 11.0 | 20.0 | 20.0 | 20.0 | 11.0 | 11.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2024-02-02 | 2024-07-31 | 0 | 129d | 2024-08-21 | 2024-11-05 | not specified | 1 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | active | not specified | it | not specified | not specified | not specified | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0.358496 | not specified | 0.0095 | 2023-12-10 | 2024-05-20 | on plan | not specified | 1.0 | on track | 1.0 | 434.0 | 358.0 | 0.55 | 0.0 | 0.0 | 0.45 | 1.0 | 0.0 | previous year | n | 3 | not specified | not specified | 1.0 | p | 59 | not specified | 1.0 | not specified | not specified | not specified | not specified | 2024-02-02 | 2024-08-02 | not specified | not specified | [6 empty] | 131d | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.45
source-to-pay (s2p) phase 1 | 36319 | implementation of an end-to-end, comprehensive solution that will, enable improved direct sourcing and supplier management capability and effiency, automate the contract lifecycle process and improve spend visibility and contract compliance. | jorge eleta | tamara johnson | project | standalone project | standalone project | bus-na/corp/it | not specified | it mfg. & supply chain na it na/corporate | not specified | tamara johnson | not specified | andrea schnieders | christian suarez | kirk kroft | not specified | sourcing | na - ops sourcing | it; legal | l5 (realised) | on track | 36319.0 | not specified | project dashboard | finance dashboard | 0.9 | 2023-12-15 | 2025-01-14 | 283d | project is completed | not specified | not specified | not specified | blue | on track | red | green | red | green | green | red | 0 | 0 | 3.0 | 0.0 | 0.0 | 13.0 | 3.0 | 3.0 | 0.0 | 0.0 | 16.0 | 3.0 | 3.0 | 0.0 | 3483000.0 | 2613000.0 | 870000.0 | 612427.87 | 446550.62 | 165877.25 | not specified | 0.0 | 0.0 | 0.0 | not specified | 612427.87 | 446550.62 | 165877.25 | not specified | 2870572.13 | 2166449.38 | 704122.75 | 0.824166560436405 | 0.829104240336778 | 0.809336494252874 | 2025-10-27 | 2023-12-15 | 2024-10-01 | 0 | 208d | 2025-01-30 | 2025-10-16 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | completed | not specified | it | not specified | not specified | not specified | realize value / close / care period | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 9.527748 | not specified | 4.936529 | 2023-10-13 | 2024-12-31 | on plan | not specified | 1.0 | on track | 1.0 | 272.0 | 13.0 | 0.1875 | 0.0 | 0.0 | 0.8125 | 0.0 | 1.0 | current year | n | 3 | not specified | not specified | 1.0 | p | 60 | not specified | 1.0 | 1.0 | not specified | not specified | not specified | 2024-02-02 | 2024-08-02 | not specified | not specified | [6 empty] | 131d | 49.0 | 0.374045801526718 | -165.0 | -1.25954198473282 | -152.0 | -1.16030534351145 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | stage 5 - care period | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.9
inventory control & cycle count - grinnell pilot + 3 sites | 37545 | not specified | jorge eleta | chris long | project | standalone project | standalone project | bus-na/corp/it | amanda jones | it mfg. & supply chain na it na/corporate | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | 37545.0 | not specified | project dashboard | finance dashboard | 0.96 | 2022-01-01 | 2026-07-31 | 1195d | w42: * software development completed * kissimmee successfully implemented on pre flush workflow * kitting functionality to be deployed to prod 10/15 * cerf submitted | w42: * successful migration of kissimmee from back flush workflow to pre flush workflow over q3 phy inv * reassignment of project team to other projects * wave updates to support cerf submittal * submission of the cerf | w42: * completion of uat for unreleased features and deployment to production * kanban functionality uat and deployment * formal closeout of project in smartsheet, wave, and tick | w42: none | green | sideways | red | green | red | red | yellow | red | 2 | 1 | 0.0 | 0.0 | 1.0 | 71.0 | 0.0 | 0.0 | 72.0 | 72.0 | 72.0 | 1.0 | 1.0 | 0.0 | 2344629.0 | 1702214.0 | 642415.0 | 3375651.76 | 2097872.76 | 1277779.0 | 895817.0 | 39000.0 | 0.0 | 39000.0 | 0.0 | 3414651.76 | 2097872.76 | 1316779.0 | 895817.0 | -1070022.76 | -395658.76 | -674364.0 | -0.456371886554333 | -0.23243773109609 | -1.04973264945557 | 2025-10-27 | 2022-01-01 | 2024-12-25 | 0 | 778d | 2025-10-28 | 2025-10-16 | not specified | 5 | not specified | not specified | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | active | not specified | it | not specified | not specified | not specified | implementation / execution | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0.85586 | 0.0 | 0.565 | 2023-06-11 | 2026-04-30 | on plan | not specified | 1.0 | on track | 0.835146443514644 | 1.0 | 13.0 | 0.0 | 0.0 | 0.0138888888888889 | 0.986111111111111 | 1.0 | 0.0 | 2026 | n | 3 | not specified | not specified | 1.0 | p | 61 | not specified | 1.0 | 1.0 | not specified | not specified | not specified | 2024-02-02 | 2024-08-02 | not specified | not specified | [6 empty] | 131d | 762.0 | 5.81679389312977 | -728.0 | -5.55725190839695 | -1064.0 | -8.12213740458015 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | stage 3 - implementation | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.96
warehouse management system - sacramento & rialto | 37698 | not specified | jorge eleta | mike doescher | project | standalone project | standalone project | bus-na/corp/it | not specified | it mfg. & supply chain na it na/corporate | not specified | fabio rivera | not specified | patrick smith | mike doescher | kirk kroft | not specified | manufacturing | na - doors & dist.: manufacturing - west | it | l3 (planned) | some issues | 37698.0 | not specified | project dashboard | finance dashboard | 0.72 | 2023-10-23 | 2026-12-18 | 825d | w35: -receiving has been launched and live for 3.5 weeks. team is performing well with any carryover trucks being completed the next day. -issue exists with uom conversions in the turns wms upload. currently finalizing root cause for fixes. all have been identified except for the inventory register report. eta tbd on fix deployment. | -launching receiving wms | -finalize inventory adjustment launch plan -start dil 9/8 for outbound, counts and adjustments | not specified | green | up | red | green | red | red | green | green | 2 | 2 | 0.0 | 0.0 | 12.0 | 182.0 | 1.0 | 1.0 | 0.0 | 0.0 | 194.0 | 12.0 | 11.0 | 1.0 | 6986707.0 | 2995151.0 | 3991556.0 | 3638326.4 | 2307676.18 | 1330650.22 | 329036.22 | 2741968.0 | 184918.0 | 2557050.0 | 280034.0 | 6380294.4 | 2492594.18 | 3887700.22 | 609070.22 | 606412.6 | 502556.82 | 103855.78 | 0.0867951955048351 | 0.167790144804052 | 0.0260188708363355 | 2025-10-27 | 2023-10-23 | 2025-05-16 | 0 | 410d | 2025-10-16 | 2025-08-27 | not specified | 4 | not specified | not specified | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | active | not specified | it | not specified | not specified | not specified | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 1.158721 | not specified | 2.874399 | 2023-10-13 | 2025-10-03 | on plan | not specified | 1.0 | on track | 0.64 | 13.0 | 63.0 | 0.0 | 0.0 | 0.0618556701030928 | 0.938144329896907 | 0.0 | 1.0 | 2026 | n | 3 | not specified | not specified | 1.0 | p | 62 | not specified | 1.0 | 1.0 | not specified | not specified | not specified | 2024-02-02 | 2024-08-02 | not specified | not specified | [6 empty] | 131d | 102.0 | 0.778625954198473 | -868.0 | -6.62595419847328 | -694.0 | -5.29770992366412 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.72
na payroll | 38211 | not specified | jorge eleta | christina hoy | project | standalone project | standalone project | bus-na/corp/it | not specified | not specified | not specified | christina andert | not specified | stan johnson | shannon messing | m.j. vaidya | not specified | sg&a | support functions: finance | hr; it; legal | l5 (realised) | on track | 38211.0 | not specified | project dashboard | finance dashboard | 0.45 | 2024-02-02 | 2024-08-02 | 131d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | on track | red | red | yellow | green | yellow | green | 0 | 0 | 11.0 | 0.0 | 0.0 | 9.0 | 11.0 | 11.0 | 20.0 | 20.0 | 20.0 | 11.0 | 11.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2024-02-02 | 2024-07-31 | 0 | 129d | 2024-08-09 | 2025-09-19 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | completed | not specified | it | not specified | not specified | not specified | realize value / close / care period | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 1.306 | not specified | 1.607 | 2024-04-03 | 2025-01-01 | on plan | not specified | 1.0 | on track | 1.0 | 446.0 | 40.0 | 0.55 | 0.0 | 0.0 | 0.45 | 1.0 | 0.0 | previous year | n | 3 | not specified | not specified | 1.0 | p | 63 | not specified | 1.0 | 1.0 | not specified | not specified | not specified | 2024-02-02 | 2024-08-02 | not specified | not specified | [6 empty] | 131d | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | stage 5 - care period | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.45
inventory control & cycle counting: windows pilot + remaining sites | 38533 | not specified | jorge eleta | chris long | project | standalone project | standalone project | bus-na/corp/it | amanda jones | mfg. & supply chain na it | not specified | chris hill | charles sieber | josh bui | christian suarez | kirk kroft | not specified | supply chain | na - ops: supply chain | it | l3 (planned) | on hold | 38533.0 | not specified | project dashboard | finance dashboard | 0.45 | 2024-02-02 | 2024-08-02 | 131d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | on track | red | red | yellow | green | yellow | green | 0 | 0 | 11.0 | 0.0 | 0.0 | 9.0 | 11.0 | 11.0 | 20.0 | 20.0 | 20.0 | 11.0 | 11.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2024-02-02 | 2024-07-31 | 0 | 129d | 2024-08-26 | 2025-10-09 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | canceled | not specified | it | not specified | not specified | not specified | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 1.441326587 | 0.0 | 2.451 | 2023-11-16 | 2026-02-04 | on plan | not specified | 1.0 | on track | 1.0 | 429.0 | 20.0 | 0.55 | 0.0 | 0.0 | 0.45 | 1.0 | 0.0 | previous year | n | 3 | not specified | not specified | 1.0 | p | 64 | not specified | 1.0 | 1.0 | not specified | not specified | not specified | 2024-02-02 | 2024-08-02 | not specified | not specified | [6 empty] | 131d | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.45
inventory control and cycle counting- remaining 12 door sites | 42196 | not specified | jorge eleta | chris long | project | standalone project | standalone project | bus-na/corp/it | amanda jones | mfg. & supply chain na it | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | 42196.0 | not specified | project dashboard | finance dashboard | not specified | 2025-04-28 | 2026-09-11 | 360d | as of 11/20/24: remaining door sites project hasn't started yet. the inventory accuracy program team has 2 out 4 plants remaining to deliver before we can transition to remaining doors. | not specified | not specified | not specified | on track | on track | red | green | red | green | yellow | green | 0 | 0 | 14.0 | 2.0 | 74.0 | 0.0 | 0.0 | 90.0 | 90.0 | 90.0 | 90.0 | 90.0 | 0.0 | 90.0 | 0.0 | 1814221.0 | 1026880.0 | 410641.41 | 222118.16 | 188523.25 | not specified | 121400.0 | 0.0 | 121400.0 | not specified | 532041.41 | 222118.16 | 309923.25 | not specified | -532041.41 | 1592102.84 | 716956.75 | 0.0 | 0.877568300664583 | 0.698189418432534 | 2025-10-27 | 2024-02-02 | 2024-07-31 | 0 | 129d | 2025-08-14 | 2024-11-20 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on-hold | not specified | it | not specified | not specified | not specified | planning | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0.932454 | 0.0 | 1.155 | 2023-06-11 | 2026-02-04 | on plan | not specified | 1.0 | on track | 0.369444444444444 | 76.0 | 343.0 | 0.155555555555556 | 0.0222222222222222 | 0.822222222222222 | 0.0 | 1.0 | 0.0 | 2026 | n | 3 | not specified | not specified | 1.0 | p | 65 | not specified | 1.0 | 1.0 | not specified | not specified | not specified | 2024-02-02 | 2024-08-02 | not specified | not specified | [6 empty] | 131d | -451.0 | -3.44274809160305 | -770.0 | -5.87786259541985 | -229.0 | -1.74809160305344 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified
reduce accessorials with edi 2-way integration (original #15398) | 58179 | implement an edi solution (214/856) that will provide our plants visibility to inbound containers from our vendors and carriers. having this visibility will allow them to plan for timely receipt of the product and avoid $200k in yearly accessorial charges.. | jorge eleta | fabio rivera | project | standalone project | standalone project | bus-na/corp/it | not specified | it na/corporate | not specified | heath webster | not specified | noora mcgee | christian suarez | kirk kroft | not specified | freight & logistics | not specified | not specified | l3 (planned) | on track | 58179.0 | not specified | project dashboard | finance dashboard | 0.29 | 2024-02-19 | 2025-03-12 | 278d | business has decided to put this initiative on hold. moving forward the initiative owner will be working with the plants and buyers on the possibility of using existing reports and dashboards that can be provided by our freight forwarder. | project estimates will be finalized by eow. projected savings has been reviewed and reduced from $900k to $200k/yr. | meet with the business monthly to review current status and requirements moving forward. | not specified | green | on track | red | red | green | green | yellow | red | 0 | 0 | 12.0 | 1.0 | 0.0 | 13.0 | 12.0 | 10.0 | 26.0 | 26.0 | 26.0 | 13.0 | 10.0 | 3.0 | 316000.0 | 200000.0 | 116000.0 | 13929.0 | 5162.0 | 8767.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 13929.0 | 5162.0 | 8767.0 | not specified | 302071.0 | 194838.0 | 107233.0 | 0.955920886075949 | 0.97419 | 0.924422413793103 | 2025-10-27 | 2024-02-19 | 2025-03-12 | 0 | 278d | 2025-09-18 | 2024-12-03 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on-hold | not specified | it | not specified | not specified | not specified | planning | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0.452577 | 0.315575 | 2023-10-17 | 2024-09-30 | on plan | not specified | 1.0 | on track | 1.0 | 41.0 | 330.0 | 0.461538461538462 | 0.0384615384615385 | 0.0 | 0.5 | 1.0 | 0.0 | current year | n | 3 | not specified | not specified | 1.0 | p | 66 | not specified | 1.0 | 1.0 | not specified | not specified | not specified | 2024-02-02 | 2024-08-02 | not specified | not specified | [6 empty] | 131d | -17.0 | -0.129770992366412 | -222.0 | -1.69465648854962 | -147.0 | -1.12213740458015 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.29
iris | 58962 | enhance material planning and replenishment functionality in titan to support material flow and inventory optimization. total savings projected for these enhancements are $4.8m (on-hand inventory reduction). | jorge eleta | christian suarez | project | standalone project | standalone project | bus-na/corp/it | not specified | it mfg. & supply chain na it na/corporate | not specified | ryan russel | chad alterio | emily cochrane | christian suarez | kirk kroft | not specified | supply chain | na - ops: supply chain | it | l3 (planned) | on track | 58962.0 | not specified | project dashboard | finance dashboard | 0.81 | 2024-02-02 | 2025-07-04 | 371d | project is pending l3 wave approval and is ready to submit a cerf then execute the delloite sow once that has approval is granted. target of 7/17 for kick off with delloite. | submitted for l3 wave approval, drafted cerf document | wave approval, cerf approval , sow execution, delloite staffing, project kick off | support following up with approvers and gaining quick approval | green | on track | red | red | red | green | yellow | green | 0 | 0 | 17.0 | 0.0 | 0.0 | 37.0 | 17.0 | 3.0 | 3.0 | 3.0 | 54.0 | 17.0 | 3.0 | 14.0 | 599000.0 | 441000.0 | 158000.0 | 518895.32 | 457187.79 | 61707.53 | not specified | 0.0 | 0.0 | 0.0 | not specified | 518895.32 | 457187.79 | 61707.53 | not specified | 80104.68 | -16187.79 | 96292.47 | 0.133730684474124 | -0.0367070068027211 | 0.609446012658228 | 2025-10-27 | 2024-02-02 | 2025-03-27 | 0 | 300d | 2025-09-18 | 2025-09-16 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | active | not specified | it | not specified | not specified | not specified | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0.0 | 0.499402 | 2024-08-04 | 2025-02-28 | on plan | not specified | 1.0 | on track | 1.0 | 41.0 | 43.0 | 0.314814814814815 | 0.0 | 0.0 | 0.685185185185185 | 0.0555555555555556 | 0.944444444444444 | current year | n | 3 | not specified | not specified | 1.0 | p | 67 | not specified | 1.0 | 1.0 | not specified | not specified | not specified | 2024-02-02 | 2024-08-02 | not specified | not specified | [6 empty] | 131d | 0.0 | 0.0 | -336.0 | -2.56488549618321 | -240.0 | -1.83206106870229 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.81
pluto phase 1 - west coast direct material | 58964 | today we incur higher fees for storing inventory at multiple 3pl warehouse facilities. consolidating all of these into the new “jeld-wen west distribution center” in rialto, ca. will save an estimated $1.1m (re-occurring) | jorge eleta | fabio rivera | project | standalone project | standalone project | bus-na/corp/it | not specified | it mfg. & supply chain na it na/corporate | not specified | fabio rivera | sam graves | justin wilcox | christian suarez | kirk kroft | not specified | supply chain | na - ops: supply chain | it | l3 (planned) | question for offline discussion | 58964.0 | not specified | project dashboard | finance dashboard | 0.66 | 2024-04-01 | 2025-01-23 | 214d | project on track with teams working on finalizing the json file structures. | data mapping work is completed. | teams are working to finalize the interface file structures by 11/1. | not specified | red | on track | red | red | green | red | green | green | 1 | 0 | 28.0 | 0.0 | 0.0 | 13.0 | 28.0 | 21.0 | 0.0 | 0.0 | 41.0 | 28.0 | 21.0 | 7.0 | 669990.0 | 405920.0 | 264070.0 | 543459.0 | 380080.0 | 163379.0 | 84158.0 | 0.0 | 0.0 | 0.0 | 0.0 | 543459.0 | 380080.0 | 163379.0 | 84158.0 | 126531.0 | 25840.0 | 100691.0 | 0.188855057538172 | 0.063657863618447 | 0.381304199644034 | 2025-10-27 | 2024-04-01 | 2025-01-31 | 0 | 220d | 2025-05-13 | 2025-01-08 | not specified | 4 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on-hold | not specified | it | not specified | not specified | not specified | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 1.146 | 0.0 | 0.56077 | 2024-04-19 | 2024-09-11 | past due for l3 | not specified | 1.0 | on track | 1.0 | 169.0 | 294.0 | 0.682926829268293 | 0.0 | 0.0 | 0.317073170731707 | 0.0 | 1.0 | current year | n | 3 | not specified | not specified | 1.0 | p | 68 | not specified | 1.0 | not specified | not specified | not specified | not specified | 2024-02-02 | 2024-08-02 | not specified | not specified | [6 empty] | 131d | -59.0 | -0.450381679389313 | -174.0 | -1.32824427480916 | -83.0 | -0.633587786259542 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.66
risk management information system (rmis) | 13382 | not specified | jorge eleta | fabio rivera | project | standalone project | standalone project | bus-na/corp/it | not specified | it na/corporate | not specified | fabio rivera | joe grammar | kelly beegle | mike crawford (r2r) | m.j. vaidya | not specified | other | support functions: global legal | it | l3 (planned) | on track | 13382.0 | not specified | project dashboard | finance dashboard | 0.88 | 2024-05-20 | 2025-07-07 | 296d | - target for go-live is currently 7/7 instead of 7/17 - progress on integrations is going well. estimated completion of all integrations is 6/4 | - claims data (broadspire) integration is complete - myehs in final testing phase - all data uploaded, including file attachments are complete (jwreportit) - cutover planning has started | - zurich api in process - to be finished 6/4 | not specified | yellow | on track | red | green | red | red | green | green | 1 | 0 | 4.0 | 1.0 | 12.0 | 9.0 | 17.0 | 7.0 | 0.0 | 0.0 | 26.0 | 17.0 | 7.0 | 10.0 | 1636857.0 | 445688.0 | 1191169.0 | 516429.0 | 139639.0 | 376790.0 | 0.0 | 561220.0 | 0.0 | 561220.0 | 0.0 | 1077649.0 | 139639.0 | 938010.0 | 0.0 | 559208.0 | 306049.0 | 253159.0 | 0.341635219203632 | 0.686688894473264 | 0.212529876113297 | 2025-10-27 | 2024-02-02 | 2024-07-31 | 0 | 129d | 2025-05-14 | 2025-10-16 | not specified | 1 | not specified | not specified | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | active | not specified | it | not specified | not specified | not specified | implementation / execution | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | -0.108 | not specified | 0.63 | 2024-05-17 | 2025-04-29 | on plan | not specified | 1.0 | on track | 1.0 | 168.0 | 13.0 | 0.153846153846154 | 0.0384615384615385 | 0.461538461538462 | 0.346153846153846 | 0.0 | 1.0 | current year | n | 3 | not specified | not specified | 1.0 | p | 70 | not specified | 1.0 | 1.0 | not specified | not specified | not specified | 2024-02-02 | 2024-08-02 | not specified | not specified | [6 empty] | 131d | -108.0 | -0.824427480916031 | -339.0 | -2.58778625954198 | -165.0 | -1.25954198473282 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | stage 3 - implementation | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.88
employee relief fund / standard for employee fundraising | 16312 | not specified | jorge eleta | julie bridges | project | standalone project | standalone project | bus-na/corp/it | not specified | not specified | not specified | julie bridges | not specified | melissa farrington | cliff jensen | m.j. vaidya | not specified | sg&a | support functions: c&c | hr; it; legal | l2 (validated) | some issues | 16312.0 | not specified | project dashboard | finance dashboard | 0.45 | 2024-02-02 | 2024-08-02 | 131d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | on track | red | red | yellow | green | yellow | green | 0 | 0 | 11.0 | 0.0 | 0.0 | 9.0 | 11.0 | 11.0 | 20.0 | 20.0 | 20.0 | 11.0 | 11.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2024-02-02 | 2024-07-31 | 0 | 129d | 2024-08-14 | 2024-11-01 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | active | not specified | it | not specified | not specified | not specified | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | -0.037 | not specified | 0.135 | 2023-10-19 | 2024-03-09 | on plan | not specified | 1.0 | on track | 1.0 | 441.0 | 362.0 | 0.55 | 0.0 | 0.0 | 0.45 | 1.0 | 0.0 | previous year | n | 3 | not specified | not specified | 1.0 | p | 71 | not specified | 1.0 | 1.0 | not specified | not specified | not specified | 2024-02-02 | 2024-08-02 | not specified | not specified | [6 empty] | 131d | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.45
inside sales / quote lead nurture | 31670 | not specified | jorge eleta | jeff stetson | project | standalone project | standalone project | bus-na/corp/it | not specified | na it | not specified | jeff stetson | not specified | loree shano | terry davis | tyce deal | not specified | growth | na - windows: commercial - sales | hr; it | l2 (validated) | on track | 31670.0 | not specified | project dashboard | finance dashboard | 0.45 | 2024-02-02 | 2024-08-02 | 131d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | on track | red | red | yellow | green | yellow | green | 0 | 0 | 11.0 | 0.0 | 0.0 | 9.0 | 11.0 | 11.0 | 20.0 | 20.0 | 20.0 | 11.0 | 11.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2024-02-02 | 2024-07-31 | 0 | 129d | 2024-08-21 | 2024-11-05 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | active | not specified | it | not specified | not specified | not specified | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 13.572 | not specified | 0.05 | 2023-12-10 | 2024-01-05 | past due for l4 | not specified | 1.0 | on track | 1.0 | 434.0 | 358.0 | 0.55 | 0.0 | 0.0 | 0.45 | 1.0 | 0.0 | previous year | n | 3 | not specified | not specified | 1.0 | p | 72 | not specified | 1.0 | not specified | not specified | not specified | not specified | 2024-02-02 | 2024-08-02 | not specified | not specified | [6 empty] | 131d | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.45
merge edi vans | 32069 | not specified | jorge eleta | max kane | project | standalone project | standalone project | it-na/corp | not specified | it na/corporate | not specified | max kane | not specified | mike doescher | mike doescher | kirk kroft | not specified | sg&a | support functions: global it - north america | it | l3 (planned) | on hold | 32069.0 | not specified | project dashboard | finance dashboard | 0.45 | 2024-02-02 | 2024-08-02 | 131d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | on track | red | red | yellow | green | yellow | green | 0 | 0 | 11.0 | 0.0 | 0.0 | 9.0 | 11.0 | 11.0 | 20.0 | 20.0 | 20.0 | 11.0 | 11.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2024-02-02 | 2024-07-31 | 0 | 129d | 2024-08-21 | 2025-09-18 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | canceled | not specified | it | not specified | not specified | not specified | planning | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0.0316 | not specified | 0.02 | 2023-10-16 | 2024-07-10 | on plan | not specified | 1.0 | on track | 1.0 | 434.0 | 41.0 | 0.55 | 0.0 | 0.0 | 0.45 | 1.0 | 0.0 | previous year | n | 3 | not specified | not specified | 1.0 | p | 73 | not specified | 1.0 | 1.0 | not specified | not specified | not specified | 2024-02-02 | 2024-08-02 | not specified | not specified | [6 empty] | 131d | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.45
establish a center of excellence (coe) for esg related questionnaires | 32792 | not specified | jorge eleta | chris hill | project | standalone project | standalone project | bus-na/corp/it | not specified | it na/corporate | not specified | chris hill | not specified | carolyn payne | mike crawford (r2r) | m.j. vaidya | not specified | sg&a | support functions: global legal | it | l4 (executed) | on track | 32792.0 | not specified | project dashboard | finance dashboard | 0.45 | 2024-02-02 | 2024-08-02 | 131d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail | blue | on track | red | red | yellow | green | yellow | green | 0 | 0 | 11.0 | 0.0 | 0.0 | 9.0 | 11.0 | 11.0 | 20.0 | 20.0 | 20.0 | 11.0 | 11.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2024-02-02 | 2024-07-31 | 0 | 129d | 2024-08-21 | 2025-09-18 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | completed | not specified | it | not specified | not specified | not specified | realize value / close / care period | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | -0.015 | not specified | 0.05 | 2023-10-17 | 2024-03-06 | due soon for l4 | not specified | 1.0 | on track | 1.0 | 434.0 | 41.0 | 0.55 | 0.0 | 0.0 | 0.45 | 1.0 | 0.0 | previous year | n | 3 | not specified | not specified | 1.0 | p | 74 | not specified | 1.0 | 1.0 | not specified | not specified | not specified | 2024-02-02 | 2024-08-02 | not specified | not specified | [6 empty] | 131d | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | stage 5 - care period | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.45
automate invention disclosure form (idf) process | 32797 | not specified | jorge eleta | chris hill | project | standalone project | standalone project | bus-na/corp/it | not specified | it na/corporate | not specified | chris hill | not specified | jan morton | mike crawford (r2r) | m.j. vaidya | not specified | other | support functions: global legal | it | l3 (planned) | on hold | 32797.0 | not specified | project dashboard | finance dashboard | 0.45 | 2024-02-02 | 2024-08-02 | 131d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | on track | red | red | yellow | green | yellow | green | 0 | 0 | 11.0 | 0.0 | 0.0 | 9.0 | 11.0 | 11.0 | 20.0 | 20.0 | 20.0 | 11.0 | 11.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2024-02-02 | 2024-07-31 | 0 | 129d | 2024-08-21 | 2025-09-18 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | canceled | not specified | it | not specified | not specified | not specified | planning | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | -0.0042 | not specified | 0.008 | 2023-10-18 | 2024-07-30 | on plan | not specified | 1.0 | on track | 1.0 | 434.0 | 41.0 | 0.55 | 0.0 | 0.0 | 0.45 | 1.0 | 0.0 | previous year | n | 3 | not specified | not specified | 1.0 | p | 75 | not specified | 1.0 | 1.0 | not specified | not specified | not specified | 2024-02-02 | 2024-08-02 | not specified | not specified | [6 empty] | 131d | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.45
rides - ecommerce dashboards | 40463 | implementation of microsoft azure platform for d&a and systems integration to enable improved data integration and analytics. | jorge eleta | tamara johnson | project | standalone project | standalone project | it-na/corp | not specified | it na/corporate | not specified | tamara johnson | not specified | tom mender | tom mender | tyce deal | not specified | sg&a | na - doors & dist: commercial - product & pricing | it | submitted for l5 approval | on track | 40463.0 | not specified | project dashboard | finance dashboard | 0.99 | 2023-01-13 | 2024-12-13 | 501d | this project is completed. | not specified | not specified | not specified | blue | on track | red | red | red | green | green | green | 0 | 0 | 2.0 | 0.0 | 0.0 | 5.0 | 2.0 | 2.0 | 0.0 | 0.0 | 7.0 | 2.0 | 2.0 | 0.0 | 0.0 | 0.0 | 0.0 | 1212582.5 | 1018613.0 | 193969.5 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 1212582.5 | 1018613.0 | 193969.5 | 0.0 | -1212582.5 | -1018613.0 | -193969.5 | 0.0 | 0.0 | 0 | 2025-10-27 | 2023-01-13 | 2024-08-30 | 0 | 426d | 2025-01-23 | 2025-10-16 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | completed | not specified | it | not specified | not specified | not specified | realize value / close / care period | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 3.7 | not specified | 1.375 | 2023-10-16 | 2024-07-29 | on plan | not specified | 1.0 | on track | 1.0 | 279.0 | 13.0 | 0.285714285714286 | 0.0 | 0.0 | 0.714285714285714 | 0.0 | 1.0 | previous year | n | 3 | not specified | not specified | 1.0 | p | 76 | not specified | 1.0 | 1.0 | not specified | not specified | not specified | 2024-02-02 | 2024-08-02 | not specified | not specified | [6 empty] | 131d | 385.0 | 2.93893129770992 | -133.0 | -1.01526717557252 | -370.0 | -2.82442748091603 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | stage 5 - care period | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.99
titan jboss upgrade | 47877 | not specified | jorge eleta | jamal mebane | project | standalone project | standalone project | it-na/corp | not specified | not specified | not specified | jamal mebane | not specified | kurt dimos | shannon messing | m.j. vaidya | not specified | sg&a | support functions: global it - north america | it | l3 (planned) | on hold | 47877.0 | not specified | project dashboard | finance dashboard | 0.45 | 2024-02-02 | 2024-08-02 | 131d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | on track | red | red | yellow | green | yellow | green | 0 | 0 | 11.0 | 0.0 | 0.0 | 9.0 | 11.0 | 11.0 | 20.0 | 20.0 | 20.0 | 11.0 | 11.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2024-02-02 | 2024-07-31 | 0 | 129d | 2024-08-26 | 2025-02-26 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on-hold | not specified | it | not specified | not specified | not specified | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 2023-10-16 | 2024-06-09 | on plan | not specified | 1.0 | on track | 1.0 | 429.0 | 245.0 | 0.55 | 0.0 | 0.0 | 0.45 | 1.0 | 0.0 | previous year | n | 3 | not specified | not specified | 1.0 | p | 77 | not specified | 1.0 | 1.0 | not specified | not specified | not specified | 2024-02-02 | 2024-08-02 | not specified | not specified | [6 empty] | 131d | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.45
hr transformation program | 38632 | not specified | shannon messing | sue murphy | program | 38632 | 38632: hr transformation program | not specified | not specified | it it-eu | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | 38632.0 | not specified | program dashboard | finance dashboard | 0.301943493150685 | 2023-08-13 | 2027-06-30 | 1013d | add the high level status of the program in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | on track | red | red | red | yellow | green | 0 | 0 | 17 | 15.0 | 8.0 | 129.0 | 27.0 | 28.0 | 41.0 | 29.0 | 162.0 | 33.0 | 13.0 | 20.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | 2024-09-05 | 2025-06-26 |  | 211d | 1.75824e12d | 2025-10-29 |  | not specified | false | not specified | not specified | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | active | not specified | other | not specified | not specified | global | see project details | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | 1.0 | on track | 0.570582428430405 | 0.0 | on track | 0.454545454545455 | 0.242424242424242 | 3.90909090909091 | 0.818181818181818 | 0.878787878787879 | 0.121212121212121 | 2027 | not specified | 2 | not specified | not specified | not specified | pg | 79 | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | [6 empty] | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | improved performance | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  | 0 |  | 0.30194
hr transformation agile project | p-0095 | not specified | shannon messing | sue murphy | project | 38632 | 38632: hr transformation program | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | finance dashboard | 0.38 | 2024-02-02 | 2024-09-05 | 155d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | on track | red | green | red | yellow | green | 3 | 1 | 12 | 0.0 | 0.0 | 6.0 | 12.0 | 12.0 | 18.0 | 18.0 | 18.0 | 12.0 | 12.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 03/10/25 | 2024-02-02 | 2024-09-05 |  | 155d | 1.728864e12d | 2024-06-07 |  | 129.0 | true | not specified | #ref | #ref | #ref | #ref | #ref | #ref | #ref | #ref | #ref | #ref | #ref | #ref | #ref | #ref | #ref | #ref | #ref | #ref | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | other | not specified | not specified | global | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | 1.0 | on track | 1.0 | 509.0 | on track | 0.0 | 0.0 | 0.5 | 1.0 | 1.5 | -0.5 | previous year | not specified | 3 | not specified | not specified | 1.0 | p | 95 | 1.0 | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | [6 empty] | not specified | not specified | not specified | not specified | not specified | -155.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  | 3 | 100 | 0.38
hr transformation project it workstream | p-0080 | it enablement of the hr transformation and shared services initiative. provision of telephone and kiosk systems, solutions and equipment. | shannon messing | bright ayalingo | project | 38632 | 38632: hr transformation program | not specified | not specified | hr transformation it na/corporate | not specified | bright ayalingo | not specified | not specified | bright ayalingo | mj vaidya | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.29 | 2023-08-13 | 2027-06-30 | 1013d | w26: on track, no action enhancements ~ genesis requirements in progress ~ migration of kiosk to intune (device management ) platform in progress r2 needs: ~ us: remaining kiosk/phone delivery: 100% of kiosk setup ~ us phones: shipped - 100%. phone setup in progress ~ eu: r2 sites kiosk complete. estonia/switzerland/sweden ~ eu phone number setup - switzerland, germany, sweden phone number - complete. - estonia, austria - complete ~ audio recordings prompt, new queues, languages, subsets - complete r2 and beyond additions: ~ call metrics/queues/teams calling features ~ evaluation of genesis call solution for hrss - meeting scheduled with genesis team 6/17 1. have an update from verizon meeting later this week to review with verizon and genesis team ~ myapps conversion - all r2 sites on myapps ~ intune project restarted - kiosk will be moved by site to intune for device management | w26: r2 hypercare. kiosk: ~ made progress on identifying the right resources for eu phone number setup. setup in progress ~ feedback on teams queues calling features | w27: ~ continue to support all sites with kiosk setups ~ continue to setup r 2.5 kiosk for eu ~ us remaining kiosk/phone delivery & setup ~ continue to confirm r 2.5 sites kiosk readiness ~ evaluation of genesis call solution >currently only used in north america . > genesis team evaluation checking with verizon if this can be leveraged for eu as well | support required: n/a impact: n/a ptg: | green | up | red | red | red | red | yellow | green | 1 | 5 | 17.0 | 15.0 | 2.0 | 117.0 | 15.0 | 10.0 | 23.0 | 11.0 | 150.0 | 33.0 | 13.0 | 20.0 | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-28 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-09-19 | 2025-06-30 | not specified | 8 | not specified | not specified | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | usd | it | not specified | not specified | global | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | 1.0 | not specified | on track | 0.570582428430405 | 40.0 | 121.0 | 0.113333333333333 | 0.1 | 0.0133333333333333 | 0.78 | 0.153333333333333 | 0.846666666666667 | 2027 | not specified | 3 | not specified | not specified | not specified | p | 150 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-10-29 | 2026-01-27 | not specified | not specified | 2023-08-13 | 2023-10-08 | 2024-02-29 | 2025-03-17 | 2026-06-30 | 2027-06-30 | not specified | 808.0 | not specified | -519.0 | not specified | -1013.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | hr transformation project it workstream | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.29
ibp supply | 23727 | not specified | jorge eleta | chad alterio | project | standalone project | standalone project | bus-na/corp/it | not specified | mfg. & supply chain na it | not specified | chad alterio | not specified | steve cooney | christian suarez | kirk kroft | not specified | supply chain | na - ops: ibp | it | l2 (validated) | cancelled | 23727.0 | not specified | project dashboard | finance dashboard | 0.45 | 2024-02-02 | 2024-08-02 | 131d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | on track | red | red | yellow | green | yellow | green | 0 | 0 | 11.0 | 0.0 | 0.0 | 9.0 | 11.0 | 11.0 | 20.0 | 20.0 | 20.0 | 11.0 | 11.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2024-02-02 | 2024-07-31 | 0 | 129d | 2024-08-21 | 2025-02-26 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | canceled | not specified | it | not specified | not specified | not specified | planning | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 2024-06-28 | 2025-02-04 | cancelled | not specified | 1.0 | on track | 1.0 | 434.0 | 245.0 | 0.55 | 0.0 | 0.0 | 0.45 | 1.0 | 0.0 | previous year | n | 3 | not specified | not specified | 1.0 | p | 78 | not specified | 1.0 | not specified | not specified | not specified | not specified |  |  | not specified | not specified | [6 empty] | not specified | not specified | not specified | not specified | not specified | -131.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.45
managed transportation - rxo - inbound freight | 15530 | not specified | jorge eleta | ryan russel | project | standalone project | standalone project | bus-na/corp/it | amanda jones | na it | not specified | ryan russel | rachael gabbard | lino santinelli | mike schipper | kirk kroft | not specified | freight & logistics | na - ops: freight / logistics | it | l5 (realised) | on track | 15530.0 | not specified | project dashboard | finance dashboard | 0.45 | 2024-02-02 | 2024-08-02 | 131d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | on track | red | red | yellow | green | yellow | green | 0 | 0 | 11.0 | 0.0 | 0.0 | 9.0 | 11.0 | 11.0 | 20.0 | 20.0 | 20.0 | 11.0 | 11.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-28 | 2024-02-02 | 2024-07-31 | 0 | 129d | 2024-08-14 | 2024-11-01 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | active | not specified | it | not specified | not specified | not specified | realize value / close / care period | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 1.772961817 | not specified | not specified | 2023-10-13 | 2024-10-04 | executed | not specified | 1.0 | on track | 1.0 | 441.0 | 362.0 | 0.55 | 0.0 | 0.0 | 0.45 | 1.0 | 0.0 | previous year | n | 3 | not specified | not specified | 1.0 | p | 81 | not specified | 1.0 | not specified | not specified | not specified | not specified |  |  | not specified | not specified | [6 empty] | not specified | not specified | not specified | not specified | not specified | -131.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | stage 5 - care period | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.45
infrastructure - legacy windows server os upgrades | 23998 | not specified | jorge eleta | brad duffey | project | standalone project | standalone project | it-infra/service | not specified | cybersecurity it infrastructure | not specified | brad duffey | not specified | gordon greenland | gordon greenland | m.j. vaidya | not specified | sg&a | support functions: global it - infrastructure / service desk | it | l3 (planned) | on track | 23998.0 | not specified | project dashboard | finance dashboard | 0.99 | 2024-01-09 | 2025-10-16 | 463d | project has completed, but competing priorities have kept us from closing out/l4. brad is working towards completing all closeout documentation and the final stakeholder meeting for closeout. current l4 status slated for 18 september. | completed | closeout on 18 sept. | not specified | green | on track | red | green | red | green | green | green | 0 | 0 | 0.0 | 0.0 | 1.0 | 9.0 | 1.0 | 0.0 | 0.0 | 0.0 | 10.0 | 1.0 | 0.0 | 1.0 | 35000.0 | 0.0 | 35000.0 | 26474.0 | 0.0 | 26474.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 26474.0 | 0.0 | 26474.0 | not specified | 8526.0 | 0.0 | 8526.0 | 0.2436 | 0.0 | 0.2436 | 2025-10-27 | 2024-01-09 | 2025-02-20 | 0 | 293d | 2025-09-19 | 2025-08-25 | not specified | 1 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | active | not specified | it | not specified | not specified | not specified | realize value / close / care period | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0.0 | 2023-10-19 | 2024-12-20 | on plan | not specified | 1.0 | on track | 1.0 | 40.0 | 65.0 | 0.0 | 0.0 | 0.1 | 0.9 | 0.0 | 1.0 | current year | n | 3 | not specified | not specified | 1.0 | p | 82 | not specified | 1.0 | 1.0 | not specified | not specified | not specified |  |  | not specified | not specified | [6 empty] | not specified | not specified | not specified | not specified | not specified | -463.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | stage 5 - care period | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.99
cybersecurity - 3rd party risk management and external benchmarking | 32782 | not specified | jorge eleta | brad duffey | project | standalone project | standalone project | it-cyber | not specified | not specified | not specified | brad duffey | not specified | m.j. vaidya | ravi ramaraj | m.j. vaidya | not specified | sg&a | support functions: global it - cyber | it | l5 (realised) | on track | 32782.0 | not specified | project dashboard | finance dashboard | 1.0 | 2023-09-23 | 2024-03-29 | 135d | project completed | project completed | project completed | no support needed at this time | green | on track | green | blue | green | green | green | green | 0 | 0 | 0.0 | 0.0 | 0.0 | 2.0 | 0.0 | 0.0 | 0.0 | 0.0 | 2.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 77475.0 | 0.0 | 77475.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 77475.0 | 0.0 | 77475.0 | 0.0 | -77475.0 | 0.0 | -77475.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2023-09-23 | 2024-03-29 | 0 | 135d | 2024-09-10 | 2024-11-05 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | completed | not specified | it | not specified | not specified | not specified | realize value / close / care period | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | -0.1 | not specified | 0.1 | 2023-10-17 | 2024-04-18 | executed | not specified | 1.0 | on track | 1.0 | 414.0 | 358.0 | 0.0 | 0.0 | 0.0 | 1.0 | 0.0 | 1.0 | previous year | n | 3 | not specified | not specified | 1.0 | p | 83 | not specified | 1.0 | not specified | not specified | not specified | not specified |  |  | not specified | not specified | [6 empty] | not specified | not specified | not specified | not specified | not specified | -135.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | stage 5 - care period | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 1
lead information governance (ig) initiative; implementing policies, processes, and related tools | 32794 | not specified | jorge eleta | miles romello | project | standalone project | standalone project | bus-na/corp/it | not specified | cybersecurity it | not specified | not specified | not specified | danielle darling | ravi ramaraj | m.j. vaidya | not specified | sg&a | support functions: global legal | it | l3 (planned) | on track | 32794.0 | not specified | project dashboard | finance dashboard | 0.38 | 2023-10-09 | 2025-12-31 | 583d | program scope being defined | policies defined. | working towards policy approvals. | no support needed. | green | on track | red | red | green | green | green | red | 0 | 0 | 3.0 | 0.0 | 2.0 | 2.0 | 4.0 | 2.0 | 0.0 | 0.0 | 7.0 | 5.0 | 2.0 | 3.0 | 800000.0 | 300000.0 | 500000.0 | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 800000.0 | 300000.0 | 500000.0 | 1.0 | 1.0 | 1 | 2025-10-27 | 2023-10-09 | 2025-12-31 | 0 | 583d | 2025-01-24 | 2025-09-18 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | canceled | not specified | it | not specified | not specified | global | planning | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0.3 | not specified | 0.3 | 2023-10-24 | 2025-12-31 | on plan | not specified | 1.0 | on track | 0.922813036020583 | 278.0 | 41.0 | 0.428571428571429 | 0.0 | 0.285714285714286 | 0.285714285714286 | 0.0 | 1.0 | current year | n | 3 | not specified | not specified | 1.0 | p | 84 | not specified | 1.0 | 1.0 | not specified | not specified | not specified |  |  | not specified | not specified | [6 empty] | not specified | not specified | not specified | not specified | not specified | -583.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.38
datacenter colo | 32865 | reduce risk for klamath assets with improved resiliency by relocating to a new collocation datacenter and migrating all non-klamath specific workloads. leverage hosted vs cloud for savings use cases. aligns with sdwan. - virtual machines in klamath falls data center to new colo datacenter - physical machines that can be virtualized (re-platformed) - virtual machines that require an os uplift (server 2019 or server 2022) | jorge eleta | jamal mebane | project | standalone project | standalone project | it-infra/service | not specified | it infrastructure na it | not specified | jamal mebane | not specified | gordon greenland | sailaja kandala | m.j. vaidya | not specified | sg&a | support functions: global it - infrastructure / service desk | not specified | l3 (planned) | some issues | 32865.0 | not specified | project dashboard | finance dashboard | 0.98 | 2023-09-01 | 2025-10-29 | 564d | • project status remains green as we work to close out project • all migration complete • environment cleanup complete | • all migration complete • environment cleanup complete | • finalizing operationalization plan documentation and lessons learned • project close | not specified | green | angle up | red | green | red | green | yellow | red | 0 | 0 | 1.0 | 1.0 | 0.0 | 25.0 | 1.0 | 2.0 | 2.0 | 2.0 | 27.0 | 2.0 | 2.0 | 0.0 | 963356.0 | 852998.0 | 110358.0 | 1107383.590534 | 907808.500534 | 199575.09 | not specified | 259597.0 | 0.0 | 259597.0 | not specified | 1366980.590534 | 907808.500534 | 459172.09 | not specified | -403624.590534 | -54810.500534 | -348814.09 | -0.418977605925535 | -0.0642563060335429 | -3.16075037604886 | 2025-10-28 | 2023-09-01 | 2025-05-09 | 0 | 441d | 2025-10-28 | 2025-10-13 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | active | not specified | it | not specified | not specified | not specified | realize value / close / care period | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0.056 | not specified | 0.853 | 2023-10-16 | 2024-08-30 | on plan | not specified | 1.0 | on track | 1.0 | 1.0 | 16.0 | 0.037037037037037 | 0.037037037037037 | 0.0 | 0.925925925925926 | 0.0740740740740741 | 0.925925925925926 | current year | n | 3 | not specified | not specified | 1.0 | p | 85 | not specified | 1.0 | 1.0 | not specified | not specified | not specified |  |  | not specified | not specified | [6 empty] | not specified | not specified | not specified | not specified | not specified | -564.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | stage 5 - care period | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.98
replace cisco uccx contact center | 32868 | moving away from our current cisco uccx contact center to a more robust, reliable and cost savings solution with integration into salesforce. implementing a single tool that provides us with these options and better call quality and reliability at a cost savings and addresses the primary concerns of poor customer call quality poor agent call quality | jorge eleta | jamal mebane | project | standalone project | standalone project | bus-na/corp/it | not specified | it infrastructure na it | not specified | jamal mebane | not specified | andrew hoel | sheri schrier | tyce deal | not specified | other | na - ops: customer service | it; legal | l5 (realised) | on track | 32868.0 | not specified | project dashboard | finance dashboard | 0.98 | 2024-04-08 | 2025-05-29 | 299d | • completed the february kpi review. overall good results on the call related kpis • addressed post go live business risks and submitted for l4 approval | • completed the february kpi review. overall good results on the call related kpis • addressed post go live business risks and submitted for l4 approval | • load february kpis into wave (pending l4 workflow approvals) • march kpi review | not specified | blue | on track | green | green | green | green | yellow | green | 0 | 0 | 5.0 | 0.0 | 0.0 | 95.0 | 5.0 | 5.0 | 1.0 | 1.0 | 100.0 | 5.0 | 5.0 | 0.0 | 0.0 | 0.0 | 0.0 | 1435624.1 | 389247.0 | 1046377.1 | 115594.0 | 2805922.36 | 0.0 | 2805922.36 | 0.0 | 4241546.46 | 389247.0 | 3852299.46 | 115594.0 | -4241546.46 | -389247.0 | -3852299.46 | 0.0 | 0.0 | 0 | 2025-10-27 | 2024-04-08 | 2025-05-29 | 0 | 299d | 2025-06-23 | 2025-10-16 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | completed | not specified | it | not specified | not specified | not specified | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0.4 | not specified | not specified | 2024-10-19 | 2025-01-16 | on plan | not specified | 1.0 | on track | 1.0 | 128.0 | 13.0 | 0.05 | 0.0 | 0.0 | 0.95 | 0.01 | 0.99 | current year | n | 3 | not specified | not specified | 1.0 | p | 86 | not specified | 1.0 | not specified | not specified | not specified | not specified |  |  | not specified | not specified | [6 empty] | not specified | not specified | not specified | not specified | not specified | -299.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.98
eliminate non-voip phone costs | 32876 | accelerate the program to eliminate non-voip phone systems across sites. these legacy phones generally have higher costs and are more difficult to support. the savings reflects the lower per line cost. we can realize this savings as we cancel the legacy services and add to our standard voip plans. | jorge eleta | jamal mebane | project | standalone project | standalone project | it-infra/service | not specified | it infrastructure na it | not specified | jamal mebane | jamal mebane | m.j. vaidya | gordon greenland | m.j. vaidya | not specified | sg&a | support functions: global it - infrastructure / service desk | it | l3 (planned) | some issues | 32876.0 | not specified | project dashboard | finance dashboard | 0.83 | 2024-07-01 | 2025-12-12 | 380d | • yellow status due to overall schedule and extended timeline. • cost savings - unable to validate savings beyond march and are working to identify source • site surveys at 86% completion • installations at 81% completion • 7 sites remaining - (5) pending pre-determination of lines, wan connectivity & site survey; (2) pending wan connectivity as pre-requisite for implementation | • site surveys at 86% completion • installations at 81% completion • bend completed. no action required. remaining pots lines are being converted to cellular by the fire alarm company. | • surveys: 5 site pending pre-determination of lines, wan connectivity & site survey • installations: 2 sites total pending installation; working to complete wan connectivity as a pre-requisite to implementation • re-dispatch survey: 0 sites | not specified | yellow | on track | red | green | red | green | green | red | 1 | 0 | 0.0 | 0.0 | 7.0 | 8.0 | 1.0 | 0.0 | 0.0 | 0.0 | 15.0 | 7.0 | 5.0 | 2.0 | 89500.0 | 89500.0 | 0.0 | 14909.0 | 1157.0 | 13752.0 | not specified | 1068.0 | 0.0 | 1068.0 | not specified | 15977.0 | 1157.0 | 14820.0 | not specified | 73523.0 | 88343.0 | -14820.0 | 0.821486033519553 | 0.987072625698324 | 0 | 2025-10-28 | 2024-02-02 | 2024-07-31 | 0 | 129d | 2025-10-08 | 2025-10-27 | not specified | 1 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | active | not specified | it | not specified | not specified | not specified | implementation / execution | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0.37408 | not specified | 0.0535 | 2023-10-16 | 2024-07-16 | on plan | not specified | 1.0 | on track | 0.915789473684211 | 21.0 | 2.0 | 0.0 | 0.0 | 0.466666666666667 | 0.533333333333333 | 0.0 | 1.0 | current year | n | 3 | not specified | not specified | 1.0 | p | 87 | not specified | 1.0 | 1.0 | not specified | not specified | not specified |  |  | not specified | not specified | [6 empty] | not specified | not specified | not specified | not specified | not specified | -380.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | stage 3 - implementation | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.83
cybersecurity - implement email dmarc | 37797 | not specified | jorge eleta | brad duffey | project | standalone project | standalone project | it-cyber | not specified | not specified | not specified | brad duffey | not specified | miles romello | miles romello | m.j. vaidya | not specified | sg&a | support functions: global it - cyber | it | l5 (realised) | on track | 37797.0 | not specified | project dashboard | finance dashboard | 1.0 | 2024-01-30 | 2024-10-31 | 198d | l4/l5 completed, closing project | l4/l5 completed, closing project | l4/l5 completed, closing project | not specified | green | on track | yellow | blue | yellow | green | green | green | 0 | 0 | 0.0 | 0.0 | 0.0 | 10.0 | 0.0 | 0.0 | 0.0 | 0.0 | 10.0 | 0.0 | 0.0 | 0.0 | 37760.0 | 0.0 | 37760.0 | 27628.0 | 0.0 | 27628.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 27628.0 | 0.0 | 27628.0 | not specified | 10132.0 | 0.0 | 10132.0 | 0.268326271186441 | 0.0 | 0.268326271186441 | 2025-10-27 | 2024-01-30 | 2024-10-24 | 0 | 193d | 2024-10-31 | 2025-09-22 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | completed | not specified | it | not specified | not specified | not specified | realize value / close / care period | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0.012 | 2023-10-17 | 2024-10-25 | on plan | not specified | 1.0 | on track | 1.0 | 363.0 | 37.0 | 0.0 | 0.0 | 0.0 | 1.0 | 0.0 | 1.0 | previous year | n | 3 | not specified | not specified | 1.0 | p | 90 | not specified | 1.0 | 1.0 | not specified | not specified | not specified |  |  | not specified | not specified | [6 empty] | not specified | not specified | not specified | not specified | not specified | -198.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | stage 5 - care period | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 1
enterprise backup solution (rubrik) - additional eu sites | 51127 | not specified | jorge eleta | ben hamnett | project | standalone project | standalone project | it-eu | not specified | it it-eu | not specified | ben hamnett | not specified | m.j. vaidya | rachael horton-farmer | rachael horton-farmer | not specified | sg&a | support functions: global it - europe | it | l5 (realised) | on track | 51127.0 | not specified | project dashboard | finance dashboard | 1.0 | 2023-01-02 | 2024-09-24 | 452d | w37: project agreed to close, moved status in wave | w37: closure | not specified | complete | blue | on track | green | blue | green | green | green | green | 0 | 0 | 0.0 | 0.0 | 0.0 | 27.0 | 0.0 | 0.0 | 0.0 | 0.0 | 27.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2023-01-02 | 2024-09-24 | 0 | 452d | 2024-09-26 | 2024-11-05 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | completed | not specified | it | not specified | not specified | eu | realize value / close / care period | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0.54279 | 2024-03-29 | 2024-11-22 | on plan | not specified | 1.0 | on track | 1.0 | 398.0 | 358.0 | 0.0 | 0.0 | 0.0 | 1.0 | 0.0 | 1.0 | previous year | n | 3 | not specified | not specified | 1.0 | p | 91 | not specified | 1.0 | 1.0 | not specified | not specified | not specified |  |  | not specified | not specified | [6 empty] | not specified | not specified | not specified | not specified | not specified | -452.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | stage 5 - care period | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 1
security upgrade - workstation update to windows 11 | 52356 | update all end user laptops and desktops to latest windows os and deploy a standard process to keep systems current (updates and patching). | jorge eleta | jamal mebane | project | standalone project | standalone project | it-infra/service | not specified | it infrastructure | not specified | jamal mebane | not specified | m.j. vaidya | gordon greenland | m.j. vaidya | not specified | sg&a | support functions: global it - infrastructure / service desk | it | l3 (planned) | on track | 52356.0 | not specified | project dashboard | finance dashboard | 0.96 | 2024-01-22 | 2025-11-27 | 484d | • overall status green. we are nearing the completion of deployments to all windows 11 eligible devices. • validated list of devices that cannot be upgraded for separate remediation opportunities. | • pushed to group 4 na batch 12 (bend-boyd + denver) and eu bach 8 (users from eauze + solihull + sheffield + penrith) on 9/30 • validated list of devices that cannot be upgraded for separate remediation opportunities. • disabled 6,600 machines in ad that have not reported into the jw network for 365 days | • preparing for upcoming deployment of group 4 na batch 13 (oceanside + kent) and eu batch 9 (finland + latvia + norway + estonia) on 9/31 • reviewing opportunities to implement risk-based strategy to auto disable devices based on inactivity threshold | not specified | green | on track | red | green | yellow | red | yellow | red | 1 | 0 | 0.0 | 0.0 | 6.0 | 234.0 | 0.0 | 0.0 | 15.0 | 15.0 | 240.0 | 6.0 | 3.0 | 3.0 | 258000.0 | 168000.0 | 90000.0 | 285970.5 | 222690.5 | 63280.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 285970.5 | 222690.5 | 63280.0 | not specified | -27970.5 | -54690.5 | 26720.0 | -0.108412790697674 | -0.325538690476191 | 0.296888888888889 | 2025-10-28 | 2024-01-22 | 2025-09-26 | 0 | 440d | 2025-10-28 | 2025-10-16 | not specified | 2 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | active | not specified | it | not specified | not specified | not specified | implementation / execution | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0.013 | not specified | 0.05 | 2024-01-04 | 2024-07-24 | on plan | not specified | 1.0 | on track | 0.956611570247934 | 1.0 | 13.0 | 0.0 | 0.0 | 0.025 | 0.975 | 0.0625 | 0.9375 | current year | n | 3 | not specified | not specified | 1.0 | p | 92 | not specified | 1.0 | 1.0 | not specified | not specified | not specified |  |  | not specified | not specified | [6 empty] | not specified | not specified | not specified | not specified | not specified | -484.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | stage 3 - implementation | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.96
cybersecurity - next gen firewall implementation | 64395 | not specified | jorge eleta | brad duffey | project | standalone project | standalone project | it-cyber | not specified | cybersecurity it | not specified | brad duffey | not specified | m.j. vaidya | miles romello | m.j. vaidya | not specified | other | support functions: global it - cyber | it | l3 (planned) | on track | 64395.0 | not specified | project dashboard | finance dashboard | 0.59 | 2024-05-01 | 2026-03-27 | 498d | p2g: replace rif'd resources with senior network engineers to pick up slack. this project continues to be understaffed, which will delay completion. aovpn repair work picking back up slowly in na, followed by eu. tunnel migrations in klamath, cisco anyconnect to azure vpn for na/eu stalled until additional resources available. eu cisco asa to fg slowly picking back up with tunnel migration research. virtual fortigate devices needed in eu on the horizon, na has stalled. we're unable to move forward with cisco to asa migrations until the prior is complete. this is also impacting the remainder of sd-wan for na (klamath). | dmz buildout completed. | azure fg buildout eu, dmz host migrations (stalled), tunnel migrations eu, aovpn remediation underway. | we need engineers to continue work that has been dropped due to attrition. | red | sideways | red | green | red | red | green | red | 2 | 7 | 0.0 | 1.0 | 32.0 | 13.0 | 2.0 | 4.0 | 0.0 | 0.0 | 46.0 | 33.0 | 29.0 | 4.0 | 165040.0 | 113584.0 | 51456.0 | 154511.5 | 101408.5 | 53103.0 | not specified | 30251.5 | 24911.5 | 5340.0 | not specified | 184763.0 | 126320.0 | 58443.0 | not specified | -19723.0 | -12736.0 | -6987.0 | -0.119504362578769 | -0.112128468798422 | -0.135785914179104 | 2025-10-27 | 2024-05-01 | 2025-04-17 | 0 | 252d | 2025-10-10 | 2025-10-13 | true | 9 | not specified | not specified | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 6.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | active | not specified | it | not specified | not specified | not specified | implementation / execution | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not planned (l2 to l4) | not specified | 1.0 | on track | 0.785140562248996 | 19.0 | 16.0 | 0.0 | 0.0217391304347826 | 0.695652173913044 | 0.282608695652174 | 0.0 | 1.0 | 2026 | n | 3 | not specified | not specified | 1.0 | p | 93 | not specified | 1.0 | not specified | not specified | not specified | not specified |  |  | not specified | not specified | [6 empty] | not specified | not specified | not specified | not specified | not specified | -498.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | stage 3 - implementation | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.59
na interim digital storefront for trad doors and distribution | 67370 | improve customer’s ability to request quote, convert a quote to an order, and enter orders directly into erp system for the doors business. benefits include easier to do business with jeld-wen for customers and streamlining of processes (reduced error through manual or re-keying work). this project will use existing systems: quick quote live (qql), talon, and mmi design. each will have some additional product capabilities and system enhancements to assist with customer useability and, in some cases, linkage between configure, price, quote (cpq) and enterprise resource management (erp) systems. | amy phillips | amy phillips | project | standalone project | standalone project | bus-na/corp/it | not specified | it na it na/corporate | not specified | amy phillips | amy phillips | victoria haugen | terry davis | tyce deal | not specified | growth | na - doors & dist: commercial - sales | it; engineering | l3 (planned) | on track | 67370.0 | not specified | project dashboard | finance dashboard | 0.9 | 2024-03-25 | 2026-03-30 | 526d | wk. 36: mmi enhancement (global specification) testing underway | 1. kicked off global specification testing for mmi enhancements 2. talon upgrade/talon-turns functionality - verifying blockers and status 3. millennium ovation sku definitions in progress | 1. review testing progress, discuss expected timing for deployment. full pallet will be deployed at the same time (although not configured for any customers). 2. review fixes from paradigm for talon upgrade/talon-turns functionality and re-test. upon uat approval, select deployment date. 3. continue work on millennium ovation skus 4. millennium functional design delivery 9/18, fd approval 9/25, fd submit for dev estimate 9/26 | not specified | green | on track | red | green | red | red | yellow | green | 0 | 2 | 3.0 | 10.0 | 13.0 | 85.0 | 4.0 | 5.0 | 21.0 | 21.0 | 111.0 | 26.0 | 21.0 | 5.0 | 992000.0 | 850000.0 | 142000.0 | 556418.75 | 323232.25 | 233186.5 | 223180.5 | 49663.0 | 47163.0 | 2500.0 | 2100.0 | 606081.75 | 370395.25 | 235686.5 | 225280.5 | 385918.25 | 479604.75 | -93686.5 | 0.389030493951613 | 0.564240882352941 | -0.659764084507042 | 2025-10-28 | 2024-03-25 | 2025-11-14 | 0 | 430d | 2025-10-27 | 2025-09-10 | not specified | 3 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | active | not specified | it | not specified | not specified | not specified | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not planned (l2 to l4) | not specified | 1.0 | on track | 0.79467680608365 | 2.0 | 49.0 | 0.027027027027027 | 0.0900900900900901 | 0.117117117117117 | 0.765765765765766 | 0.189189189189189 | 0.810810810810811 | 2026 | n | 3 | not specified | not specified | 1.0 | p | 94 | not specified | 1.0 | not specified | not specified | not specified | not specified |  |  | not specified | not specified | [6 empty] | not specified | not specified | not specified | not specified | not specified | -526.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.9
managed transportation - rxo - outbound freight program | pg-0097 | not specified | ryan russel | rachael gabbard | program | pg-0097 | pg-0097: managed transportation - rxo - outbound freight program | bus-na/corp/it | amanda jones | mfg. & supply chain na it | not specified | ryan russel | not specified | lino santinelli | chris franks | kirk kroft | not specified | supply chain | na - ops: freight / logistics | not specified | not specified | on track | not specified | not specified | program dashboard | finance dashboard | 0.945661914460285 | 2024-03-25 | 2025-09-26 | 395d | on track | 2 plants updated in 3g | not specified | not specified | green | on track | on track | green | red | red | yellow | red | 3 | 2 | 5.0 | 4.0 | 0.0 | 127.0 | 5.0 | 2.0 | 7.0 | 3.0 | 136.0 | 9.0 | 5.0 | 4.0 | 0.0 | 0.0 | 0.0 | 4130252.96 | 0.0 | 4130252.96 | not specified | 328990.39 | 0.0 | 328990.39 | not specified | 4459243.35 | 0.0 | 4459243.35 | not specified | -4459243.35 | 0.0 | -4459243.35 | 0.0 | 0.0 | 0 |  | 2024-03-25 | 2025-07-01 | 0 | 332d | 2025-10-16 | 2025-10-29 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | active | not specified | it | not specified | not specified | not specified | see project details | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 1.0 | 13.0 | 0.0 | 0.0367647058823529 | 0.0294117647058824 | 0.0 | 0.933823529411765 | 0.0514705882352941 | 0.948529411764706 | current year | not specified | 2 | not specified | not specified | not specified | pg | 97 | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | [6 empty] | not specified | not specified | not specified | not specified | not specified | -395.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.94566
managed transportation - rxo - outbound freight | 15671 | not specified | rachael gabbard | ryan russel | project | pg-0097 | pg-0097: managed transportation - rxo - outbound freight program | bus-na/corp/it | amanda jones | it mfg. & supply chain na it | not specified | ryan russel | not specified | lino santinelli | mike schipper | kirk kroft | not specified | freight & logistics | not specified | not specified | not specified | on track | 15671.0 | not specified | project dashboard | financial dashboard | 0.92 | 2024-03-25 | 2024-11-25 | 176d | complete | complete | complete | complete | blue | on track | green | green | yellow | red | yellow | green | 3 | 2 | 4.0 | 4.0 | 0.0 | 96.0 | 4.0 | 1.0 | 5.0 | 1.0 | 104.0 | 8.0 | 4.0 | 4.0 | 4400000.0 | 1700000.0 | 2700000.0 | 4400000.0 | 1700000.0 | 2700000.0 | not specified | not specified | 0.0 | 0.0 | not specified | 4400000.0 | 1700000.0 | 2700000.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2024-03-25 | 2025-07-01 | 0 | 332d | 2025-08-14 | 2025-07-23 | not specified | 9 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | completed | not specified | it | not specified | not specified | not specified | realize value / close / care period | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 7.167475713 | not specified | 2.648217 | 2023-11-13 | 2024-05-15 | due soon for l4 | not specified | 1.0 | on track | 1.0 | 76.0 | 98.0 | 0.0384615384615385 | 0.0384615384615385 | 0.0 | 0.923076923076923 | 0.0480769230769231 | 0.951923076923077 | previous year | n | 3 | not specified | not specified | 1.0 | p | 21 | not specified | 1.0 | 1.0 | not specified | not specified | not specified | 2024-03-25 | 2024-12-30 | not specified | not specified | [6 empty] | 201d | 0.0 | 0.0 | 35.0 | 0.174129353233831 | 25.0 | 0.124378109452736 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | stage 5 - care period | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.92
it managed transportation - rxo - outbound freight (15671) | p-0096 | not specified | ryan russel | christian suarez | project | pg-0097 | pg-0097: managed transportation - rxo - outbound freight program | bus-na/corp/it | amanda jones, jorge eleta | it mfg. & supply chain na it na/corporate | not specified | ryan russel | not specified | lino santinelli | mike schipper | kirk kroft | not specified | freight & logistics | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | finance dashboard | 0.96 | 2024-07-15 | 2025-09-26 | 315d | team met and discussed final closeout tasks. it has been reccomended that there be a follow on project to make some enhancements and fix some pain points. | not specified | finalize budget, draft l5 deck, l5 gate review, draft new project for enhancements (stop level status, resolve unfeasable routes) | no support required at this time. | green | on track | red | green | red | green | yellow | green | 0 | 0 | 1.0 | 0.0 | 0.0 | 31.0 | 1.0 | 1.0 | 2.0 | 2.0 | 32.0 | 1.0 | 1.0 | 0.0 | 2335872.0 | 1759438.0 | 576434.0 | 1703088.55 | 1386195.61 | 316892.94 | not specified | 0.0 | 0.0 | 0.0 | not specified | 1703088.55 | 1386195.61 | 316892.94 | not specified | 632783.45 | 373242.39 | 259541.06 | 0.270898169933969 | 0.212137279062974 | 0.45025286502878 | 2025-10-27 | 2024-06-06 | 2024-11-29 | 0 | 127d | 2025-10-16 | 2025-09-17 | not specified | 5 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | active | not specified | it | not specified | not specified | not specified | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 7.167475713 | not specified | 2.648217 | 2023-11-13 | 2024-05-15 | due soon for l4 | not specified | not specified | on track | 1.0 | 13.0 | 42.0 | 0.03125 | 0.0 | 0.0 | 0.96875 | 0.0625 | 0.9375 | current year | n | 3 | not specified | not specified | 1.0 | p | 96 | not specified | 1.0 | 1.0 | not specified | not specified | not specified |  |  | not specified | not specified | [6 empty] | not specified | not specified | not specified | not specified | not specified | -315.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.96
digital storefront and customer quoting tool for traditional doors | 22686 | placing an order with the traditional doors bu is difficult for our customers to make and for our internal resources to manage. resulting in slow transactions, wasted time, lower profit margins, and possible mistakes or re-work. this project's objective is to create a digital storefront and cpq tool that our customers can use to place stock and special orders (doors version of qql). the tool will be the first step to building a foundation needed to expand the use of a cpq engine and storefront integration into windows, retail and e-comm in the future. | jorge eleta | amy phillips | project | standalone project | standalone project | bus-na/corp/it | not specified | na it | not specified | amy phillips | not specified | marshal livingstone | shannon messing | tyce deal | not specified | not specified | na - custexp: marketing | it; engineering | l3 (planned) | on track | 22686.0 | not specified | project dashboard | finance dashboard | 0.43 | 2024-06-06 | 2024-11-29 | 127d | project cancelled and replaced by project 72664 | not specified | not specified | not specified | on track | on track | red | red | green | green | yellow | red | 0 | 0 | 11.0 | 0.0 | 0.0 | 9.0 | 11.0 | 11.0 | 20.0 | 20.0 | 20.0 | 11.0 | 11.0 | 0.0 | 19032000.0 | 10332000.0 | 8700000.0 | 1291464.54 | 211990.0 | 1079474.54 | 1079474.54 | 0.0 | 0.0 | 0.0 | 0.0 | 1291464.54 | 211990.0 | 1079474.54 | 1079474.54 | 17740535.46 | 10120010.0 | 7620525.46 | 0.932142468474149 | 0.979482191250484 | 0.875922466666667 | 2025-10-27 | 2024-06-06 | 2024-11-29 | 0 | 127d | 2025-01-31 | 2025-01-31 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | canceled | not specified | it | not specified | not specified | not specified | planning | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 3.6911 | not specified | 12.192 |  |  | not specified | not specified | 1.0 | on track | 1.0 | 271.0 | 271.0 | 0.55 | 0.0 | 0.0 | 0.45 | 1.0 | 0.0 | previous year | n | 3 | not specified | not specified | 1.0 | p | 98 | not specified | 1.0 | 1.0 | not specified | not specified | not specified |  |  | not specified | not specified | [6 empty] | not specified | not specified | not specified | not specified | not specified | -127.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.43
contractor/installer program for r&r market | 22687 | not specified | jorge eleta | amy phillips | project | standalone project | standalone project | bus-na/corp/it | not specified | na it | not specified | amy phillips | not specified | tami armagost | terry davis | kirk kroft | not specified | not specified | na - custexp: marketing | hr; it; legal | l3 (planned) | on track | 22687.0 | not specified | project dashboard | finance dashboard | 0.43 | 2024-06-06 | 2024-11-29 | 127d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | on track | green | green | green | green | yellow | green | 0 | 0 | 0.0 | 0.0 | 11.0 | 9.0 | 11.0 | 11.0 | 20.0 | 20.0 | 20.0 | 11.0 | 11.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2024-06-06 | 2024-11-29 | 0 | 127d | 2024-08-14 | 2024-11-01 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | active | not specified | it | not specified | not specified | not specified | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 8.4465 | not specified | 2.0 |  |  | not specified | not specified | 1.0 | on track | 1.0 | 441.0 | 362.0 | 0.0 | 0.0 | 0.55 | 0.45 | 1.0 | 0.0 | previous year | n | 3 | not specified | not specified | 1.0 | p | 99 | not specified | 1.0 | 1.0 | not specified | not specified | not specified |  |  | not specified | not specified | [6 empty] | not specified | not specified | not specified | not specified | not specified | -127.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.43
us timekeeping | 58313 | not specified | jorge eleta | christina hoy | project | standalone project | standalone project | bus-na/corp/it | not specified | not specified | not specified | not specified | not specified | stan johnson | not specified | m.j. vaidya | not specified | other | support functions: finance | hr; it | l0 (idea) | on track | 58313.0 | not specified | project dashboard | finance dashboard | 0.43 | 2024-06-06 | 2024-11-29 | 127d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | on track | green | green | green | green | yellow | green | 0 | 0 | 3.0 | 0.0 | 8.0 | 9.0 | 11.0 | 11.0 | 20.0 | 20.0 | 20.0 | 11.0 | 11.0 | 0.0 | 0.0 | 0.0 | 0.0 | 14908.6666666666 | 14908.6666666666 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 14908.6666666666 | 14908.6666666666 | 0.0 | not specified | -14908.6666666666 | -14908.6666666666 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2024-06-06 | 2024-11-29 | 0 | 127d | 2024-08-26 | 2025-09-23 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | active | not specified | it | not specified | not specified | not specified | ideation | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | -0.062 | not specified | 0.82 |  |  | not planned (l2 to l4) | not specified | 1.0 | on track | 1.0 | 429.0 | 36.0 | 0.15 | 0.0 | 0.4 | 0.45 | 1.0 | 0.0 | previous year | n | 3 | not specified | not specified | 1.0 | p | 101 | not specified | 1.0 | not specified | not specified | not specified | not specified |  |  | not specified | not specified | [6 empty] | not specified | not specified | not specified | not specified | not specified | -127.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.43
finch | 4356 | footprint consolidation project to optimize patio door supply chain locations to better serve retail partners and reduce freight cost. | sam graves | sam graves | project | standalone project | standalone project | bus-na/corp/it | amanda jones | na it | not specified | not specified | sam graves | andrea chitti | not specified | not specified | not specified | not specified | na - doors & dist.: manufacturing - central south | not specified | l3 (planned) | on track | 4356.0 | not specified | project dashboard | finance dashboard | 0.43 | 2024-06-06 | 2024-11-29 | 127d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | on track | green | green | green | green | yellow | green | 0 | 0 | 138.0 | 91.0 | 1.0 | 109.0 | 138.0 | 128.0 | 320.0 | 311.0 | 339.0 | 230.0 | 208.0 | 22.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2024-06-06 | 2024-11-29 | 0 | 127d | 2025-02-07 | 2024-11-05 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | active | not specified | other | not specified | not specified | not specified | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | 1.0 | 1.0 | on track | 1.0 | 264.0 | 358.0 | 0.407079646017699 | 0.268436578171091 | 0.00294985250737463 | 0.321533923303835 | 0.943952802359882 | 0.056047197640118 | previous year | not specified | 3 | not specified | not specified | not specified | p | 102 | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | [6 empty] | not specified | not specified | not specified | not specified | not specified | -127.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.43
identify a document management system | 32795 | not specified | jorge eleta | mike crawford (r2r) | project | standalone project | standalone project | bus-na/corp/it | not specified | not specified | not specified | mike crawford (r2r) | not specified | danielle darling | mike crawford (r2r) | m.j. vaidya | not specified | other | support functions: global legal | it | l2 (validated) | on hold | 32795.0 | not specified | project dashboard | finance dashboard | 0.43 | 2024-06-06 | 2024-11-29 | 127d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | on track | red | red | green | green | yellow | green | 0 | 0 | 11.0 | 0.0 | 0.0 | 9.0 | 11.0 | 11.0 | 20.0 | 20.0 | 20.0 | 11.0 | 11.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2024-06-06 | 2024-11-29 | 0 | 127d | 2025-02-21 | 2025-09-23 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on-hold | not specified | it | not specified | not specified | not specified | planning | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0.4 | not specified | 0.0892 | 2024-03-31 | 2025-02-28 | past due for l3 | not specified | 1.0 | on track | 1.0 | 250.0 | 36.0 | 0.55 | 0.0 | 0.0 | 0.45 | 1.0 | 0.0 | previous year | n | 3 | not specified | not specified | not specified | p | 103 | not specified | 1.0 | not specified | not specified | not specified | not specified |  |  | not specified | not specified | [6 empty] | not specified | not specified | not specified | not specified | not specified | -127.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.43
jeld-wen machine guarding team | 22974 | not specified | jeff benson | jeff benson | program | 22974 | 22974: jeld-wen machine guarding team | bus-na/corp/it | amanda jones | not specified | not specified | not specified | jeff benson | crystal pollin | not specified | not specified | not specified | sg&a | support functions: eh&s | engineering | l3 (planned) | on track | 22974.0 | not specified | program dashboard | finance dashboard | 0.457177322074789 | 2024-04-16 | 2026-09-30 | 642d | add the high level status of the program in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | on track | green | on track | red | green | green | green | 0 | 0 | 98.0 | 10.0 | 17.0 | 391.0 | 40.0 | 108.0 | 12.0 | 7.0 | 516.0 | 125.0 | 43.0 | 82.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 |  | 2024-06-06 | 2024-11-29 | 0 | 127d | 2025-09-08 | 2025-10-29 | not specified | 1 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | active | not specified | engineering | not specified | not specified | not specified | see project details | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0.0 | not specified | 1.88 | 2023-10-18 | 2024-01-12 | past due for l3 | not specified | 1.0 | on track | 0.626168224299065 | 51.0 | 0.0 | 0.189922480620155 | 0.0193798449612403 | 0.0329457364341085 | 0.757751937984496 | 0.0232558139534884 | 0.976744186046512 | 2026 | n | 2 | not specified | not specified | 1.0 | p | 105 | not specified | 1.0 | not specified | not specified | not specified | not specified |  |  | not specified | not specified | [6 empty] | not specified | not specified | not specified | not specified | not specified | -642.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.45718
machine guarding team: chiloquin | p-0187 | not specified | jeff benson | jeff benson | project | 22974 | 22974: jeld-wen machine guarding team | bus-na/corp/it | amanda jones | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | finance dashboard | 0.88 | 2024-04-16 | 2026-09-30 | 642d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | on track | red | green | red | green | yellow | red | 0 | 0 | 98.0 | 10.0 | 17.0 | 391.0 | 40.0 | 108.0 | 12.0 | 7.0 | 516.0 | 125.0 | 43.0 | 82.0 | 320000.0 | 320000.0 | 0.0 | 111410.0 | 0.0 | 111410.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 111410.0 | 0.0 | 111410.0 | not specified | 208590.0 | 320000.0 | -111410.0 | 0.65184375 | 1.0 | 0 | 2025-10-27 | 2024-06-06 | 2024-11-29 | 0 | 127d | 2025-09-08 | 2024-11-01 | true | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | active | not specified | engineering | not specified | not specified | not specified | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.626168224299065 | 51.0 | 362.0 | 0.189922480620155 | 0.0193798449612403 | 0.0329457364341085 | 0.757751937984496 | 0.0232558139534884 | 0.976744186046512 | 2026 | not specified | 3 | not specified | not specified | 1.0 | p | 187 | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | [6 empty] | not specified | not specified | not specified | not specified | not specified | -642.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.88
machine guarding team: grand rapids | p-0188 | not specified | jeff benson | jeff benson | project | 22974 | 22974: jeld-wen machine guarding team | bus-na/corp/it | amanda jones | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | finance dashboard | 0.19 | 2024-06-06 | 2024-11-29 | 127d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | on track | red | green | green | green | green | red | 0 | 0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 200000.0 | 200000.0 | 0.0 | 65700.0 | 0.0 | 65700.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 65700.0 | 0.0 | 65700.0 | not specified | 134300.0 | 200000.0 | -65700.0 | 0.6715 | 1.0 | 0 | 2025-10-27 | 2024-06-06 | 2024-11-29 | 0 | 127d |  | 2024-11-01 | true | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | active | not specified | engineering | not specified | not specified | not specified | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 1.0 | not specified | 362.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 1.0 | previous year | not specified | 3 | not specified | not specified | 1.0 | p | 188 | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | [6 empty] | not specified | not specified | not specified | not specified | not specified | -127.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.19
machine guarding team: grinnell doors | p-0189 | not specified | jeff benson | jeff benson | project | 22974 | 22974: jeld-wen machine guarding team | bus-na/corp/it | amanda jones | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | finance dashboard | 0.19 | 2024-06-06 | 2024-11-29 | 127d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | on track | green | green | green | green | green | green | 0 | 0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 370000.0 | 370000.0 | 0.0 | 297965.2 | 0.0 | 297965.2 | not specified | 0.0 | 0.0 | 0.0 | not specified | 297965.2 | 0.0 | 297965.2 | not specified | 72034.8 | 370000.0 | -297965.2 | 0.194688648648649 | 1.0 | 0 | 2025-10-27 | 2024-06-06 | 2024-11-29 | 0 | 127d |  | 2024-11-01 | true | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | active | not specified | engineering | not specified | not specified | not specified | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 1.0 | not specified | 362.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 1.0 | previous year | not specified | 3 | not specified | not specified | 1.0 | p | 189 | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | [6 empty] | not specified | not specified | not specified | not specified | not specified | -127.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.19
machine guarding team: ligonier | p-0190 | not specified | jeff benson | jeff benson | project | 22974 | 22974: jeld-wen machine guarding team | bus-na/corp/it | amanda jones | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | finance dashboard | 0.19 | 2024-06-06 | 2024-11-29 | 127d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | on track | green | green | green | green | green | green | 0 | 0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 220000.0 | 220000.0 | 0.0 | 135220.4 | 0.0 | 135220.4 | not specified | 0.0 | 0.0 | 0.0 | not specified | 135220.4 | 0.0 | 135220.4 | not specified | 84779.6 | 220000.0 | -135220.4 | 0.385361818181818 | 1.0 | 0 | 2025-10-27 | 2024-06-06 | 2024-11-29 | 0 | 127d |  | 2024-11-01 | true | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | active | not specified | engineering | not specified | not specified | not specified | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 1.0 | not specified | 362.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 1.0 | previous year | not specified | 3 | not specified | not specified | 1.0 | p | 190 | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | [6 empty] | not specified | not specified | not specified | not specified | not specified | -127.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.19
machine guarding team: ludlow | p-0191 | not specified | jeff benson | jeff benson | project | 22974 | 22974: jeld-wen machine guarding team | bus-na/corp/it | amanda jones | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | finance dashboard | 0.19 | 2024-06-06 | 2024-11-29 | 127d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | on track | red | green | green | green | green | red | 0 | 0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 100000.0 | 100000.0 | 0.0 | 109000.0 | 0.0 | 109000.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 109000.0 | 0.0 | 109000.0 | not specified | -9000.0 | 100000.0 | -109000.0 | -0.09 | 1.0 | 0 | 2025-10-27 | 2024-06-06 | 2024-11-29 | 0 | 127d |  | 2024-11-01 | true | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | active | not specified | engineering | not specified | not specified | not specified | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 1.0 | not specified | 362.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 1.0 | previous year | not specified | 3 | not specified | not specified | 1.0 | p | 191 | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | [6 empty] | not specified | not specified | not specified | not specified | not specified | -127.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.19
machine guarding team: rocklin | p-0192 | not specified | jeff benson | jeff benson | project | 22974 | 22974: jeld-wen machine guarding team | bus-na/corp/it | amanda jones | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | finance dashboard | 0.19 | 2024-06-06 | 2024-11-29 | 127d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | on track | red | green | green | green | green | red | 0 | 0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 100000.0 | 100000.0 | 0.0 | 109000.0 | 0.0 | 109000.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 109000.0 | 0.0 | 109000.0 | not specified | -9000.0 | 100000.0 | -109000.0 | -0.09 | 1.0 | 0 | 2025-10-28 | 2024-06-06 | 2024-11-29 | 0 | 127d |  | 2024-11-01 | true | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | active | not specified | engineering | not specified | not specified | not specified | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 1.0 | not specified | 362.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 1.0 | previous year | not specified | 3 | not specified | not specified | 1.0 | p | 192 | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | [6 empty] | not specified | not specified | not specified | not specified | not specified | -127.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.19
machine guarding team: sacramento | p-0193 | not specified | jeff benson | jeff benson | project | 22974 | 22974: jeld-wen machine guarding team | bus-na/corp/it | amanda jones | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | finance dashboard | 0.19 | 2024-06-06 | 2024-11-29 | 127d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | on track | red | green | green | green | green | red | 0 | 0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 100000.0 | 100000.0 | 0.0 | 109000.0 | 0.0 | 109000.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 109000.0 | 0.0 | 109000.0 | not specified | -9000.0 | 100000.0 | -109000.0 | -0.09 | 1.0 | 0 | 2025-10-27 | 2024-06-06 | 2024-11-29 | 0 | 127d |  | 2024-11-01 | true | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | active | not specified | engineering | not specified | not specified | not specified | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 1.0 | not specified | 362.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 1.0 | previous year | not specified | 3 | not specified | not specified | 1.0 | p | 193 | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | [6 empty] | not specified | not specified | not specified | not specified | not specified | -127.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.19
machine guarding team: stockton | p-0194 | not specified | jeff benson | jeff benson | project | 22974 | 22974: jeld-wen machine guarding team | bus-na/corp/it | amanda jones | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | finance dashboard | 0.19 | 2024-06-06 | 2024-11-29 | 127d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | on track | red | green | green | green | green | red | 0 | 0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 100000.0 | 100000.0 | 0.0 | 109000.0 | 0.0 | 109000.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 109000.0 | 0.0 | 109000.0 | not specified | -9000.0 | 100000.0 | -109000.0 | -0.09 | 1.0 | 0 | 2025-10-27 | 2024-06-06 | 2024-11-29 | 0 | 127d |  | 2024-11-01 | true | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | active | not specified | engineering | not specified | not specified | not specified | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 1.0 | not specified | 362.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 1.0 | previous year | not specified | 3 | not specified | not specified | 1.0 | p | 194 | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | [6 empty] | not specified | not specified | not specified | not specified | not specified | -127.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.19
machine guarding team: sulphur springs | p-0195 | not specified | jeff benson | jeff benson | project | 22974 | 22974: jeld-wen machine guarding team | bus-na/corp/it | amanda jones | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | finance dashboard | 0.19 | 2024-06-06 | 2024-11-29 | 127d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | on track | green | green | green | green | green | green | 0 | 0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 370000.0 | 370000.0 | 0.0 | 299108.0 | 0.0 | 299108.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 299108.0 | 0.0 | 299108.0 | not specified | 70892.0 | 370000.0 | -299108.0 | 0.1916 | 1.0 | 0 | 2025-10-27 | 2024-06-06 | 2024-11-29 | 0 | 127d |  | 2024-11-01 | true | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | active | not specified | engineering | not specified | not specified | not specified | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 1.0 | not specified | 362.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 1.0 | previous year | not specified | 3 | not specified | not specified | 1.0 | p | 195 | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | [6 empty] | not specified | not specified | not specified | not specified | not specified | -127.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.19
interface as400 to ax for intercompany orders | 33793 | not specified | karolin koch | michael schwaiger | project | standalone project | standalone project | it-eu | not specified | it it-eu | not specified | it pm not required | not specified | ersan g�ltekin | markus ellinger | rachael horton-farmer | not specified | sg&a | dach: commercial - germany steel | it | submitted for l4 approval | on track | 33793.0 | not specified | project dashboard | finance dashboard | 0.43 | 2024-06-06 | 2024-11-29 | 127d | w36: project handed over to michael schwaiger in july (bau) | not specified | not specified | not specified | blue | on track | green | green | green | green | yellow | green | 0 | 0 | 4.0 | 0.0 | 7.0 | 9.0 | 11.0 | 11.0 | 20.0 | 20.0 | 20.0 | 11.0 | 11.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2024-06-06 | 2024-11-29 | 0 | 127d | 2024-09-16 | 2025-10-16 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | completed | not specified | it | not specified | not specified | central eu | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0.0814 | not specified | 0.055 | 2023-10-13 | 2025-11-28 | on plan | not specified | 1.0 | on track | 1.0 | 408.0 | 13.0 | 0.2 | 0.0 | 0.35 | 0.45 | 1.0 | 0.0 | previous year | n | 3 | not specified | not specified | 1.0 | p | 112 | not specified | 1.0 | 1.0 | not specified | not specified | not specified |  |  | not specified | not specified | [6 empty] | not specified | not specified | not specified | not specified | not specified | -127.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.43
special order catalog – abs distribution | 67358 | not specified | not specified | mike crawford (brm) | project | standalone project | standalone project | not specified | amanda jones | na it | not specified | mike crawford (brm) | emily bartlett | carmen wagner | mike crawford (brm) | terry davis | not specified | growth | na - doors & dist: commercial - sales | it | submitted for l3 approval | on track | 67358.0 | not specified | project dashboard | finance dashboard | 0.73 | 2024-06-03 | 2025-01-31 | 175d | on 10/3 received approval from doug baxter to move forward with the pricing changes made for rev 1. requirements sessions are complete and will finalize requirements on 10/9 with the business and hand-off to it dev team. | not specified | not specified | not specified | green | on track | red | red | red | red | yellow | green | 1 | 0 | 16.0 | 5.0 | 0.0 | 31.0 | 5.0 | 15.0 | 5.0 | 3.0 | 52.0 | 21.0 | 9.0 | 12.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2024-06-06 | 2024-11-29 | 0 | 127d | 2025-02-07 | 2024-11-05 | not specified | 14 | not specified | not specified | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | active | not specified | it | not specified | not specified | not specified | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | 1.0 | on track | 1.0 | 264.0 | 358.0 | 0.307692307692308 | 0.0961538461538462 | 0.0 | 0.596153846153846 | 0.0961538461538462 | 0.903846153846154 | current year | not specified | 3 | not specified | not specified | 1.0 | p | 117 | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | [6 empty] | not specified | not specified | not specified | not specified | not specified | -175.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.73
nike program | pg-0119 | not specified | jim copeland | jim copeland | program | pg-0119 | pg-0119: nike program | eng-it | amanda jones | not specified | not specified | ryan russel | not specified | not specified | not specified | kirk kroft | not specified | manufacturing | not specified | not specified | not specified | on track | not specified | not specified | program dashboard | finance dashboard | 0.352792307692308 | 2022-08-15 | 2027-11-30 | 1382d | add the high level status of the program in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | on track | red | on track | red | red | yellow | red | 0 | 0 | 33.0 | 3.0 | 1702.0 | 657.0 | 35.0 | 36.0 | 134.0 | 134.0 | 2395.0 | 1738.0 | 1726.0 | 12.0 | 14125000.0 | 12500000.0 | 1625000.0 | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 14125000.0 | 12500000.0 | 1625000.0 | 1.0 | 1.0 | 1 |  | 2022-08-15 | 2027-03-19 | 0 | 1200d | 2025-10-01 | 2025-10-29 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 11 | 7 | 5 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | active | not specified | it | not specified | not specified | not specified | see project details | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.606367583212735 | 28.0 | 0.0 | 0.0137787056367432 | 0.00125260960334029 | 0.710647181628393 | 0.274321503131524 | 0.0559498956158664 | 0.944050104384134 | 2027 | not specified | 2 | not specified | not specified | not specified | pg | 119 | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | [6 empty] | not specified | not specified | not specified | not specified | not specified | -1382.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.35279
nike - garland | 2932 | not specified | jorge eleta | christian suarez | project | pg-0119 | pg-0119: nike program | eng-it | amanda jones | automation it mfg. & supply chain na it na/corporate | not specified | ryan russel | jim copeland | casey haynes | christian suarez | kirk kroft | not specified | manufacturing | na - doors & dist.: manufacturing - south central | engineering; hr; it | l4 (executed) | on track | 2932.0 | not specified | project dashboard | project finance dashboard | 0.99 | 2022-08-15 | 2025-09-19 | 810d | sat run complete | sat run complete | sat approval and ramp | business and plant readiness risks need to be addressed | green | up | red | green | green | red | green | green | 4 | 0 | 4.0 | 0.0 | 0.0 | 654.0 | 4.0 | 0.0 | 0.0 | 0.0 | 658.0 | 4.0 | 0.0 | 4.0 | 14800000.0 | 12400000.0 | 2400000.0 | 13612743.9 | 11861245.9 | 1751498.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 13612743.9 | 11861245.9 | 1751498.0 | 0.0 | 1187256.1 | 538754.1 | 648502.0 | 0.0802200067567568 | 0.0434479112903226 | 0.270209166666667 | 2025-10-27 | 2022-08-15 | 2025-10-08 | 0 | 823d | 2025-10-01 | 2025-09-16 | not specified | 4 | 1.0 | not specified | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | active | not specified | it | not specified | not specified | not specified | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 6.065896 | not specified | 14.8 | 2023-09-28 | 2025-02-05 | on plan | not specified | 1.0 | on track | 1.0 | 28.0 | 43.0 | 0.0060790273556231 | 0.0 | 0.0 | 0.993920972644377 | 0.0 | 1.0 | current year | n | 3 | not specified | not specified | 1.0 | p | 131 | 1.0 | 1.0 | 1.0 | not specified | not specified | not specified | 2025-10-29 | 2026-01-27 | not specified | not specified | 2024-09-03 | [5 empty] | not specified | 1171.0 | not specified | 130.0 | not specified | -810.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.99
nike - kissimmee | 4365 | not specified | jim copeland | jim copeland | project | pg-0119 | pg-0119: nike program | eng-it | amanda jones | automation na it | not specified | not specified | jim copeland | casey haynes | not specified | not specified | not specified | manufacturing | na - doors & dist.: manufacturing - southeast / michigan | engineering | l2 (validated) | on hold | 4365.0 | not specified | project dashboard | project finance dashboard | 0.16 | 2025-02-25 | 2027-11-30 | 721d | 12/4/24 cerf at samantha and updated pending trantek updated quote. due date for submittal is 12/15/24 by business. | 12/4/24 cerf at samantha and updated pending trantek updated quote. due date for submittal is 12/15/24 by business. | cerf final submittal. team kickoff scheduled for 2/3. | none at this time | yellow | sideways | red | green | red | red | yellow | green | 8 | 0 | 4.0 | 1.0 | 544.0 | 3.0 | 6.0 | 9.0 | 1.0 | 1.0 | 552.0 | 549.0 | 543.0 | 6.0 | 0.0 | not specified | not specified | 500000.0 | 500000.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 500000.0 | 500000.0 | 0.0 | 0.0 | -500000.0 | -500000.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2024-08-19 | 2026-09-18 | 0 | 545d | 2025-10-01 | 2024-12-04 | not specified | 8 | 1.0 | not specified | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | it | not specified | not specified | not specified | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 5.9 | not specified | 9.9444 | 2023-10-13 | 2025-03-10 | on plan | not specified | 1.0 | on track | 0.245492371705964 | 28.0 | 329.0 | 0.0072463768115942 | 0.00181159420289855 | 0.985507246376812 | 0.00543478260869565 | 0.00181159420289855 | 0.998188405797102 | 2027 | n | 3 | not specified | not specified | 1.0 | p | 132 | 1.0 | 1.0 | 1.0 | not specified | not specified | not specified | 2025-10-29 | 2026-01-27 | not specified | not specified | 2024-09-03 | [5 empty] | not specified | 246.0 | not specified | -672.0 | not specified | -721.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.16
nike - rocklin | 4367 | not specified | jim copeland | jim copeland | project | pg-0119 | pg-0119: nike program | eng-it | amanda jones | automation na it | not specified | not specified | jim copeland | casey haynes | not specified | not specified | not specified | manufacturing | na - doors & dist.: manufacturing - west | engineering | l3 (planned) | on hold | 4367.0 | not specified | project dashboard | project finance dashboard | 0.0 | 2024-10-21 | 2027-04-20 | 652d | on track | not specified | not specified | not specified | on track | on track | red | red | yellow | yellow | yellow | green | 8 | 0 | 25.0 | 1.0 | 610.0 | 0.0 | 25.0 | 26.0 | 1.0 | 1.0 | 636.0 | 636.0 | 635.0 | 1.0 | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2024-10-21 | 2027-03-19 | 0 | 630d | 2025-10-01 |  | not specified | 8 | 1.0 | not specified | 0 | 0 | 0 | 2 | 1 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | it | not specified | not specified | not specified | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 6.05 | not specified | 9.2 | 2023-10-13 | 2026-02-10 | on plan | not specified | 1.0 | on track | 0.411042944785276 | 28.0 | on track | 0.0393081761006289 | 0.00157232704402516 | 0.959119496855346 | 0.0 | 0.00157232704402516 | 0.998427672955975 | 2027 | n | 3 | not specified | not specified | 1.0 | p | 133 | 1.0 | 1.0 | 1.0 | not specified | not specified | not specified | 2025-10-29 | 2026-01-27 | not specified | not specified | 2024-09-03 | [5 empty] | not specified | 373.0 | not specified | -448.0 | not specified | -652.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0
nike - grinnell | 4368 | not specified | jim copeland | jim copeland | project | pg-0119 | pg-0119: nike program | eng-it | amanda jones | automation na it | not specified | not specified | jim copeland | casey haynes | not specified | not specified | not specified | manufacturing | na - doors & dist.: manufacturing - midwest & steel | engineering | l3 (planned) | on hold | 4368.0 | not specified | project dashboard | project finance dashboard | 0.0 | 2026-02-23 | 2027-09-28 | 417d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | sideways | red | green | red | red | yellow | green | 8 | 0 | 0.0 | 1.0 | 548.0 | 0.0 | 0.0 | 1.0 | 132.0 | 132.0 | 549.0 | 549.0 | 548.0 | 1.0 | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2024-12-02 | 2026-12-18 | 0 | 535d | 2025-07-10 | 2024-10-30 | not specified | 8 | 1.0 | not specified | 0 | 0 | 0 | 2 | 5 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | active | not specified | it | not specified | not specified | not specified | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 4.55 | not specified | 9.7 | 2023-10-13 | 2026-03-04 | on plan | not specified | 1.0 | on track | 0.0 | 111.0 | 364.0 | 0.0 | 0.00182149362477231 | 0.998178506375228 | 0.0 | 0.240437158469945 | 0.759562841530055 | 2027 | n | 3 | not specified | not specified | 1.0 | p | 134 | 1.0 | 1.0 | 1.0 | not specified | not specified | not specified | 2025-10-29 | 2026-01-27 | not specified | not specified | 2024-09-03 | [5 empty] | not specified | -117.0 | not specified | -609.0 | not specified | -417.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0
en program scandinavia | 62251 | not specified | mateus hermann | nadezda melnikova | program | 62251 | 62251: en program scandinavia | not specified | nadezda melnikova | r&d europe r&d europe north | not specified | awaiting it pm appointment | not specified | nadezda melnikova | peter sorensen | rachael horton-farmer | not specified | other | nordics: manufacturing - sweden | engineering; it | l1 (identified) | on track | 62251.0 | not specified | program dashboard | finance dashboard | 0.120176975945017 | 2024-06-01 | 2032-11-09 | 2202d | priority 1 projects: 40mm platform ei30 up to 33db - uncertainly with the steel frame development - decision on how to proceed - nov 6th. 2 key rnd technicians have resigned. internal testing is on hold before the recruitment is in place. 60mm platform ei60 up to 43db - on hold, won't start before 2026 when recruitment of rnd steel expert is completed (a candidate is expected to start in nov). 60+88mm platform ei30 up to 47db - pm is defining the assortment (60% completed). rnd will resource the project in nov 2025. tentative gate 1 - feb 2026. | glue development testing started. new acoustic sealing development - alternative suppliers are contacted. assortment of the combination of steel frame with wooden door is finalized. the testing transferred to rise was completed on 16/10, the result is not satisfying (integrity failure). harmonization #44. kicking plates. ops reached the agreement. | hardware changes - meeting booked pm & proc in nov. xal re-programming at sdrf started in sept. concept a & c puc update. steel frame set puc calculation is in progress. harmonization: color of hinges and screws will be handled in sprint 5 (a separate project). program own hours estimation is being revisited. business case need to be updated with the new figures. resource requirements for 2026 onwards to be included into functional budgets. approach to certification and go to market - pm to define. | substitute pvc edge lipping with abs - decision is needed on how to handle the topic. #3 hinge milling depth 3228/3278. cerf approval is postponed to q1 2026. if not approved then this will have a negative impact on the entire en program. risk management - acoustic testing program. the latest indication is that ce marking is mandatory starting from 03/2030. meaning cannot delay acoustic testing program to 2029-2030. | yellow | on track | green | on track | green | red | yellow | red | 21 | 1 | 38.0 | 279.0 | 1647.0 | 452.0 | 38.0 | 56.0 | 811.0 | 658.0 | 2416.0 | 1964.0 | 1831.0 | 133.0 | 4974305.88235292 | 347058.823529411 | 4627247.05882351 | 1236581.65882352 | 0.0 | 1236581.65882352 | not specified | 8133388.23529409 | 858823.529411762 | 7274564.70588233 | not specified | 9369969.89411761 | 858823.529411762 | 8511146.36470585 | not specified | -4395664.01176469 | -511764.705882351 | -3883899.30588234 | -0.883673846306668 | -1.47457627118644 | -0.839354211372027 |  | 2024-06-01 | 2032-11-09 | 0 | 2202d | 2025-10-29 | 2025-10-29 | true | 37 | 1.0 | not specified | 0 | 0 | 1 | 0 | 2 | 17 | 0 | 2 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0 | not specified | 4228160.0 | 295000.0 | 3933160.0 | 1051094.41 | 0.0 | 1051094.41 | not specified | 6913380.0 | 730000.0 | 6183380.0 | not specified | 7964474.41 | 730000.0 | 7234474.41 | not specified | -3736314.41 | -435000.0 | -3301314.41 | -0.883673846306668 | -1.47457627118644 | -0.839354211372027 | not specified | active | eur | r&d | not specified | not specified | north eu | see project details | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not planned (l2 to l4) | not specified | 1.0 | on track | 0.167120799273388 | 0.0 | 0.0 | 0.0157284768211921 | 0.115480132450331 | 0.681705298013245 | 0.187086092715232 | 0.33567880794702 | 0.66432119205298 | 2032 | n | 2 | not specified | not specified | not specified | pg | 123 | not specified | 1.0 | not specified | not specified | not specified | not specified |  |  | not specified | not specified | [6 empty] | not specified | not specified | not specified | not specified | not specified | -2202.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.12018
documentation & harmonization | p-0137 | not specified | mateus hermann | nadezda melnikova | project | 62251 | 62251: en program scandinavia | not specified | nadezda melnikova | r&d europe r&d europe north | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.67 | 2024-06-01 | 2027-06-16 | 793d | sprint 4 is progressing well. some rnd resources were moved to enable vd92 project and support ei30 40mm external testing preparation. the impact on sprint 4 is to be evaluated once the resources are back. forserum. implementation dependency on cpq. the team cannot move forward with 4 topics. expecting double work as we are forced to implement in the existing system. | harmonization #44 kick plates - ops reached the decision on how to proceed and rnd can continue the documentation work. | #33 hardware standardization (cable loop placement). implementation might not be possible as rnd is not ready with the input. misunderstanding between the teams. the meeting is booked to see how we can recover this topic and still implement in sprint 4. | mechanical locks / single point locks 1m delayed by forserum - matrix for lock/striker combination and placement of locktype vs height. door blank. update erp sdrf is 1 month delayed. forserum is not able to share prioritising other work. | yellow | sideways | red | green | yellow | red | yellow | green | 2 | 1 | 18.0 | 53.0 | 309.0 | 268.0 | 18.0 | 9.0 | 59.0 | 36.0 | 648.0 | 380.0 | 333.0 | 47.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2024-06-01 | 2027-06-09 | 0 | 788d | 2025-10-28 | 2025-10-23 | true | 3 | 1.0 | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | r&d | multiple | sustaining | north eu | implementation / execution | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.4640605296343 | 1.0 | 6.0 | 0.0277777777777778 | 0.0817901234567901 | 0.476851851851852 | 0.41358024691358 | 0.0910493827160494 | 0.908950617283951 | 2027 | not specified | 3 | not specified | not specified | 1.0 | p | 211 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2024-06-01 | 2027-06-09 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | -7.0 | not specified | -793.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | stage 3 - implementation | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.67
01-62251 ei2 30, 40mm (l,ol) | p-0138 | not specified | mateus hermann | nadezda melnikova | project | 62251 | 62251: en program scandinavia | not specified | nadezda melnikova | r&d europe r&d europe north | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.2 | 2024-09-01 | 2030-03-25 | 1451d | external testing program is confirmed. 10 external tests required. execution starts in dec 2025. internal testing is on hold. rnd technician in charge left the company. recruitment starts in nov. the timeline of the glue development is negatively affected (the furnace break down) by at least 1 month. rnd technician in charge is leaving the company on 31/10/2025. new acoustic sealing development - low engagement of trelleborg- the timeline is negatively affected. | glue development testing is in progress. new acoustic sealing development - alternative suppliers are contacted. | change point analysis of new acoustic sealing - booked in nov. ops testing & qua evaluation - sonder felding is in progress through oct-nov. sampling preparation for the external testing through nov. | internal fire testing l/ol is being delayed and must be replanned. changes in rnd staff, a new rnd technician is required to execute the testing. olar took on an interim role to support the testing. | yellow | sideways | red | green | red | red | yellow | green | 4 | 0 | 4.0 | 137.0 | 400.0 | 110.0 | 4.0 | 15.0 | 147.0 | 19.0 | 651.0 | 541.0 | 519.0 | 22.0 | 866117.647058821 | 217647.058823529 | 648470.588235292 | 18117.6470588235 | 0.0 | 18117.6470588235 | 0.0 | 749176.470588233 | 217647.058823529 | 531529.411764704 | 0.0 | 767294.117647056 | 217647.058823529 | 549647.058823527 | 0.0 | 98823.5294117644 | 0.0 | 98823.5294117644 | 0.114099429502852 | 0.0 | 0.152394775036285 | 2025-10-27 | 2024-09-01 | 2028-05-17 | 0 | 968d | 2025-10-29 | 2025-10-24 | true | 5 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 736200.0 | 185000.0 | 551200.0 | 15400.0 | 0.0 | 15400.0 | 0.0 | 636800.0 | 185000.0 | 451800.0 | 0.0 | 652200.0 | 185000.0 | 467200.0 | 0.0 | 84000.0 | 0.0 | 84000.0 | 0.114099429502852 | 0.0 | 0.152394775036284 | not specified | active | eur | r&d | multiple | sustaining | north eu | development | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.20882150241213 | 0.0 | 5.0 | 0.00614439324116744 | 0.210445468509985 | 0.614439324116744 | 0.168970814132104 | 0.225806451612903 | 0.774193548387097 | 2030 | not specified | 3 | not specified | not specified | 1.0 | p | 198 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2024-09-01 | 2028-05-17 | not specified | not specified | 2024-12-19 | 2027-02-24 | 2027-11-19 |  | 2028-05-17 |  | not specified | 0.0 | not specified | -677.0 | not specified | -1451.0 | not specified | not specified | 2024-12-19 00:00:00 | 2026-06-05 00:00:00 | 2027-12-14 00:00:00 | not specified | 2028-02-15 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0 | 264d | -25d | 92d | dates not set | 0.0 | 0.181943487250172 | -0.0172294968986906 | 0.0634045485871813 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | stage 2 - development | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.2
02-62251 ei2 30, 60mm (pl,al) | p-0139 | not specified | mateus hermann | nadezda melnikova | project | 62251 | 62251: en program scandinavia | not specified | nadezda melnikova | r&d europe r&d europe north | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.02 | 2025-10-20 | 2029-02-22 | 874d | p2 project starts once rnd team starts to work on the p1 fire exap drawings | not specified | not specified | not specified | green | sideways | green | green | green | green | yellow | green | 0 | 0 | 0.0 | 3.0 | 79.0 | 0.0 | 0.0 | 0.0 | 3.0 | 2.0 | 82.0 | 82.0 | 79.0 | 3.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-06-02 | 2029-08-13 | 0 | 1096d | 2025-10-22 | 2025-03-21 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | r&d | multiple | sustaining | north eu | pre-tollgate | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.0091533180778032 | 7.0 | 222.0 | 0.0 | 0.0365853658536585 | 0.963414634146341 | 0.0 | 0.0365853658536585 | 0.963414634146342 | 2029 | not specified | 3 | not specified | not specified | 1.0 | p | 199 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-06-02 | 2029-08-13 | not specified | not specified | [6 empty] | not specified | -140.0 | not specified | 172.0 | not specified | -874.0 | not specified | not specified | 2026-02-24 00:00:00 | 2027-04-07 00:00:00 | 2028-09-21 00:00:00 | not specified | 2029-01-25 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | stage 0 - pre-tollgate | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.02
03-62251 ei2 60, 60mm (vl,nl) | p-0140 | not specified | mateus hermann | nadezda melnikova | project | 62251 | 62251: en program scandinavia | not specified | nadezda melnikova | r&d europe r&d europe north | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.05 | 2025-02-24 | 2029-05-07 | 1096d | with the key r&d resource leaving the project is put on hold. | the team have evaluated acceptable risk to delay acoustic & durability and some other internal testing. if ce marking becomes mandatory prior to 2029 we must test what we dont have already covered in range. | r&d to solve engineering challenge in ei60 constructions, wood+steel frames and collaboration with glue suppliers to look more heat resistance of the glue (sprint 3-4 focus). focus on the vl core development - the ideation session between rnd and ops is taking place on april 8th. | back filling the r&d technician role has started. | red | angle down | red | green | green | green | yellow | green | 3 | 0 | 0.0 | 38.0 | 94.0 | 4.0 | 0.0 | 0.0 | 107.0 | 107.0 | 136.0 | 132.0 | 120.0 | 12.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 1002352.94117647 | 211764.705882352 | 790588.235294115 | 0.0 | 1002352.94117647 | 211764.705882352 | 790588.235294115 | 0.0 | -1002352.94117647 | -211764.705882352 | -790588.235294115 | 0.0 | 0.0 | 0 | 2025-04-25 | 2025-02-24 | 2029-05-07 | 0 | 1096d | 2025-10-22 | 2025-05-28 | not specified | 4 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 852000.0 | 180000.0 | 672000.0 | 0.0 | 852000.0 | 180000.0 | 672000.0 | 0.0 | -852000.0 | -180000.0 | -672000.0 | 0.0 | 0.0 | 0.0 | not specified | on-hold | eur | r&d | multiple | sustaining | north eu | initiation / validation / feasibility | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.162408759124088 | 7.0 | 154.0 | 0.0 | 0.279411764705882 | 0.691176470588235 | 0.0294117647058824 | 0.786764705882353 | 0.213235294117647 | 2029 | not specified | 3 | not specified | not specified | 1.0 | p | 200 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-02-24 | 2029-05-07 | not specified | not specified | 2026-01-30 | 2027-04-12 | 2029-01-15 |  | 2029-05-07 |  | not specified | 0.0 | not specified | 0.0 | not specified | -1096.0 | not specified | not specified | 2026-02-27 00:00:00 | 2027-04-12 00:00:00 | 2029-01-15 00:00:00 | not specified | 2029-05-07 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | -28d | 0 | 0 | 0 | dates not set | -0.0255474452554745 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | stage 1 - feasibility | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.05
04-62251 glass walls (ol,pl, ru, vl) | p-0141 | not specified | mateus hermann | nadezda melnikova | project | 62251 | 62251: en program scandinavia | not specified | nadezda melnikova | r&d europe r&d europe north | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.0 | 2026-05-01 | 2028-06-30 | 566d | receiving of certificates in stacking of partition project serves as p4 project start date | not specified | not specified | not specified | green | sideways | yellow | yellow | yellow | green | yellow | green | 0 | 0 | 0.0 | 6.0 | 87.0 | 0.0 | 0.0 | 2.0 | 93.0 | 93.0 | 93.0 | 93.0 | 90.0 | 3.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2026-04-06 | 2028-06-05 | 0 | 566d | 2025-09-12 | 2025-03-21 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | r&d | multiple | sustaining | north eu | pre-tollgate | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.0 | 47.0 | 222.0 | 0.0 | 0.0645161290322581 | 0.935483870967742 | 0.0 | 1.0 | 0.0 | 2028 | not specified | 3 | not specified | not specified | 1.0 | p | 201 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2026-04-06 | 2028-06-05 | not specified | not specified | 2026-06-01 | 2027-04-26 | 2028-02-14 |  | 2028-06-05 |  | not specified | -25.0 | not specified | -25.0 | not specified | -566.0 | not specified | not specified | 2026-06-26 00:00:00 | 2027-05-21 00:00:00 | 2028-03-10 00:00:00 | not specified | 2028-06-30 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | -25d | -25d | -25d | -25d | dates not set | -0.0441696113074205 | -0.0441696113074205 | -0.0441696113074205 | -0.0441696113074205 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | stage 0 - pre-tollgate | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0
05-62251 ei2 30, 60mm (rl,ru,gt,hl) | p-0142 | not specified | mateus hermann | nadezda melnikova | project | 62251 | 62251: en program scandinavia | not specified | nadezda melnikova | r&d europe r&d europe north | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.0 | 2026-02-02 | 2029-05-03 | 849d | p5 project starts once rnd team starts to work on the p3 fire exap drawings | not specified | not specified | not specified | green | sideways | yellow | green | yellow | green | yellow | green | 0 | 0 | 0.0 | 3.0 | 81.0 | 0.0 | 0.0 | 0.0 | 84.0 | 84.0 | 84.0 | 84.0 | 84.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2028-06-02 | 2030-12-30 | 0 | 672d | 2025-09-12 | 2025-03-21 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | r&d | multiple | sustaining | north eu | pre-tollgate | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.0 | 47.0 | 222.0 | 0.0 | 0.0357142857142857 | 0.964285714285714 | 0.0 | 1.0 | 0.0 | 2029 | not specified | 3 | not specified | not specified | 1.0 | p | 202 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2028-06-02 | 2030-12-30 | not specified | not specified | [6 empty] | not specified | 851.0 | not specified | 606.0 | not specified | -849.0 | not specified | not specified | 2026-05-05 00:00:00 | not specified | 2028-11-23 00:00:00 | not specified | 2029-05-03 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | stage 0 - pre-tollgate | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0
06-62251 ei2 60, 60mm (gts,rls) | p-0143 | not specified | mateus hermann | nadezda melnikova | project | 62251 | 62251: en program scandinavia | not specified | nadezda melnikova | r&d europe r&d europe north | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.0 | 2028-09-25 | 2031-08-19 | 757d | p6 project starts once rnd team starts to work on the p3 fire exap drawings | not specified | not specified | not specified | green | sideways | yellow | green | yellow | green | yellow | green | 0 | 0 | 0.0 | 9.0 | 88.0 | 0.0 | 0.0 | 9.0 | 97.0 | 97.0 | 97.0 | 97.0 | 88.0 | 9.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2028-04-11 | 2031-04-02 | 0 | 777d | 2025-09-02 | 2025-03-21 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | r&d | multiple | sustaining | north eu | pre-tollgate | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.0 | 57.0 | 222.0 | 0.0 | 0.0927835051546392 | 0.907216494845361 | 0.0 | 1.0 | 0.0 | 2031 | not specified | 3 | not specified | not specified | 1.0 | p | 203 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2028-04-11 | 2031-04-02 | not specified | not specified | [6 empty] | not specified | -167.0 | not specified | -139.0 | not specified | -757.0 | not specified | not specified | 2029-06-05 00:00:00 | 2030-06-25 00:00:00 | 2031-04-29 00:00:00 | not specified | 2031-08-19 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | stage 0 - pre-tollgate | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0
07-62251 ei2 30, 40mm (o,ol ) steel frame | p-0145 | not specified | mateus hermann | nadezda melnikova | project | 62251 | 62251: en program scandinavia | not specified | nadezda melnikova | r&d europe r&d europe north | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.15 | 2024-09-02 | 2030-03-25 | 1451d | the internal concept testing started 14th march 2025 which was expected to be wrapped up by mid june 2025 is extended till middle of nov. the already revised timeline is negatively affected (furnace break down & as a result of it testing back log) by at least 2,5 month. | assortment of the combination of steel frame with wooden door is finalized. the testing transferred to rise was completed on 16/10, the result is not satisfying (integrity failure). | sustainability review is in progress. rnd visits the steel frame suppliers on nov 3-5. the main stakeholders to decide how to proceed with the project on nov 6th. another round of internal testing is planned middle of nov. cost calculation for door set with steel frame. | not specified | yellow | sideways | red | green | red | red | yellow | green | 4 | 0 | 2.0 | 5.0 | 68.0 | 26.0 | 2.0 | 4.0 | 20.0 | 20.0 | 101.0 | 75.0 | 67.0 | 8.0 | 259999.999999999 | 0.0 | 259999.999999999 | 61778.8235294116 | 0.0 | 61778.8235294116 | 0.0 | 197647.058823529 | 0.0 | 197647.058823529 | 0.0 | 259425.88235294 | 0.0 | 259425.88235294 | 0.0 | 574.117647058822 | 0.0 | 574.117647058822 | 0.00220814479638009 | 0.0 | 0.00220814479638009 | 2025-10-27 | 2024-09-02 | 2028-09-15 | 0 | 1055d | 2025-10-28 | 2025-10-23 | not specified | 4 | not specified | not specified | 0 | 0 | 1 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 221000.0 | 0.0 | 221000.0 | 52512.0 | 0.0 | 52512.0 | 0.0 | 168000.0 | 0.0 | 168000.0 | 0.0 | 220512.0 | 0.0 | 220512.0 | 0.0 | 488.0 | 0.0 | 488.0 | 0.00220814479638009 | 0.0 | 0.00220814479638009 | not specified | active | eur | r&d | multiple | sustaining | north eu | development | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.20882150241213 | 1.0 | 6.0 | 0.0198019801980198 | 0.0495049504950495 | 0.673267326732673 | 0.257425742574257 | 0.198019801980198 | 0.801980198019802 | 2030 | not specified | 3 | not specified | not specified | 1.0 | p | 204 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2024-09-02 | 2028-09-15 | not specified | not specified | 2024-12-19 | 2026-08-14 | 2028-06-16 |  | 2028-09-15 |  | not specified | 0.0 | not specified | -556.0 | not specified | -1451.0 | not specified | not specified | 2024-12-19 00:00:00 | 2026-10-22 00:00:00 | 2028-04-20 00:00:00 | not specified | 2028-06-22 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0 | -69d | 57d | 85d | dates not set | 0.0 | -0.0475534114403859 | 0.0392832529290145 | 0.0585802894555479 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | stage 2 - development | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.15
08-62251 ei2 30, 60mm (pl,al,rl,ru,hl) steel frame | p-0146 | not specified | mateus hermann | nadezda melnikova | project | 62251 | 62251: en program scandinavia | not specified | nadezda melnikova | r&d europe r&d europe north | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.0 | 2026-02-02 | 2029-04-19 | 839d | p8 project starts once rnd team starts to work on the p3 fire exap drawings | not specified | not specified | not specified | green | sideways | green | green | green | green | yellow | green | 0 | 0 | 0.0 | 3.0 | 81.0 | 0.0 | 0.0 | 0.0 | 84.0 | 84.0 | 84.0 | 84.0 | 84.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2027-09-09 | 2031-05-05 | 0 | 953d | 2025-09-12 | 2025-03-21 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | r&d | multiple | sustaining | north eu | pre-tollgate | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.0 | 47.0 | 222.0 | 0.0 | 0.0357142857142857 | 0.964285714285714 | 0.0 | 1.0 | 0.0 | 2029 | not specified | 3 | not specified | not specified | 1.0 | p | 205 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2027-09-09 | 2031-05-05 | not specified | not specified | [6 empty] | not specified | 584.0 | not specified | 746.0 | not specified | -839.0 | not specified | not specified | 2026-05-19 00:00:00 | not specified | 2028-11-16 00:00:00 | not specified | 2029-03-01 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | stage 0 - pre-tollgate | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0
09-62251 ei260, 60mm (nl,vl,rls,gts) steel frame | p-0147 | not specified | mateus hermann | nadezda melnikova | project | 62251 | 62251: en program scandinavia | not specified | nadezda melnikova | r&d europe r&d europe north | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.0 | 2030-10-25 | 2032-11-09 | 533d | p9 project starts once rnd team starts to work on the p3 fire exap drawings | not specified | not specified | not specified | green | sideways | green | green | green | green | yellow | green | 0 | 0 | 0.0 | 5.0 | 88.0 | 0.0 | 0.0 | 5.0 | 93.0 | 93.0 | 93.0 | 93.0 | 88.0 | 5.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2030-10-25 | 2032-11-09 | 0 | 533d | 2025-09-02 | 2025-03-21 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | r&d | multiple | sustaining | north eu | pre-tollgate | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.0 | 57.0 | 222.0 | 0.0 | 0.0537634408602151 | 0.946236559139785 | 0.0 | 1.0 | 0.0 | 2032 | not specified | 3 | not specified | not specified | 1.0 | p | 206 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2030-10-25 | 2032-11-09 | not specified | not specified | 2030-12-23 | 2031-06-30 | 2032-07-20 |  | 2032-11-09 |  | not specified | 0.0 | not specified | 0.0 | not specified | -533.0 | not specified | not specified | 2030-12-23 00:00:00 | 2031-06-30 00:00:00 | 2032-07-20 00:00:00 | not specified | 2032-11-09 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0 | 0 | 0 | 0 | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | stage 0 - pre-tollgate | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0
62251 implementation forserum | p-0148 | not specified | mateus hermann | nadezda melnikova | project | 62251 | 62251: en program scandinavia | not specified | nadezda melnikova | r&d europe r&d europe north | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.28 | 2024-12-16 | 2027-03-16 | 587d | dependency with cpq. the team cannot move forward with the implementation. expecting double work as we are forced to implement in the existing system. #39. glass aperture size. different rules on both sites. #36. amount of hinges. glazing- implement drawings to local quality systems & update erp glass types / sizes. implement drawings to local quality systems testing objects (internal & external) manufacturing - significant load is expected in oct-nov 2025. | internal testing and quality evaluation of concepts a and c is completed. no additional testing is expected. sonder felding is performing the testing in oct-nov. the team agreed in case forserum missed on smth critical sdrf will catch it. door blank - implementation is completed design. decoration (routering and moulding) - implementation is completed | frame - mounting update erp forserum - missing how to connect the new name in erp frame set. update erp in progress frame components: make reference drawings for erp setup - it help may be needed for extra fields in erp steel frame – thresholds - in progress hinges (wooden frames) - to start in nov harmonization to start: #7 size of kicking plates. forserum. #25 chamferd and no chamferd in the bottom of the door leaf. forserum. #36. amount & type of hinges. forserum. testing objects (internal & external) manufacturing - significant load is expected in oct-nov. | #33 hardware standardization (cable loop placement). implementation might not be possible as rnd is not ready with the input. misunderstanding between the teams. a meeting a booked to see what can be done. mechanical locks / single point locks 1m delayed. emma to support. matrix for lock/striker combination forserum placement of locktype vs height forserum door blank. update erp sdrf is 1 month delayed. forserum is not able to share prioritising other work. emma to support. | yellow | angle up | yellow | green | green | green | green | green | 0 | 0 | 13.0 | 0.0 | 122.0 | 20.0 | 13.0 | 5.0 | 0.0 | 0.0 | 155.0 | 135.0 | 119.0 | 16.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2024-12-16 | 2027-03-16 | 0 | 587d | 2025-10-28 | 2025-10-23 | true | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | r&d | multiple | sustaining | north eu | implementation / execution | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.388415672913118 | 1.0 | 6.0 | 0.0838709677419355 | 0.0 | 0.787096774193548 | 0.129032258064516 | 0.0 | 1.0 | 2027 | not specified | 3 | not specified | not specified | 1.0 | p | 207 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2024-12-16 | 2027-03-16 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | 0.0 | not specified | -587.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified | 2025-07-02 | not specified | not specified | false | stage 3 - implementation | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.28
11-62251 ei2 60, 87mm (hls) | p-0242 | not specified | mateus hermann | nadezda melnikova | project | 62251 | 62251: en program scandinavia | not specified | nadezda melnikova | r&d europe r&d europe north | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.0 | 2030-07-29 | 2032-02-06 | 400d | p11 project starts once rnd team starts to work on the p5 fire exap drawings | not specified | not specified | not specified | green | sideways | green | green | green | green | yellow | green | 0 | 0 | 0.0 | 0.0 | 1.0 | 0.0 | 0.0 | 0.0 | 1.0 | 1.0 | 1.0 | 1.0 | 1.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2030-07-29 | 2032-02-06 | 0 | 400d | 2025-09-02 | 2025-03-21 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | r&d | multiple | sustaining | north eu | pre-tollgate | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.0 | 57.0 | 222.0 | 0.0 | 0.0 | 1.0 | 0.0 | 1.0 | 0.0 | 2032 | not specified | 3 | not specified | not specified | 1.0 | p | 208 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2030-07-29 | 2032-02-06 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | 0.0 | not specified | -400.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | stage 0 - pre-tollgate | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0
62251 implementation sonder felding | p-0243 | not specified | mateus hermann | nadezda melnikova | project | 62251 | 62251: en program scandinavia | not specified | nadezda melnikova | r&d europe r&d europe north | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.15 | 2025-02-10 | 2027-09-13 | 676d | xal reprograming has started. internal testing and quality evaluation of concepts a and c is in progress through oct-nov | new fields created in xal. harmonization. #34 assembly of finger protection on frame - equipment is found, ecm to be raised to procure it. | testing of newly created fields in xal. rul es set up - test xal through nov. | #3 hinge milling depth 3228/3278. cerf approval is postponed to q1 2026. if not approved then this will have a negative impact on the entire en program. door blank. update erp sdrf. amount of item numbers regarding ml and mlb need clarification with forserum and the colleagues in charge are working on other priority topics. the implementation is delayed by by at least 1 months. | yellow | sideways | yellow | green | yellow | green | green | green | 0 | 0 | 1.0 | 3.0 | 138.0 | 22.0 | 1.0 | 7.0 | 0.0 | 0.0 | 164.0 | 142.0 | 138.0 | 4.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-02-10 | 2027-08-20 | 0 | 660d | 2025-10-28 | 2025-10-23 | true | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | r&d | multiple | sustaining | north eu | implementation / execution | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.27810650887574 | 1.0 | 6.0 | 0.00609756097560976 | 0.0182926829268293 | 0.841463414634146 | 0.134146341463415 | 0.0 | 1.0 | 2027 | not specified | 3 | not specified | not specified | 1.0 | p | 209 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-02-10 | 2027-08-20 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | -24.0 | not specified | -676.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified | 2025-07-02 | not specified | not specified | false | stage 3 - implementation | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.15
13-62251 ei2 30, 40mm (ml) | p-0269 | not specified | nadezda melnikova | nadezda melnikova | project | 62251 | 62251: en program scandinavia | not specified | nadezda melnikova | r&d europe r&d europe north | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.0 | 2030-07-29 | 2032-02-17 | 407d | p13 project starts once p11 feasibility ends | not specified | not specified | not specified | green | sideways | green | green | green | green | yellow | green | 1 | 0 | 0.0 | 0.0 | 1.0 | 0.0 | 0.0 | 0.0 | 1.0 | 1.0 | 1.0 | 1.0 | 1.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2030-07-29 | 2032-02-17 | 0 | 407d | 2025-09-02 | 2025-03-21 | not specified | 1 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | r&d | multiple | sustaining | north eu | pre-tollgate | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.0 | 57.0 | 222.0 | 0.0 | 0.0 | 1.0 | 0.0 | 1.0 | 0.0 | 2032 | not specified | 3 | not specified | not specified | 1.0 | p | 210 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2030-07-29 | 2032-02-17 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | 0.0 | not specified | -407.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | 13-62251 ei30 40mm (ml) | not specified |  | not specified | not specified | false | stage 0 - pre-tollgate | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0
62251 implementation rakvere | p-0283 | pmo000102 ei30 40mm steel mini & s-frames | brian schweitz | nadezda melnikova | project | 62251 | 62251: en program scandinavia | not specified | nadezda melnikova | r&d europe r&d europe north | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.06 | 2025-08-01 | 2026-12-18 | 361d | rakvere committed to the implementation timeline. | agreement with rnd: rakvere will step out from the proofreading process. all what is related to harmonization of frames, rakvere need to be involved into meetings where decisions are made and details are discussed. | frame - mounting & #41. predrilling for consumer and project market. - implementation is in progress and expected to be completed in dec. | not specified | green | angle up | red | yellow | red | green | yellow | green | 0 | 0 | 0.0 | 14.0 | 10.0 | 2.0 | 0.0 | 0.0 | 22.0 | 21.0 | 26.0 | 24.0 | 20.0 | 4.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-09-08 | 2026-05-01 | 0 | 170d | 2025-10-27 | 2025-10-23 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | r&d | interior | sustaining | north eu | implementation / execution | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.177285318559557 | 2.0 | 6.0 | 0.0 | 0.538461538461538 | 0.384615384615385 | 0.0769230769230769 | 0.846153846153846 | 0.153846153846154 | 2026 | not specified | 3 | not specified | not specified | 1.0 | p | 162 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-09-08 | 2026-05-01 | not specified | not specified | [6 empty] | not specified | 38.0 | not specified | -231.0 | not specified | -361.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified | 2025-07-02 | not specified | not specified | false | stage 3 - implementation | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.06
platform program | pg-0136 | not specified | mateus hermann | boel sandberg | program | pg-0136 | pg-0136: platform program | not specified | boel sandberg | r&d europe r&d europe north | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | program dashboard | finance dashboard | 0.604721065778518 | 2023-12-14 | 2027-09-28 | 989d | platform program do only consist of kupio factory. remaining projects are now cut out from smartsheet program and run as projects | åstorp project will be run as seperate project starting again in aug and will be a seperate project not included in platform program | meeting with åstorp to align start up date | not specified | green | on track | yellow | on track | schedule not set | red | yellow | green | 0 | 0 | 1.0 | 94.0 | 52.0 | 142.0 | 3.0 | 47.0 | 115.0 | 115.0 | 289.0 | 147.0 | 91.0 | 56.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 |  | 2023-12-14 | 2025-12-02 | 0 | 514d | 2025-09-23 | 2025-10-29 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | r&d | not specified | not specified | north eu | see project details | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.495449949443883 | 36.0 | 0.0 | 0.00346020761245675 | 0.325259515570934 | 0.179930795847751 | 0.491349480968858 | 0.397923875432526 | 0.602076124567474 | 2027 | not specified | 2 | not specified | not specified | not specified | pg | 136 | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | [6 empty] | not specified | not specified | not specified | not specified | not specified | -989.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.60472
consolidation of category c products across europe - interior 1 | 48088 | not specified | mateus hermann | boel sandberg | project | pg-0136 | pg-0136: platform program | not specified | boel sandberg | r&d europe r&d europe north | not specified | not specified | boel sandberg | elisa uussalu | not specified | not specified | not specified | sourcing | europe: sourcing (direct & indirect) | engineering | l3 (planned) | on hold | 48088.0 | not specified | project dashboard | project finance dashboard | 0.99 | 2024-11-22 | 2024-11-22 | 1d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | up | yellow | yellow | green | green | yellow | green | 0 | 0 | 0.0 | 93.0 | 0.0 | 1.0 | 0.0 | 0.0 | 94.0 | 94.0 | 94.0 | 93.0 | 88.0 | 5.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-05-07 | 2025-05-07 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | canceled | eur | r&d | interior | vave | north eu | pre-tollgate | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0.168827472 | not specified | 0.00253 | 2023-10-17 | 2025-08-29 | on plan | not specified | 1.0 | on track | 1.0 | 175.0 | 175.0 | 0.0 | 0.98936170212766 | 0.0 | 0.0106382978723404 | 1.0 | 0.0 | previous year | n | 3 | not specified | not specified | 1.0 | p | 292 | 1.0 | 1.0 | 1.0 | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | 40.0 | not specified | 216.0 | not specified | -1.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | stage 0 - pre-tollgate | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.99
hdf eu standardization/tender | 5329 | not specified | mateus hermann | boel sandberg | project | pg-0136 | pg-0136: platform program | not specified | boel sandberg | r&d europe r&d europe north | not specified | not specified | boel sandberg | jan dziubak | not specified | not specified | not specified | sourcing | europe: sourcing (direct & indirect) | engineering | l5 (realised) | on track | 5329.0 | not specified | project dashboard | project finance dashboard | 1.0 | 2024-04-25 | 2025-02-13 | 211d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | sideways | yellow | blue | yellow | green | yellow | green | 0 | 0 | 0.0 | 0.0 | 0.0 | 7.0 | 0.0 | 0.0 | 7.0 | 7.0 | 7.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-02-18 | 2025-04-03 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | completed | eur | r&d | interior | vave | north eu | realize value / close / care period | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0.26136 | not specified | 0.044 | 2023-08-11 | 2024-06-19 | executed | not specified | 1.0 | on track | 1.0 | 253.0 | 209.0 | 0.0 | 0.0 | 0.0 | 1.0 | 1.0 | 0.0 | current year | n | 3 | not specified | not specified | 1.0 | p | 291 | 1.0 | 1.0 | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | 251.0 | not specified | 133.0 | not specified | -211.0 | not specified | not specified | 2024-04-25 00:00:00 | 2024-04-25 00:00:00 | 2024-04-25 00:00:00 | not specified | 2024-04-25 00:00:00 | 2025-02-13 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | stage 5 - care period | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 1
eu platform harmonization nordic | 66912 | not specified | boel sandberg | boel sandberg | project | pg-0136 | pg-0136: platform program | not specified | boel sandberg | r&d europe r&d europe north | not specified | not specified | boel sandberg | boel sandberg | not specified | not specified | not specified | manufacturing | nordics: manufacturing - finland | engineering | l3 (planned) | on track | 66912.0 | not specified | project dashboard | project finance dashboard | 0.52 | 2023-12-14 | 2027-09-28 | 989d | platform åstorp implementation put on paused | decsion to put the design and implementation phase on hold | not specified | not specified | green | sideways | red | green | red | red | yellow | green | 6 | 3 | 1.0 | 1.0 | 52.0 | 134.0 | 3.0 | 47.0 | 14.0 | 14.0 | 188.0 | 54.0 | 3.0 | 51.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2023-12-14 | 2025-12-02 | 0 | 514d | 2025-09-23 | 2025-09-23 | not specified | 11 | not specified | not specified | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | on-hold | eur | r&d | multiple | vave | north eu | development | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0.9427 | not specified | 0.0869 | 2024-08-16 | 2028-12-29 | on plan | not specified | 1.0 | on track | 0.495449949443883 | 36.0 | 36.0 | 0.00531914893617021 | 0.00531914893617021 | 0.276595744680851 | 0.712765957446809 | 0.074468085106383 | 0.925531914893617 | 2027 | n | 3 | not specified | not specified | 1.0 | p | 285 | 1.0 | 1.0 | not specified | not specified | not specified | not specified | 2023-12-14 | 2025-12-02 | not specified | not specified | 2024-07-01 | 2024-12-20 | 2025-04-02 |  | 2025-05-27 |  | not specified | 0.0 | not specified | -665.0 | not specified | -989.0 | not specified | not specified | 2024-07-01 00:00:00 | 2025-02-06 00:00:00 | 2025-04-17 00:00:00 | not specified | 2025-05-28 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0 | -48d | -15d | -1d | dates not set | 0.0 | -0.0485338725985844 | -0.0151668351870576 | -0.00101112234580384 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | stage 2 - development | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.52
builders paradise - divestiture | p-0153 | jeld-wen has entered into a contract to sell builders paradise. it will be engaging in activities to disengage any shared services with builders paradise. | ryan russel | ryan russel | project | standalone project | standalone project | bus-na/corp/it | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | finance dashboard | 0.38 | 2024-06-06 | 2024-11-29 | 127d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | on track | green | green | green | green | yellow | green | 0 | 0 | 3.0 | 0.0 | 10.0 | 9.0 | 13.0 | 13.0 | 22.0 | 22.0 | 22.0 | 13.0 | 13.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2024-06-06 | 2024-11-29 | 0 | 127d | 2024-08-26 | 2025-05-28 | true | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on-hold | not specified | it | not specified | not specified | not specified | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 1.0 | 429.0 | 154.0 | 0.136363636363636 | 0.0 | 0.454545454545455 | 0.409090909090909 | 1.0 | 0.0 | previous year | not specified | 3 | not specified | not specified | not specified | p | 153 | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | [6 empty] | not specified | not specified | not specified | not specified | not specified | -127.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.38
thames | 4995 | erp consolidation into one system (prms) for logstor sales market, swe and nor. | amer basic | amer basic | program | 4995 | 4995: thames | it-eu | not specified | it it north eu it-eu | not specified | amer basic | peter moller | not specified | peter sørensen | rachael horton - farmer | not specified | not specified | not specified | not specified | not specified | on track | 4995.0 | not specified | program dashboard | finance dashboard | 0.642579113924051 | 2024-02-29 | 2026-04-23 | 561d | see workstream updates | not specified | not specified | not specified | yellow | on track | yellow | on track | red | green | yellow | red | 0 | 0 | 108.0 | 499.0 | 61.0 | 714.0 | 91.0 | 74.0 | 876.0 | 857.0 | 1239.0 | 525.0 | 435.0 | 172.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 |  | 2024-08-01 | 2025-08-31 | 0 | 282d | 2025-10-14 | 2025-10-29 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | it | not specified | not specified | north eu | see project details | not specified | increase revenue | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | 1.0 | on track | 0.775401069518717 | 15.0 | 0.0 | 0.0871670702179177 | 0.40274414850686 | 0.0492332526230831 | 0.576271186440678 | 0.707021791767555 | 0.292978208232445 | 2026 | n | 2 | not specified | not specified | not specified | p | 154 | not specified | 1.0 | not specified | not specified | not specified | not specified |  |  | not specified | not specified | [6 empty] | not specified | not specified | not specified | not specified | not specified | -561.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | focussed growth | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.64258
project thames: infrastructure | 57216 | eu infrastructure consolidation | ben bridgewater | amer basic | project | 4995 | 4995: thames | not specified | not specified | it it north eu it-eu infrastructure | not specified | amer basic | not specified | jens schjott | peter sorensen | rachael horton-farmer | not specified | other | support functions: global it - europe | it | l1 (identified) | on track | 57216.0 | not specified | project dashboard | project finance dashboard | 0.66 | 2024-08-01 | 2026-04-23 | 451d | w42: network has been setup in the new office over lte as we are struggling with isp providers to take over the existing fiber lines. escalations are in place with nitel and tdc. next step is a ramp up test procedure with few user to ensure that the lte network is "good enough" prior a potential full-scale office move by end of october. to remove all it dependency in current office we need the existing vpn/firewall migrated (currently no plan/date for this). | w42: network over lte established and works. need further testing to prove it is sufficient with more users. | w43: evaluate initial network quality testing, and proceed with moving more users to the new office for final quality testing prior full scale move. | ptg:vpn/firewall- need timeline (dependency for exiting old logstor) | yellow | sideways | red | green | red | green | green | green | 0 | 0 | 4.0 | 12.0 | 44.0 | 82.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 241176.470588234 | 152941.176470588 | 88235.2941176467 | 9635.29411764703 | 9635.29411764703 | 0.0 | 0.0 | 113529.411764705 | 25294.1176470587 | 88235.2941176467 | 0.0 | 123164.705882353 | 34929.4117647058 | 88235.2941176467 | 0.0 | 118011.764705882 | 118011.764705882 | 0.0 | 0.489317073170733 | 0.771615384615384 | 0 | 2025-10-27 | 2024-08-01 | 2025-08-31 | 0 | 282d |  | 2025-10-22 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 205000.0 | 130000.0 | 75000.0 | 8190.0 | 8190.0 | 0.0 | 0.0 | 96500.0 | 21500.0 | 75000.0 | 0.0 | 104690.0 | 29690.0 | 75000.0 | 0.0 | 100310.0 | 100310.0 | 0.0 | 0.489317073170732 | 0.771615384615385 | 0.0 | not specified | active | eur | it | not specified | not specified | eu | realize value / close / care period | not specified | increase revenue | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not planned (l2 to l4) | not specified | 1.0 | on track | 0.720620842572062 | not specified | 7.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 1.0 | 2026 | n | 3 | not specified | not specified | not specified | p | 164 | 1.0 | 1.0 | not specified | not specified | not specified | not specified | 2024-08-01 | 2025-08-31 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | -235.0 | not specified | -451.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | focussed growth | 0.0 | one | not specified | project thames: infrastructure | not specified |  | not specified | not specified | false | stage 5 - care period | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.66
project thames: sales workstream | p-0156 | transfer consumer sales into prms. develop prms and onboard dk users | amer basic | amer basic | project | 4995 | 4995: thames | it-eu | not specified | it it north eu it-eu | not specified | amer basic | dorthe schou | peter moller | peter sørensen | rachael horton - farmer | not specified | not specified | not specified | not specified | l3 (planned) | on track | not specified | not specified | project dashboard | project finance dashboard | 0.92 | 2024-08-12 | 2025-12-15 | 351d | w25:final dk customer group moved to åstorp. no it issues reported. | w25: no it issues during go live | w26: handover ic200/prms integration to bau | none at this moment | blue | sideways | red | green | red | green | yellow | green | 0 | 0 | 0.0 | 0.0 | 14.0 | 131.0 | 0.0 | 0.0 | 26.0 | 26.0 | 145.0 | 14.0 | 14.0 | 0.0 | 741176.470588233 | 741176.470588233 | 0.0 | 449067.776470587 | 369366.694117646 | 79701.0823529409 | 37877.7999999999 | 116826.117647058 | 0.0 | 116826.117647058 | 0.0 | 565893.894117645 | 369366.694117646 | 196527.199999999 | 37877.7999999999 | 175282.576470588 | 371809.776470587 | -196527.199999999 | 0.236492365079366 | 0.501648111111111 | 0 | 2025-10-27 | 2024-08-12 | 2025-07-07 | 0 | 236d | 2025-10-14 | 2025-10-16 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 630000.0 | 630000.0 | 0.0 | 381707.61 | 313961.69 | 67745.92 | 32196.13 | 99302.2 | 0.0 | 99302.2 | 0.0 | 481009.81 | 313961.69 | 167048.12 | 32196.13 | 148990.19 | 316038.31 | -167048.12 | 0.236492365079365 | 0.501648111111111 | 0.0 | not specified | completed | eur | it | not specified | not specified | north eu | realize value / close / care period | not specified | increase revenue | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.905982905982906 | 15.0 | 13.0 | 0.0 | 0.0 | 0.096551724137931 | 0.903448275862069 | 0.179310344827586 | 0.820689655172414 | current year | not specified | 3 | not specified | not specified | not specified | p | 165 | 1.0 | not specified | not specified | not specified | dorthe schou | not specified | 2024-08-12 | 2025-07-07 | not specified | not specified | 2024-11-01 | 2024-11-01 | 2024-11-01 | 2025-02-24 | 2025-07-07 | 2025-07-07 | not specified | 0.0 | not specified | -161.0 | not specified | -351.0 | not specified | not specified | 2024-11-01 00:00:00 | 2024-11-01 00:00:00 | 2024-11-01 00:00:00 | 2025-03-24 00:00:00 | 2025-12-15 00:00:00 | 2025-12-15 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0 | 0 | 0 | -161d | -161d | 0.0 | 0.0 | 0.0 | -0.458689458689459 | -0.458689458689459 | not specified | not specified | not specified | not specified | focussed growth | 0.0 | one | not specified | project thames: sales workstream | not specified |  | not specified | not specified | false | stage 5 - care period | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.92
project thames: terminal workstream | p-0157 | move terminal logstor to åstorp. it exit from logstor. | amer basic | amer basic | project | 4995 | 4995: thames | it-eu | not specified | not specified | not specified | amer basic | stefan ekberg | peter moller | peter sørensen | rachael horton - farmer | not specified | not specified | not specified | not specified | l3 (planned) | on track | not specified | not specified | project dashboard | project finance dashboard | 0.0 |  |  | 0 | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | sideways | yellow | yellow | schedule not set | green | yellow | green | 0 | 0 | 27.0 | 56.0 | 0.0 | 40.0 | 27.0 | 14.0 | 117.0 | 117.0 | 123.0 | 83.0 | 69.0 | 14.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-07-22 | 2024-10-30 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | it | not specified | not specified | north eu | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.0 | 99.0 | 364.0 | 0.219512195121951 | 0.455284552845528 | 0.0 | 0.32520325203252 | 0.951219512195122 | 0.048780487804878 | not specified | not specified | 3 | not specified | not specified | not specified | p | 166 | 1.0 | not specified | not specified | not specified | stefan ekberg | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | not specified | not specified | not specified | not specified | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | focussed growth | 0.0 | one | not specified | project thames: terminal workstream | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0
project thames: new location for office staff | p-0227 | not specified | amer basic | peter moller | project | 4995 | 4995: thames | not specified | not specified | not specified | not specified | amer basic | peter moller | peter moller | peter sørensen | rachael horton - farmer | not specified | other | not specified | not specified | l3 (planned) | on track | not specified | not specified | project dashboard | project finance dashboard | 0.0 |  |  | 0 | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | sideways | yellow | yellow | schedule not set | green | yellow | green | 0 | 0 | 0.0 | 62.0 | 0.0 | 0.0 | 0.0 | 0.0 | 62.0 | 62.0 | 62.0 | 62.0 | 53.0 | 9.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2024-10-28 | 2024-10-30 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | it | not specified | not specified | eu | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | 1.0 | not specified | on track | 0.0 | 366.0 | 364.0 | 0.0 | 1.0 | 0.0 | 0.0 | 1.0 | 0.0 | not specified | not specified | 3 | not specified | not specified | 1.0 | p | 167 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | not specified | not specified | not specified | not specified | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | project thames: new location for office staff | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0
project thames: exit site | p-0228 | not specified | amer basic | peter moller | project | 4995 | 4995: thames | not specified | not specified | it it north eu it-eu | not specified | amer basic | peter moller | peter moller | peter sørensen | rachael horton - farmer | not specified | other | not specified | not specified | l3 (planned) | on track | not specified | not specified | project dashboard | project finance dashboard | 1.0 | 2025-04-01 | 2025-04-16 | 12d | this project is on hold by the business | not specified | not specified | not specified | green | on track | yellow | blue | yellow | green | yellow | green | 0 | 0 | 0.0 | 15.0 | 0.0 | 54.0 | 0.0 | 0.0 | 68.0 | 53.0 | 69.0 | 15.0 | 0.0 | 15.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-04-16 | 2025-04-14 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | on-hold | eur | it | not specified | not specified | north eu | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | 1.0 | not specified | on track | 1.0 | 196.0 | 198.0 | 0.0 | 0.217391304347826 | 0.0 | 0.782608695652174 | 0.985507246376812 | 0.014492753623188 | current year | not specified | 3 | not specified | not specified | 1.0 | p | 168 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | -90.0 | not specified | 71.0 | not specified | -12.0 | not specified | not specified | 2025-04-01 00:00:00 | 2025-04-01 00:00:00 | 2025-04-01 00:00:00 | 2025-04-01 00:00:00 | 2025-04-01 00:00:00 | 2025-04-01 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | project thames: exit site | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 1
manufacturing move est | p-0237 | not specified | amer basic | amer basic | project | 4995 | 4995: thames | not specified | not specified | not specified | not specified | amer basic | not specified | not specified | peter sørensen | rachael horton - farmer | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.34 | 2024-02-29 | 2025-06-30 | 348d | on track | not specified | not specified | not specified | on track | on track | red | yellow | red | green | yellow | green | 0 | 0 | 5.0 | 65.0 | 1.0 | 2.0 | 2.0 | 4.0 | 73.0 | 73.0 | 73.0 | 71.0 | 53.0 | 18.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-02-21 |  | #invalid value | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | on track | eur | it | not specified | not specified | eu | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | 1.0 | not specified | on track | 1.0 | 250.0 | on track | 0.0684931506849315 | 0.89041095890411 | 0.0136986301369863 | 0.0273972602739726 | 1.0 | 0.0 | current year | not specified | 3 | not specified | not specified | 1.0 | p | 193 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | 307.0 | not specified | -4.0 | not specified | -348.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | manufacturing move est | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.34
manufacturing move outsourcing | p-0238 | not specified | amer basic | amer basic | project | 4995 | 4995: thames | not specified | not specified | not specified | not specified | amer basic | not specified | not specified | peter sørensen | rachael horton - farmer | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.83 | 2024-04-01 | 2025-04-23 | 278d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | sideways | yellow | yellow | yellow | green | yellow | green | 0 | 0 | 6.0 | 58.0 | 1.0 | 24.0 | 7.0 | 0.0 | 62.0 | 58.0 | 89.0 | 65.0 | 53.0 | 12.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-02-21 | 2024-10-30 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | it | not specified | not specified | eu | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | 1.0 | not specified | on track | 1.0 | 250.0 | 364.0 | 0.0674157303370787 | 0.651685393258427 | 0.0112359550561798 | 0.269662921348315 | 0.696629213483146 | 0.303370786516854 | current year | not specified | 3 | not specified | not specified | 1.0 | p | 194 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | 275.0 | not specified | 64.0 | not specified | -278.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | manufacturing move outsourcing | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.83
manufacturing move swe | p-0239 | not specified | amer basic | amer basic | project | 4995 | 4995: thames | not specified | not specified | not specified | not specified | amer basic | not specified | not specified | peter sørensen | rachael horton - farmer | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.61 | 2024-02-29 | 2025-08-29 | 392d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | sideways | red | yellow | red | green | yellow | green | 0 | 0 | 58.0 | 113.0 | 0.0 | 175.0 | 51.0 | 52.0 | 325.0 | 325.0 | 345.0 | 170.0 | 87.0 | 83.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-08-28 | 2024-10-30 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | it | not specified | not specified | eu | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | 1.0 | not specified | on track | 1.0 | 62.0 | 364.0 | 0.168115942028986 | 0.327536231884058 | 0.0 | 0.507246376811594 | 0.942028985507246 | 0.057971014492754 | current year | not specified | 3 | not specified | not specified | 1.0 | p | 195 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | 307.0 | not specified | -64.0 | not specified | -392.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | manufacturing move swe | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.61
manufacturing move fi | p-0240 | not specified | amer basic | amer basic | project | 4995 | 4995: thames | not specified | not specified | not specified | not specified | amer basic | not specified | not specified | peter sørensen | rachael horton - farmer | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.34 | 2024-02-29 | 2025-06-30 | 348d | on track | not specified | not specified | not specified | on track | on track | red | yellow | red | green | yellow | green | 0 | 0 | 5.0 | 65.0 | 1.0 | 2.0 | 2.0 | 4.0 | 73.0 | 73.0 | 73.0 | 71.0 | 53.0 | 18.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-02-21 |  | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | on track | eur | it | not specified | not specified | eu | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | 1.0 | not specified | on track | 1.0 | 250.0 | on track | 0.0684931506849315 | 0.89041095890411 | 0.0136986301369863 | 0.0273972602739726 | 1.0 | 0.0 | current year | not specified | 3 | not specified | not specified | 1.0 | p | 196 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | 307.0 | not specified | -4.0 | not specified | -348.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | manufacturing move fi | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.34
manufacturing move dk | p-0241 | not specified | amer basic | amer basic | project | 4995 | 4995: thames | not specified | not specified | not specified | not specified | amer basic | not specified | not specified | peter sørensen | rachael horton - farmer | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.82 | 2024-02-29 | 2025-06-30 | 348d | on track | not specified | not specified | not specified | on track | on track | red | yellow | red | green | yellow | green | 0 | 0 | 3.0 | 53.0 | 0.0 | 204.0 | 2.0 | 0.0 | 70.0 | 70.0 | 260.0 | 56.0 | 53.0 | 3.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-07-01 |  | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | on track | eur | it | not specified | not specified | eu | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | 1.0 | not specified | on track | 1.0 | 120.0 | on track | 0.0115384615384615 | 0.203846153846154 | 0.0 | 0.784615384615385 | 0.269230769230769 | 0.730769230769231 | current year | not specified | 3 | not specified | not specified | 1.0 | p | 197 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | 307.0 | not specified | -4.0 | not specified | -348.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | manufacturing move dk | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.82
tg: data alignment with titan | 41717 | titan to teamguru data connectivity | joel busack | joel busack | project | standalone project | standalone project | not specified | not specified | na it | not specified | not specified | not specified | joel busack | not specified | not specified | not specified | manufacturing | na - ops: supply chain | not specified | l2 (validated) | on hold | 41717.0 | not specified | project dashboard | finance dashboard | 0.38 | 2024-06-06 | 2024-11-29 | 127d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | on track | green | green | green | green | yellow | green | 0 | 0 | 3.0 | 0.0 | 10.0 | 9.0 | 13.0 | 13.0 | 22.0 | 22.0 | 22.0 | 13.0 | 13.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2024-06-06 | 2024-11-29 | 0 | 127d | 2024-08-26 | 2025-02-26 | true | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on-hold | not specified | other | not specified | not specified | not specified | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0.130553 | not specified | not specified | 2023-04-11 | 2023-12-30 | past due for l4 | not specified | 1.0 | on track | 1.0 | 429.0 | 245.0 | 0.136363636363636 | 0.0 | 0.454545454545455 | 0.409090909090909 | 1.0 | 0.0 | previous year | n | 3 | not specified | not specified | not specified | p | 155 | not specified | 1.0 | not specified | not specified | not specified | not specified |  |  | not specified | not specified | [6 empty] | not specified | not specified | not specified | not specified | not specified | -127.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.38
north star delivery metric | 68053 | establish a zero tolerance otif metric and a series of enhancements that will help us understand why we are missing our established promise dates to customers. these enhancements will include customer order profiles and order reason codes that will help define our performance at a line-item level. | chad alterio | christian suarez | project | standalone project | standalone project | not specified | not specified | it mfg. & supply chain na it na/corporate | not specified | fabio rivera | not specified | nikki smith | christian suarez | kirk kroft | not specified | supply chain | na - ops: supply chain | it | l3 (planned) | on track | 68053.0 | not specified | project dashboard | finance dashboard | 0.86 | 2024-06-10 | 2026-01-08 | 414d | wk 30: -promise date and reason codes are live with titan -mmi is estimated to launch reason codes first week of august -abs is set to launch promise date in august and reason codes late august/early september | -launch of promise date for titan and mmi -launch of reason codes for titan -reason code functionality complete for mmi -promise date functionality in test for abs | -launch of reason codes for mmi - july 31 -launch of promise date for abs - aug 15 -resnap logic for titan - july 31 | not specified | green | on track | red | green | red | green | yellow | red | 0 | 0 | 4.0 | 0.0 | 6.0 | 45.0 | 4.0 | 2.0 | 1.0 | 1.0 | 55.0 | 10.0 | 6.0 | 4.0 | 777923.0 | 618361.0 | 159562.0 | 985084.5 | 885165.5 | 99919.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 985084.5 | 885165.5 | 99919.0 | not specified | -207161.5 | -266804.5 | 59643.0 | -0.26630077784048 | -0.431470451726419 | 0.373792005615372 | 2025-10-27 | 2024-06-10 | 2025-03-13 | 0 | 199d | 2025-10-16 | 2025-07-23 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | active | not specified | it | not specified | not specified | not specified | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not planned (l2 to l4) | not specified | 1.0 | on track | 0.876811594202899 | 13.0 | 98.0 | 0.0727272727272727 | 0.0 | 0.109090909090909 | 0.818181818181818 | 0.0181818181818182 | 0.981818181818182 | 2026 | n | 3 | not specified | not specified | 1.0 | p | 168 | not specified | 1.0 | not specified | not specified | not specified | not specified |  |  | not specified | not specified | [6 empty] | not specified | not specified | not specified | not specified | not specified | -414.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.86
infrastructure plant refreshes | pg-0173 | not specified | cyndi maples | jamal mebane | program | pg-0173 | pg-0173: infrastructure plant refreshes | it-infra/service | not specified | not specified | not specified | jamal mebane | not specified | not specified | not specified | kirk kroft | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | program dashboard | finance dashboard | 0.580899805447471 | 2024-01-03 | 2025-11-21 | 493d | add the high level status of the program in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | on track | red | on track | red | green | yellow | red | 0 | 0 | 125.0 | 328.0 | 1.0 | 297.0 | 110.0 | 125.0 | 478.0 | 291.0 | 751.0 | 454.0 | 298.0 | 156.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 |  | 2024-02-02 | 2025-06-26 | 0 | 365d | 2025-09-18 | 2025-10-29 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | active | not specified | it | not specified | not specified | not specified | see project details | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.96551724137931 | 41.0 | 0.0 | 0.166444740346205 | 0.436750998668442 | 0.00133155792276964 | 0.395472703062583 | 0.636484687083888 | 0.363515312916112 | current year | not specified | 2 | not specified | not specified | not specified | pg | 173 | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | [6 empty] | not specified | not specified | not specified | not specified | not specified | -493.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.5809
sacramento - network deployment and cutover | p-0174 | network upgrade and deployment of wireless are a dependency for deployment of wms. summary requirements: cerf funding - approved under #8542. network devices are within current standard and are supported by manufacturer. wireless coverage is deployed to cover full building. deploy external wireless coverage for truck parking and space between buildings. | cyndi maples | cyndi maples | project | pg-0173 | pg-0173: infrastructure plant refreshes | not specified | not specified | not specified | not specified | cyndi maples | not specified | gordon greenland | darin lowery | kirk kroft | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | finance dashboard | 1.0 | 2024-02-29 | 2024-09-27 | 152d | close project. open att invoice pending transferred ownership to tiffany thomas since it takes 2-3 months for an invoice to get to jeld-wen. | not specified | not specified | not specified | blue | on track | yellow | blue | yellow | green | green | green | 0 | 0 | 0.0 | 0.0 | 0.0 | 50.0 | 0.0 | 0.0 | 0.0 | 0.0 | 50.0 | 0.0 | 0.0 | 0.0 | 177345.0 | 149130.0 | 28215.0 | 135902.5 | 125712.0 | 10190.5 | not specified | 0.0 | 0.0 | 0.0 | not specified | 135902.5 | 125712.0 | 10190.5 | not specified | 41442.5 | 23418.0 | 18024.5 | 0.233682934393414 | 0.157030778515389 | 0.638826865142655 | 2025-10-27 | 2024-02-29 | 2024-09-25 | 0 | 150d | 2024-09-27 | 2024-11-05 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | completed | not specified | it | not specified | not specified | not specified | realize value / close / care period | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 1.0 | 397.0 | 358.0 | 0.0 | 0.0 | 0.0 | 1.0 | 0.0 | 1.0 | previous year | not specified | 3 | not specified | not specified | not specified | p | 174 | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | [6 empty] | not specified | not specified | not specified | not specified | not specified | -152.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | stage 5 - care period | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 1
rantoul network upgrade | p-0175 | equipment is being transitioned from the hawkins facility into the rantoul plant. to ensure connectivity for the equipment, wireless needs to be expanded to provide full site connectivity. | cyndi maples | cyndi maples | project | pg-0173 | pg-0173: infrastructure plant refreshes | not specified | not specified | not specified | not specified | cyndi maples | not specified | gordon greenland | john marchionda | kirk kroft | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | finance dashboard | 1.0 | 2024-05-22 | 2024-11-04 | 119d | itlt - l4/l5 approved. schipper, mj, gordon. project closed. | not specified | not specified | not specified | blue | on track | green | blue | green | green | green | green | 0 | 0 | 0.0 | 0.0 | 0.0 | 60.0 | 0.0 | 0.0 | 0.0 | 0.0 | 60.0 | 0.0 | 0.0 | 0.0 | 387558.0 | 329588.0 | 57970.0 | 269319.91 | 257971.91 | 11348.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 269319.91 | 257971.91 | 11348.0 | not specified | 118238.09 | 71616.09 | 46622.0 | 0.305084890519613 | 0.217289737490443 | 0.80424357426255 | 2025-10-27 | 2024-05-22 | 2024-11-14 | 0 | 127d | 2025-01-30 | 2024-11-05 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | completed | not specified | it | not specified | not specified | not specified | realize value / close / care period | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 1.0 | 272.0 | 358.0 | 0.0 | 0.0 | 0.0 | 1.0 | 0.0 | 1.0 | previous year | not specified | 3 | not specified | not specified | not specified | p | 175 | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | [6 empty] | not specified | not specified | not specified | not specified | not specified | -119.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | stage 5 - care period | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 1
kissimmee wh network expansion | p-0178 | not specified | cyndi maples | jamal mebane | project | pg-0173 | pg-0173: infrastructure plant refreshes | not specified | not specified | it infrastructure na it | not specified | jamal mebane | not specified | not specified | not specified | kirk kroft | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | finance dashboard | 0.19 | 2024-06-06 | 2024-11-29 | 127d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | on track | red | red | green | green | yellow | green | 0 | 0 | 19.0 | 0.0 | 0.0 | 9.0 | 19.0 | 19.0 | 28.0 | 28.0 | 28.0 | 19.0 | 19.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2024-06-06 | 2024-11-29 | 0 | 127d | 2025-01-10 | 2025-05-27 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | active | not specified | it | not specified | not specified | not specified | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 1.0 | 292.0 | 155.0 | 0.678571428571429 | 0.0 | 0.0 | 0.321428571428571 | 1.0 | 0.0 | previous year | not specified | 3 | not specified | not specified | 1.0 | p | 178 | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | [6 empty] | not specified | not specified | not specified | not specified | not specified | -127.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.19
stayton wh expansion | 33119 | not specified | cyndi maples | jamal mebane | project | pg-0173 | pg-0173: infrastructure plant refreshes | not specified | not specified | it infrastructure na it | not specified | jeff landry | not specified | ryan lahoda | not specified | kirk kroft | not specified | footprint | na - windows: manufacturing - vinyl & vpi | it | l1 (identified) | on track | not specified | not specified | project dashboard | finance dashboard | 0.0 | 2024-05-03 | 2025-04-11 | 246d | • scope defined; approvals in progress • budgetary costs captured • target implementation scheduled week of mar 17 | • scope defined; approvals in progress • budgetary costs captured • target implementation scheduled week of mar 17 | • receipt of bom • approval of sow • cerf creation and approval | not specified | green | on track | red | yellow | red | green | yellow | green | 0 | 0 | 14.0 | 20.0 | 0.0 | 22.0 | 1.0 | 14.0 | 20.0 | 0.0 | 56.0 | 34.0 | 4.0 | 30.0 | 0.0 | 0.0 | 0.0 | 13364.59 | 11806.59 | 1558.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 13364.59 | 11806.59 | 1558.0 | not specified | -13364.59 | -11806.59 | -1558.0 | 0.0 | 0.0 | 0 | 2025-10-28 | 2024-06-06 | 2024-11-29 | 0 | 127d | 2025-09-18 | 2025-02-14 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | active | not specified | it | not specified | not specified | not specified | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 1.0 | 41.0 | 257.0 | 0.25 | 0.357142857142857 | 0.0 | 0.392857142857143 | 0.357142857142857 | 0.642857142857143 | current year | not specified | 3 | not specified | not specified | 1.0 | p | 171 | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | [6 empty] | not specified | not specified | not specified | not specified | not specified | -246.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0
coral springs network upgrade | 41627 | not specified | cyndi maples | jeff landry | project | pg-0173 | pg-0173: infrastructure plant refreshes | not specified | not specified | it infrastructure | not specified | jeff landry | not specified | sailaja kandala | christian suarez | sailaja kandala | not specified | sg&a | support functions: global it - infrastructure / service desk | it | l3 (planned) | on hold | 41627.0 | not specified | project dashboard | finance dashboard | 0.19 | 2024-06-06 | 2024-11-29 | 127d | no activity; on hold on project roadmap prioritization due to pm capacity. | not specified | not specified | not specified | blue | on track | red | red | green | green | yellow | green | 0 | 0 | 19.0 | 0.0 | 0.0 | 9.0 | 19.0 | 19.0 | 28.0 | 28.0 | 28.0 | 19.0 | 19.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2024-06-06 | 2024-11-29 | 0 | 127d | 2025-02-20 | 2025-09-16 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on-hold | not specified | it | not specified | not specified | not specified | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 1.0 | 251.0 | 43.0 | 0.678571428571429 | 0.0 | 0.0 | 0.321428571428571 | 1.0 | 0.0 | previous year | not specified | 3 | not specified | not specified | 1.0 | p | 172 | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | [6 empty] | not specified | not specified | not specified | not specified | not specified | -127.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified | 2025-09-17 | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.19
towanda infrastructure upgrade | p-0236 | upgrade towanda plant infrastructure | jamal mebane | jamal mebane | project | pg-0173 | pg-0173: infrastructure plant refreshes | not specified | not specified | it infrastructure | not specified | jamal mebane | not specified | not specified | mike doescher | kirk kroft | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.0 | 2024-09-03 | 2024-11-28 | 63d | project cancelled | not specified | not specified | not specified | green | sideways | red | yellow | green | red | yellow | green | 2 | 2 | 7.0 | 55.0 | 0.0 | 0.0 | 7.0 | 7.0 | 56.0 | 4.0 | 62.0 | 62.0 | 16.0 | 46.0 | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2024-06-06 | 2024-12-03 | 0 | 129d | 2025-01-07 | 2025-02-17 | not specified | 5 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | canceled | not specified | it | not specified | not specified | not specified | initiation / validation / feasibility | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 1.0 | 295.0 | 254.0 | 0.112903225806452 | 0.887096774193548 | 0.0 | 0.0 | 0.903225806451613 | 0.096774193548387 | previous year | not specified | 3 | not specified | not specified | not specified | p | 105 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-10-29 | 2026-01-27 | not specified | not specified | 2024-09-10 | [5 empty] | not specified | 421.0 | not specified | 425.0 | not specified | -63.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | towanda infrastructure upgrade | not specified |  | not specified | not specified | false | stage 1 - feasibility | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0
project harmoney west in-house lamination | 11901 | part of a larger business project to implement a new facility to extrude vinyl for vpi windows manufacturing process. this project will implement the network and phone infrastructure to support the manufacturing operations at the new extrusion facility. | jorge eleta | jamal mebane | project | pg-0173 | pg-0173: infrastructure plant refreshes | bus-na/corp/it | amanda jones | it infrastructure mfg. & supply chain na it | not specified | jeff landry | jon funk | john neill (jw) | ty pearsall | kirk kroft | not specified | manufacturing | na - windows: manufacturing - vinyl & vpi | it | l3 (planned) | on track | 11901.0 | not specified | project dashboard | finance dashboard | 0.95 | 2024-02-02 | 2024-08-02 | 131d | • implementation work complete with two non-critical, open items • awaiting update from plant on electrical inspection and construction completion to complete. • re-visit tentatively schedule 4/23-4/25 | • implementation work complete with two non-critical, open items • awaiting update from plant on electrical inspection and construction completion to complete. • re-visit tentatively schedule 4/23-4/25 | • confirmation construction completion and readiness • re-visit to close out open items | not specified | blue | on track | red | red | yellow | green | green | red | 0 | 0 | 4.0 | 0.0 | 0.0 | 35.0 | 4.0 | 4.0 | 0.0 | 0.0 | 39.0 | 4.0 | 4.0 | 0.0 | 3132115.0 | 3114423.0 | 17692.0 | 932758.89 | 932758.89 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 932758.89 | 932758.89 | 0.0 | not specified | 2199356.11 | 2181664.11 | 17692.0 | 0.702195197175072 | 0.700503467255411 | 1 | 2025-10-27 | 2024-02-02 | 2024-07-31 | -2d | 129d | 2025-05-12 | 2025-10-16 | not specified | 1 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | completed | not specified | it | not specified | not specified | not specified | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 1.624462138 | not specified | 3.082114 | 2023-11-29 | 2024-10-14 | on plan | not specified | 1.0 | on track | 1.0 | 170.0 | 13.0 | 0.102564102564103 | 0.0 | 0.0 | 0.897435897435898 | 0.0 | 1.0 | previous year | n | 3 | not specified | not specified | 1.0 | p | 52 | not specified | 1.0 | 1.0 | not specified | not specified | not specified | 2024-02-02 | 2024-08-02 | not specified | not specified | [6 empty] | 131d | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.95
project harmoney east in-house lamination | 11830 | the statesville facility requires additional manufacturing space to accommodate the vinyl extrusion process. in order to accommodate the line space, storage of some materials will be moved external of the facility. wireless coverage will be required within this external area to support the scanning in and out of inventory. | jamal mebane | jamal mebane | project | pg-0173 | pg-0173: infrastructure plant refreshes | it-infra/service | amanda jones | it infrastructure mfg. & supply chain na it | not specified | jeff landry | jon funk | troy fink | ty pearsall | kirk kroft | not specified | manufacturing | na - windows: manufacturing - vinyl & vpi | it | l4 (executed) | on track | 11830.0 | not specified | project dashboard | finance dashboard | 0.87 | 2024-06-05 | 2025-11-21 | 383d | statesville wireless expansion completed & post install survey received | statesville wireless expansion completed & post install survey received | not specified | not specified | blue | on track | red | red | red | green | yellow | green | 0 | 0 | 12.0 | 12.0 | 1.0 | 16.0 | 12.0 | 12.0 | 17.0 | 7.0 | 41.0 | 25.0 | 25.0 | 0.0 | 2407645.0 | 2389953.0 | 17692.0 | 1734551.2 | 1730204.42 | 4346.78 | not specified | 0.0 | 0.0 | 0.0 | not specified | 1734551.2 | 1730204.42 | 4346.78 | not specified | 673093.8 | 659748.58 | 13345.22 | 0.279565218294225 | 0.276050859577573 | 0.754308161881076 | 2025-10-27 | 2024-06-06 | 2024-11-29 | 0 | 127d | 2025-04-01 | 2025-10-16 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | completed | not specified | it | not specified | not specified | not specified | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 3.585284867 | not specified | 2.414827 | 2023-12-18 | 2024-10-14 | on plan | not specified | 1.0 | intake | 0.955613577023499 | 211.0 | 13.0 | 0.292682926829268 | 0.292682926829268 | 0.024390243902439 | 0.390243902439024 | 0.414634146341463 | 0.585365853658537 | current year | y | 3 | not specified | not specified | 1.0 | p | 220 | not specified | 1.0 | not specified | not specified | not specified | not specified |  |  | not specified | not specified | [6 empty] | not specified | not specified | not specified | not specified | not specified | -383.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.87
oceanside network and phone upgrade | 41643 | not specified | jamal mebane | jamal mebane | project | pg-0173 | pg-0173: infrastructure plant refreshes | not specified | not specified | not specified | not specified | jamal mebane | not specified | gordon greenland | christian suarez | gordon greenland | not specified | sg&a | support functions: global it - infrastructure / service desk | it | l3 (planned) | on hold | 41643.0 | not specified | project dashboard | finance dashboard | 0.19 | 2024-06-06 | 2024-11-29 | 127d | test-most recent update | test-most recent update | test-most recent update | test-most recent update | green | on track | red | red | green | green | yellow | green | 0 | 0 | 20.0 | 0.0 | 0.0 | 9.0 | 20.0 | 20.0 | 29.0 | 29.0 | 29.0 | 20.0 | 20.0 | 0.0 | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2024-06-06 | 2024-11-29 | 0 | 127d | 2025-01-28 | 2025-02-26 | true | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on-hold | not specified | it | not specified | not specified | not specified | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0.4 | 2023-10-16 | 2025-01-31 | on plan | not specified | 1.0 | on track | 1.0 | 274.0 | 245.0 | 0.689655172413793 | 0.0 | 0.0 | 0.310344827586207 | 1.0 | 0.0 | previous year | n | 3 | not specified | not specified | 1.0 | p | 222 | not specified | 1.0 | 1.0 | not specified | not specified | not specified |  |  | not specified | not specified | [6 empty] | not specified | not specified | not specified | not specified | not specified | -127.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.19
abs stockton - network | p-0263 | infrastructure plant upgrade | jamal mebane | jamal mebane | project | pg-0173 | pg-0173: infrastructure plant refreshes | not specified | not specified | it infrastructure na it | not specified | jamal mebane | not specified | not specified | mike doescher | kirk kroft | not specified | infrastructure | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 1.0 | 2024-01-03 | 2025-03-19 | 316d | test-most recent update | test-most recent update | test-most recent update | test-most recent update | green | up | yellow | blue | yellow | green | yellow | green | 0 | 0 | 0.0 | 0.0 | 0.0 | 72.0 | 0.0 | 0.0 | 37.0 | 37.0 | 72.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | 106576.67 | 91823.67 | 14753.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 106576.67 | 91823.67 | 14753.0 | 0.0 | -106576.67 | -91823.67 | -14753.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-05-21 | 2025-01-28 | not specified | 1 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | active | not specified | it | not specified | not specified | not specified | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 1.0 | 161.0 | 274.0 | 0.0 | 0.0 | 0.0 | 1.0 | 0.513888888888889 | 0.486111111111111 | current year | not specified | 3 | not specified | not specified | not specified | p | 136 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-10-29 | 2026-01-27 | not specified | not specified |  | 2025-01-24 | 2025-02-20 | 2025-02-20 | 2025-03-18 |  | not specified | 665.0 | not specified | 314.0 | not specified | -316.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 1
bend wireless expansion | p-0265 | plant infrastructure upgrade | jamal mebane | jamal mebane | project | pg-0173 | pg-0173: infrastructure plant refreshes | not specified | not specified | it infrastructure | not specified | jamal mebane | not specified | not specified | not specified | kirk kroft | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.56 | 2024-05-06 | 2024-11-13 | 138d | updated to on hold based on plant infrastructure prioritization and pm capacity. | not specified | not specified | not specified | green | sideways | yellow | yellow | yellow | green | yellow | green | 0 | 0 | 8.0 | 75.0 | 0.0 | 15.0 | 6.0 | 8.0 | 75.0 | 28.0 | 98.0 | 83.0 | 63.0 | 20.0 | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2024-11-13 | 2025-02-17 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on-hold | not specified | it | not specified | not specified | not specified | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 1.0 | 350.0 | 254.0 | 0.0816326530612245 | 0.76530612244898 | 0.0 | 0.153061224489796 | 0.76530612244898 | 0.23469387755102 | previous year | not specified | 3 | not specified | not specified | not specified | p | 138 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-10-29 | 2026-01-27 | not specified | not specified | [6 empty] | not specified | 541.0 | not specified | 440.0 | not specified | -138.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.56
abs denver network upgrade | p-0325 | refresh plant network. part of the pg-0173: infrastructure plant refreshes | jamal mebane | jamal mebane | project | pg-0173 | pg-0173: infrastructure plant refreshes | not specified | not specified | not specified | not specified | jamal mebane | not specified | not specified | not specified | kirk kroft | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.0 |  |  | 0 | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | sideways | yellow | yellow | schedule not set | green | yellow | green | 0 | 0 | 0.0 | 113.0 | 0.0 | 0.0 | 0.0 | 0.0 | 113.0 | 55.0 | 113.0 | 113.0 | 53.0 | 60.0 | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2024-11-26 | 2024-11-26 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | usd | it | not specified | not specified | not specified | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.0 | 337.0 | 337.0 | 0.0 | 1.0 | 0.0 | 0.0 | 1.0 | 0.0 | not specified | not specified | 3 | not specified | not specified | not specified | p | 255 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | not specified | not specified | not specified | not specified | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | abs denver network upgrade | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0
coppell infrastructure refresh | p-0454 | not specified | jamal mebane | jamal mebane | project | pg-0173 | pg-0173: infrastructure plant refreshes | not specified | not specified | it infrastructure | not specified | jamal mebane | not specified | not specified | not specified | kirk kroft | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.0 | 2025-01-01 | 2025-06-26 | 127d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | blue | sideways | red | red | green | green | yellow | green | 0 | 0 | 22.0 | 53.0 | 0.0 | 0.0 | 22.0 | 22.0 | 75.0 | 75.0 | 75.0 | 75.0 | 75.0 | 0.0 | 0.0 | not specified | not specified | 153982.78 | 152024.78 | 1958.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 153982.78 | 152024.78 | 1958.0 | 0.0 | -153982.78 | -152024.78 | -1958.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-08-28 | 2025-10-16 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 130885.363 | 129221.063 | 1664.3 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 130885.363 | 129221.063 | 1664.3 | 0.0 | -130885.363 | -129221.063 | -1664.3 | 0.0 | 0.0 | 0.0 | not specified | completed | usd | it | not specified | not specified | not specified | ideation | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 1.0 | 62.0 | 13.0 | 0.293333333333333 | 0.706666666666667 | 0.0 | 0.0 | 1.0 | 0.0 | current year | not specified | 3 | not specified | not specified | 1.0 | p | 403 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | 0.0 | not specified | -127.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | coppell infrastructure refresh | not specified |  | not specified | 2025-05-12 00:00:00 | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0
spec alignment across distribution- abs/mmi | 22629 | define door system strategy for product line and consolidate specifications within jw and distribution (abs/mmi). this project is 2 phases. phase 1 will formalize the product line strategy and consolidate retail. phase 2 will push the final system to warranty and market. | emily bartlett | emily bartlett | project | standalone project | standalone project | not specified | amanda jones | mfg. & supply chain na it | not specified | not specified | emily bartlett | matt goodman | not specified | not specified | not specified | npi / npd | na - doors & dist: commercial - product & pricing | engineering | l3 (planned) | on track | 22629.0 | not specified | project dashboard | finance dashboard | 0.72 | 2024-03-25 | 2025-10-31 | 420d | abs inswing sills abs: inswing - composite modular sill - the pos have been cut and we expect the samples to ship from gpi on 12/6. samples will go to dallas, denver, realto, and aaron. upon review, aaron will forward his samples to sacramento. we expect these samples to be in by 12/20. abs: inswing - specialty 5 5/8 oak cap sill - matt and aaron should be receiving samples of these sills any time now for preliminary inspection. abs: inswing - 5 5/8 retro sill - models of sills have been created and aaron is working to create the drawings of the sill type. mmi: outswing - 5 5/8 modular bumper - of the initial samples received there were some bad parts. aaron has followed-up with gpi on the issues experienced and is shipping examples of those bad parts back to gpi for review. those bad parts are set to ship back to gpi by 12/6. aaron is shipping the 5 initial samples to sidman for plant validation and those are set to ship to sidman on 12/5. we expect the remaining samples coming from asia to be in by the end of december 2024. ada sills mmi - outswing ada sill - aaron has completed the drawings for the ada parts, the prototype was built and water tested, but did not pass. a second, alternative sample is being built now and expect that to be finished this week for testing to begin next week. abs - saddle sill - po has been cut for these saddle sills. gpi has confirmed the order and we expect those to ship by 12/6 for arrival within 2 weeks. mmi saddle sill - po has been cut for these sills, but these sills require tooling by gpi. gpi has confirmed the order and we expect samples to arrive in january 2025. mmi - inswing ada sill - this is a new profile for gpi and will require tooling. we have completed the po process, but won't expect samples until february 2025. | not specified | sweeps, weather stripping and astrigals are on aaron's radar and will kick-off in the near future now that the sills are making progress. | not specified | green | on track | red | yellow | red | red | yellow | green | 1 | 0 | 17.0 | 35.0 | 3.0 | 56.0 | 15.0 | 11.0 | 54.0 | 38.0 | 110.0 | 54.0 | 14.0 | 40.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2024-06-06 | 2024-11-29 | 0 | 127d | 2025-10-02 | 2024-12-05 | not specified | 1 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | active | not specified | other | not specified | not specified | not specified | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 4.408 | not specified | 1.341138333 | 2023-10-13 | 2024-11-29 | on plan | not specified | 1.0 | on track | 0.995238095238095 | 27.0 | 328.0 | 0.154545454545455 | 0.318181818181818 | 0.0272727272727273 | 0.509090909090909 | 0.490909090909091 | 0.509090909090909 | current year | n | 3 | not specified | not specified | not specified | p | 186 | not specified | 1.0 | 1.0 | not specified | not specified | not specified |  |  | not specified | not specified | [6 empty] | not specified | not specified | not specified | not specified | not specified | -420.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.72
rfid kuopio [system fix] | 23214 | rfid system implementation into kuoipo | ben hamnett | ben hamnett | project | standalone project | standalone project | it-eu | not specified | it it north eu it-eu | not specified | ben hamnett | not specified | antti rinkinen | peter sorensen | rachael horton-farmer | not specified | manufacturing | nordics: manufacturing - finland | it | l4 (executed) | on track | 23214.0 | not specified | project dashboard | finance dashboard | 1.0 | 2023-03-13 | 2024-10-17 | 419d | w42: gate approved pending evidence of increased scan accuracy. requested this from ville. ready to close | w42: gate approved | no further action | not specified | blue | on track | yellow | blue | yellow | green | green | green | 0 | 0 | 0.0 | 0.0 | 0.0 | 6.0 | 0.0 | 0.0 | 0.0 | 0.0 | 6.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2023-03-13 | 2024-08-29 | 0 | 384d | 2025-03-05 | 2024-11-05 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | completed | not specified | it | not specified | not specified | north eu | realize value / close / care period | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0.0891 | not specified | 0.0 | 2023-10-17 | 2024-02-12 | on plan | not specified | 1.0 | on track | 1.0 | 238.0 | 358.0 | 0.0 | 0.0 | 0.0 | 1.0 | 0.0 | 1.0 | previous year | n | 3 | not specified | not specified | 1.0 | p | 198 | not specified | 1.0 | 1.0 | not specified | not specified | not specified |  |  | not specified | not specified | [6 empty] | not specified | not specified | not specified | not specified | not specified | -419.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | stage 5 - care period | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 1
demand-driven planning & execution process | 13744 | not specified | chad alterio | fabio rivera | project | standalone project | standalone project | not specified | not specified | mfg. & supply chain na it | not specified | heath webster | not specified | steve cooney | christian suarez | kirk kroft | not specified | supply chain | na - ops: supply chain | it | l3 (planned) | on hold | 13744.0 | not specified | project dashboard | finance dashboard | 0.0 | 2024-09-16 | 2025-03-10 | 126d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | on track | red | red | yellow | green | yellow | green | 0 | 0 | 42.0 | 0.0 | 0.0 | 0.0 | 42.0 | 42.0 | 42.0 | 42.0 | 42.0 | 42.0 | 42.0 | 0.0 | 5300000.0 | 3710000.0 | 1590000.0 | 24452.0 | 6453.0 | 17999.0 | 12375.0 | 3600000.0 | 2880000.0 | 720000.0 | 48000.0 | 3624452.0 | 2886453.0 | 737999.0 | 60375.0 | 1675548.0 | 823547.0 | 852001.0 | 0.316141132075472 | 0.221980323450135 | 0.535849685534591 | 2025-10-27 | 2024-06-06 | 2024-11-29 | 0 | 127d | 2025-04-11 | 2024-11-01 | true | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | active | not specified | it | not specified | not specified | not specified | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | -0.81 | not specified | 2.160445 | 2023-10-16 | 2025-10-11 | on plan | not specified | 1.0 | on track | 1.0 | 201.0 | 362.0 | 1.0 | 0.0 | 0.0 | 0.0 | 1.0 | 0.0 | current year | n | 3 | not specified | not specified | 1.0 | p | 199 | not specified | 1.0 | 1.0 | not specified | not specified | not specified |  |  | not specified | not specified | [6 empty] | not specified | not specified | not specified | not specified | not specified | -126.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0
project avon | 34019 | site closure | ben hamnett | ben hamnett | project | standalone project | standalone project | it-eu | not specified | it it north eu it-eu | not specified | not specified | not specified | not specified | not specified | rachael horton - farmer | not specified | not specified | not specified | not specified | not specified | on track | 34019.0 | not specified | project dashboard | finance dashboard | 0.0 | 2024-08-26 | 2024-08-29 | 4d | w37: now closed | w37: now closed | now closed | complete | blue | on track | yellow | green | yellow | green | green | green | 0 | 0 | 0.0 | 0.0 | 0.0 | 2.0 | 0.0 | 0.0 | 0.0 | 0.0 | 2.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2024-06-06 | 2024-11-29 | 0 | 127d | 2024-09-17 | 2024-11-05 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | completed | not specified | it | not specified | not specified | north eu | realize value / close / care period | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | 1.0 | 1.0 | on track | 1.0 | 407.0 | 358.0 | 0.0 | 0.0 | 0.0 | 1.0 | 0.0 | 1.0 | previous year | n | 3 | not specified | not specified | not specified | p | 200 | not specified | 1.0 | not specified | not specified | not specified | not specified |  |  | not specified | not specified | [6 empty] | not specified | not specified | not specified | not specified | not specified | -4.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | stage 5 - care period | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0
windows tsm realignment | p-0215 | realigning systems/applications to the windows restructure. documenting the tasks and effort involved to be able to reproduce this project in the future. | garrett farmer | garrett farmer | project | standalone project | standalone project | bus-na/corp/it | not specified | not specified | not specified | garrett farmer | not specified | not specified | terry davis | terry davis | troy conroy | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | finance dashboard | 0.89 | 2024-08-05 | 2024-11-14 | 74d | working on completing the assignments and territories. once this is completed there will be more work for structures. | not specified | communication updates and ssm changes. | not specified | green | on track | yellow | green | yellow | green | green | green | 0 | 0 | 1.0 | 0.0 | 4.0 | 28.0 | 5.0 | 4.0 | 0.0 | 0.0 | 33.0 | 5.0 | 4.0 | 1.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2024-08-05 | 2024-11-11 | 0 | 71d | 2024-11-07 | 2024-08-12 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | it | not specified | not specified | not specified | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 1.0 | 356.0 | 443.0 | 0.0303030303030303 | 0.0 | 0.121212121212121 | 0.848484848484849 | 0.0 | 1.0 | previous year | not specified | 3 | not specified | not specified | not specified | p | 215 | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | [6 empty] | not specified | not specified | not specified | not specified | not specified | -74.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.89
consolidate mobile device contracts/support | 54781 | not specified | jamal mebane | not assigned | project | standalone project | standalone project | it-infra/service | not specified | not specified | not specified | not specified | not specified | gordon greenland | gordon greenland | gordon greenland | not specified | sg&a | support functions: global it - infrastructure / service desk | it | l1 (identified) | on track | 54781.0 | not specified | project dashboard | finance dashboard | 0.19 | 2024-06-06 | 2024-11-29 | 127d | test-most recent update | test-most recent update | test-most recent update | test-most recent update | green | on track | red | red | green | red | yellow | green | 2 | 2 | 20.0 | 0.0 | 0.0 | 9.0 | 20.0 | 20.0 | 28.0 | 28.0 | 29.0 | 20.0 | 20.0 | 0.0 | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2024-06-06 | 2024-11-29 | 0 | 127d | 2025-02-20 | 2024-11-05 | true | 5 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | active | not specified | it | not specified | not specified | global | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0.15 | not specified | not specified | 2023-12-12 | 2024-02-29 | past due for l4 | not specified | 1.0 | on track | 1.0 | 251.0 | 358.0 | 0.689655172413793 | 0.0 | 0.0 | 0.310344827586207 | 0.96551724137931 | 0.0344827586206899 | previous year | n | 3 | not specified | not specified | 1.0 | p | 217 | not specified | 1.0 | not specified | not specified | not specified | not specified |  |  | not specified | not specified | [6 empty] | not specified | not specified | not specified | not specified | not specified | -127.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.19
mobile security management | 32880 | not specified | jamal mebane | not assigned | project | standalone project | standalone project | it-infra/service | not specified | not specified | not specified | it pm not required | not specified | dan stroup | ravi ramaraj | terry davis | not specified | sg&a | support functions: global it - infrastructure / service desk | it | l5 (realised) | on track | 32880.0 | not specified | project dashboard | finance dashboard | 0.19 | 2024-06-06 | 2024-11-29 | 127d | test-most recent update | test-most recent update | test-most recent update | test-most recent update | green | on track | red | red | green | red | yellow | green | 2 | 2 | 20.0 | 0.0 | 0.0 | 9.0 | 20.0 | 20.0 | 29.0 | 29.0 | 29.0 | 20.0 | 20.0 | 0.0 | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2024-06-06 | 2024-11-29 | 0 | 127d | 2025-02-24 | 2024-11-05 | true | 5 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | active | not specified | it | not specified | not specified | not specified | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0.096 | not specified | 0.0 | 2024-11-04 | 2024-06-13 | past due for l5 | not specified | 1.0 | on track | 1.0 | 247.0 | 358.0 | 0.689655172413793 | 0.0 | 0.0 | 0.310344827586207 | 1.0 | 0.0 | previous year | n | 3 | not specified | not specified | 1.0 | p | 218 | not specified | 1.0 | not specified | not specified | not specified | not specified |  |  | not specified | not specified | [6 empty] | not specified | not specified | not specified | not specified | not specified | -127.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.19
centralized software license management | 32883 | not specified | jamal mebane | cyndi maples | project | standalone project | standalone project | not specified | not specified | it infrastructure | not specified | not specified | not specified | ravi ramaraj | ravi ramaraj | ravi ramaraj | not specified | sg&a | support functions: global it - infrastructure / service desk | it | l3 (planned) | on hold | 32883.0 | not specified | project dashboard | finance dashboard | 0.0 | 2024-09-05 | 2024-09-30 | 18d | meeting with jorge and ravi, 9/19. decision jaya leading efforts for 9/30 phase 1 implementation and deloitte transition. wave project on hold until jaya complete with 9/30 implementation and a reassessment and next steps can be determined. no it pmo, pm(c. maples) actions or assignment at this time. | not specified | not specified | not specified | red | on track | red | yellow | green | green | yellow | green | 4 | 0 | 1.0 | 32.0 | 0.0 | 15.0 | 1.0 | 1.0 | 32.0 | 22.0 | 43.0 | 28.0 | 25.0 | 3.0 | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2024-06-06 | 2024-11-29 | 0 | 127d | 2025-01-28 | 2025-09-18 | not specified | 6 | not specified | not specified | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | canceled | not specified | it | not specified | not specified | not specified | implementation / execution | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0.3168 | not specified | not specified | 2023-10-16 | 2024-12-07 | past due for l4 | not specified | 1.0 | on track | 1.0 | 274.0 | 41.0 | 0.0232558139534884 | 0.744186046511628 | 0.0 | 0.348837209302326 | 0.744186046511628 | 0.255813953488372 | previous year | n | 3 | not specified | not specified | 1.0 | p | 221 | not specified | 1.0 | 1.0 | not specified | not specified | not specified |  |  | not specified | not specified | [6 empty] | not specified | not specified | not specified | not specified | not specified | -18.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | stage 3 - implementation | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0
stop new hire/new equipment policy | 32881 | not specified | jamal mebane | jamal mebane | project | standalone project | standalone project | not specified | not specified | not specified | not specified | jamal mebane | not specified | gordon greenland | gordon greenland | gordon greenland | not specified | sg&a | support functions: global it - infrastructure / service desk | it; legal | l5 (realised) | on track | 32881.0 | not specified | project dashboard | finance dashboard | 0.19 | 2024-06-06 | 2024-11-29 | 127d | test-most recent update | test-most recent update | test-most recent update | test-most recent update | green | on track | red | red | green | red | yellow | green | 2 | 2 | 20.0 | 0.0 | 0.0 | 9.0 | 20.0 | 20.0 | 29.0 | 29.0 | 29.0 | 20.0 | 20.0 | 0.0 | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2024-06-06 | 2024-11-29 | 0 | 127d | 2025-01-28 | 2024-11-05 | true | 5 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | active | not specified | it | not specified | not specified | not specified | realize value / close / care period | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0.0 | not specified | not specified | 2023-10-16 | 2024-10-04 | on plan | not specified | 1.0 | on track | 1.0 | 274.0 | 358.0 | 0.689655172413793 | 0.0 | 0.0 | 0.310344827586207 | 1.0 | 0.0 | previous year | n | 3 | not specified | not specified | 1.0 | p | 223 | not specified | 1.0 | not specified | not specified | not specified | not specified |  |  | not specified | not specified | [6 empty] | not specified | not specified | not specified | not specified | not specified | -127.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | stage 5 - care period | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.19
laptop and workstation returns | 32882 | not specified | jamal mebane | jamal mebane | project | standalone project | standalone project | not specified | not specified | not specified | not specified | it pm not required | not specified | m.j. vaidya | mike schipper | terry davis | not specified | sg&a | support functions: global it - infrastructure / service desk | it; hr | l4 (executed) | on track | 32882.0 | not specified | project dashboard | finance dashboard | 0.19 | 2024-06-06 | 2024-11-29 | 127d | test-most recent update | test-most recent update | test-most recent update | test-most recent update | green | on track | red | red | green | red | yellow | green | 2 | 2 | 20.0 | 0.0 | 0.0 | 9.0 | 20.0 | 20.0 | 29.0 | 29.0 | 29.0 | 20.0 | 20.0 | 0.0 | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2024-06-06 | 2024-11-29 | 0 | 127d | 2025-01-28 | 2024-11-05 | true | 5 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | active | not specified | it | not specified | not specified | not specified | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0.0 | not specified | not specified | 2023-10-16 | 2024-06-13 | past due for l5 | not specified | 1.0 | on track | 1.0 | 274.0 | 358.0 | 0.689655172413793 | 0.0 | 0.0 | 0.310344827586207 | 1.0 | 0.0 | previous year | n | 3 | not specified | not specified | 1.0 | p | 224 | not specified | 1.0 | not specified | not specified | not specified | not specified |  |  | not specified | not specified | [6 empty] | not specified | not specified | not specified | not specified | not specified | -127.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.19
cybersecurity global sd-wan implementation | pg-0225 | jeld-wen's global network is currently flat and it's a major security concern. security breach at one location can propagate to another location/region, potentially disrupting operations. as part of zero trust implementation (phase 1), we aim to improve the security posture by modernizing the network and increasing the availability while reducing the network circuit costs. | charlotte fox | brad duffey, ben hamnett | program | pg-0225 | pg-0225: cybersecurity global sd-wan implementation | it-cyber | not specified | cybersecurity it it-eu | not specified | brad duffey, ben hamnett | not specified | not specified | jens schjøtt | m.j. vaidya, rachael horton-farmer | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | program dashboard | finance dashboard | 0.62619477006312 | 2023-10-20 | 2026-04-16 | 650d | 30/65 sites in north american have been migrated to sd-wan. eu sites circuit installations have been scheduled for approximately 15 sites. | na sites migrated to sd-wan, eu sites beginning circuit focs. | continuation of na site conversions and eu circuit installations. | no support needed at this time. | green | on track | green | on track | red | green | yellow | green | 5 | 9 | 9.0 | 2.0 | 35.0 | 173.0 | 10.0 | 13.0 | 3.0 | 3.0 | 219.0 | 46.0 | 28.0 | 18.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 |  | 2023-10-20 | 2025-10-03 | 0 | 511d | 2025-10-24 | 2025-10-29 | not specified | 21 | not specified | not specified | 0 | 1 | 0 | 1 | 2 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 3.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | active | not specified | it | not specified | not specified | global | see project details | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.813846153846154 | 5.0 | 0.0 | 0.0410958904109589 | 0.0091324200913242 | 0.159817351598174 | 0.789954337899543 | 0.0136986301369863 | 0.986301369863014 | 2026 | not specified | 2 | not specified | not specified | not specified | pg | 225 | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | [6 empty] | not specified | not specified | not specified | not specified | not specified | -650.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.62619
cybersecurity - network segmentation - phase 1 - global sd-wan implementation (na) | 34102 | not specified | jorge eleta | brad duffey | project | pg-0225 | pg-0225: cybersecurity global sd-wan implementation | it-cyber | not specified | cybersecurity it | not specified | brad duffey | not specified | m.j. vaidya | gordon greenland | m.j. vaidya | not specified | sg&a | support functions: global it - cyber | it | l3 (planned) | on track | 34102.0 | not specified | project dashboard | finance dashboard | 0.68 | 2023-10-20 | 2026-04-16 | 650d | no status change this week. p2g: klamath is at a standstill due to dependencies from the ngfw - cisco asa to fortigate project. personnel needed to complete. knowledge of klamath architecture also needed since rif. sulphur springs is green. budget overrun is due to capital labor. | 64 out of 66 sites completed and on sd-wan. mpls circuit decommissioning underway. | sulphur springs, tx circuit installation, klamath migration once off asa devices | experienced personnel needed to assist with project completion. our current resources do not have availability. | red | sideways | red | green | red | green | green | green | 0 | 0 | 0.0 | 1.0 | 18.0 | 47.0 | 0.0 | 1.0 | 0.0 | 0.0 | 66.0 | 19.0 | 5.0 | 14.0 | 2566454.0 | 2300000.0 | 266454.0 | 2418070.9 | 2231317.67 | 186753.23 | not specified | 107116.33 | 50810.04 | 56306.29 | not specified | 2525187.23 | 2282127.71 | 243059.52 | not specified | 41266.77 | 17872.29 | 23394.48 | 0.0160792946220739 | 0.00777056086956522 | 0.0877993199576662 | 2025-10-27 | 2023-10-20 | 2025-08-28 | 0 | 485d | 2025-10-10 | 2025-10-13 | true | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | active | not specified | it | not specified | not specified | not specified | implementation / execution | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0.142 | not specified | 0.7585 | 2023-10-17 | 2025-04-25 | on plan | not specified | 1.0 | on track | 0.813846153846154 | 19.0 | 16.0 | 0.0 | 0.0151515151515152 | 0.272727272727273 | 0.712121212121212 | 0.0 | 1.0 | 2026 | n | 3 | not specified | not specified | 1.0 | p | 88 | not specified | 1.0 | 1.0 | not specified | not specified | not specified |  |  | not specified | not specified | [6 empty] | not specified | not specified | not specified | not specified | not specified | -650.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | stage 3 - implementation | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.68
cybersecurity - network segmentation - phase 1 - global sd-wan implementation (eu) | 57805 | jeld-wen's global network is currently flat and it's a major security concern. security breach at one location can propagate to another location/region, potentially disrupting operations. as part of zero trust implementation (phase 1), we aim to improve the security posture by modernizing the network and increasing the availability while reducing the network circuit costs. this initiative is for the eu deployment and is linked to the na initiative #34102. | charlotte fox | ben hamnett | project | pg-0225 | pg-0225: cybersecurity global sd-wan implementation | it-eu | not specified | cybersecurity it it-eu | not specified | ben hamnett | ben hamnett | sven ortmeier | jens schjott | rachael horton-farmer | not specified | sg&a | support functions: global it - europe | it | l3 (planned) | some issues | 57805.0 | not specified | project dashboard | finance dashboard | 0.55 | 2024-02-27 | 2025-11-28 | 459d | w43: 36/39 circuits active 33/40 fg installs 26/40 sites cutover 22 mpls decomms complete | w43: nur35 fg check scheduled, and cutover week after. hum26 cutover scheduled with kasia on site next week. hus14 circuit moved and ready for cutover | w44: hum26 cutover | not specified | green | on track | yellow | green | yellow | green | yellow | green | 0 | 0 | 9.0 | 1.0 | 17.0 | 126.0 | 10.0 | 12.0 | 3.0 | 3.0 | 153.0 | 27.0 | 23.0 | 4.0 | 99745.0 | 30287.0 | 69458.0 | 87717.0 | 25172.0 | 62545.0 | not specified | 6637.0 | 2000.0 | 4637.0 | not specified | 94354.0 | 27172.0 | 67182.0 | not specified | 5391.0 | 3115.0 | 2276.0 | 0.0540478219459622 | 0.102849407336481 | 0.0327680036856806 | 2025-10-27 | 2024-02-27 | 2025-10-03 | 0 | 419d | 2025-10-24 | 2025-10-24 | not specified | 1 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | active | not specified | it | not specified | not specified | eu | implementation / execution | not specified | compliance | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0.0 | not specified | 0.055 | 2024-05-07 | 2025-01-17 | due soon for l3 | not specified | 1.0 | on track | 0.952069716775599 | 5.0 | 5.0 | 0.0588235294117647 | 0.0065359477124183 | 0.111111111111111 | 0.823529411764706 | 0.0196078431372549 | 0.980392156862745 | current year | n | 3 | not specified | not specified | 1.0 | p | 152 | not specified | 1.0 | not specified | not specified | not specified | not specified |  |  | not specified | not specified | [6 empty] | not specified | not specified | not specified | not specified | not specified | -459.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | improved performance | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | stage 3 - implementation | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.55
cradle to cradle - phase 2 | p-0230 | to obtain cradle to cradle (c2c) certification for a larger portion of jeld-wen products in scandinavia, finland, and the baltics, thereby reinforcing our commitment to sustainability and enhancing our market position. | jorgen knudsen | jorgen knudsen | project | standalone project | standalone project | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | finance dashboard | 1.0 | 2024-10-01 | 2025-07-14 | 205d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | on track | red | blue | red | red | green | green | 2 | 2 | 0.0 | 0.0 | 0.0 | 97.0 | 0.0 | 0.0 | 0.0 | 0.0 | 97.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2024-06-06 | 2024-12-03 | 0 | 129d | 2025-10-20 | 2024-08-27 | not specified | 5 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | other | not specified | not specified | eu | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 1.0 | 9.0 | 428.0 | 0.0 | 0.0 | 0.0 | 1.0 | 0.0 | 1.0 | current year | not specified | 3 | not specified | not specified | not specified | p | 230 | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | [6 empty] | not specified | not specified | not specified | not specified | not specified | -205.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 1
re-door - reuse of fire rated doors | 59709 | this project aims to verify the fire safety performance of used fire-rated doors and to create a method that allows jeld-wen to resell them with updated certification without requiring a new full-scale fire resistance test. this will enable us to achieve full circularity of our fire-rated doors.l the project scope includes setting up a system where our service team will be trained by dbi, the danish institute of fire and security, to re-certify doors on site. this will be a service that we can offer to our customers who want to reuse existing doors instead of buying new ones. the project will also explore the feasibility of refurbishing doors at our site in sdr. felding. we are considering different sales channels and supply chain options. doors can come from various sources, such as demolition companies, used building materials dealers, etc.. | jorgen knudsen | jorgen knudsen | project | standalone project | standalone project | not specified | not specified | r&d europe | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | 59709.0 | not specified | project dashboard | project finance dashboard | 1.0 | 2024-09-03 | 2024-09-10 | 6d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | sideways | red | blue | yellow | red | yellow | green | 10 | 0 | 0.0 | 5.0 | 0.0 | 76.0 | 0.0 | 0.0 | 6.0 | 6.0 | 81.0 | 5.0 | 0.0 | 5.0 | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2024-06-06 | 2024-12-03 | 0 | 129d | 2025-07-28 | 2024-10-30 | not specified | 14 | not specified | not specified | 0 | 4 | 0 | 0 | 1 | 1 | 0 | 1 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | active | usd | r&d | technical | npd | eu | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not planned (l2 to l4) | not specified | 1.0 | on track | 1.0 | 93.0 | 364.0 | 0.0 | 0.0617283950617284 | 0.0 | 0.938271604938272 | 0.0740740740740741 | 0.925925925925926 | previous year | n | 3 | not specified | not specified | not specified | p | 115 | 1.0 | 1.0 | not specified | not specified | not specified | not specified | 2025-10-29 | 2026-01-27 | not specified | not specified | 2024-09-03 | [5 empty] | not specified | 421.0 | not specified | 504.0 | not specified | -6.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 1
salesforce re-org and related initiatives | pg-0254 | not specified | richard guest | not specified | program | pg-0254 | pg-0254: salesforce re-org and related initiatives | not specified | not specified | it it-eu | not specified | not specified | not specified | not specified | not specified | rachael horton - farmer | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | program dashboard | finance dashboard | not specified |  |  | not specified | w11: local teams still concerned with data quality. process of data fixing to be defined. training delivery in norway. | w11: training delivery prep. | w11: customer approach to be defined during sf/cpq go live checkpoint 6 w12: go live in sweden on 19th march | not specified | blue | on track | blue | on track | schedule not set | blue | blue | green | 0 | 0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 |  |  |  | 0 | not specified |  | 2025-10-29 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | completed | eur | it | not specified | not specified | eu | see project details | not specified | not specified | on track | on track | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 1.0 | not specified | not specified | 2 | not specified | not specified | not specified | not specified | 124 | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | [6 empty] | not specified | not specified | not specified | not specified | not specified | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified
salesforce re-org | 41127 | not specified | richard guest | richard guest | project | standalone project | standalone project | not specified | not specified | it it-eu | not specified | richard guest | not specified | richard guest | rachael horton-farmer | rachael horton-farmer | not specified | sg&a | support functions: global it - europe | it | l3 (planned) | on track | 41127.0 | not specified | project dashboard | project finance dashboard | 0.67 | 2024-06-13 | 2025-03-03 | 188d | w43: status amber * uk timeline at risk (2 weeks behind due to resource); resource risk extends into next year as credera support ends. * to green: agree and implement resource mitigation options. | w43: * uk- requirements gathered, build and data cleansing started. * de- 85% requirements gathered. * no/se- work on infor continues to address pain points in customer self-serve, quote visibility, and pricing. agreed approach — use pcoo for large/project quotes and infor for small, retail, and customer quotes. | w44: * uk- working through mitigation options for timeline.continue focusing on build. * de- data cleansing activities to start in nov. * no/se- pcoo remains an ongoing risk; agreed to deliver benefits for external users while assessing infor’s fit for full migration and internal use. * resource- decision needed on continuing with credera support next year or accepting a 6-month roadmap delay. | not specified | yellow | sideways | yellow | yellow | green | green | yellow | green | 5 | 0 | 0.0 | 86.0 | 71.0 | 11.0 | 1.0 | 2.0 | 140.0 | 138.0 | 168.0 | 157.0 | 146.0 | 11.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2024-01-01 | 2025-05-01 | 0 | 349d | 2025-10-22 | 2025-10-22 | not specified | 5 | not specified | not specified | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | it | not specified | not specified | eu | not specified | not specified | increase revenue | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | -0.022 | not specified | 0.0 | 2023-12-10 | 2025-12-19 | on plan | not specified | 1.0 | on track | 1.0 | 7.0 | 7.0 | 0.0 | 0.511904761904762 | 0.422619047619048 | 0.0654761904761905 | 0.833333333333333 | 0.166666666666667 | current year | n | 3 | not specified | not specified | 1.0 | p | 268 | 1.0 | 1.0 | 1.0 | not specified | not specified | not specified | 2024-01-01 | 2025-05-01 | not specified | not specified | [6 empty] | not specified | -164.0 | not specified | 59.0 | not specified | -188.0 | not specified | not specified | not specified | not specified | not specified | 2025-03-03 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | focussed growth | 0.0 | one | not specified | salesforce re-org | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.67
germany - e - offer bos/bbe | 12275 | not specified | richard guest | lisa schulze-egberding | project | standalone project | standalone project | not specified | not specified | it it central eu it-eu | not specified | lisa schulze-egberding | not specified | martin ott | markus ellinger | rachael horton-farmer | not specified | growth | dach: commercial - germany | it | l4 (executed) | on track | 12275.0 | not specified | project dashboard | project finance dashboard | 0.42 | 2024-11-04 | 2025-06-26 | 169d | wk15: initiative submitted for l4 | wk15: n/a | wk16: l4 gate review | wk15: n/a | blue | up | red | red | yellow | green | yellow | green | 0 | 0 | 10.0 | 40.0 | 14.0 | 11.0 | 24.0 | 24.0 | 53.0 | 53.0 | 75.0 | 64.0 | 63.0 | 1.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-03-11 | 2025-05-12 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | completed | eur | it | not specified | not specified | central eu | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 2.6642 | not specified | 0.9891321 | 2023-11-10 | 2024-01-10 | on plan | not specified | 1.0 | on track | 1.0 | 232.0 | 170.0 | 0.133333333333333 | 0.533333333333333 | 0.186666666666667 | 0.146666666666667 | 0.706666666666667 | 0.293333333333333 | current year | n | 3 | not specified | not specified | 1.0 | p | 269 | 1.0 | 1.0 | 1.0 | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | 58.0 | not specified | 0.0 | not specified | -169.0 | not specified | not specified | not specified | not specified | not specified | not specified | 2025-02-10 00:00:00 | 2025-03-17 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | germany - e - offer bos/bbe | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.42
austria - service portal | 12374 | creation of online portal for dana products (lead generation) | karolin koch | karolin koch | project | standalone project | standalone project | it-eu | not specified | it it central eu it-eu | not specified | karolin koch | not specified | gertraud scheuchel | markus ellinger | rachael horton-farmer | not specified | growth | dach: commercial - austria | it | l3 (planned) | on track | 12374.0 | not specified | project dashboard | project finance dashboard | 0.49 | 2023-09-13 | 2026-03-31 | 665d | w43: project behind for stage l3 implementation - project schedule amended and go live date pushed back - build supplier delayed due to missing input - build salesforce delayed due to capacity [path to green defined for issues with salesforce integration & supplier build] | w43: - build (ongoing) - mockup for salesforce drafted to be verified by jw - go live date pushed back | w44: - build (ongoing) | impact: n/a p2g: n'a | yellow | angle down | red | green | yellow | red | yellow | green | 0 | 3 | 16.0 | 0.0 | 28.0 | 61.0 | 16.0 | 11.0 | 1.0 | 1.0 | 105.0 | 44.0 | 35.0 | 9.0 | 82352.9411764703 | 82352.9411764703 | 0.0 | 65352.9411764704 | 65352.9411764704 | 0.0 | 0.0 | 16470.5882352941 | 16470.5882352941 | 0.0 | 0.0 | 81823.5294117644 | 81823.5294117644 | 0.0 | 0.0 | 529.411764705881 | 529.411764705881 | 0.0 | 0.00642857142857144 | 0.00642857142857144 | 0 | 2025-10-27 | 2023-09-13 | 2026-03-06 | 0 | 648d | 2025-10-28 | 2025-10-21 | not specified | 18 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0.0 | not specified | 70000.0 | 70000.0 | 0.0 | 55550.0 | 55550.0 | 0.0 | 0.0 | 14000.0 | 14000.0 | 0.0 | 0.0 | 69550.0 | 69550.0 | 0.0 | 0.0 | 450.0 | 450.0 | 0.0 | 0.00642857142857143 | 0.00642857142857143 | 0.0 | not specified | active | eur | it | not specified | not specified | central eu | not specified | not specified | reduce risk | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0.3542 | not specified | 0.066 | 2023-10-20 | 2024-09-13 | on plan | not specified | 1.0 | on track | 0.83609022556391 | 1.0 | 8.0 | 0.152380952380952 | 0.0 | 0.266666666666667 | 0.580952380952381 | 0.00952380952380953 | 0.990476190476191 | 2026 | n | 3 | not specified | not specified | not specified | p | 267 | 1.0 | 1.0 | 1.0 | not specified | not specified | not specified | 2023-09-13 | 2026-03-06 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | -25.0 | not specified | -665.0 | not specified | not specified | 2023-09-13 00:00:00 | 2023-09-13 00:00:00 | 2024-10-21 00:00:00 | 2024-10-21 00:00:00 | 2025-12-11 00:00:00 | 2026-03-06 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | improved performance | 0.0 | one | not specified | austria - service portal | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.49
project cortado | 56232 | amc/smc insourcing | jonathan funk | jon funk | project | standalone project | standalone project | not specified | amanda jones | na it | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | 56232.0 | not specified | project dashboard | project finance dashboard | 0.51 | 2024-08-29 | 2026-11-24 | 584d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | sideways | red | green | red | green | yellow | green | 1 | 0 | 0.0 | 0.0 | 17.0 | 102.0 | 12.0 | 12.0 | 17.0 | 17.0 | 119.0 | 17.0 | 17.0 | 0.0 | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2024-06-06 | 2024-12-03 | 0 | 129d | 2025-08-28 | 2024-10-30 | not specified | 5 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | active | not specified | transformation | not specified | not specified | not specified | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not planned (l2 to l4) | not specified | 1.0 | on track | 0.522260273972603 | 62.0 | 364.0 | 0.0 | 0.0 | 0.142857142857143 | 0.857142857142857 | 0.142857142857143 | 0.857142857142857 | 2026 | n | 3 | not specified | not specified | not specified | p | 127 | 1.0 | 1.0 | not specified | not specified | not specified | not specified | 2025-10-29 | 2026-01-27 | not specified | not specified | 2024-08-29 | [5 empty] | not specified | 426.0 | not specified | -301.0 | not specified | -584.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.51
cybersecurity - identity and access management | 68615 | identity and access management (iam) is crucial for protecting data and ensuring that only authorized users, machines, and applications gain access to the right resources at the right time. * safeguarding digital identities: iam helps prevent identity-based attacks and data breaches by controlling who can access sensitive resources. * compliance with regulations: iam ensures compliance with industry standards and regulations by managing user access and permissions. * minimizing human errors: centralized control reduces the risk of accidental data exposure or unauthorized access due to human mistakes. * improved confidentiality: iam restricts access to sensitive data, protecting it from unauthorized users. * improved accessibility: iam enables secure access for employees, contractors, and partners, whether they’re on-site or remote. * single sign-on (sso): iam simplifies user authentication by allowing users to log in once and access multiple resources without re-entering credentials. * streamlined resource integrations: iam ensures that the right people have the right level of access to company resources, even as roles change. * potential cost benefit from decoupling redundant iam solutions currently in place | brad duffey | ryan russel | project | standalone project | standalone project | not specified | not specified | cybersecurity it | not specified | ryan russel | not specified | miles romello | not specified | m.j. vaidya | not specified | other | support functions: global it - cyber | it | l1 (identified) | on hold | 68615.0 | not specified | project dashboard | project finance dashboard | 0.38 | 2024-06-06 | 2024-12-03 | 129d | project has been placed on hold at the request of mj to work on project justification | not specified | not specified | project justification support and alignment with leadership. | red | down | red | red | green | red | yellow | green | 7 | 0 | 7.0 | 15.0 | 73.0 | 32.0 | 17.0 | 52.0 | 52.0 | 49.0 | 123.0 | 91.0 | 57.0 | 34.0 | 1441187.0 | 1037238.0 | 403949.0 | 504460.75 | 214896.0 | 289564.75 | 0.0 | 936726.0 | 822342.0 | 114384.0 | 0.0 | 1441186.75 | 1037238.0 | 403948.75 | 0.0 | 0.25 | 0.0 | 0.25 | 1.73468120376e-07 | 0.0 | 6.18890008392e-07 | 2025-10-27 | 2024-06-06 | 2024-12-03 | 0 | 129d | 2025-08-25 | 2025-03-31 | not specified | 13 | not specified | not specified | 0 | 1 | 0 | 2 | 1 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on-hold | not specified | it | not specified | not specified | global | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not planned (l2 to l4) | not specified | 1.0 | on track | 1.0 | 65.0 | 212.0 | 0.0569105691056911 | 0.121951219512195 | 0.59349593495935 | 0.260162601626016 | 0.422764227642276 | 0.577235772357724 | previous year | n | 3 | not specified | not specified | not specified | p | 128 | 1.0 | 1.0 | not specified | not specified | not specified | not specified | 2025-10-29 | 2026-01-27 | not specified | not specified | 2024-09-03 | [5 empty] | not specified | 510.0 | not specified | 420.0 | not specified | -129.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.38
evaluate uc communications for professional track workers | 32867 | aligns with e5 investment in microsoft. e5 includes team's voice licensing which we already own. the cisco contract for call manager through att/nds ends on 01/25/2025. we will be changing over to team's voice with operator connect to support internal and external calling and driving significant cost savings. cisco contact center is covered under a separate initiative. (initiative #32868) this is for the remaining telephony features in cisco call manager (phones for making and receiving calls not part of customer service) | cyndi maples | jamal mebane | project | standalone project | standalone project | not specified | not specified | it infrastructure na it | not specified | jamal mebane | not specified | gordon greenland | gordon greenland | m.j. vaidya | not specified | sg&a | support functions: global it - infrastructure / service desk | it | l3 (planned) | some issues | 32867.0 | not specified | project dashboard | project finance dashboard | 0.5 | 2024-08-27 | 2025-10-17 | 299d | • pm status remains yellow due to high risk of aggressive schedule to meet a required completion constraint of current cisco voice contract. • vz east region cutover completed 5/13 (msft) & 5/14 (vz) • vz central region cutover completed 6/10 (msft) & 7/3 (vz) • vz west region cutover completed 6/24 (msft) & 7/16 (vz) • vz canada region port order request submitted. awaiting foc. • vz other plants - 4 plants scheduled 7/28. awaiting foc. (pottsville, coral springs, rantoul, mt vernon) • vz misc. - craigsville + extra numbers. orders request in progress. awaiting confirmation. • service desk cutover completed 6/25 | • vz west region cutover competed 7/16 | • vz misc. plants in progress - scheduled 7/28. awaiting foc. (pottsville, coral springs, rantoul, mt vernon) | not specified | yellow | angle up | red | green | red | red | green | red | 3 | 7 | 0.0 | 0.0 | 8.0 | 70.0 | 8.0 | 5.0 | 0.0 | 0.0 | 78.0 | 8.0 | 5.0 | 3.0 | 351719.0 | 281337.0 | 70382.0 | 395337.2 | 182406.84 | 212930.36 | 0.0 | 12998.7 | 0.0 | 12998.7 | 0.0 | 408335.9 | 182406.84 | 225929.06 | 0.0 | -56616.9 | 98930.16 | -155547.06 | -0.160971969100333 | 0.351642905128014 | -2.21004035122617 | 2025-10-28 | 2024-08-27 | 2025-04-30 | 0 | 177d | 2025-08-27 | 2025-09-16 | not specified | 10 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 6.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | active | not specified | it | not specified | not specified | not specified | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0.556 | not specified | 0.198 | 2024-12-10 | 2024-12-11 | due soon for l2 | not specified | 1.0 | on track | 1.0 | 63.0 | 43.0 | 0.0 | 0.0 | 0.102564102564103 | 0.897435897435898 | 0.0 | 1.0 | current year | n | 3 | not specified | not specified | not specified | p | 129 | 1.0 | 1.0 | not specified | not specified | not specified | not specified | 2025-10-29 | 2026-01-27 | not specified | not specified | 2024-09-16 | [5 empty] | not specified | 428.0 | not specified | 102.0 | not specified | -299.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.5
test maintenance project | p-0260 | (not a real project) | mitch perry | mitch perry | project | standalone project | standalone project | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.25 | 2024-06-06 | 2024-12-03 | 129d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | sideways | red | red | green | red | yellow | green | 2 | 2 | 24.0 | 5.0 | 0.0 | 9.0 | 24.0 | 24.0 | 38.0 | 38.0 | 38.0 | 29.0 | 29.0 | 0.0 | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2024-11-05 | 2024-06-06 | 2024-12-03 | 0 | 129d | 2025-09-15 | 2024-10-30 | not specified | 5 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | active | not specified | other | not specified | not specified | not specified | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 1.0 | 44.0 | 364.0 | 0.631578947368421 | 0.131578947368421 | 0.0 | 0.236842105263158 | 1.0 | 0.0 | previous year | not specified | 3 | not specified | not specified | not specified | p | 130 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-10-29 | 2026-01-27 | not specified | not specified | 2024-09-03 | [5 empty] | not specified | 510.0 | not specified | 420.0 | not specified | -129.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.25
(jorge) 22630 special order program rebuild including catalog and retail commercial actions- doors portion | p-0261 | (this project is a temporary version for jorge to include it financials for wave #22630) | jorge eleta | emily bartlett | not specified | not specified | standalone project | not specified | not specified | not specified | not specified | (it pm not required) | not specified | not specified | mike crawford (brm) | tyce deal | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | finance dashboard | 0.25 | 2024-06-06 | 2024-12-03 | 129d | test-most recent update | test-most recent update | test-most recent update | test-most recent update | green | on track | red | red | green | red | yellow | green | 2 | 2 | 24.0 | 5.0 | 0.0 | 9.0 | 24.0 | 24.0 | 38.0 | 38.0 | 38.0 | 29.0 | 29.0 | 0.0 | 0.0 | not specified | not specified | 735550.0 | 636973.0 | 98577.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 735550.0 | 636973.0 | 98577.0 | 0.0 | -735550.0 | -636973.0 | -98577.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2024-06-06 | 2024-12-03 | 0 | 129d | 2025-02-24 | 2025-02-27 | true | 5 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | active | not specified | it | not specified | not specified | not specified | not specified | not specified | not specified | on track | on track | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 1.0 | 247.0 | 244.0 | 0.631578947368421 | 0.131578947368421 | 0.0 | 0.236842105263158 | 1.0 | 0.0 | previous year | not specified | 4 | not specified | not specified | not specified | not specified | 135 | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | [6 empty] | not specified | not specified | not specified | not specified | not specified | -129.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.25
athens | 70970 | not specified | garrett farmer | amy phillips | project | standalone project | standalone project | not specified | not specified | not specified | not specified | amy phillips | not specified | gordon greenland | not specified | m.j. vaidya | not specified | not specified | support functions: global it - infrastructure / service desk | it | l1 (identified) | on track | 70970.0 | not specified | project dashboard | project finance dashboard | 0.58 | 2024-09-16 | 2025-10-06 | 276d | we are working on getting initial contract details together with jmi. we are ensuring all scope needed to be included in the contract is gathered and aligned on. | met with hr and have made some progress with needed next steps to accomplish. | determine the costs associated with separation packages. progress on contract work. | not specified | green | sideways | red | yellow | red | red | yellow | green | 1 | 0 | 39.0 | 59.0 | 11.0 | 110.0 | 54.0 | 50.0 | 122.0 | 108.0 | 219.0 | 109.0 | 66.0 | 43.0 | 0.0 | not specified | not specified | 89163.0 | 0.0 | 89163.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 89163.0 | 0.0 | 89163.0 | 0.0 | -89163.0 | 0.0 | -89163.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2024-09-16 | 2025-04-07 | 0 | 146d | 2025-05-20 | 2024-11-18 | not specified | 2 | not specified | not specified | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | active | not specified | it | not specified | not specified | global | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | 1.0 | 1.0 | on track | 1.0 | 162.0 | 345.0 | 0.178082191780822 | 0.269406392694064 | 0.0502283105022831 | 0.502283105022831 | 0.557077625570776 | 0.442922374429224 | current year | not specified | 3 | not specified | not specified | not specified | p | 137 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-10-29 | 2026-01-27 | not specified | not specified | 2024-10-17 | 2024-10-24 | 2025-04-04 | 2025-04-04 |  |  | not specified | 408.0 | not specified | 113.0 | not specified | -276.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.58
ptm services review | p-0267 | the purpose of this initiative is to better understand all of the functions ptm’s are fulfilling and determine if there are areas that can effectively be supported in other ways that would allow us to more effectively utilize our existing ptm’s | ryan russel | ryan russel | project | standalone project | standalone project | not specified | not specified | not specified | not specified | ryan russel | not specified | mike schipper | ryan russel | kirk kroft | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.0 | 2025-01-01 | 2025-06-26 | 127d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | sideways | red | red | green | green | yellow | green | 0 | 0 | 6.0 | 54.0 | 15.0 | 0.0 | 22.0 | 22.0 | 75.0 | 75.0 | 75.0 | 75.0 | 75.0 | 0.0 | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-02-24 | 2024-10-30 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | active | not specified | it | not specified | not specified | not specified | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 1.0 | 247.0 | 364.0 | 0.08 | 0.72 | 0.2 | 0.0 | 1.0 | 0.0 | current year | not specified | 3 | not specified | not specified | not specified | p | 140 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-10-29 | 2026-01-27 | not specified | not specified | [6 empty] | not specified | 301.0 | not specified | 215.0 | not specified | -127.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0
o2c-27 automation | 70040 | automation of the o2c-27 control, which requires a sample of invoices be traced to supporting approved pricing agreements/tables, supporting shipping documents, and payment confirmations. by automating this process, or at least a portion of this reconciliation process, it will increase the effectiveness of the control process, reducing deficiencies/exceptions identified in the control execution, allow the organization to place more reliance on the control and decrease the time spent by the business performing a compliance task. | garrett farmer | garrett farmer | project | standalone project | standalone project | not specified | not specified | it na/corporate | not specified | garrett farmer | not specified | elizabeth chaney | shannon messing | m.j. vaidya | not specified | pricing | support functions: finance | it | submitted for l3 approval | on track | 70040.0 | not specified | project dashboard | project finance dashboard | 1.0 | 2024-09-27 | 2025-01-29 | 89d | completed all sprints. we were able to complete all demos and the business is very happy with the outcome. we are now in the evaluation of poc and next step is to determine next phase and if/when we proceed. | completed poc | decision on next phase. | not specified | green | sideways | red | blue | green | red | yellow | yellow | 1 | 0 | 0.0 | 4.0 | 9.0 | 55.0 | 0.0 | 11.0 | 13.0 | 13.0 | 68.0 | 13.0 | 0.0 | 13.0 | 2705927.0 | 2081203.0 | 624724.0 | 2761168.2 | 2139951.96 | 621216.24 | 503623.24 | 33838.0 | 0.0 | 33838.0 | 0.0 | 2795006.2 | 2139951.96 | 655054.24 | 503623.24 | -89079.2000000002 | -58748.96 | -30330.24 | -0.0329200307325365 | -0.0282283659979349 | -0.0485498236021027 | 2025-10-28 | 2024-09-27 | 2025-01-29 | 0 | 89d | 2025-03-12 | 2025-01-08 | not specified | 1 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | not specified | it | not specified | not specified | not specified | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0.0 | not specified | not specified | 2024-12-07 | 2025-06-27 | on plan | not specified | 1.0 | on track | 1.0 | 231.0 | 294.0 | 0.0 | 0.0588235294117647 | 0.132352941176471 | 0.808823529411765 | 0.191176470588235 | 0.808823529411765 | current year | n | 3 | not specified | not specified | not specified | p | 141 | 1.0 | 1.0 | not specified | not specified | not specified | not specified | 2025-10-29 | 2026-01-27 | not specified | not specified | 2024-10-10 | 2024-10-24 | 2024-10-31 |  |  |  | not specified | 397.0 | not specified | 363.0 | not specified | -89.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 1
pecan | 68934 | network initiative | andrea chitti | andrea chitti | project | standalone project | standalone project | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | 68934.0 | not specified | project dashboard | project finance dashboard | 0.38 | 2025-01-01 | 2025-06-26 | 127d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | sideways | red | red | green | green | yellow | green | 0 | 0 | 60.0 | 64.0 | 3.0 | 32.0 | 48.0 | 51.0 | 159.0 | 159.0 | 159.0 | 127.0 | 92.0 | 35.0 | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-28 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-05-22 | 2024-10-30 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | usd | other | not specified | not specified | not specified | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | 1.0 | 1.0 | on track | 1.0 | 160.0 | 364.0 | 0.377358490566038 | 0.40251572327044 | 0.0188679245283019 | 0.20125786163522 | 1.0 | 0.0 | current year | n | 3 | not specified | not specified | not specified | p | 143 | 1.0 | 1.0 | not specified | not specified | not specified | not specified | 2025-10-29 | 2026-01-27 | not specified | not specified | [6 empty] | not specified | 301.0 | not specified | 215.0 | not specified | -127.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | pecan | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.38
osprey | 68730 | network initiative | andrea chitti | andrea chitti | project | standalone project | standalone project | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | 68730.0 | not specified | project dashboard | project finance dashboard | 0.0 |  |  | 0 | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | sideways | yellow | yellow | schedule not set | green | yellow | green | 0 | 0 | 31.0 | 1.0 | 1.0 | 1.0 | 0.0 | 32.0 | 22.0 | 22.0 | 34.0 | 33.0 | 1.0 | 32.0 | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-28 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-02-21 | 2024-10-30 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | usd | other | not specified | not specified | not specified | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | 1.0 | 1.0 | on track | 0.0 | 250.0 | 364.0 | 0.911764705882353 | 0.0294117647058824 | 0.0294117647058824 | 0.0294117647058824 | 0.647058823529412 | 0.352941176470588 | not specified | n | 3 | not specified | not specified | not specified | p | 144 | 1.0 | 1.0 | not specified | not specified | not specified | not specified | 2025-10-29 | 2026-01-27 | not specified | not specified | [6 empty] | not specified | not specified | not specified | not specified | not specified | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | osprey | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0
cybersecurity - transition from okta to microsoft | 32872 | as part of zero trust strategy, consolidating the identity and access under microsoft will help to improve the security posture and reduce the licensing cost with okta. there will be a significant change management activities including multi-factor authentication enrollment, application authentication etc. | brad duffey | brad duffey | project | standalone project | standalone project | not specified | not specified | cybersecurity it | not specified | brad duffey | not specified | m.j. vaidya | miles romello | m.j. vaidya | not specified | sg&a | support functions: global it - cyber | it | l3 (planned) | on track | 32872.0 | not specified | project dashboard | project finance dashboard | 0.81 | 2024-06-01 | 2026-02-19 | 449d | p2g: decision point made for postponing external salesforce users until jan 19, 2026, will allow focus for completing all but four applications (that rely on salesforce/experience cloud). 18 apps remaining to migrate, going slower than anticipated due to resource constraints. primary qql resource caught up in rif, unable to move forward with sf migration from a qql standpoint. we must free up fred to work on continuing to migrate apps, which will not happen because he's also the primary resource on sf testing.. sf testing has begun, again resource constrained and no definable completion date due to entra learning curves. budget is irreparable - we must finish the project and hold costs down as much as possible. | north american knowledge and production workers completed eu kw completed | na prosite and jw.com migrations pending migration date agreement with cmd. | no additional support needed at this time. | yellow | sideways | red | green | red | green | yellow | red | 1 | 0 | 2.0 | 2.0 | 82.0 | 179.0 | 8.0 | 31.0 | 1.0 | 1.0 | 265.0 | 86.0 | 75.0 | 11.0 | 250000.0 | 0.0 | 250000.0 | 264465.5 | 0.0 | 264465.5 | 0.0 | 16500.0 | 0.0 | 16500.0 | 0.0 | 280965.5 | 0.0 | 280965.5 | 0.0 | -30965.5 | 0.0 | -30965.5 | -0.123862 | 0.0 | -0.123862 | 2025-10-28 | 2024-06-01 | 2025-11-28 | 0 | 390d | 2025-10-10 | 2025-10-16 | not specified | 1 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | usd | it | not specified | not specified | not specified | implementation / execution | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0.4 | not specified | 0.258 | 2024-03-10 | 2025-04-04 | past due for l3 | not specified | 1.0 | on track | 0.819599109131403 | 19.0 | 13.0 | 0.00754716981132076 | 0.00754716981132076 | 0.309433962264151 | 0.675471698113208 | 0.00377358490566038 | 0.99622641509434 | 2026 | n | 3 | not specified | not specified | not specified | p | 149 | 1.0 | 1.0 | not specified | not specified | not specified | not specified | 2025-10-29 | 2026-01-27 | not specified | not specified | 2024-10-17 | 2024-10-17 | 2024-12-05 | 2025-01-09 | 2025-11-27 | 2025-11-27 | not specified | 515.0 | not specified | -23.0 | not specified | -449.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | cybersecurity - transition from okta to microsoft | not specified |  | not specified | not specified | false | stage 3 - implementation | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.81
pmo000663 ei60 for export cert | 12284 | pmo000663 ei60 for export certification | christian wienand | andrás fejes | project | standalone project | standalone project | not specified | andrás fejes | r&d europe r&d europe central | not specified | not specified | andr�s fejes | oliver b�wing | not specified | not specified | not specified | growth | dach: commercial - germany | engineering | l3 (planned) | on track | 12284.0 | not specified | project dashboard | project finance dashboard | 0.59 | 2024-05-01 | 2026-09-03 | 612d | durability finished with positive result. 2/3 fire tests finished with positive result. smoke test positive. rc test positive. pilot run successful on 16.10.25 | 2 fire tests were finished with positive results. durability positive smoke accomplished with positive result rc accomplished with positive result pilot run successfully made | 1 more fire test on cw44 reports of the tests | not specified | green | sideways | yellow | green | yellow | green | yellow | green | 4 | 0 | 0.0 | 0.0 | 47.0 | 67.0 | 0.0 | 0.0 | 3.0 | 3.0 | 114.0 | 47.0 | 41.0 | 6.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2024-05-01 | 2026-10-15 | 0 | 642d | 2025-10-22 | 2025-10-22 | not specified | 4 | not specified | not specified | 0 | 3 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | r&d | technical | npd | central eu | implementation / execution | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | 1.0 | on track | 0.638888888888889 | 7.0 | 7.0 | 0.0 | 0.0 | 0.412280701754386 | 0.587719298245614 | 0.0263157894736842 | 0.973684210526316 | 2026 | not specified | 3 | not specified | not specified | not specified | p | 157 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2024-05-01 | 2026-10-15 | not specified | 2024-05-31 00:00:00 | 2024-10-17 | 2025-07-18 | 2025-12-11 |  | 2026-10-15 | 2026-10-15 | not specified | 0.0 | not specified | 42.0 | not specified | -612.0 | not specified | 2024-05-31 00:00:00 | 2024-10-17 00:00:00 | 2025-09-04 00:00:00 | 2025-12-11 00:00:00 | not specified | 2026-09-03 00:00:00 | 2026-09-03 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0 | -48d | 0 | 42d | 42d | 0.0 | -0.0784313725490196 | 0.0 | 0.0686274509803922 | 0.0686274509803922 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | stage 3 - implementation | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.59
pmo000637 change pvc edgeband fr 3 to 2mm | 49063 | pmo000637 change pvc edgebanding from 3mm to 2mm | magnus hoff | kira svane kristensen | project | standalone project | standalone project | not specified | kira svane kristensen | r&d europe r&d europe north | not specified | not specified | kira svane kristensen | kira svane kristensen | not specified | not specified | not specified | npi / npd | europe: product rationalisation | engineering | l5 (realised) | on track | 49063.0 | not specified | project dashboard | project finance dashboard | 1.0 | 2024-06-01 | 2025-02-20 | 189d | week 8 gate 3+4 approved. | gate 3+4 passed. | follow-up meeting to close project 20/3-2025. | no support needed | green | up | red | blue | red | green | green | green | 0 | 0 | 0.0 | 0.0 | 0.0 | 12.0 | 0.0 | 0.0 | 0.0 | 0.0 | 12.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2024-06-01 | 2025-01-10 | 0 | 160d | 2025-05-22 | 2025-04-02 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | r&d | technical | vave | north eu | realize value / close / care period | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | 1.0 | on track | 1.0 | 160.0 | 210.0 | 0.0 | 0.0 | 0.0 | 1.0 | 0.0 | 1.0 | current year | not specified | 3 | not specified | not specified | not specified | p | 158 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2024-06-01 | 2025-01-10 | not specified | not specified |  |  |  |  | 2025-01-10 |  | not specified | 0.0 | not specified | -41.0 | not specified | -189.0 | not specified | not specified | not specified | not specified | not specified | not specified | 2025-02-20 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | -41d | dates not set | 0.0 | 0.0 | 0.0 | -0.216931216931217 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | stage 5 - care period | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 1
pmo000641 alum primer change | p-0280 | pmo000641 aluminium primer change | martin zagora | boel sandberg | project | standalone project | standalone project | not specified | boel sandberg | r&d europe r&d europe north | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.89 | 2024-11-22 | 2025-11-25 | 263d | decision to push gate 2 and combine with gate 3 made by olar and boel | internal discussion and approval about cold check method in r&d. a couple of adjustments and then planning for communication to other stakeholder by end of sep | gate 2 andgate 3 combined 25/11 | not specified | yellow | angle up | red | green | red | red | yellow | green | 4 | 0 | 0.0 | 14.0 | 6.0 | 27.0 | 1.0 | 3.0 | 20.0 | 7.0 | 47.0 | 20.0 | 8.0 | 12.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-10-02 | 2025-09-29 | not specified | 9 | not specified | not specified | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | r&d | exterior | sustaining | north eu | development | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.927756653992396 | 27.0 | 30.0 | 0.0 | 0.297872340425532 | 0.127659574468085 | 0.574468085106383 | 0.425531914893617 | 0.574468085106383 | current year | not specified | 3 | not specified | not specified | not specified | p | 159 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | 40.0 | not specified | -152.0 | not specified | -263.0 | not specified | 2024-11-22 00:00:00 | 2025-04-17 00:00:00 | 2025-11-25 00:00:00 | 2025-11-25 00:00:00 | not specified | 2025-11-25 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | stage 2 - development | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.89
pmo000448 uk white oak range-howdens | 11864 | pmo000448 uk white oak 'lite' range for howdens | not specified | scott mcbride | project | standalone project | standalone project | not specified | scott mcbride | r&d europe r&d europe uk r&d europe uk / france | not specified | it pm not required | scott mcbride | ross hawkings | adam painter | rachael horton-farmer | not specified | npi / npd | uk: commercial | it; engineering | submitted for l4 approval | on track | 11864.0 | not specified | project dashboard | project finance dashboard | 0.88 | 2022-09-01 | 2025-11-06 | 831d | - first container delivered - first production completed - second container arrived at port - due in penrith 29th may - project now handed over to penrith ops team with support from project team only when required - gates 3 & 4 passed 22nd may | - first container delivered - first production completed - second container arrived at port - due in penrith 29th may - project now handed over to penrith ops team with support from project team only when required - gates 3 & 4 passed 22nd may | - aid any actions escalated from operations | not specified | green | angle up | yellow | green | yellow | green | yellow | green | 0 | 0 | 4.0 | 1.0 | 0.0 | 96.0 | 4.0 | 5.0 | 6.0 | 6.0 | 101.0 | 5.0 | 5.0 | 0.0 | 91764.7058823526 | 0.0 | 91764.7058823526 | 90359.9999999997 | 0.0 | 90359.9999999997 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 90359.9999999997 | 0.0 | 90359.9999999997 | 0.0 | 1404.70588235294 | 0.0 | 1404.70588235294 | 0.0153076923076924 | 0.0 | 0.0153076923076924 | 2025-10-27 | 2022-09-01 | 2025-10-30 | 0 | 826d | 2025-10-22 | 2025-07-17 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 78000.0 | not specified | 78000.0 | 76806.0 | 0.0 | 76806.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 76806.0 | 0.0 | 76806.0 | 0.0 | 1194.0 | 0.0 | 1194.0 | 0.0153076923076923 | 0.0 | 0.0153076923076923 | not specified | completed | eur | r&d | interior | npd | uk / france | realize value / close / care period | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | 1.0 | on track | 0.992779783393502 | 7.0 | 104.0 | 0.0396039603960396 | 0.0099009900990099 | 0.0 | 0.950495049504951 | 0.0594059405940594 | 0.940594059405941 | current year | not specified | 3 | not specified | not specified | 1.0 | p | 161 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2022-09-01 | 2025-10-30 | not specified | not specified | 2024-10-31 | 2025-02-20 | 2025-03-20 |  | 2025-05-16 | 2025-10-08 | not specified | 0.0 | not specified | -7.0 | not specified | -831.0 | not specified | not specified | 2024-10-31 00:00:00 | 2025-02-27 00:00:00 | 2025-05-22 00:00:00 | not specified | 2025-05-22 00:00:00 | 2025-10-08 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0 | -7d | -63d | -6d | 0 | 0.0 | -0.00842358604091456 | -0.075812274368231 | -0.0072202166064982 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | stage 5 - care period | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.88
pmo000740 - smart door system for apartments (steel) | 69758 | product launch of smart door system for steel apartment doors incl. rc3 security doors. the 4210 steel security apartment door launched 1st of april have approval for the dormakaba dkey lock solution. jw are first door supplier to have a single point smart lock approved for rc3. the smart lock has already 3rd part suppliers to administrate multiple locks which makes this solution fit for apartment buildings no product development needed | kira svane kristensen | kira svane kristensen | project | standalone project | standalone project | not specified | kira svane kristensen | r&d europe r&d europe north | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | 69758.0 | not specified | project dashboard | project finance dashboard | 0.99 | 2024-10-14 | 2025-04-04 | 125d | week 19 after launch meeting with sales and marketing. no orders yet. | feedback from sales dk is that customers are beginning to focus more on electronical lock systems. two projects where electronic locks are in focus, one could be with steel doors. | continue monthly after launch meetings with sales and marketing. | no support needed | green | up | red | green | red | green | green | green | 1 | 0 | 1.0 | 0.0 | 0.0 | 67.0 | 1.0 | 0.0 | 0.0 | 0.0 | 68.0 | 1.0 | 0.0 | 1.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2024-10-14 | 2025-03-05 | 0 | 103d | 2025-04-11 | 2025-05-09 | not specified | 1 | not specified | not specified | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | r&d | steel | npd | north eu | realize value / close / care period | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not planned (l2 to l4) | not specified | 1.0 | on track | 1.0 | 201.0 | 173.0 | 0.0147058823529412 | 0.0 | 0.0 | 0.985294117647059 | 0.0 | 1.0 | current year | n | 3 | not specified | not specified | not specified | p | 174 | 1.0 | 1.0 | not specified | not specified | not specified | not specified | 2024-10-14 | 2025-03-05 | not specified | not specified | 2024-12-12 |  |  |  | 2025-02-27 |  | not specified | 0.0 | not specified | -30.0 | not specified | -125.0 | not specified | not specified | 2024-12-04 00:00:00 | not specified | not specified | not specified | 2025-03-27 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 8d | dates not set | dates not set | -28d | dates not set | 0.064 | 0.0 | 0.0 | -0.224 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | stage 5 - care period | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.99
yule programme | 67931 | not specified | ben bridgewater | dom gaffey | program | 67931 | 67931: yule programme | not specified | not specified | it it-eu | not specified | not specified | not specified | not specified | adam painter | rachael horton - farmer | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | program dashboard | finance dashboard | 0.489461688734534 | 2024-08-19 | 2026-12-25 | 615d | - wk43 programme - 8 months remaining to revised programme schedule new location - 17 contracts left to finalise, 13 are past due - initial fitout works are underway this month commercial - gap closing activity - mbp - doorkit run-rate tracking +25% above budget +15% 6+6 for q3 £300k - gap closing activity- persimmon - indirect via hubs - overperforming +£200k above budget penrith - 3rd line machine delivery commenced it, systems & processses - applications workshops completed operations - chris williams seconded to lead the operations workstream yule business case - commercial business case - currently behind plan (partially market + price / cost challenges in fy25) - forecasted to recover but it will take an extra year - operations business case - currently ahead of plan but will fall behind in 2026 due to project delay of 6 months - overall savings will be delivered but delayed | - wk43 programme - workstream interdependencies mapped - x2 day operations & alignment workshop planned new location - building scan completed - containment and power to fibre & cabinet - planning permission submitted - kiwa (fire engineers) - contract setup - fk restoration (fitout) - fk have reviewed and shared comments on the jct contract which is now with eversheds for review - mecalux (racking) - verbal agreement on contract terms - pumps, tanks and housing for sprinklers (fk / alpine) - po placed - compressors (fk/pps) - po placed - power civils internal (stanfords) - po placed - adrad (heating, gas & water) - po placed - doorkit line - essepigi visit (build on track for dec fat) - cold press line - build commenced commercial - persimmon - proceeding to contract negotiations based on awarding jw 75% share - bellway - sales pitch (positive feedback) - barratt redrow - v2 redline back with barratt penrith - glazing team relocated to new glazing area - 3rd line foundations dug - 3rd line roof modification - purlins modified to allow quick removal and replacement so ready for craning the presses in via the roof - x4 trailers arrived and offloaded it, systems & processes - bessemer - all pos approved and issued - bessemer - fibre line fed from off off-premises to interior - bessemer - cabinet delivered and built - application workshops completed people & culture - hrbp penrith - starts 03-nov - hrbp sheffield - interim at interview stage - return to office plan agreed products - list setup for penrith vs sheffield manufacture operations - labour phasing documented - housebuilder review with chrism and markh to understand forecasted changes closure - documentation - 129 boxes removed from site. - hot press and progressive - visit from jw france reached out to liquidity services as they are interested in providing an offer for all excess equipment and machinery. introduction via louise. will pick this up in november. formm office start up meeting (17.10.25) introductions sos planning. communications - latest newsletter sent to print | -- wk43 programme new location - power civils internal - starting 27-oct - power civils external - starting 10-nov - sprinklers site survey w/c 20-oct - sprinklers final drawings - 14-nov - sprinklers - risk team / insurance visit planned w/c 17-nov - license of alteration submission oct-25 commercial - taylor wimpey review - nov - barratt redrow - legal teams review - w/c 03-nov - persimmon - legal contract penrith - 3rd line press foundation concrete pour - 3rd line press delivery and positioning - 3rd line installation start it, systems & processes - penrith 3rd line - dis commencing cabling 27-oct - bessemer offices - dis meeting with formm - share applications plan - get copy of previously used test scripts people & culture - penrith 3rd line recruitment - employee onboarding process updates - operational skills matrices update - change agent training - nov products - present / review slab list at oct yule operations workshop - handover list to it - oct - cf160 fire test 10-nov - bi-fold - b&q review nov - plastic packaging to card - review cost & barriers - signage - supplier prices operations - stock build - present stock build proposal during operations workshop 22-oct - create comprehensive plan on smartsheets - oct closure - office - agree target completion date for office fitout - hot press & progressive - supply further information (tooling, tooling shaft size and pit cylinder positions) - machinery - contact liquidity services regarding excess equipment and machinery offer - site sale - agree marketing timeline - next meeting 09-dec communications - xmas yule newsletter | wk43 new location - 17 contracts left to finalise - fk restoration (fitout) jct contract is the highest priority - signed off contract is needed in oct | yellow | on track | green | on track | green | green | yellow | green | 0 | 0 | 42.0 | 252.0 | 886.0 | 450.0 | 44.0 | 292.0 | 184.0 | 159.0 | 1626.0 | 1176.0 | 719.0 | 457.0 | 464994.117647057 | 464994.117647057 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | 398000.564705881 | 398000.564705881 | 0.0 | not specified | 398000.564705881 | 398000.564705881 | 0.0 | not specified | 66993.5529411762 | 66993.5529411762 | 0.0 | 0.14407397943048 | 0.14407397943048 | 0 |  | 2024-08-01 | 2026-12-23 | 0 | 625d | 2025-10-28 | 2025-10-29 | not specified | 0 | not specified | not specified | 2 | 6 | 6 | 2 | 10 | 12 | 0 | 7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 395245.0 | 395245.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | 338300.48 | 338300.48 | 0.0 | not specified | 338300.48 | 338300.48 | 0.0 | not specified | 56944.52 | 56944.52 | 0.0 | 0.14407397943048 | 0.14407397943048 | 0.0 | not specified | active | eur | it | not specified | not specified | eu | see project details | not specified | not specified | on track | on track | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.508943089430894 | 1.0 | 0.0 | 0.025830258302583 | 0.154981549815498 | 0.54489544895449 | 0.276752767527675 | 0.113161131611316 | 0.886838868388684 | 2026 | not specified | 2 | not specified | not specified | not specified | not specified | 175 | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | [6 empty] | not specified | not specified | not specified | not specified | not specified | -615.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.48946
programme management | p-0296 | not specified | ben bridgewater | andrew grafton | project | 67931 | 67931: yule programme | not specified | not specified | not specified | not specified | not specified | not specified | not specified | adam painter | rachael horton - farmer | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.0 | 2024-08-30 | 2026-11-30 | 587d | wk42 | wk42 - cross workstream colloboration / interdependency discussion session01 - charter signed off by each w/s lead - planned 6 monthly review | wk42 - yule plan on a page - 6 monthly review - cross workstream colloboration / interdependency discussion session02 - resource tool sharing - share charter with hamish and dom | wk42 - fk fitout (jct) contract agreement - simon | yellow | sideways | red | green | red | green | green | green | 6 | 0 | 4.0 | 0.0 | 53.0 | 18.0 | 4.0 | 2.0 | 0.0 | 0.0 | 75.0 | 57.0 | 47.0 | 10.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2024-08-01 | 2026-04-28 | 0 | 454d | 2025-10-27 | 2025-10-17 | not specified | 6 | not specified | not specified | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | it | not specified | not specified | eu | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.517887563884157 | 2.0 | 12.0 | 0.0533333333333333 | 0.0 | 0.706666666666667 | 0.24 | 0.0 | 1.0 | 2026 | not specified | 3 | not specified | not specified | 1.0 | p | 176 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2024-08-01 | 2026-04-28 | not specified | not specified | [6 empty] | not specified | -29.0 | not specified | -216.0 | not specified | -587.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | programme management | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0
people & culture | p-0297 | not specified | ben bridgewater | sallyann charlton | project | 67931 | 67931: yule programme | not specified | not specified | not specified | not specified | not specified | not specified | not specified | adam painter | rachael horton - farmer | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.8 | 2024-10-01 | 2026-01-21 | 342d | wk 43- w/e 24.10.2025 - project planning - culture - talent acquisition | see attached penrith pulse hrbp recruitment - penrith hrbp joins 3/11, sheffield 12 month ftc at interview stage. ta plan - training manager and quality engineer roles live/interviewing, vsl interviews being arranged. continuing to working with ops on transition plan, building detail into plan and aligning to key dates. difficult to allocate time this week due to leave and 2 day yule workshop | further steps for hr recruitment. rto to move to 2 days from 1st jan 26. remaining outstanding questions from some teams being addressed. training of change agents and agree list of activity. socialising and issuing of site charter. meeting with gmb mid october. further steps for hr recruitment sheffield and penrith recruitment 3rd line. visiting penrith on monday 3rd november. to support with pro-wfm cutover and to deliver change recognition to the team. revert to key priorities in plan. | budget sign off to support transition plan confirmation assumed for office staff transition 1 april 26 clt agreement on changes to cultural roadmap after discussions | yellow | sideways | yellow | green | green | green | yellow | green | 7 | 0 | 4.0 | 80.0 | 47.0 | 48.0 | 8.0 | 34.0 | 58.0 | 38.0 | 179.0 | 131.0 | 42.0 | 89.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2024-08-20 | 2026-03-31 | 0 | 421d | 2025-10-24 | 2025-10-24 | not specified | 7 | not specified | not specified | 0 | 1 | 0 | 1 | 1 | 3 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | it | not specified | not specified | eu | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.824561403508772 | 5.0 | 5.0 | 0.0223463687150838 | 0.446927374301676 | 0.262569832402235 | 0.268156424581006 | 0.324022346368715 | 0.675977653631285 | 2026 | not specified | 3 | not specified | not specified | 1.0 | p | 177 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2024-08-20 | 2026-03-31 | not specified | not specified | [6 empty] | not specified | -42.0 | not specified | 69.0 | not specified | -342.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | people & culture | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.8
communications | p-0298 | not specified | ben bridgewater | amy simpson | project | 67931 | 67931: yule programme | not specified | not specified | not specified | not specified | not specified | not specified | not specified | adam painter | rachael horton - farmer | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.87 | 2024-08-20 | 2026-01-30 | 379d | wk 42: comms on track | wk 42: need to discuss content for festive newsletter | wk 43: contributions for festive newsletter due | still lacking in content from channel streams | on track | on track | green | green | green | green | yellow | green | 0 | 0 | 0.0 | 2.0 | 1.0 | 35.0 | 0.0 | 2.0 | 1.0 | 1.0 | 38.0 | 3.0 | 3.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2024-08-20 | 2026-01-30 | 0 | 379d | 2025-10-16 | 2025-10-17 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | on track | eur | it | not specified | not specified | eu | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.823218997361478 | 13.0 | 12.0 | 0.0 | 0.0526315789473684 | 0.0263157894736842 | 0.921052631578947 | 0.0263157894736842 | 0.973684210526316 | 2026 | not specified | 3 | not specified | not specified | 1.0 | p | 178 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2024-08-20 | 2026-01-30 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | 0.0 | not specified | -379.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | communications | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.87
it systems & process (connectivity, infrastructure, systems) | p-0299 | implementation of the it infrastructure, connectivity and supporting systems to enable sheffield manufacturing move and closure. support penrith expansion | ben bridgewater | joe burrell | project | 67931 | 67931: yule programme | not specified | not specified | it it uk / france / export it-eu yule it | not specified | kaia simson | andrew grafton | hamish white | adam painter | rachael horton - farmer | not specified | footprint | uk: manufacturing | not specified | l3 (planned) | on track | not specified | not specified | project dashboard | project finance dashboard | 0.37 | 2024-10-28 | 2026-08-04 | 462d | w43: status: infrastructure: green ¦ applications: amber | w43: infrastructure: penrith: the contractor in penrith is already onsite to fix the baskets. dan will liaise with them next week bessemer: need to liaise with ben hamnett the bt internal fibre install. business operating model - workshops: currently conducting a fit/gap analysis on the workshop outputs project yule convened a 2-day "yule workshop" that brought all the workstreams together and each workstream socialised their status updates (scope, project risks etc) applications: currently, ray is working on the door kits sku rationalisation design and build test phase: betrand (it tester based in france) has now received the same it titan test scripts as previously used in both france and the uk. we are currently arranging training for him in the titan corporate code (i need a named personnel in france to carry out that training); then he will need to meet with ray to understand the uk titan bespoke code that he needs to test/regression test pmo: the project plan (and initial scope statement) have now been drafted | w44: infrastructure: penrith: 27/10 dis to start 3rd line infrastructure cabling bessemer: kick-off meeting with form (office fit out company) scheduled for fri 17th oct to align sheffield disposal work with the transition plan applications: to agree the priority requirements that need to be worked in in phase one, and to get working on these test phase : betrand to have started his training in titan corporate code/functions pmo: to have socialised the project plan and it process review workshop notes with the business | not specified | yellow | sideways | red | red | red | red | yellow | green | 8 | 1 | 21.0 | 147.0 | 176.0 | 44.0 | 18.0 | 199.0 | 116.0 | 112.0 | 384.0 | 340.0 | 75.0 | 265.0 | 464994.117647057 | 464994.117647057 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 398000.564705881 | 398000.564705881 | 0.0 | 0.0 | 398000.564705881 | 398000.564705881 | 0.0 | 0.0 | 66993.5529411762 | 66993.5529411762 | 0.0 | 0.14407397943048 | 0.14407397943048 | 0 | 2025-10-27 | 2024-10-28 | 2026-03-06 | 0 | 355d | 2025-10-27 | 2025-10-29 | not specified | 30 | not specified | not specified | 0 | 2 | 3 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 395245.0 | 395245.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 338300.48 | 338300.48 | 0.0 | 0.0 | 338300.48 | 338300.48 | 0.0 | 0.0 | 56944.52 | 56944.52 | 0.0 | 0.14407397943048 | 0.14407397943048 | 0.0 | not specified | active | eur | it | not specified | not specified | uk / france / export | implementation / execution | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.569264069264069 | 2.0 | 0.0 | 0.0546875 | 0.3828125 | 0.458333333333333 | 0.114583333333333 | 0.302083333333333 | 0.697916666666667 | 2026 | not specified | 3 | not specified | not specified | 1.0 | p | 179 | 1.0 | not specified | not specified | not specified | andrew grafton | not specified | 2024-10-28 | 2026-03-06 | not specified | not specified |  |  |  | 2024-10-31 | 2025-07-01 | 2026-02-23 | not specified | 0.0 | not specified | -151.0 | not specified | -462.0 | not specified | not specified | not specified | not specified | not specified | 2024-10-31 00:00:00 | 2025-10-06 00:00:00 | 2026-02-23 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | -97d | 0 | 0.0 | 0.0 | 0.0 | -0.20995670995671 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | it systems & process (connectivity, infrastructure, systems) | not specified |  | not specified | not specified | false | stage 3 - implementation | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.37
commercial | p-0300 | not specified | ben bridgewater | chris miller | project | 67931 | 67931: yule programme | not specified | not specified | not specified | not specified | not specified | not specified | not specified | adam painter | rachael horton - farmer | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.59 | 2024-08-19 | 2026-12-23 | 613d | w42: - mbp sales performing £1.1m above budget ytd. - persimmon sales direct getting close to budget & indirect via hubs overperforming. +£200k above budget (linked to gap closing activity) - mbp doorkit successful run-rate improvement (linked to gap closing activity) tracking +25% above budget +15% 6+6 for q3 £300k. | w42: - successful meeting with bellway, pitched for the first time with positive feedback inc their options team. - staircraft qbr, again positive & now fully aware of yule & what that means for them, exploring potential change in model moving forward. - v2 redline now back with barratt redrow, follow up f2f with legal teams w/c 3rd nov. w41: - first draft barratt redrow contract sent to customer for review. - positive feedback from persimmon would like to press ahead on contract negotiations based on awarding jw 75% share. | w42: - taylor wimpey review november - tri-wall packaging review with customer feedback session. - staircraft reciprocal lining internal discussion. w41: - prioritise persimmon contract next with legal. - bellway meeting booked oct. | w42: w41: - review our cost to serve assumptions. - make or buy assessment on linings product. | yellow | angle down | yellow | green | green | green | green | green | 5 | 0 | 0.0 | 1.0 | 18.0 | 14.0 | 0.0 | 3.0 | 0.0 | 0.0 | 33.0 | 19.0 | 8.0 | 11.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2024-08-19 | 2026-12-23 | 0 | 613d | 2025-10-16 | 2025-10-17 | not specified | 8 | not specified | not specified | 0 | 0 | 1 | 0 | 1 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | it | not specified | not specified | eu | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.510603588907015 | 13.0 | 12.0 | 0.0 | 0.0303030303030303 | 0.545454545454545 | 0.424242424242424 | 0.0 | 1.0 | 2026 | not specified | 3 | not specified | not specified | 1.0 | p | 180 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2024-08-19 | 2026-12-23 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | 0.0 | not specified | -613.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | commercial | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.59
penrith | p-0302 | not specified | ben bridgewater | neil kenny | project | 67931 | 67931: yule programme | not specified | not specified | not specified | not specified | not specified | not specified | not specified | adam painter | rachael horton - farmer | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.81 | 2024-08-20 | 2026-06-01 | 465d | w40 | w40 | w40 | w40 | on track | on track | green | green | green | green | green | green | 7 | 0 | 0.0 | 0.0 | 38.0 | 75.0 | 0.0 | 7.0 | 0.0 | 0.0 | 113.0 | 38.0 | 36.0 | 2.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2024-08-20 | 2026-06-03 | 0 | 467d | 2025-10-21 | 2025-10-10 | not specified | 8 | not specified | not specified | 0 | 2 | 0 | 1 | 3 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | on track | eur | it | not specified | not specified | eu | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.670967741935484 | 8.0 | 19.0 | 0.0 | 0.0 | 0.336283185840708 | 0.663716814159292 | 0.0 | 1.0 | 2026 | not specified | 3 | not specified | not specified | 1.0 | p | 182 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2024-08-20 | 2026-06-03 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | 2.0 | not specified | -465.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | penrith 3rd line | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.81
new location | p-0303 | not specified | ben bridgewater | gavin handbury | project | 67931 | 67931: yule programme | not specified | not specified | yule it | not specified | not specified | not specified | not specified | adam painter | rachael horton - farmer | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.51 | 2024-08-20 | 2026-09-17 | 543d | wk 42 - measured building survey complete. - ongoing design collaboration. - visit to essepigi | wk 42 vendor onboard, contracts and pos: - vendor onboard 14 in place 7 in process completed this week 2 - contracts: 3 in place, 15 in process, - completed this week 1 (kiwa) jct contract returned from fk and is now sat with jw / eversheds. expecting eversheds comments 17/10. legal setting up call 20th to put all comments together and review. po's: main fit out and racking are main po's to be placed. waiting on contract. mecalux has a price uplift due to in rack sprinkler installation. po's placed since last update: - site water infrastructure - adrad - site gas infrastructure - adrad - heating in manufacturing area. - adrad - civil work for power upgrade (internal) - stanfords - measured building survey completed. discrepancies found in landlords as is drawings. accurate drawings required for sprinkler installation and slab location. outputs to be used for contractors to work accurately to an installation plan and for jw to develop digital 3d factory. planning: submitted hv - mpn site survey in readiness for internal installation. start date 27th october stanford internal civil work - start date 27th oct. rogers external start date w/c 10 november. new machines: - visit to essepigi for progress update. confirmed and agreed all key dates. proposed fat criteria, health and safety site acceptance criteria agreed, function and performance test criteria agreed. progress build review - build v spec review. (caught pilot hole drilling unit was wrong, design for grade 10 butt hinge rather than door kit square hinge - essepigi to rectify). door kit line build will be complete beginning of nov. esspeigi testing to commence ready for fat in december. drawing and spec review of door set machine. improvement to be implemented on evevolution to how the machine detects door squareness (check at 4 points rather than 2). software setup and operation training. electrical build progress and full engineering evaluation completed. critical spare parts identified. cold press rebuild. - rebuild started. fencing and signage in place. line 1 dismantle started. | wk 42 sprinklers - detail site survey w/c 20th october. - final drawings to be completed ready for insurance approval friday14th november. - visit to alpine planned w/c 17th november: ken alleman - risk team, zurich engineer - name tbc & chris gibbs zurich engineering account manager (online) and jeld-wen project team. potential to reduce the installation timeline by 2 weeks. licence to alter next submission before end of october. it data cab: - jw team in 17th and 18th oct to install containment and power ready for cab install and fibre install. cold press rebuild - continue dismantle of line 1 and refurb of pre-crush. gnc machine move costs due 20th/21st oct mhe - reaching final stages of mhe supplier. to appoint supplier. design team meetings with contractors ongoing (weekly - mondays) | wk 42 -legal - jct contract to returned by fk. with our legal and eversheds to review and agree or red pen and send back. - sourcing - dl company. contract setup. | yellow | angle up | yellow | green | yellow | green | yellow | green | 10 | 0 | 12.0 | 15.0 | 490.0 | 164.0 | 12.0 | 41.0 | 3.0 | 3.0 | 681.0 | 517.0 | 477.0 | 40.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2024-08-19 | 2026-07-10 | 0 | 495d | 2025-10-28 | 2025-10-17 | not specified | 10 | not specified | not specified | 2 | 0 | 1 | 0 | 2 | 2 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | it | not specified | not specified | eu | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.574585635359116 | 1.0 | 12.0 | 0.0176211453744493 | 0.0220264317180617 | 0.719530102790015 | 0.240822320117474 | 0.00440528634361234 | 0.995594713656388 | 2026 | not specified | 3 | not specified | not specified | 1.0 | p | 183 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2024-08-19 | 2026-07-10 | not specified | not specified | [6 empty] | not specified | -1.0 | not specified | -69.0 | not specified | -543.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | new location | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.51
closure | p-0304 | not specified | ben bridgewater | richard bertram | project | 67931 | 67931: yule programme | not specified | not specified | not specified | not specified | not specified | not specified | not specified | adam painter | rachael horton - farmer | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.23 | 2024-10-04 | 2026-12-25 | 581d | m1 documentation: completed m2 inventory: june 26.​ m3 environmental management: sept 26.​ m4 asset disposition: linked to sale. oct 26.​ m5 site disposition: oct 26.​ m6 dilapidation: nov 26.​ m7 utility shutdown: aug – dec 27.​ m8 site secured: july 26.​ m9 site closure: dec 26.​ m10 site sold: may 26.​ | documentation / archiving project, 129 boxes of archiving removed from site. m1 milestone completed. hot press and progressive. continuation of discussions with france re progressive and hot press. cédric requested more info re progressive around tooling, tooling shaft size and pit cylinder poistons. reached out to liquidity services as they are interested in providing an offer for all excess equipment and machinery. introduction via louise. will pick this up in november. main office start date jan 5th. hub april 20th. formm office start up meeting (13.11.25) introductions sos planning. dim drawings this week. construction drawing for the cob on 4th november 2025. a. partitions setting out plan b. elevations of key areas – glazed partitions and feature walls c. door schedule (not including the showroom space) d. bespoke elements – 5no tea points (not including main canteen kitchen) and print point e. walls, floors, and ceiling finishes plans. f. coordination of all furniture, fabrics and finishes in line with formm furniture quote/schedule g. coded ff&e plan to match formm ff&e quote. 1 no revision to all information to capture any comments once issued for construction | continuation work: hot press and progressive. france visit 1st dec with dg. e&o. office fit out. sos date to be confirmed > visuals with lw. transition and timing plan to be worked in with rb gh rf. o/a office planning richard lisa & claire alongside lucy & sallyann. site moves / closure planning and ar = disposition planning nov - jan. ar control final list for rb. rb dn to create asset non transferable and sell off / remove form site list planning. site sale next meeting 9th december. to agree marketing timeline. | timing plan for office fit out tbc. jw site sale instruction. delap's conditioning.. | yellow | angle up | yellow | green | yellow | green | green | green | 3 | 0 | 0.0 | 0.0 | 30.0 | 8.0 | 0.0 | 2.0 | 0.0 | 0.0 | 38.0 | 30.0 | 3.0 | 27.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2024-09-01 | 2026-09-25 | 0 | 540d | 2025-10-21 | 2025-10-23 | not specified | 3 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | it | not specified | not specified | eu | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.480206540447504 | 8.0 | 6.0 | 0.0 | 0.0 | 0.789473684210526 | 0.210526315789474 | 0.0 | 1.0 | 2026 | not specified | 3 | not specified | not specified | 1.0 | p | 184 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2024-09-01 | 2026-09-25 | not specified | not specified | [6 empty] | not specified | -33.0 | not specified | -91.0 | not specified | -581.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | closure | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.23
product | p-0305 | not specified | ben bridgewater | lisa ward | project | 67931 | 67931: yule programme | not specified | not specified | not specified | not specified | not specified | not specified | not specified | adam painter | rachael horton - farmer | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.95 | 2024-10-14 | 2026-01-16 | 330d | rationalisation product deletions standardisation of product specs across customers construction standardisation across both manufacturing sites: cf160 construction, lock block size, glazed door construction/rationalisation, bi-fold rationalisation. packaging signage office fitout | rationalisation door slabs work continues. construction standardisation see upcoming packaging see upcoming signage see upcoming office fitout see upcoming | rationalisation work to be completed and presented for review next week. on track for end oct handover to it. construction standardisation fire test dates 10th nov. customer approval required on no filling of pin holes and packaging to be agreed with b&q. bi-fold presentation and agreement with b&q f2f meeting nov. packaging november - assessment of cost impacts of changes and customer acceptance. signage review positioning on hubb/m1 side of building. awaiting supplier prices. office fitout meeting to visualise everything! | not specified | green | sideways | yellow | green | yellow | green | green | green | 0 | 0 | 1.0 | 0.0 | 4.0 | 44.0 | 2.0 | 0.0 | 0.0 | 0.0 | 49.0 | 5.0 | 0.0 | 5.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2024-10-14 | 2025-12-05 | 0 | 300d | 2025-10-17 | 2025-10-17 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | it | not specified | not specified | eu | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.827272727272727 | 12.0 | 12.0 | 0.0204081632653061 | 0.0 | 0.0816326530612245 | 0.897959183673469 | 0.0 | 1.0 | 2026 | not specified | 3 | not specified | not specified | 1.0 | p | 185 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2024-10-14 | 2025-12-05 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | -42.0 | not specified | -330.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | product | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.95
operations | p-0450 | not specified | temi aderiye | amy doona | project | 67931 | 67931: yule programme | not specified | not specified | yule it | not specified | amy doona | not specified | not specified | adam painter | rachael horton - farmer | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.06 | 2025-07-01 | 2026-08-31 | 305d | wk42: - planning phase well under way, key deliverables and interdependencies have been populated in to the gannt and some agreement reached with key stakeholders - framework agreed for ehs framework transition - core disciplines agreed for manufacturing cadences | wk42: - quick wins prepared for it and will be shared today in reference to base slabs, howden and b&q. - after a period of handover chris is now dedicated to the operations workstream | wk42: - operations qbr next week will really elevate this workstream - further work on rationalisation required, chris working with ross on the glazed, raked heads, bi-folds, kit base slabs, cut downs, extra trimmable and pgp skins (door sets/non door sets) | wk42: | green | sideways | red | green | red | green | yellow | green | 1 | 0 | 0.0 | 7.0 | 29.0 | 0.0 | 0.0 | 2.0 | 6.0 | 5.0 | 36.0 | 36.0 | 28.0 | 8.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-09-30 | 2025-10-17 | not specified | 1 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | it | not specified | not specified | uk / france / export | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.285245901639344 | 29.0 | 12.0 | 0.0 | 0.194444444444444 | 0.805555555555556 | 0.0 | 0.166666666666667 | 0.833333333333333 | 2026 | not specified | 3 | not specified | not specified | 1.0 | p | 399 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | -181.0 | not specified | -431.0 | not specified | -305.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | transition | not specified |  | not specified | 2025-04-16 00:00:00 | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.06
warehouse management uk | p-0415 | warehouse management processes in the uk rely on manual activities and spreadsheets, leading to inefficiencies, errors, and operational bottlenecks. in scope : implement new business processes supported by a new warehouse management system penrith and new sheffield coe in scope functions affected; distribution, goods in, operations, planning, finance, supply chain and it supports digital manufacturing and supply chain it big rock | kaia simson | joe burrell | project | standalone project | standalone project | not specified | not specified | it it uk / france / export it-eu | not specified | kaia simson | not specified | not specified | adam painter | rachael horton - farmer | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.25 | 2025-02-24 | 2027-02-09 | 512d | w37: * status amber: the project is currently on hold. * path to green: understand the business case and review timeline. | w37: * n/a | w38: * review of process flow documentation & known areas of efficiency loss and business case for wms | not specified | yellow | sideways | yellow | green | green | green | green | green | 4 | 0 | 2.0 | 0.0 | 41.0 | 12.0 | 3.0 | 2.0 | 0.0 | 0.0 | 55.0 | 43.0 | 41.0 | 2.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-02-24 | 2027-02-09 | 0 | 512d | 2025-10-02 | 2025-09-17 | not specified | 4 | not specified | not specified | 0 | 0 | 3 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | on-hold | eur | it | not specified | not specified | uk / france / export | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.34765625 | 27.0 | 42.0 | 0.0363636363636364 | 0.0 | 0.745454545454546 | 0.218181818181818 | 0.0 | 1.0 | 2027 | not specified | 3 | not specified | not specified | not specified | p | 363 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-02-24 | 2027-02-09 | not specified | not specified | 2025-03-03 | 2025-11-06 | 2026-04-17 | 2027-01-04 | 2027-02-08 | 2027-02-08 | not specified | 0.0 | not specified | 0.0 | not specified | -512.0 | not specified | not specified | 2025-03-03 00:00:00 | 2025-11-06 00:00:00 | 2026-04-17 00:00:00 | 2027-01-04 00:00:00 | 2027-02-08 00:00:00 | 2027-02-08 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | warehouse management uk | not specified | 2025-09-17 | not specified | 2025-02-24 00:00:00 | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.25
electronic proof of delivery | p-0416 | uk strategy is to move into the housebuilder and commercial market, changing the distribution model to be lower volume but higher frequency.​ to support this model and provide our customer service teams with traceability of orders once left the factory, there is a requirement to track deliveries in real time​ | kaia simson | joe burrell | project | standalone project | standalone project | not specified | not specified | it it uk / france / export it-eu | not specified | kaia simson | not specified | not specified | adam painter | rachael horton - farmer | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.37 | 2025-02-24 | 2026-01-22 | 239d | w37: * status green- on track | w37 * n/a | w38: * understand business case, options, pricing | not specified | green | sideways | red | green | green | red | yellow | green | 2 | 0 | 6.0 | 1.0 | 27.0 | 18.0 | 10.0 | 10.0 | 35.0 | 35.0 | 52.0 | 34.0 | 32.0 | 2.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-02-24 | 2026-01-22 | 0 | 239d | 2025-10-10 | 2025-09-16 | not specified | 3 | not specified | not specified | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | it | not specified | not specified | uk / france / export | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.744769874476987 | 19.0 | 43.0 | 0.115384615384615 | 0.0192307692307692 | 0.519230769230769 | 0.346153846153846 | 0.673076923076923 | 0.326923076923077 | 2026 | not specified | 3 | not specified | not specified | not specified | p | 364 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-02-24 | 2026-01-22 | not specified | not specified | 2025-03-03 | 2025-04-14 | 2025-10-29 | 2025-10-23 | 2026-01-22 | 2026-01-22 | not specified | 0.0 | not specified | 0.0 | not specified | -239.0 | not specified | not specified | 2025-03-03 00:00:00 | 2025-04-14 00:00:00 | 2025-10-29 00:00:00 | 2025-10-23 00:00:00 | 2026-01-22 00:00:00 | 2026-01-22 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | electronic proof of delivery | not specified |  | not specified | 2025-02-24 00:00:00 | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.37
traceability - manual tracking | p-0308 | reduce overstock and shortages with real-time inventory accuracy tracking and management. impacted production, planning, customer service. | ben bridgewater | joe burrell | project | standalone project | standalone project | not specified | not specified | it it uk / france / export it-eu | not specified | kaia simson | andrew grafton | hamish white | adam painter | rachael horton - farmer | not specified | footprint | uk: manufacturing | not specified | l3 (planned) | on track | not specified | not specified | project dashboard | project finance dashboard | 0.19 | 2024-11-11 | 2025-10-07 | 237d | w30: * status amber- scope to improve inventory accuracy suggest moving to backflushing, which is highly transformational.program. full scope and timing with yule to be reviewed. * path to green/blue- to be agreed with business for the project to be cancelled and to be restarted in 2026 once yule implemented. | w30: n/a | w31: * path to green/blue- to be agreed with business for the project to be cancelled and to be restarted in 2026 once yule implemented. | not specified | yellow | sideways | red | red | green | yellow | yellow | green | 2 | 1 | 43.0 | 0.0 | 0.0 | 14.0 | 43.0 | 40.0 | 46.0 | 46.0 | 57.0 | 43.0 | 40.0 | 3.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2024-11-11 | 2025-10-07 | 0 | 237d | 2025-10-09 | 2025-07-22 | not specified | 4 | not specified | not specified | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | on-hold | eur | it | not specified | not specified | uk / france / export | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 1.0 | 20.0 | 99.0 | 0.754385964912281 | 0.0 | 0.0 | 0.245614035087719 | 0.807017543859649 | 0.192982456140351 | current year | not specified | 3 | not specified | not specified | not specified | p | 188 | 1.0 | not specified | not specified | not specified | andrew grafton | not specified | 2024-11-11 | 2025-10-07 | not specified | not specified | 2024-11-11 | 2025-02-24 | 2025-05-19 | 2025-07-29 | 2025-09-11 | 2025-10-07 | not specified | 0.0 | not specified | 0.0 | not specified | -237.0 | not specified | not specified | 2024-11-11 00:00:00 | 2025-03-17 00:00:00 | 2025-05-19 00:00:00 | 2025-07-29 00:00:00 | 2025-09-11 00:00:00 | 2025-10-07 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0 | -21d | 0 | 0 | 0 | 0.0 | -0.0886075949367089 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | titan - inventory accuracy - backflush - cycle count | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.19
uk synergy document management system, archive replacement | 69294 | ktlo and cost reduction/avoidance initiative in uk to replace legacy dms synergy dms and archive is a hosted solution servicing the uk only. the annual hosting costs are £53.7k. vendor for synergy has quoted us £30k to upgrade this instance to a newer hosted version costs are high compared to pan eu dms lasernet and dma autoform simplification & standardization of it estate uk titan documents in “dot matrix style” format, e.g invoices, order ack and credit/debit notes. opportunity to modernize via new dms | kaia simson | joe burrell | project | standalone project | standalone project | not specified | not specified | it it uk / france / export it-eu | not specified | kaia simson | not specified | adam painter | adam painter | rachael horton-farmer | not specified | other | support functions: global it - europe | it | l1 (identified) | on track | 69294.0 | not specified | project dashboard | project finance dashboard | 0.62 | 2025-01-01 | 2025-06-26 | 127d | w17: * status: cancelled | w17: * decision to cancel | w18: * project cancelled. | not specified | blue | sideways | red | red | green | red | green | green | 3 | 1 | 34.0 | 0.0 | 0.0 | 20.0 | 34.0 | 30.0 | 0.0 | 0.0 | 54.0 | 34.0 | 30.0 | 4.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-09-22 | 2025-05-12 | not specified | 4 | not specified | not specified | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | canceled | eur | it | not specified | not specified | uk / france / export | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not planned (l2 to l4) | not specified | 1.0 | on track | 1.0 | 37.0 | 170.0 | 0.62962962962963 | 0.0 | 0.0 | 0.37037037037037 | 0.0 | 1.0 | current year | n | 3 | not specified | not specified | not specified | p | 190 | 1.0 | 1.0 | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | 0.0 | not specified | -127.0 | not specified | not specified | 2025-01-01 00:00:00 | 2025-01-01 00:00:00 | 2025-03-24 00:00:00 | 2025-03-28 00:00:00 | 2025-03-28 00:00:00 | 2025-06-26 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | uk synergy document management system, archive replacement | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.62
cfin expansion | pg-0312 | not specified | meridith fix | meridith fix | program | pg-0312 | pg-0312: cfin expansion | not specified | not specified | it it-eu | not specified | meridith fix | not specified | not specified | mike crawford (r2r) | mj vaidya | not specified | sg&a | not specified | not specified | not specified | on track | not specified | not specified | program dashboard | finance dashboard | 0.836666666666667 | 2024-06-03 | 2026-06-05 | 525d | add the high level status of the program in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | on track | green | on track | green | red | green | yellow | 0 | 0 | 0.0 | 1.0 | 91.0 | 283.0 | 0.0 | 11.0 | 0.0 | 0.0 | 375.0 | 92.0 | 70.0 | 22.0 | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 |  | 2024-06-03 | 2026-06-05 | 0 | 525d | 2025-10-27 | 2025-10-29 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 1 | 1 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | usd | it | not specified | not specified | global | see project details | not specified | not specified | on track | on track | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | 1.0 | not specified | on track | 0.700952380952381 | 2.0 | 0.0 | 0.0 | 0.00266666666666667 | 0.242666666666667 | 0.754666666666667 | 0.0 | 1.0 | 2026 | not specified | 2 | not specified | not specified | not specified | not specified | 192 | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | [6 empty] | not specified | not specified | not specified | not specified | not specified | -525.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.83667
na cfin expansion | 37438 | part of the cfin expansion program, this project includes implementation of cfin across remaining north america entities. wave 1 of the program includes abs and vpi. wave 2 of the program includes remaining businesses in europe (see eu cfin expansion initiative 16061). wave 3 includes mmi and lacantina. | meridith fix | meridith fix | project | pg-0312 | pg-0312: cfin expansion | bus-na/corp/it | not specified | it na/corporate | not specified | meridith fix | not specified | stan johnson | mike crawford (r2r) | m.j. vaidya | not specified | sg&a | support functions: finance | it | l3 (planned) | on track | 37438.0 | not specified | project dashboard | finance dashboard | 0.86 | 2024-06-03 | 2026-05-29 | 520d | w1 - iterative dev/test cycles for credit exposure integration from cfin to turns continues. w3 - lacantina go live delayed again. | w1 - expedited solution for bill to requirement designed and development in progress. w3 - iterative dev/credit exposure and prepayments cycle continues. | w1 - load turns historical invoices to basware. continue turns development and testing for credit exposure. w3 - set up separate test database in syspro to prevent daily data refresh from replacing data manually keyed for testing. | not specified | yellow | angle up | yellow | green | green | green | green | green | 0 | 0 | 0.0 | 1.0 | 36.0 | 194.0 | 0.0 | 5.0 | 0.0 | 0.0 | 231.0 | 37.0 | 28.0 | 9.0 | 4975000.0 | 3509574.0 | 1465426.0 | 3471580.6 | 2683157.44 | 788423.16 | 850377.16 | 968699.0 | 516523.0 | 452176.0 | 321471.0 | 4440279.6 | 3199680.44 | 1240599.16 | 1171848.16 | 534720.4 | 309893.56 | 224826.84 | 0.107481487437186 | 0.0882994802218161 | 0.153420807328381 | 2025-10-27 | 2024-06-03 | 2026-05-29 | 0 | 520d | 2025-10-27 | 2025-10-27 | not specified | 4 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | it | not specified | not specified | not specified | implementation / execution | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 4.2 | not specified | 0.120862 | 2023-10-16 | 2026-01-07 | on plan | not specified | 1.0 | on track | 0.707692307692308 | 2.0 | 2.0 | 0.0 | 0.00432900432900433 | 0.155844155844156 | 0.83982683982684 | 0.0 | 1.0 | 2026 | n | 3 | not specified | not specified | 1.0 | p | 47 | not specified | 1.0 | 1.0 | not specified | not specified | not specified | 2024-02-02 | 2024-07-31 | not specified | not specified | [6 empty] | 129d | -122.0 | -0.945736434108527 | -667.0 | -5.17054263565892 | -391.0 | -3.03100775193798 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | stage 3 - implementation | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.86
eu cfin expansion | 16061 | part of the cfin expansion program, this project includes the implementation of cfin and basware in austria, germany, poland, hungary, czech republic and netherlands. | meridith fix | steve elsey | project | pg-0312 | pg-0312: cfin expansion | not specified | not specified | it it-eu | not specified | steve elsey | not specified | anne carter | mike crawford (r2r) | mj vaidya | not specified | sg&a | support functions: finance | not specified | l3 (planned) | on track | 16061.0 | not specified | project dashboard | project finance dashboard | 0.81 | 2024-09-09 | 2026-06-05 | 455d | w43 go/no-go meeting held, with authority to go. all final tests wrapped up. some still remain in basware but now in the blackout period for the code migration | final etl for the delta loads for october completed. basware migrate the test environment to prd. | sap end-users active from monday, replication from austria live from tuesday am. start running hypercare calls for austria. plan for remaining countries | not specified | green | angle up | red | green | green | red | green | green | 1 | 6 | 0.0 | 0.0 | 55.0 | 89.0 | 0.0 | 6.0 | 0.0 | 0.0 | 144.0 | 55.0 | 42.0 | 13.0 | 4380003.0 | 3058400.0 | 1321603.0 | 3011670.65 | 2245458.66 | 766211.99 | 765586.99 | 1903041.0 | 1098752.0 | 804289.0 | 734289.0 | 4914711.65 | 3344210.66 | 1570500.99 | 1499875.99 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2024-09-09 | 2026-06-05 | 0 | 455d | 2025-10-27 | 2025-10-24 | not specified | 14 | 1.0 | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 1 | 1 | 0.0 | not specified | 3723002.55 | 2599640.0 | 1123362.55 | 2559920.0525 | 1908639.861 | 651280.1915 | 650748.9415 | 1617584.85 | 933939.2 | 683645.65 | 624145.65 | 4177504.9025 | 2842579.061 | 1334925.8415 | 1274894.5915 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | usd | it | not specified | not specified | eu | not specified | not specified | cost reduction | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | 1.0 | 1.0 | on track | 0.654945054945055 | 2.0 | 5.0 | 0.0 | 0.0 | 0.381944444444444 | 0.618055555555556 | 0.0 | 1.0 | 2026 | n | 3 | not specified | not specified | not specified | p | 191 | 1.0 | 1.0 | not specified | not specified | not specified | not specified | 2024-09-09 | 2026-06-05 | not specified | not specified |  |  |  | 2025-09-04 |  |  | not specified | 0.0 | not specified | 0.0 | not specified | -455.0 | not specified | not specified | not specified | not specified | not specified | 2025-10-16 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | improved performance | 0.0 | one | not specified | eu cfin expansion | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.81
enabler: eu timekeeping - pro wfm | 39369 | upgrade existing kronos t&a solution (ukg workforce central - wfc) to ukg pro workforce management (pro wfm) due to end of life in december 2025. ukg have confirmed there will be no extension to this timeline and wfc licenses will not be available. 9 countries to migrate uk, fi, dk, se, ee, lv, no, ch and hu c. 4,200 employees. enabling c4,200 employees in 9 countries to continue to be paid for exception payments over and above standard working hours (i.e. overtime, sickness etc). | charlotte fox | charlotte fox | program | 39369 | 39369: enabler: eu timekeeping - pro wfm | it-eu | not specified | hr transformation it it-eu | not specified | olusola ogidi | not specified | sharon delooze | rachael horton-farmer | rachael horton-farmer | not specified | other | support functions: hr | hr; it | l3 (planned) | on track | 39369.0 | not specified | program dashboard | finance dashboard | 0.633201423785595 | 2024-03-01 | 2027-03-04 | 785d | w43 phase 1:amber as agreed to keep in amber to keep focus. 6/9 ch additional data uploaded into system, timecard alignment/analysis still ongoing though 100% matches which is positive. minor issues still being identified and work through with simms. uk/hu cutover is progressing with all people data uploaded to system ready for validations. phase 2: sow sign-off pending (rachael on holiday). sub-steerco meeting decision to go ahead with proposed timeline, pending budget approval, sow signature and historical data solution. | w43: phase 1: cutover call scheduled for hu/uk. meeting scheduled for uk on the clocks timeline alignment. aligned to seperate the wc manager training based on feedback from the training. phase 2: project timeline baselined in principle, pending important updates | w44: phase 1: uk and hu final cutover planning. data validation for hu and uk. comms to be sent to as reminder for hu/ uk. phase 2: test-case writing kick-off, recommendation/decision on ukg data hub (sow sign-off expected w45) | phase 1: impact:ch to not be able to fully test as intended. ptg: additional testing be carried out by technical lead to identify any additional issues, implement fix if possible. local team to be informed of new timelines once impact assessment has been completed by project team and simms. support required: : elt and clt to be kept informed, may require a further assessment and alignment of go live date if necessary. phase 2: impact: under assessment plan to green: evaluate timeline, perform prioritisation activities, review budget, document risks & mitigation support required: guidance input from senior business stakeholders and steerco committee | yellow | on track | yellow | on track | green | green | green | green | 24 | 28 | 54.0 | 48.0 | 553.0 | 1398.0 | 60.0 | 75.0 | 75.0 | 74.0 | 2049.0 | 651.0 | 573.0 | 78.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 |  | 2024-03-01 | 2027-03-04 | 0 | 785d | 2025-10-29 | 2025-10-29 | not specified | 249 | 1.0 | not specified | 1 | 0 | 0 | 0 | 11 | 2 | 0 | 0 | 10 | 2 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 18.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | it | not specified | not specified | eu | see project details | not specified | compliance | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 1.514742949 | 2024-12-07 | 2026-06-02 | on plan | not specified | 1.0 | on track | 0.552866242038217 | 0.0 | 0.0 | 0.0263543191800879 | 0.0234260614934114 | 0.269887750122011 | 0.682284040995608 | 0.0366032210834553 | 0.963396778916545 | 2027 | n | 2 | not specified | not specified | not specified | pg | 158 | not specified | 1.0 | 1.0 | not specified | not specified | not specified |  |  | not specified | not specified | [6 empty] | not specified | not specified | not specified | not specified | not specified | -785.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | improved performance | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.6332
sweden pro wfm upgrade | p-0159 | upgrade sweden’s existing kronos t&a solution (ukg workforce central - wfc) to ukg pro workforce management (pro wfm) due to end of life in december 2025. | charlotte fox | olusola ogidi | project | 39369 | 39369: enabler: eu timekeeping - pro wfm | bus-eu/it | not specified | hr transformation it it north eu it-eu | not specified | charlotte fox | not specified | sharon delooze | rachael horton - farmer | rachael horton - farmer | not specified | other | not specified | not specified | l3 (planned) | on track | not specified | not specified | project dashboard | project finance dashboard | 0.99 | 2024-10-11 | 2025-10-21 | 268d | w42: go live complete. 2nd go live complete but required manual interventions therefore hypercare can not be closed. | w42: go live complete. 2nd go live complete but required manual interventions therefore hypercare can not be closed | w43: integration fix is implemented but reqires some more testing. | support required: n/a impact: n/a plan to green: n/a | green | up | yellow | green | yellow | green | green | green | 0 | 0 | 0.0 | 0.0 | 1.0 | 100.0 | 1.0 | 0.0 | 0.0 | 0.0 | 101.0 | 1.0 | 0.0 | 1.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-28 | 2024-10-11 | 2025-10-14 | 0 | 263d | 2025-10-17 | 2025-10-22 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | it | not specified | not specified | north eu | realize value / close / care period | not specified | compliance | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 1.0 | 12.0 | 7.0 | 0.0 | 0.0 | 0.0099009900990099 | 0.99009900990099 | 0.0 | 1.0 | current year | not specified | 3 | not specified | not specified | not specified | p | 212 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2024-10-11 | 2025-10-14 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | -7.0 | not specified | -268.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | improved performance | 0.0 | one | not specified | sweden pro wfm upgrade | not specified |  | not specified | not specified | false | stage 5 - care period | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.99
finland pro wfm upgrade | p-0160 | upgrade finland’s existing kronos t&a solution (ukg workforce central - wfc) to ukg pro workforce management (pro wfm) due to end of life in december 2025. | charlotte fox | olusola ogidi | project | 39369 | 39369: enabler: eu timekeeping - pro wfm | bus-eu/it | not specified | hr transformation it it north eu it-eu | not specified | charlotte fox | not specified | sharon delooze | rachael horton - farmer | rachael horton - farmer | not specified | other | not specified | not specified | l3 (planned) | on track | not specified | not specified | project dashboard | project finance dashboard | 0.94 | 2024-11-15 | 2025-11-14 | 261d | w42: go live complete.. | w42: go live completed and monitoring hypercare.... | w43: monitor for issues for hypercare. prepare for 2nd payroll. | support required: n/a impact: n/a plan to green: n/a | green | up | green | green | green | green | green | green | 0 | 0 | 0.0 | 0.0 | 6.0 | 81.0 | 0.0 | 0.0 | 0.0 | 0.0 | 87.0 | 6.0 | 5.0 | 1.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2024-11-15 | 2025-11-14 | 0 | 261d | 2025-10-17 | 2025-10-22 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | it | not specified | not specified | north eu | realize value / close / care period | not specified | compliance | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.954022988505747 | 12.0 | 7.0 | 0.0 | 0.0 | 0.0689655172413793 | 0.931034482758621 | 0.0 | 1.0 | current year | not specified | 3 | not specified | not specified | not specified | p | 213 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2024-11-15 | 2025-11-14 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | 0.0 | not specified | -261.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | improved performance | 0.0 | one | not specified | finland pro wfm upgrade | not specified |  | not specified | not specified | false | stage 5 - care period | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.94
norway pro wfm upgrade | p-0161 | upgrade norway’s existing kronos t&a solution (ukg workforce central - wfc) to ukg pro workforce management (pro wfm) due to end of life in december 2025. | charlotte fox | olusola ogidi | project | 39369 | 39369: enabler: eu timekeeping - pro wfm | bus-eu/it | not specified | hr transformation it it north eu it-eu | not specified | charlotte fox | not specified | sharon delooze | rachael horton - farmer | rachael horton - farmer | not specified | other | not specified | not specified | l3 (planned) | on track | not specified | not specified | project dashboard | project finance dashboard | 0.92 | 2024-12-15 | 2025-12-04 | 254d | w42: go live complete.. | w42: go live completed and monitoring hypercare... | w43: monitor for issues for hypercare. prepare for 2nd payroll. | support required: n/a impact: n/a plan to green: n/a | green | up | green | green | green | green | green | green | 0 | 0 | 0.0 | 0.0 | 6.0 | 81.0 | 0.0 | 0.0 | 0.0 | 0.0 | 87.0 | 6.0 | 5.0 | 1.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2024-12-15 | 2025-12-04 | 0 | 254d | 2025-10-17 | 2025-10-22 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | it | not specified | not specified | north eu | realize value / close / care period | not specified | compliance | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.897637795275591 | 12.0 | 7.0 | 0.0 | 0.0 | 0.0689655172413793 | 0.931034482758621 | 0.0 | 1.0 | current year | not specified | 3 | not specified | not specified | not specified | p | 214 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2024-12-15 | 2025-12-04 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | 0.0 | not specified | -254.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | improved performance | 0.0 | one | not specified | norway pro wfm upgrade | not specified |  | not specified | not specified | false | stage 5 - care period | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.92
uk pro wfm upgrade | p-0162 | upgrade the uk’s existing kronos t&a solution (ukg workforce central - wfc) to ukg pro workforce management (pro wfm) due to end of life in december 2025. | charlotte fox | olusola ogidi | project | 39369 | 39369: enabler: eu timekeeping - pro wfm | bus-eu/it | not specified | hr transformation it it uk / france / export it-eu | not specified | charlotte fox | not specified | sharon delooze | rachael horton - farmer | rachael horton - farmer | not specified | other | not specified | not specified | l3 (planned) | on track | not specified | not specified | project dashboard | project finance dashboard | 0.83 | 2024-11-07 | 2026-01-01 | 301d | w43: additional data has been uploaded to pro wfm for validations. meeting to be scheduled with the local team for the clocks handover. | w43: additional data has been uploaded to pro wfm for validations. meeting to be scheduled with the local team for the clocks handover. | w44: update users guides as per feedback from local teams, start to draft reminder comms and prepare for cutover. validations of the data. plan for the hypercare. | support required: n/a impact: n/a ptg: n/a | green | sideways | green | green | green | green | green | green | 0 | 0 | 4.0 | 0.0 | 20.0 | 68.0 | 5.0 | 4.0 | 0.0 | 0.0 | 92.0 | 24.0 | 21.0 | 3.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2024-11-07 | 2026-01-01 | 0 | 301d | 2025-10-27 | 2025-10-27 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | it | not specified | not specified | uk / france / export | implementation / execution | not specified | compliance | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.847176079734219 | 2.0 | 2.0 | 0.0434782608695652 | 0.0 | 0.217391304347826 | 0.739130434782609 | 0.0 | 1.0 | 2026 | not specified | 3 | not specified | not specified | not specified | p | 215 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2024-11-07 | 2026-01-01 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | 0.0 | not specified | -301.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | improved performance | 0.0 | one | not specified | uk pro wfm upgrade | not specified |  | not specified | not specified | false | stage 3 - implementation | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.83
latvia pro wfm upgrade | p-0163 | upgrade latvia’s existing kronos t&a solution (ukg workforce central - wfc) to ukg pro workforce management (pro wfm) due to end of life in december 2025. | charlotte fox | olusola ogidi | project | 39369 | 39369: enabler: eu timekeeping - pro wfm | bus-eu/it | not specified | hr transformation it it north eu it-eu | not specified | charlotte fox | not specified | sharon delooze | rachael horton - farmer | rachael horton - farmer | not specified | other | not specified | not specified | l3 (planned) | on track | not specified | not specified | project dashboard | project finance dashboard | 0.92 | 2025-01-27 | 2025-12-19 | 235d | w42: go live complete and in hypercare. | w42: go live completed and monitoring hypercare... | w43: monitor for issues for hypercare. prepare for 2nd payroll. | support required: n/a impact: n/a plan to green: n/a | green | up | green | green | green | green | green | green | 0 | 0 | 0.0 | 0.0 | 6.0 | 81.0 | 0.0 | 0.0 | 0.0 | 0.0 | 87.0 | 6.0 | 5.0 | 1.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-27 | 2025-12-19 | 0 | 235d | 2025-10-17 | 2025-10-22 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | it | not specified | not specified | north eu | realize value / close / care period | not specified | compliance | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.842553191489362 | 12.0 | 7.0 | 0.0 | 0.0 | 0.0689655172413793 | 0.931034482758621 | 0.0 | 1.0 | current year | not specified | 3 | not specified | not specified | not specified | p | 216 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-01-27 | 2025-12-19 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | 0.0 | not specified | -235.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | improved performance | 0.0 | one | not specified | latvia pro wfm upgrade | not specified |  | not specified | not specified | false | stage 5 - care period | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.92
estonia pro wfm upgrade | p-0164 | upgrade estonia’s existing kronos t&a solution (ukg workforce central - wfc) to ukg pro workforce management (pro wfm) due to end of life in december 2025. | charlotte fox | olusola ogidi | project | 39369 | 39369: enabler: eu timekeeping - pro wfm | bus-eu/it | not specified | hr transformation it it north eu it-eu | not specified | charlotte fox | not specified | sharon delooze | rachael horton - farmer | rachael horton - farmer | not specified | other | not specified | not specified | l3 (planned) | on track | not specified | not specified | project dashboard | project finance dashboard | 0.89 | 2025-01-20 | 2025-12-04 | 229d | w42: hypercare in progress | w42: hypercare in progress | w43: hypercare bridge call in motion | support required: regional gm approval to maintain go-live. impact: n/a ptg:n/a | green | sideways | green | green | green | green | green | green | 0 | 0 | 0.0 | 0.0 | 10.0 | 77.0 | 0.0 | 0.0 | 0.0 | 0.0 | 87.0 | 10.0 | 9.0 | 1.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-20 | 2025-12-04 | 0 | 229d | 2025-10-17 | 2025-10-22 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | it | not specified | not specified | north eu | realize value / close / care period | not specified | compliance | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.88646288209607 | 12.0 | 7.0 | 0.0 | 0.0 | 0.114942528735632 | 0.885057471264368 | 0.0 | 1.0 | current year | not specified | 3 | not specified | not specified | not specified | p | 217 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-01-20 | 2025-12-04 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | 0.0 | not specified | -229.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | improved performance | 0.0 | one | not specified | estonia pro wfm upgrade | not specified |  | not specified | not specified | false | stage 5 - care period | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.89
denmark pro wfm upgrade | p-0165 | upgrade denmark’s existing kronos t&a solution (ukg workforce central - wfc) to ukg pro workforce management (pro wfm) due to end of life in december 2025. | charlotte fox | olusola ogidi | project | 39369 | 39369: enabler: eu timekeeping - pro wfm | bus-eu/it | not specified | hr transformation it it north eu it-eu | not specified | charlotte fox | not specified | sharon delooze | rachael horton - farmer | rachael horton - farmer | not specified | other | not specified | not specified | l3 (planned) | on track | not specified | not specified | project dashboard | project finance dashboard | 0.98 | 2024-12-08 | 2025-11-10 | 241d | w42: go live complete and hypercare.. | w42: go live completed and monitoring hypercare. | w43: monitor for issues for hypercare. prepare for 2nd payroll. | support required: n/a impact: n/a plan to green: n/a | green | up | green | green | green | green | green | green | 0 | 0 | 0.0 | 0.0 | 3.0 | 108.0 | 1.0 | 0.0 | 0.0 | 0.0 | 111.0 | 3.0 | 2.0 | 1.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2024-12-08 | 2025-11-10 | 0 | 241d | 2025-10-17 | 2025-10-22 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | it | not specified | not specified | north eu | realize value / close / care period | not specified | compliance | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.966804979253112 | 12.0 | 7.0 | 0.0 | 0.0 | 0.027027027027027 | 0.972972972972973 | 0.0 | 1.0 | current year | not specified | 3 | not specified | not specified | not specified | p | 218 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2024-12-08 | 2025-11-10 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | 0.0 | not specified | -241.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | improved performance | 0.0 | one | not specified | denmark pro wfm upgrade | not specified |  | not specified | not specified | false | stage 5 - care period | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.98
hungary pro wfm upgrade | p-0166 | upgrade hungary’s existing kronos t&a solution (ukg workforce central - wfc) to ukg pro workforce management (pro wfm) due to end of life in december 2025. | charlotte fox | olusola ogidi | project | 39369 | 39369: enabler: eu timekeeping - pro wfm | bus-eu/it | not specified | hr transformation it it central eu it-eu | not specified | charlotte fox | not specified | sharon delooze | rachael horton - farmer | rachael horton - farmer | not specified | other | not specified | not specified | l3 (planned) | on track | not specified | not specified | project dashboard | project finance dashboard | 0.75 | 2025-01-20 | 2026-01-05 | 251d | w43: additional data has been uploaded to pro wfm for validations. meeting to be scheduled with the local team for the clocks handover. | w43: additional data has been uploaded to pro wfm for validations. meeting to be scheduled with the local team for the clocks handover. | w44: update users guides as per feedback from local teams, start to draft reminder comms and prepare for cutover. validations of the data. plan for the hypercare. | support required: n/a impact: n/a ptg: n/a | green | sideways | yellow | green | yellow | green | green | green | 0 | 0 | 0.0 | 0.0 | 19.0 | 69.0 | 3.0 | 1.0 | 0.0 | 0.0 | 88.0 | 19.0 | 17.0 | 2.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-20 | 2025-12-11 | 0 | 234d | 2025-10-17 | 2025-10-27 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | it | not specified | not specified | central eu | implementation / execution | not specified | compliance | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.808764940239044 | 12.0 | 2.0 | 0.0 | 0.0 | 0.215909090909091 | 0.784090909090909 | 0.0 | 1.0 | 2026 | not specified | 3 | not specified | not specified | not specified | p | 219 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-01-20 | 2025-12-11 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | -25.0 | not specified | -251.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | improved performance | 0.0 | one | not specified | hungary pro wfm upgrade | not specified |  | not specified | not specified | false | stage 3 - implementation | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.75
switzerland pro wfm upgrade | p-0167 | upgrade switzerland’s existing kronos t&a solution (ukg workforce central - wfc) to ukg pro workforce management (pro wfm) due to end of life in december 2025. | charlotte fox | olusola ogidi | project | 39369 | 39369: enabler: eu timekeeping - pro wfm | bus-eu/it | not specified | hr transformation it it central eu it-eu | not specified | charlotte fox | not specified | sharon delooze | rachael horton - farmer | rachael horton - farmer | not specified | other | not specified | not specified | l3 (planned) | on track | not specified | not specified | project dashboard | project finance dashboard | 0.62 | 2025-01-06 | 2026-01-28 | 278d | w38: go-live at risk. unable to achieve uat sign-off to proceed with cutover prep. uat in progress however full state of technical issues not fully understood as not all issues are recorded in the uat tool open project. presented soft go-live option to steerco. | w38: go-live at risk. unable to achieve uat sign-off to proceed with cutover prep. uat in progress however full state of technical issues not fully understood as not all issues are recorded in the uat tool open project. presented soft go-live option to steerco. | w39: provide assurance to regional gm of the action plan on technical issues to enable a soft go-live on original go live date. gain approval. commence work on the soft go-live technical solution. ensure all issues are in open project. re-plan the project. | impact: downgrade to soft go-live and reverse uat ptg: proposal shared with steerco on the 15th september, key members unable to attend. obtain full steerco sign off w/c 17/09 on high level plan and prepare detailed plan. support required: full steerco sign-off | yellow | sideways | red | green | red | green | green | green | 0 | 0 | 0.0 | 0.0 | 32.0 | 61.0 | 0.0 | 2.0 | 0.0 | 0.0 | 93.0 | 32.0 | 28.0 | 4.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-06 | 2025-12-04 | 0 | 239d | 2025-10-22 | 2025-10-27 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | it | not specified | not specified | central eu | not specified | not specified | compliance | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.766187050359712 | 7.0 | 2.0 | 0.0 | 0.0 | 0.344086021505376 | 0.655913978494624 | 0.0 | 1.0 | 2026 | not specified | 3 | not specified | not specified | not specified | p | 220 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-01-06 | 2025-12-04 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | -55.0 | not specified | -278.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | improved performance | 0.0 | one | not specified | switzerland pro wfm upgrade | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.62
eu european blueprint & integrations project | p-0207 | design a standard pro wfm solution for europe which aligns to canada (live since 2021) and north america (going live in h2 2024) which can be deployed across all locations as part of the programme. | charlotte fox | olusola ogidi | project | 39369 | 39369: enabler: eu timekeeping - pro wfm | not specified | not specified | hr transformation it it-eu | not specified | charlotte fox | not specified | sharon delooze | rachael horton - farmer | rachael horton - farmer | not specified | other | not specified | not specified | l3 (planned) | on track | not specified | not specified | project dashboard | project finance dashboard | 0.79 | 2024-03-01 | 2026-02-10 | 508d | w40: phase 1: amber as agreed to keep profiled. amber also because of close monitoring required for ch and hu. estonia go live successfully completed. 6/9 go live completed. | w40: phase 1: aligned with hu and ch on the plan for go live. go live date is dependent on successfully complete the uat. plan for ch now extends to f26 due to hyper care. full end to end plan documented and aligned with project team and simms. additional data for hu updated in to system earlier than planned. | w41: no,fi and lv to start to prepare for payroll. ch additional data to uploaded into system. hu to finalise uat. initiate pre cutover phase for both hu and uk. | phase 1: impact: delay of up to 4 weeks for ch and hu. this is has been assessed by the project team and s&a also need alignment with clt particularly for ch. plan to green: assess the impacts of the delay to overall project plan and delivery by simms support required: n/a | yellow | sideways | yellow | green | green | green | yellow | green | 0 | 0 | 35.0 | 41.0 | 53.0 | 314.0 | 35.0 | 36.0 | 74.0 | 73.0 | 440.0 | 126.0 | 95.0 | 31.0 | 1620045.92941176 | 1161254.47058823 | 458791.458823528 | 1268661.31764705 | 1031997.0 | 236664.317647058 | 0.0 | 192036.023529411 | 120514.035294117 | 71521.9882352939 | 0.0 | 1460697.34117647 | 1152511.03529411 | 308186.305882352 | 0.0 | 159348.588235294 | 8743.43529411766 | 150605.152941176 | 0.0983605374035004 | 0.00752930172978253 | 0.328264944877942 | 2025-10-27 | 2024-03-01 | 2026-02-10 | 0 | 508d | 2025-10-29 | 2025-10-09 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 1377039.04 | 987066.3 | 389972.74 | 1078362.12 | 877197.45 | 201164.67 | 0.0 | 163230.62 | 102436.93 | 60793.69 | 0.0 | 1241592.74 | 979634.38 | 261958.36 | 0.0 | 135446.3 | 7431.92000000004 | 128014.38 | 0.0983605374035002 | 0.00752930172978253 | 0.328264944877942 | not specified | active | eur | it | not specified | not specified | eu | implementation / execution | not specified | compliance | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.854330708661417 | 0.0 | 20.0 | 0.0795454545454546 | 0.0931818181818182 | 0.120454545454545 | 0.713636363636364 | 0.168181818181818 | 0.831818181818182 | 2026 | not specified | 3 | not specified | not specified | not specified | p | 221 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2024-03-01 | 2026-02-10 | not specified | not specified | 2024-03-28 | 2024-05-01 | 2024-07-04 | 2025-05-05 | 2026-01-12 | 2026-02-10 | not specified | 0.0 | not specified | 0.0 | not specified | -508.0 | not specified | not specified | 2024-03-28 00:00:00 | 2024-05-01 00:00:00 | 2024-07-04 00:00:00 | 2025-07-25 00:00:00 | 2026-01-12 00:00:00 | 2026-02-10 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | improved performance | 0.0 | one | not specified | eu european blueprint & integrations project | not specified |  | not specified | not specified | false | stage 3 - implementation | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.79
phase 2 eu blueprint alignment & integrations | p-0256 | eu timekeeping standardisation - plan to cerf and l3 submission | charlotte fox | charlotte fox | project | 39369 | 39369: enabler: eu timekeeping - pro wfm | not specified | not specified | it it-eu | not specified | charlotte fox | not specified | sharon delooze | adam painter | rachael horton - farmer | not specified | other | support functions: hr | not specified | l1 (identified) | on track | not specified | not specified | project dashboard | project finance dashboard | 0.47 | 2024-07-29 | 2027-03-04 | 679d | w42: sow not signed off yet. meeting with hrbps to evaluate the current country go-live sequence proposal, decision to keep current go-live sequence. review of standard report format suggestion instead of customised report. | w42: badge evaluation being performed by ukg. | w43: sow sign-off pending. follow up sub-steerco with decision for the proposed timeline to be baselined. | support required: guidance input from senior business stakeholders and steerco committee impact: under assessment plan to green: evaluate timeline, perform prioritisation activities, review budget, document risks & mitigation | yellow | sideways | yellow | green | green | green | green | yellow | 0 | 0 | 14.0 | 7.0 | 328.0 | 98.0 | 14.0 | 31.0 | 0.0 | 0.0 | 447.0 | 349.0 | 317.0 | 32.0 | 2197202.30588235 | 132655.364705882 | 2064546.94117646 | 762653.913701468 | 125282.188235294 | 637371.725466174 | 0.0 | 1443018.97647058 | 7373.17647058821 | 1435645.8 | 0.0 | 2205672.89017205 | 132655.364705882 | 2073017.52546617 | 0.0 | -8470.58428970601 | 0.0 | -8470.58428970601 | -0.00385516812313029 | 0.0 | -0.00410287803138016 | 2025-10-27 | 2024-07-29 | 2027-03-04 | 0 | 679d | 2025-10-29 | 2025-10-27 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 1867621.96 | 112757.06 | 1754864.9 | 648255.82664625 | 106489.86 | 541765.96664625 | 0.0 | 1226566.13 | 6267.2 | 1220298.93 | 0.0 | 1874821.95664625 | 112757.06 | 1762064.89664625 | 0.0 | -7199.99664625013 | 0.0 | -7199.99664625013 | -0.0038551681231303 | 0.0 | -0.00410287803138015 | not specified | active | eur | it | not specified | not specified | eu | development | not specified | compliance | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.483063328424153 | 0.0 | 2.0 | 0.0313199105145414 | 0.0156599552572707 | 0.733780760626398 | 0.21923937360179 | 0.0 | 1.0 | 2027 | not specified | 3 | not specified | not specified | not specified | p | 233 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2024-07-29 | 2027-03-04 | not specified | not specified | 2024-08-23 | 2025-02-02 | 2025-02-02 | 2025-12-31 | 2027-02-04 | 2027-03-04 | not specified | 0.0 | not specified | 0.0 | not specified | -679.0 | not specified | not specified | 2024-08-23 00:00:00 | 2025-02-02 00:00:00 | 2025-02-02 00:00:00 | 2026-06-16 00:00:00 | 2027-02-04 00:00:00 | 2027-03-04 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | fixing the dilutive business | 0.0 | one | not specified | plan to l3 | not specified |  | not specified | not specified | false | stage 2 - development | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.47
germany pro wfm upgrade | p-0409 | not specified | olusola ogidi | sabine uhlemann | project | 39369 | 39369: enabler: eu timekeeping - pro wfm | not specified | not specified | it it central eu it-eu | not specified | olusola ogidi | not specified | not specified | rachael horton - farmer | rachael horton - farmer | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.93 | 2025-03-03 | 2025-10-31 | 175d | w42: sow not signed off yet. meeting with hrbps to evaluate the current country go-live sequence proposal, decision to keep current go-live sequence. review of standard report format suggestion instead of customised report. | w42: badge evaluation being performed by ukg. | w43: sow sign-off pending. follow up sub-steerco with decision for the proposed timeline to be baselined. | support required: guidance input from senior business stakeholders and steerco committee impact: under assessment plan to green: evaluate timeline, perform prioritisation activities, review budget, document risks & mitigation | yellow | sideways | yellow | green | green | green | yellow | green | 0 | 0 | 1.0 | 0.0 | 1.0 | 130.0 | 1.0 | 1.0 | 1.0 | 1.0 | 131.0 | 1.0 | 1.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-03-03 | 2026-04-06 | 0 | 286d | 2025-10-17 | 2025-10-27 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | it | not specified | not specified | central eu | not specified | not specified | compliance | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.988571428571429 | 12.0 | 2.0 | 0.00763358778625954 | 0.0 | 0.00763358778625954 | 0.992366412213741 | 0.00763358778625954 | 0.992366412213741 | current year | not specified | 3 | not specified | not specified | 1.0 | p | 357 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-03-03 | 2026-04-06 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | 157.0 | not specified | -175.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | fixing the dilutive business | 0.0 | one | not specified | germany pro wfm upgrade | not specified |  | not specified | 2025-02-21 00:00:00 | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.93
austria pro wfm upgrade | p-0410 | not specified | olusola ogidi | sabine uhlemann | project | 39369 | 39369: enabler: eu timekeeping - pro wfm | not specified | not specified | it it central eu it-eu | not specified | olusola ogidi | not specified | not specified | rachael horton - farmer | rachael horton - farmer | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 1.0 | 2025-03-03 | 2025-08-29 | 130d | w42: sow not signed off yet. meeting with hrbps to evaluate the current country go-live sequence proposal, decision to keep current go-live sequence. review of standard report format suggestion instead of customised report. | w42: badge evaluation being performed by ukg. | w43: sow sign-off pending. follow up sub-steerco with decision for the proposed timeline to be baselined. | support required: guidance input from senior business stakeholders and steerco committee impact: under assessment plan to green: evaluate timeline, perform prioritisation activities, review budget, document risks & mitigation | yellow | sideways | yellow | blue | green | green | green | green | 0 | 0 | 0.0 | 0.0 | 0.0 | 130.0 | 0.0 | 0.0 | 0.0 | 0.0 | 130.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-03-03 | 2026-03-05 | 0 | 264d | 2025-10-15 | 2025-10-27 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | it | not specified | not specified | central eu | not specified | not specified | compliance | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 1.0 | 14.0 | 2.0 | 0.0 | 0.0 | 0.0 | 1.0 | 0.0 | 1.0 | current year | not specified | 3 | not specified | not specified | 1.0 | p | 358 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-03-03 | 2026-03-05 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | 188.0 | not specified | -130.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | fixing the dilutive business | 0.0 | one | not specified | austria pro wfm upgrade | not specified |  | not specified | 2025-02-21 00:00:00 | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 1
france pro wfm upgrade | p-0411 | not specified | olusola ogidi | olusola ogidi | project | 39369 | 39369: enabler: eu timekeeping - pro wfm | not specified | not specified | it it uk / france / export it-eu | not specified | olusola ogidi | not specified | not specified | rachael horton - farmer | rachael horton - farmer | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.0 | 2026-01-11 | 2026-11-23 | 226d | project commences jan 2026 | not specified | not specified | not specified | green | sideways | green | green | green | green | green | green | 0 | 0 | 0.0 | 0.0 | 17.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 17.0 | 17.0 | 17.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2026-01-11 | 2026-11-23 | 0 | 226d | 2025-03-03 | 2025-03-17 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | it | not specified | not specified | central eu | not specified | not specified | compliance | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.0 | 240.0 | 226.0 | 0.0 | 0.0 | 1.0 | 0.0 | 0.0 | 1.0 | 2026 | not specified | 3 | not specified | not specified | 1.0 | p | 359 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2026-01-11 | 2026-11-23 | not specified | not specified |  |  |  | 2026-10-14 |  |  | not specified | 0.0 | not specified | 0.0 | not specified | -226.0 | not specified | not specified | not specified | not specified | not specified | 2026-10-14 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | fixing the dilutive business | 0.0 | one | not specified | france pro wfm upgrade | not specified |  | not specified | 2025-02-21 00:00:00 | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0
netherlands pro wfm upgrade | p-0412 | not specified | olusola ogidi | olusola ogidi | project | 39369 | 39369: enabler: eu timekeeping - pro wfm | not specified | not specified | it it uk / france / export it-eu | not specified | olusola ogidi | not specified | not specified | rachael horton - farmer | rachael horton - farmer | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.0 | 2026-01-11 | 2026-11-23 | 226d | project commences jan 2026 | not specified | not specified | not specified | green | sideways | green | green | green | green | green | green | 0 | 0 | 0.0 | 0.0 | 17.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 17.0 | 17.0 | 17.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2026-01-11 | 2026-11-23 | 0 | 226d | 2025-03-03 | 2025-03-17 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | it | not specified | not specified | uk / france / export | not specified | not specified | compliance | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.0 | 240.0 | 226.0 | 0.0 | 0.0 | 1.0 | 0.0 | 0.0 | 1.0 | 2026 | not specified | 3 | not specified | not specified | 1.0 | p | 360 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2026-01-11 | 2026-11-23 | not specified | not specified |  |  |  | 2026-10-14 |  |  | not specified | 0.0 | not specified | 0.0 | not specified | -226.0 | not specified | not specified | not specified | not specified | not specified | 2026-10-14 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | fixing the dilutive business | 0.0 | one | not specified | netherlands pro wfm upgrade | not specified |  | not specified | 2025-02-21 00:00:00 | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0
czechia pro wfm upgrade | p-0413 | not specified | olusola ogidi | olusola ogidi | project | 39369 | 39369: enabler: eu timekeeping - pro wfm | not specified | not specified | it it uk / france / export it-eu | not specified | olusola ogidi | not specified | not specified | rachael horton - farmer | rachael horton - farmer | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.0 | 2026-01-11 | 2027-01-05 | 257d | project commences jan 2026 | not specified | not specified | not specified | green | sideways | green | green | green | green | green | green | 0 | 0 | 0.0 | 0.0 | 17.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 17.0 | 17.0 | 17.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2026-01-11 | 2027-01-05 | 0 | 257d | 2025-07-14 | 2025-03-17 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | it | not specified | not specified | uk / france / export | not specified | not specified | compliance | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.0 | 107.0 | 226.0 | 0.0 | 0.0 | 1.0 | 0.0 | 0.0 | 1.0 | 2027 | not specified | 3 | not specified | not specified | 1.0 | p | 361 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2026-01-11 | 2027-01-05 | not specified | not specified |  |  |  | 2026-10-30 |  |  | not specified | 0.0 | not specified | 0.0 | not specified | -257.0 | not specified | not specified | not specified | not specified | not specified | 2026-10-30 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | fixing the dilutive business | 0.0 | one | not specified | czechia pro wfm upgrade | not specified |  | not specified | 2025-02-21 00:00:00 | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0
poland pro wfm upgrade | p-0414 | not specified | olusola ogidi | olusola ogidi | project | 39369 | 39369: enabler: eu timekeeping - pro wfm | not specified | not specified | it it uk / france / export it-eu | not specified | olusola ogidi | not specified | not specified | rachael horton - farmer | rachael horton - farmer | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.0 | 2026-01-11 | 2027-01-05 | 257d | project commences jan 2026 | not specified | not specified | not specified | green | sideways | green | green | green | green | green | green | 0 | 0 | 0.0 | 0.0 | 17.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 17.0 | 17.0 | 17.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2026-01-11 | 2027-01-05 | 0 | 257d | 2025-07-14 | 2025-03-17 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | it | not specified | not specified | uk / france / export | not specified | not specified | compliance | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.0 | 107.0 | 226.0 | 0.0 | 0.0 | 1.0 | 0.0 | 0.0 | 1.0 | 2027 | not specified | 3 | not specified | not specified | 1.0 | p | 362 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2026-01-11 | 2027-01-05 | not specified | not specified |  |  |  | 2026-10-30 |  |  | not specified | 0.0 | not specified | 0.0 | not specified | -257.0 | not specified | not specified | not specified | not specified | not specified | 2026-10-30 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | fixing the dilutive business | 0.0 | one | not specified | poland pro wfm upgrade | not specified |  | not specified | 2025-02-21 00:00:00 | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0
finland pricing structure | p-0314 | initiative to leverage titan functionalities to implement structural pricing in finland | amer basic | amer basic | project | standalone project | standalone project | not specified | not specified | it it north eu it-eu | not specified | amer basic | not specified | not specified | peter sørensen | rachael horton - farmer | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.0 | 2025-01-01 | 2025-06-26 | 127d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | sideways | red | red | green | green | yellow | green | 0 | 0 | 22.0 | 53.0 | 0.0 | 0.0 | 22.0 | 22.0 | 75.0 | 50.0 | 75.0 | 75.0 | 75.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-10-14 | 2025-10-15 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | on-hold | eur | it | not specified | not specified | eu | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 1.0 | 15.0 | 14.0 | 0.293333333333333 | 0.706666666666667 | 0.0 | 0.0 | 1.0 | 0.0 | current year | not specified | 3 | not specified | not specified | not specified | p | 222 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | 0.0 | not specified | -127.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | finland pricing structure | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0
edi process improvements | pg-0315 | not specified | amer basic | joe burrell | program | pg-0315 | pg-0315: edi process improvements | not specified | not specified | it it-eu | not specified | amer basic | not specified | not specified | peter sørensen | rachael horton - farmer | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | program dashboard | finance dashboard | 0.761356673960613 | 2024-01-23 | 2025-06-26 | 373d | add the high level status of the program in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | on track | yellow | on track | green | green | yellow | green | 0 | 0 | 5.0 | 84.0 | 2.0 | 76.0 | 6.0 | 6.0 | 122.0 | 106.0 | 167.0 | 91.0 | 79.0 | 12.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 |  | 2024-01-23 | 2025-06-26 | 0 | 373d | 2025-10-15 | 2025-10-29 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | it | not specified | not specified | eu | see project details | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 1.0 | 14.0 | 0.0 | 0.029940119760479 | 0.502994011976048 | 0.0119760479041916 | 0.455089820359281 | 0.730538922155689 | 0.269461077844311 | current year | not specified | 2 | not specified | not specified | not specified | pg | 315 | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | [6 empty] | not specified | not specified | not specified | not specified | not specified | -373.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.76136
edi process improvements - france | 48852 | improvement of our edi process in france to drive efficiencies and savings | amer basic | joe burrell | project | pg-0315 | pg-0315: edi process improvements | not specified | not specified | it it uk / france / export it-eu | not specified | amer basic | not specified | not specified | adam painter | rachael horton - farmer | not specified | not specified | not specified | not specified | not specified | on track | 48852.0 | not specified | project dashboard | project finance dashboard | 0.99 | 2024-09-02 | 2025-06-26 | 214d | w34 status green: on track | w34 : hypercare. issue with manual edi date change due to holiday. ticket raised waiting approval to change the code from us. plan reviewed. | w35 :issue with manual edi date change due to holiday on going action plan updated with tasks. | none at this point | green | sideways | yellow | yellow | green | green | yellow | green | 0 | 0 | 3.0 | 15.0 | 2.0 | 63.0 | 4.0 | 5.0 | 53.0 | 53.0 | 83.0 | 20.0 | 20.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-10-15 | 2025-08-26 | not specified | 1 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | it | not specified | not specified | eu | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | 1.0 | 1.0 | on track | 1.0 | 14.0 | 64.0 | 0.036144578313253 | 0.180722891566265 | 0.0240963855421687 | 0.759036144578313 | 0.63855421686747 | 0.36144578313253 | current year | n | 3 | not specified | not specified | not specified | p | 148 | 1.0 | 1.0 | not specified | not specified | not specified | not specified | 2025-10-29 | 2026-01-27 | not specified | not specified | 2025-02-19 | 2025-02-19 | 2025-02-19 | 2025-06-05 |  |  | not specified | 422.0 | not specified | 215.0 | not specified | -214.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | edi process improvements - france | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.99
edi process improvements - finland | 48850 | improvement of our edi process in finland to drive efficiencies and savings | amer basic | joe burrell | project | pg-0315 | pg-0315: edi process improvements | not specified | not specified | it it-eu | not specified | amer basic | not specified | not specified | peter sørensen | rachael horton - farmer | not specified | not specified | not specified | not specified | not specified | on track | 48850.0 | not specified | project dashboard | project finance dashboard | 0.56 | 2024-01-23 | 2024-12-26 | 243d | project on-hold | not specified | review in q1 2025 if to re-start this project | none at this point. | green | sideways | yellow | yellow | yellow | green | yellow | green | 0 | 0 | 2.0 | 69.0 | 0.0 | 13.0 | 2.0 | 1.0 | 69.0 | 53.0 | 84.0 | 71.0 | 59.0 | 12.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2024-01-23 | 2024-11-27 | 0 | 222d | 2025-10-15 | 2024-12-09 | not specified | 13 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | on-hold | eur | it | not specified | not specified | eu | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | 1.0 | 1.0 | on track | 1.0 | 14.0 | 324.0 | 0.0238095238095238 | 0.821428571428571 | 0.0 | 0.154761904761905 | 0.821428571428571 | 0.178571428571429 | previous year | n | 3 | not specified | not specified | not specified | p | 223 | 1.0 | 1.0 | not specified | not specified | not specified | not specified | 2024-01-23 | 2024-11-27 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | -29.0 | not specified | -243.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | edi process improvements - finland | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.56
project dee | 65828 | implementation of new mes system in rakvere to support mto volume ramp-up, and it exit from dobele. | amer basic | amer basic | program | 65828 | 65828: project dee | it-eu | not specified | it it-eu | not specified | amer basic | not specified | olli nevanlinna | peter sørensen | rachael horton - farmer | not specified | footprint | nordics: footprint | not specified | l3 (planned) | on track | 65828.0 | not specified | program dashboard | finance dashboard | 0.711578947368421 | 2023-08-01 | 2025-08-08 | 529d | see workstream updates | not specified | not specified | not specified | blue | on track | yellow | on track | red | red | yellow | green | 0 | 0 | 0.0 | 113.0 | 34.0 | 124.0 | 40.0 | 40.0 | 113.0 | 112.0 | 271.0 | 147.0 | 97.0 | 50.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 |  | 2023-08-01 | 2025-01-07 | 0 | 376d | 2025-02-17 | 2025-10-29 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | completed | not specified | it | not specified | not specified | eu | see project details | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | 1.0 | 1.0 | on track | 1.0 | 254.0 | 0.0 | 0.0 | 0.416974169741697 | 0.125461254612546 | 0.457564575645757 | 0.416974169741697 | 0.583025830258303 | current year | n | 2 | not specified | not specified | not specified | pg | 202 | not specified | 1.0 | not specified | not specified | not specified | not specified |  |  | not specified | not specified | [6 empty] | not specified | not specified | not specified | not specified | not specified | -529.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.71158
mes rakvere | p-0203 | implementation of new mes system in rakvere to support mto volume-ramp up and replace existing legacy tools including homemade mes | amer basic | amer basic | project | 65828 | 65828: project dee | not specified | not specified | it it north eu it-eu | not specified | amer basic | not specified | olli nevanlinna | peter sørensen | rachael horton - farmer | not specified | footprint | nordics: footprint | not specified | l3 (planned) | on track | not specified | not specified | project dashboard | project finance dashboard | 0.59 | 2023-08-01 | 2025-08-08 | 529d | it project on-hold: mes development is completed, pending tasks are business testing in production and updating the master data. w04 agreed to move it project on-hold until the business completed the uat and master data (machine resources, input materials, production routes, etc). | not specified | none this week (it project is on-hold) | impact: as the business has not completed necessary production testing and updating the master data we don´t know when we can go live. ptg: the business is expected to complete pending tasks by february and reach out to it pm when we have achieved system acceptance prior go live. | yellow | sideways | red | yellow | red | red | yellow | green | 4 | 0 | 0.0 | 62.0 | 34.0 | 72.0 | 40.0 | 40.0 | 62.0 | 61.0 | 168.0 | 96.0 | 46.0 | 50.0 | 378325.411764705 | 378325.411764705 | 0.0 | 355457.176470587 | 355457.176470587 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 355457.176470587 | 355457.176470587 | 0.0 | 0.0 | 22868.2352941176 | 22868.2352941176 | 0.0 | 0.0604459404073555 | 0.0604459404073555 | 0 | 2025-10-27 | 2023-08-01 | 2024-11-05 | 0 | 331d | 2025-01-24 | 2025-01-27 | not specified | 7 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 321576.6 | 321576.6 | 0.0 | 302138.6 | 302138.6 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 302138.6 | 302138.6 | 0.0 | 0.0 | 19438.0 | 19438.0 | 0.0 | 0.0604459404073555 | 0.0604459404073555 | 0.0 | not specified | on-hold | eur | it | not specified | not specified | north eu | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | 1.0 | not specified | on track | 1.0 | 278.0 | 275.0 | 0.0 | 0.369047619047619 | 0.202380952380952 | 0.428571428571429 | 0.369047619047619 | 0.630952380952381 | current year | not specified | 3 | not specified | not specified | not specified | p | 224 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2023-08-01 | 2024-11-05 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | -276.0 | not specified | -529.0 | not specified | not specified | not specified | not specified | not specified | 2025-02-03 00:00:00 | 2025-04-01 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | mes rakvere | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.59
it exit dobele | p-0204 | support exit from dobele by relocation it infrastructure and it equipment, and remove any existing it services | amer basic | amer basic | project | 65828 | 65828: project dee | not specified | not specified | it it north eu it-eu | not specified | amer basic | not specified | olli nevanlinna | peter sørensen | rachael horton - farmer | not specified | footprint | nordics: footprint | not specified | l3 (planned) | on track | not specified | not specified | project dashboard | project finance dashboard | 0.99 | 2024-01-01 | 2024-11-18 | 231d | w06: project is complete, need to finalize the closure documents and close in l4-l5 gate | w06: none this week | w07: finalize project closure documentation. confirm that titan entity is deactivated. | none at this point | blue | sideways | red | green | red | green | yellow | green | 0 | 0 | 0.0 | 51.0 | 0.0 | 52.0 | 0.0 | 0.0 | 51.0 | 51.0 | 103.0 | 51.0 | 51.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2024-01-01 | 2025-01-07 | 0 | 267d | 2025-02-17 | 2025-02-17 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | completed | eur | it | not specified | not specified | north eu | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | 1.0 | not specified | on track | 1.0 | 254.0 | 254.0 | 0.0 | 0.495145631067961 | 0.0 | 0.504854368932039 | 0.495145631067961 | 0.504854368932039 | previous year | not specified | 3 | not specified | not specified | not specified | p | 225 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2024-01-01 | 2025-01-07 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | 50.0 | not specified | -231.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | it exit dobele | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.99
hp doorsets with cable transfer in ri- and rv steelframes | 37314 | not specified | mateus hermann | kira svane kristensen | project | standalone project | standalone project | not specified | kira svane kristensen | r&d europe r&d europe north | not specified | not specified | kira svane kristensen | brian schweitz | not specified | not specified | not specified | npi / npd | nordics: commercial - denmark | engineering | l5 (realised) | on track | 37314.0 | not specified | project dashboard | project finance dashboard | 1.0 | 2024-03-27 | 2024-09-26 | 132d | project gate 4 completed | not specified | not specified | not specified | green | on track | yellow | blue | yellow | green | green | green | 0 | 0 | 0.0 | 0.0 | 0.0 | 26.0 | 0.0 | 0.0 | 0.0 | 0.0 | 26.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2024-06-06 | 2024-11-28 | 0 | 126d | 2025-04-02 | 2025-04-02 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | r&d | technical | sustaining | north eu | realize value / close / care period | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0.0 | not specified | 0.022 | 2023-10-13 | 2024-02-12 | on plan | not specified | 1.0 | on track | 1.0 | 210.0 | 210.0 | 0.0 | 0.0 | 0.0 | 1.0 | 0.0 | 1.0 | previous year | n | 3 | not specified | not specified | 1.0 | p | 226 | 1.0 | 1.0 | 1.0 | not specified | not specified | not specified | 2024-06-06 | 2024-11-28 | not specified | not specified | [6 empty] | not specified | 71.0 | not specified | 63.0 | not specified | -132.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | stage 5 - care period | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 1
stacking of partitions | 62875 | currently, our approvals do not permit stacking partitions on top of a door or another partition without a load-bearing wall construction between the products. the aim of this project is to update our approvals to include this configuration as an approved solution for future sales. the scope of this project involves testing glass partitions stacked on top of each other, as well as those placed adjacent to doors. the solutions will undergo testing in accordance with the en standard. some modifications to the construction will be needed to enhance performance. these improvements will later on be implemented in production. | kira svane kristensen | kira svane kristensen | project | standalone project | standalone project | not specified | kira svane kristensen | r&d europe r&d europe north | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | 62875.0 | not specified | project dashboard | project finance dashboard | 0.23 | 2024-06-06 | 2027-12-15 | 920d | week 40 plan for development until design freeze with r&d. design freeze meeting booked in november. | dicussions with dbi about top light sizes. with change sizes to 600mm instead of 900mm for easier development. | r&d to continue development to finalise clips solution for 12 november. design freeze booked in november. | no support needed. | yellow | sideways | red | green | yellow | red | yellow | green | 4 | 1 | 0.0 | 0.0 | 91.0 | 43.0 | 1.0 | 3.0 | 16.0 | 16.0 | 134.0 | 91.0 | 90.0 | 1.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2024-06-06 | 2027-09-30 | 0 | 866d | 2025-10-09 | 2025-10-03 | not specified | 5 | not specified | not specified | 0 | 1 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | r&d | technical | npd | north eu | development | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not planned (l2 to l4) | not specified | 1.0 | on track | 0.396739130434783 | 20.0 | 26.0 | 0.0 | 0.0 | 0.67910447761194 | 0.32089552238806 | 0.119402985074627 | 0.880597014925373 | 2027 | n | 3 | not specified | not specified | not specified | p | 227 | 1.0 | 1.0 | not specified | not specified | not specified | not specified | 2024-06-06 | 2027-09-30 | not specified | not specified | 2024-09-12 | 2025-09-12 | 2027-09-30 |  | 2027-09-30 |  | not specified | 0.0 | not specified | -76.0 | not specified | -920.0 | not specified | not specified | 2024-09-12 00:00:00 | 2025-11-27 00:00:00 | 2027-12-15 00:00:00 | not specified | 2027-12-15 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0 | -76d | -76d | -76d | dates not set | 0.0 | -0.0826086956521739 | -0.0826086956521739 | -0.0826086956521739 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | stage 2 - development | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.23
pmo000600 - swedoor steel storage door | 4748 | sourcing of storage steel door with fire classifications ei2 30 & ei2 60 from 3rd part supplier (saku metal or t-tammer). replacement of discontinued 4250 steel door produced by domoferm the goal is to relaunch a cost efficient steel door to be used in commercial projects for storage-, back- and side doors etc. | kira svane kristensen | kira svane kristensen | project | standalone project | standalone project | not specified | kira svane kristensen | r&d europe r&d europe north | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | 4748.0 | not specified | project dashboard | project finance dashboard | 0.96 | 2024-11-14 | 2025-05-09 | 127d | week 21 stc meeting held and decision was to cancel project due to lack of customer commitment. | cancel project due to lack of customer commitment, | - | - | yellow | down | yellow | yellow | green | green | yellow | green | 0 | 0 | 0.0 | 57.0 | 0.0 | 14.0 | 0.0 | 0.0 | 70.0 | 70.0 | 71.0 | 57.0 | 49.0 | 8.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-07-16 | 2025-05-21 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | canceled | eur | r&d | steel | npd | north eu | initiation / validation / feasibility | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0.22473 | not specified | 0.02904 | 2023-09-11 | 2025-01-07 | on plan | not specified | 1.0 | on track | 1.0 | 105.0 | 161.0 | 0.0 | 0.802816901408451 | 0.0 | 0.197183098591549 | 0.985915492957747 | 0.0140845070422529 | current year | n | 3 | not specified | not specified | not specified | p | 228 | 1.0 | 1.0 | 1.0 | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | 48.0 | not specified | 48.0 | not specified | -127.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | stage 1 - feasibility | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.96
wall covering frames mittweida | p-0150 | not specified | mateus hermann | andras fejes | project | standalone project | standalone project | not specified | andrás fejes | r&d europe r&d europe central | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.52 | 2024-09-09 | 2026-03-16 | 396d | sourcing still doing negotiations, progress very slow. jw (gábor takács) visitied deventer personally, but no final agreements yet. | jw personal visit at deventer | agreement with deventer on terms and conditions of dev. part to be able to start tooling. | alignment with deventer on the ciritcal points of our contractual documents on a higher level. | red | down | red | green | green | green | yellow | green | 1 | 1 | 7.0 | 2.0 | 58.0 | 43.0 | 8.0 | 19.0 | 1.0 | 1.0 | 110.0 | 67.0 | 62.0 | 5.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2024-01-01 | 2026-06-10 | 0 | 638d | 2025-10-22 | 2025-10-22 | true | 2 | not specified | not specified | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | r&d | interior | npd | central eu | initiation / validation / feasibility | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.752525252525253 | 7.0 | 7.0 | 0.0636363636363636 | 0.0181818181818182 | 0.527272727272727 | 0.390909090909091 | 0.00909090909090909 | 0.990909090909091 | 2026 | not specified | 3 | not specified | not specified | 1.0 | p | 231 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2024-01-01 | 2026-06-10 | not specified | not specified | 2024-01-01 |  | 2024-10-17 |  | 2024-12-19 | 2024-12-19 | not specified | -252.0 | not specified | 86.0 | not specified | -396.0 | not specified | not specified | 2025-11-13 00:00:00 | not specified | 2025-12-11 00:00:00 | not specified | 2026-02-16 00:00:00 | 2026-02-16 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | -682d | dates not set | -420d | -424d | -424d | -1.72222222222222 | 0.0 | -1.06060606060606 | -1.07070707070707 | -1.07070707070707 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | stage 1 - feasibility | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.52
re-launch fd30/fd60 range 3 | p-0151 | not specified | mateus hermann | scott mcbride | project | standalone project | standalone project | not specified | scott mcbride | r&d europe r&d europe uk r&d europe uk / france | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.29 | 2023-02-24 | 2026-06-11 | 860d | - fd60 hw lipping updated foa received from kiwa to allow implementation - request from r&d to use range 3 project to test and implement assa abloy el560 lock that lost its certification through the kiwa request for new evidence - external test completed for unlatched double fd60 sa - passed 61 minutes - fd30 da external test failed 18th feb | - fd60 hw lipping updated foa received from kiwa to allow implementation - in-person meeting in sdrf to complete handover of hw lipping from r&d to ops - external test completed for unlatched double fd60 sa - passed 61 minutes | - fd60 hw lipping internal implementation actions - receive report for unlatched double fd60 sa - agree plan for fd30 da test evidence submission or re-test | - ifc/kiwa/dbi situation is creating backlog of actions required to complete and delaying launch of products (unlatched fd60 sa) - decision/support needed to confirm costing methodology - how to handle intercompany sales because that the erp (xal) is not 100% updated - support needed on updates in erp system due to absences - who will implement? | yellow | sideways | red | yellow | red | red | yellow | green | 7 | 2 | 2.0 | 72.0 | 117.0 | 108.0 | 17.0 | 84.0 | 155.0 | 149.0 | 299.0 | 191.0 | 110.0 | 81.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2024-06-06 | 2024-11-15 | 0 | 117d | 2025-10-17 | 2025-04-09 | not specified | 12 | not specified | not specified | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | completed | eur | r&d | technical | npd | uk / france | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.812790697674419 | 12.0 | 203.0 | 0.00668896321070234 | 0.240802675585284 | 0.391304347826087 | 0.361204013377926 | 0.518394648829431 | 0.481605351170569 | 2026 | not specified | 3 | not specified | not specified | 1.0 | p | 232 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2024-06-06 | 2024-11-15 | not specified | not specified | [6 empty] | not specified | 468.0 | not specified | -573.0 | not specified | -860.0 | not specified | not specified | not specified | 2025-10-10 00:00:00 | 2026-02-18 00:00:00 | not specified | 2026-02-16 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.29
materials mgmt: plan for every part initiative | 15836 | not specified | ryan russel | ryan russel | project | standalone project | standalone project | bus-na/corp/it | jorge eleta | it mfg. & supply chain na it na/corporate | not specified | ryan russel | not specified | josh bui | christian suarez | kirk kroft | not specified | supply chain | na - ops: supply chain | it | l3 (planned) | on hold | 15836.0 | not specified | project dashboard | finance dashboard | 0.46 | 2023-12-18 | 2025-03-31 | 336d | during socialization it has been determined that this project will be cancelled and handled as a titan enhancement request and be limited to adding the new schema. | not specified | pending final approval from josh to cancel the project. | not specified | green | on track | red | green | red | red | yellow | red | 0 | 2 | 3.0 | 0.0 | 30.0 | 47.0 | 9.0 | 29.0 | 19.0 | 19.0 | 80.0 | 33.0 | 7.0 | 26.0 | 729500.0 | 376000.0 | 353500.0 | 15219.0 | 3960.5 | 11258.5 | not specified | 85867.2 | 59914.8 | 25952.4 | not specified | 101086.2 | 63875.3 | 37210.9 | not specified | 628413.8 | 312124.7 | 316289.1 | 0.86143084304318 | 0.830118882978723 | 0.894735785007072 | 2024-09-30 | 2023-12-18 | 2025-06-27 | 400d | 1.7283456e12d | 2024-10-08 | 2024-11-01 | not specified | 2 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | canceled | not specified | it | not specified | not specified | not specified | planning | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | -0.54 | 4.0 | 0.529771 | 2023-10-19 | 2025-04-01 | on plan | not specified | not specified | on track | 1.0 | 386.0 | 362.0 | 0.0375 | 0.0 | 0.375 | 0.5875 | 0.2375 | 0.7625 | current year | not specified | 3 | not specified | not specified | 1.0 | p | 3 | not specified | 1.0 | 1.0 | not specified | not specified | not specified | 2024-02-02 | 2024-07-31 | not specified | not specified | [6 empty] | 129d | 46.0 | 0.356589147286822 | -243.0 | -1.88372093023256 | -207.0 | -1.6046511627907 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified | 2024-11-11 | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.46
as/400 operating system going out of support | 33336 | upgrade of os for as/400 test and prod environments in sweden and germany from version 7.1 to 7.5 | karolin koch | karolin koch | project | standalone project | standalone project | it-eu | not specified | it it central eu it-eu | not specified | karolin koch | not specified | markus ellinger | markus ellinger | rachael horton-farmer | not specified | sg&a | support functions: global it - europe | it | submitted for l4 approval | on track | 33336.0 | not specified | project dashboard | project finance dashboard | 1.0 | 2023-09-12 | 2025-09-26 | 534d | on track | not specified | not specified | not specified | on track | on track | yellow | blue | yellow | green | green | green | 0 | 0 | 0.0 | 0.0 | 0.0 | 34.0 | 0.0 | 0.0 | 0.0 | 0.0 | 34.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 16611.7647058823 | 0.0 | 16611.7647058823 | 0.0 | 3764.70588235293 | 0.0 | 3764.70588235293 | 0.0 | 20376.4705882352 | 0.0 | 20376.4705882352 | 0.0 | -20376.4705882352 | 0.0 | -20376.4705882352 | 0.0 | 0.0 | 0 | 2025-10-27 | 2023-09-12 | 2025-08-25 | 0 | 510d | 2025-09-16 |  | #invalid value | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 14120.0 | 0.0 | 14120.0 | 0.0 | 3200.0 | 0.0 | 3200.0 | 0.0 | 17320.0 | 0.0 | 17320.0 | 0.0 | -17320.0 | 0.0 | -17320.0 | 0.0 | 0.0 | 0.0 | not specified | on track | eur | it | not specified | not specified | central eu | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 2023-12-10 | 2024-10-13 | on plan | not specified | 1.0 | on track | 1.0 | 43.0 | on track | 0.0 | 0.0 | 0.0 | 1.0 | 0.0 | 1.0 | current year | n | 3 | not specified | not specified | not specified | p | 234 | 1.0 | 1.0 | 1.0 | not specified | not specified | not specified | 2023-09-12 | 2025-08-25 | not specified | not specified |  |  |  | 2025-06-13 | 2025-08-25 |  | not specified | 0.0 | not specified | -32.0 | not specified | -534.0 | not specified | not specified | not specified | not specified | not specified | 2025-06-13 00:00:00 | 2025-09-13 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | -19d | dates not set | 0.0 | 0.0 | 0.0 | -0.0355805243445693 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | as/400 operating system going out of support | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 1
lacantina webcrm to salesforce migration | 50697 | lacantina currently uses a tool called webcrm for tracking service tickets related to warrantee and chargeable work for customers. webcrm support of the application and the it systems that run it are not well documented and we have lost the resource recently who had that knowledge. we have encountered an unplanned outage that exposed the risk this poses to the business and the possibility to impact our customers. | ryan russel | ryan russel | project | standalone project | standalone project | not specified | not specified | not specified | not specified | ryan russel | not specified | not specified | not specified | kirk kroft | not specified | not specified | not specified | not specified | not specified | cancelled | 50697.0 | not specified | project dashboard | project finance dashboard | 0.0 | 2025-01-01 | 2025-06-26 | 127d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | sideways | red | green | green | red | yellow | green | 1 | 0 | 0.0 | 53.0 | 22.0 | 0.0 | 22.0 | 22.0 | 75.0 | 50.0 | 75.0 | 75.0 | 75.0 | 0.0 | 0.0 | not specified | not specified | 1602.0 | 0.0 | 1602.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 1602.0 | 0.0 | 1602.0 | 0.0 | -1602.0 | 0.0 | -1602.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2024-11-13 | 2025-05-28 | not specified | 6 | not specified | not specified | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 1361.7 | 0.0 | 1361.7 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 1361.7 | 0.0 | 1361.7 | 0.0 | -1361.7 | 0.0 | -1361.7 | 0.0 | 0.0 | 0.0 | not specified | canceled | usd | it | not specified | not specified | not specified | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not planned (l2 to l4) | not specified | 1.0 | on track | 1.0 | 350.0 | 154.0 | 0.0 | 0.706666666666667 | 0.293333333333333 | 0.0 | 1.0 | 0.0 | current year | n | 3 | not specified | not specified | not specified | p | 235 | 1.0 | 1.0 | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | 0.0 | not specified | -127.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | lacantina webcrm to salesforce migration | not specified | 2025-05-28 | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0
oettingen: kl2 machine setup automation | 39393 | not specified | karolin koch | karolin koch | project | standalone project | standalone project | bus-eu/it | not specified | it it central eu it-eu | not specified | karolin koch | not specified | not specified | markus ellinger | rachael horton - farmer | not specified | manufacturing | not specified | it | l3 (planned) | cancelled | 39393.0 | not specified | project dashboard | project finance dashboard | 0.0 | 2025-01-01 | 2025-06-26 | 127d | w37: project on hold, hand over to bau | not specified | not specified | not specified | red | sideways | red | red | green | green | yellow | green | 0 | 0 | 6.0 | 54.0 | 15.0 | 0.0 | 22.0 | 22.0 | 75.0 | 75.0 | 75.0 | 75.0 | 75.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-02-21 | 2024-11-18 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | on-hold | eur | it | not specified | not specified | central eu | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 2023-11-10 | 2025-06-27 | on plan | not specified | 1.0 | on track | 1.0 | 250.0 | 345.0 | 0.08 | 0.72 | 0.2 | 0.0 | 1.0 | 0.0 | current year | n | 3 | not specified | not specified | 1.0 | p | 236 | 1.0 | 1.0 | 1.0 | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | 0.0 | not specified | -127.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | oettingen: kl2 machine setup automation | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0
legacy windows server os risk - europe | 39395 | risk mitigation project to consolidate, upgrade and decommission legacy servers across 20 different hosting locations in europe | ben hamnett | ben hamnett | project | standalone project | standalone project | not specified | not specified | it it-eu | not specified | ben hamnett | not specified | jens schjott | rachael horton-farmer | rachael horton-farmer | not specified | sg&a | support functions: global it - europe | it | l3 (planned) | on hold | 39395.0 | not specified | project dashboard | project finance dashboard | 0.29 | 2022-12-19 | 2025-09-03 | 708d | project on hold | not specified | not specified | not specified | red | sideways | red | red | red | yellow | yellow | green | 3 | 0 | 6.0 | 0.0 | 7.0 | 17.0 | 13.0 | 10.0 | 30.0 | 30.0 | 30.0 | 13.0 | 10.0 | 3.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2024-11-25 | 2024-11-18 | not specified | 6 | not specified | not specified | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | on-hold | eur | it | not specified | not specified | eu | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0.0 | not specified | 0.08976 | 2023-10-13 | 2025-01-05 | on plan | not specified | 1.0 | on track | 1.0 | 338.0 | 345.0 | 0.2 | 0.0 | 0.233333333333333 | 0.566666666666667 | 1.0 | 0.0 | current year | n | 3 | not specified | not specified | not specified | p | 237 | 1.0 | 1.0 | 1.0 | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | 744.0 | not specified | -69.0 | not specified | -708.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | legacy windows server os risk - europe | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.29
end customer configurator | 12404 | creation of online configurator for dana products (b2b) | karolin koch | karolin koch | project | standalone project | standalone project | bus-eu/it | not specified | it it central eu it-eu | not specified | karolin koch | not specified | christoph eibl | markus ellinger | rachael horton-farmer | not specified | growth | dach: commercial - austria | it | l3 (planned) | on track | 12404.0 | not specified | project dashboard | project finance dashboard | 0.28 | 2023-09-12 | 2026-04-20 | 680d | w41: project lagging behind schedule for implementation due to delayed cerf approval | w41: - cerf approval ongoing, improvements supplied - project plan updated with supplier through times & amended for new timeline (resource availability) | w42: - pm on leave next steps: re-baseline. | impact: n/a p2g: n'a | green | sideways | red | red | red | green | green | green | 0 | 1 | 0.0 | 0.0 | 42.0 | 17.0 | 2.0 | 1.0 | 0.0 | 0.0 | 59.0 | 42.0 | 37.0 | 5.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2023-09-12 | 2025-02-28 | 0 | 384d | 2025-10-23 | 2025-10-09 | not specified | 10 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | it | not specified | not specified | central eu | planning | not specified | increase revenue | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0.3025 | not specified | 0.33 | 2023-12-10 | 2025-02-28 | on plan | not specified | 1.0 | on track | 0.819117647058824 | 6.0 | 20.0 | 0.0 | 0.0 | 0.711864406779661 | 0.288135593220339 | 0.0 | 1.0 | 2026 | n | 3 | not specified | not specified | not specified | p | 238 | 1.0 | 1.0 | 1.0 | not specified | not specified | not specified | 2023-09-12 | 2025-02-28 | not specified | not specified |  |  | 2025-06-06 | 2026-04-10 | 2026-05-20 | 2027-01-22 | not specified | 0.0 | not specified | -416.0 | not specified | -680.0 | not specified | not specified | not specified | not specified | 2025-08-07 00:00:00 | 2026-11-23 00:00:00 | 2027-01-04 00:00:00 | 2027-06-15 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | -62d | -229d | -144d | 0.0 | 0.0 | -0.0911764705882353 | -0.336764705882353 | -0.211764705882353 | not specified | not specified | not specified | not specified | focussed growth | 0.0 | one | not specified | end customer configurator | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.28
erp pps/l upgrade, spital | 39284 | migration of legacy erp from physical, local server into the virtual cluster austria upgrade of os from hpux to linux and programming language to open cobol | karolin koch | karolin koch | project | standalone project | standalone project | it-eu | not specified | it it central eu it-eu | not specified | karolin koch | not specified | michael tasch | markus ellinger | rachael horton-farmer | not specified | sg&a | support functions: global it - europe | it | l3 (planned) | some issues | 39284.0 | not specified | project dashboard | project finance dashboard | 0.54 | 2023-04-12 | 2026-07-16 | 852d | on track | not specified | not specified | not specified | on track | on track | red | green | red | green | yellow | green | 0 | 0 | 5.0 | 0.0 | 16.0 | 12.0 | 5.0 | 4.0 | 13.0 | 13.0 | 33.0 | 21.0 | 17.0 | 4.0 | 45997.6470588234 | 0.0 | 45997.6470588234 | 27803.8705882352 | 0.0 | 27803.8705882352 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 27803.8705882352 | 0.0 | 27803.8705882352 | 0.0 | 18193.7764705882 | 0.0 | 18193.7764705882 | 0.39553711187273 | 0.0 | 0.39553711187273 | 2025-10-27 | 2023-04-12 | 2025-12-26 | 0 | 708d | 2025-09-30 |  | #invalid value | 16 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 39098.0 | not specified | 39098.0 | 23633.29 | 0.0 | 23633.29 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 23633.29 | 0.0 | 23633.29 | 0.0 | 15464.71 | 0.0 | 15464.71 | 0.39553711187273 | 0.0 | 0.39553711187273 | not specified | on track | eur | it | not specified | not specified | central eu | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | -0.0008855 | not specified | 0.042108 | 2023-11-10 | 2024-11-19 | on plan | not specified | 1.0 | on track | 0.78169014084507 | 29.0 | on track | 0.151515151515152 | 0.0 | 0.484848484848485 | 0.363636363636364 | 0.393939393939394 | 0.606060606060606 | 2026 | n | 3 | not specified | not specified | not specified | p | 239 | 1.0 | 1.0 | 1.0 | not specified | not specified | not specified | 2023-04-12 | 2025-12-26 | not specified | not specified |  |  |  | 2023-05-12 | 2025-04-17 |  | not specified | 0.0 | not specified | -202.0 | not specified | -852.0 | not specified | not specified | not specified | not specified | not specified | 2023-05-12 00:00:00 | 2026-07-16 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | -455d | dates not set | 0.0 | 0.0 | 0.0 | -0.534037558685446 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | erp pps/l upgrade, spital | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.54
tollgate governance and process 2.0 | p-0232 | internal project for pmo europe to make a project plan for tollgate improvements, training sessions, templates etc. (this is not a wave project but i would like to govern these tasks in smartsheets projectplan to track the trainings, updates of processes. | boel sandberg | boel sandberg | project | standalone project | standalone project | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.0 | 2025-01-01 | 2025-06-26 | 127d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | sideways | yellow | green | green | yellow | green | green | 2 | 0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d |  | 2024-11-14 | not specified | 2 | not specified | not specified | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | other | multiple | npd | north eu | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 1.0 | not specified | 349.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 1.0 | current year | not specified | 3 | not specified | not specified | not specified | p | 240 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | 0.0 | not specified | -127.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0
pmo000096 harm chipboard frames | 11805 | pmo000096 harmonization of german and austria chipboard frames manufactured in mittweida | not specified | philipp nothdurft | project | standalone project | standalone project | not specified | philipp nothdurft | r&d europe r&d europe central | not specified | not specified | not specified | philipp nothdurft | not specified | not specified | not specified | manufacturing | dach: manufacturing - germany | engineering | l3 (planned) | on track | 11805.0 | not specified | project dashboard | project finance dashboard | 0.99 | 2024-11-12 | 2026-01-16 | 309d | g4 completed | - | - | - | green | sideways | red | green | red | green | green | green | 0 | 0 | 0.0 | 0.0 | 4.0 | 26.0 | 0.0 | 0.0 | 0.0 | 0.0 | 30.0 | 4.0 | 4.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2024-11-12 | 2025-04-30 | 0 | 122d | 2025-10-22 | 2025-04-23 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | r&d | technical | npd | central eu | realize value / close / care period | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | 1.0 | on track | 0.815533980582524 | 7.0 | 189.0 | 0.0 | 0.0 | 0.133333333333333 | 0.866666666666667 | 0.0 | 1.0 | 2026 | not specified | 3 | not specified | not specified | 1.0 | p | 241 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2024-11-12 | 2025-04-30 | not specified | not specified |  |  | 2025-04-10 |  | 2025-04-30 | 2025-04-30 | not specified | 0.0 | not specified | -261.0 | not specified | -309.0 | not specified | not specified | not specified | not specified | 2025-04-10 00:00:00 | not specified | 2025-04-30 00:00:00 | 2026-01-16 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | 0 | 0 | -261d | 0.0 | 0.0 | 0.0 | 0.0 | -0.844660194174757 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | stage 5 - care period | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.99
pmo000477 full impl typ65 ger&ch | 12285 | pmo000477 full implementation typ65 in 2025- ger and ch | not specified | philipp nothdurft | project | standalone project | standalone project | not specified | philipp nothdurft | r&d europe r&d europe central | not specified | not specified | not specified | philipp nothdurft | not specified | not specified | not specified | sg&a | dach: commercial - germany | engineering | l3 (planned) | on track | 12285.0 | not specified | project dashboard | project finance dashboard | 0.38 | 2024-07-01 | 2026-02-20 | 430d | implementation is taking place. all documents are spread within the company | all documents available | impementation of documents in it-systems g3 meeting | - | green | sideways | red | red | red | green | green | green | 0 | 0 | 20.0 | 0.0 | 5.0 | 0.0 | 20.0 | 16.0 | 0.0 | 0.0 | 25.0 | 25.0 | 21.0 | 4.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-10-28 | 2025-07-15 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | r&d | technical | npd | central eu | implementation / execution | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | 1.0 | on track | 0.809302325581395 | 1.0 | 106.0 | 0.8 | 0.0 | 0.2 | 0.0 | 0.0 | 1.0 | 2026 | not specified | 3 | not specified | not specified | 1.0 | p | 242 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | 184.0 | not specified | -239.0 | not specified | -430.0 | not specified | not specified | not specified | not specified | 2025-07-23 00:00:00 | not specified | 2025-10-01 00:00:00 | 2026-02-20 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | stage 3 - implementation | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.38
qlikview to tableau migration | 33339 | migration of qlikview dashboards and reports to cloud-based tableau platform | ben hamnett | ben hamnett | project | standalone project | standalone project | not specified | not specified | it it-eu | not specified | ben hamnett | ieva juknaite | graham whetton | graham whetton | rachael horton-farmer | not specified | sg&a | support functions: global it - europe | it | l3 (planned) | some issues | 33339.0 | not specified | project dashboard | project finance dashboard | 0.71 | 2024-01-29 | 2025-11-03 | 461d | w43: 92% dashboards live (22/24) 96% old dashbaords decommissioned. de sales explorer calls progressing | w43: produktion calc dashboard live. 3/6 de_sales calls complete and 2 users happy to sign off. arranged calls for remainder before work begins | w44: further meetings with remaining explorer license holders to establish requirements/progress | not specified | yellow | sideways | red | green | red | green | green | red | 1 | 0 | 0.0 | 0.0 | 7.0 | 89.0 | 3.0 | 3.0 | 0.0 | 0.0 | 96.0 | 7.0 | 3.0 | 4.0 | 411764.705882352 | 411764.705882352 | 0.0 | 171614.117647058 | 171614.117647058 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 171614.117647058 | 171614.117647058 | 0.0 | 0.0 | 240150.588235293 | 240150.588235293 | 0.0 | 0.583222857142856 | 0.583222857142856 | 0 | 2025-10-27 | 2024-01-29 | 2025-03-07 | 0 | 290d | 2025-09-19 | 2025-10-24 | not specified | 1 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 350000.0 | 350000.0 | 0.0 | 145872.0 | 145872.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 145872.0 | 145872.0 | 0.0 | 0.0 | 204128.0 | 204128.0 | 0.0 | 0.583222857142857 | 0.583222857142857 | 0.0 | not specified | active | eur | it | not specified | not specified | eu | implementation / execution | not specified | ktlo | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0.0 | not specified | 0.3828 | 2023-12-10 | 2025-01-14 | on plan | not specified | 1.0 | on track | 0.993492407809111 | 40.0 | 5.0 | 0.0 | 0.0 | 0.0729166666666667 | 0.927083333333333 | 0.0 | 1.0 | current year | n | 3 | not specified | not specified | not specified | p | 243 | 1.0 | 1.0 | 1.0 | not specified | not specified | not specified | 2024-01-29 | 2025-03-07 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | -241.0 | not specified | -461.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | improved performance | 0.0 | one | not specified | qlikview to tableau migration | not specified |  | not specified | not specified | false | stage 3 - implementation | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.71
pmo000668 ei90 w/pu edge cert | 12283 | pmo000668 ei90 with pu edge certification | christian wienand | andrás fejes | project | standalone project | standalone project | not specified | andrás fejes | r&d europe r&d europe central | not specified | not specified | andr�s fejes | oliver b�wing | not specified | not specified | not specified | growth | dach: commercial - germany | engineering | l3 (planned) | on track | 12283.0 | not specified | project dashboard | project finance dashboard | 0.69 | 2024-05-01 | 2026-05-06 | 526d | certification process runs at dibt.. erp implementation planning with as400 and eoffer teams was conducted | agreement on as400 implementation with av colleagues | track certification process at dibt. | not specified | green | sideways | red | green | red | green | green | green | 2 | 0 | 0.0 | 0.0 | 24.0 | 52.0 | 0.0 | 0.0 | 0.0 | 0.0 | 76.0 | 24.0 | 23.0 | 1.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2024-05-01 | 2025-11-13 | 0 | 402d | 2025-10-22 | 2025-10-22 | not specified | 2 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | r&d | technical | npd | central eu | implementation / execution | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | 1.0 | on track | 0.743346007604563 | 7.0 | 7.0 | 0.0 | 0.0 | 0.315789473684211 | 0.68421052631579 | 0.0 | 1.0 | 2026 | not specified | 3 | not specified | not specified | not specified | p | 244 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2024-05-01 | 2025-11-13 | not specified | not specified | 2024-09-05 | 2024-09-05 | 2025-03-06 |  | 2025-11-13 |  | not specified | 0.0 | not specified | -174.0 | not specified | -526.0 | not specified | not specified | 2024-09-05 00:00:00 | 2024-09-05 00:00:00 | 2025-03-27 00:00:00 | not specified | 2026-05-06 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0 | 0 | -21d | -174d | dates not set | 0.0 | 0.0 | -0.0399239543726236 | -0.330798479087452 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | pmo000668 ei90 w/pu edge cert | not specified |  | not specified | not specified | false | stage 3 - implementation | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.69
pmo000480-2 wpc threshold-cert doors | p-0276 | pmo000480-2 wpc threshold - phase 2 - certified doors | not specified | philipp nothdurft | project | standalone project | standalone project | not specified | philipp nothdurft | r&d europe r&d europe central | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.94 | 2024-12-03 | 2026-01-13 | 291d | g4 delayed: not all stakeholders availabel | not specified | not specified | not specified | green | sideways | green | green | green | green | green | green | 0 | 0 | 0.0 | 0.0 | 5.0 | 16.0 | 0.0 | 0.0 | 0.0 | 0.0 | 21.0 | 5.0 | 4.0 | 1.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2024-12-03 | 2026-02-09 | 0 | 310d | 2025-10-22 | 2025-07-11 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | r&d | exterior | vave | central eu | implementation / execution | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.814432989690722 | 7.0 | 110.0 | 0.0 | 0.0 | 0.238095238095238 | 0.761904761904762 | 0.0 | 1.0 | 2026 | not specified | 3 | not specified | not specified | 1.0 | p | 245 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2024-12-03 | 2026-02-09 | not specified | not specified |  |  | 2025-02-18 |  | 2025-04-24 | 2026-02-09 | not specified | 0.0 | not specified | 27.0 | not specified | -291.0 | not specified | not specified | not specified | not specified | 2025-02-18 00:00:00 | not specified | 2025-10-30 00:00:00 | 2026-01-13 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | 0 | -189d | 27d | 0.0 | 0.0 | 0.0 | -0.649484536082474 | 0.0927835051546392 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | pmo000480-2 wpc threshold-cert doors | not specified |  | not specified | not specified | false | stage 3 - implementation | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.94
entra id implementation | 72067 | not specified | not specified | jeff stetson | project | standalone project | standalone project | not specified | not specified | it na/corporate | not specified | not specified | not specified | jeff stetson | not specified | not specified | not specified | not specified | support functions: global it - north america | it | l1 (identified) | on track | 72067.0 | not specified | project dashboard | project finance dashboard | 0.0 | 2025-01-01 | 2025-06-26 | 127d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | sideways | green | green | green | green | yellow | green | 0 | 0 | 0.0 | 53.0 | 22.0 | 0.0 | 22.0 | 22.0 | 75.0 | 75.0 | 75.0 | 75.0 | 75.0 | 0.0 | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2024-11-18 | 2025-09-18 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | canceled | usd | it | not specified | not specified | not specified | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not planned (l2 to l4) | not specified | 1.0 | on track | 1.0 | 345.0 | 41.0 | 0.0 | 0.706666666666667 | 0.293333333333333 | 0.0 | 1.0 | 0.0 | current year | n | 3 | not specified | not specified | 1.0 | p | 247 | 1.0 | 1.0 | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | 0.0 | not specified | -127.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | entra id implementation | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0
eu capitalisation [it resource] | 62808 | capitalise it resources for fy24 | ben bridgewater | ben bridgewater | project | standalone project | standalone project | not specified | not specified | it it-eu | not specified | ben bridgewater | not specified | rachael horton-farmer | rachael horton-farmer | rachael horton-farmer | not specified | sg&a | support functions: global it - europe | it | l4 (executed) | on track | 62808.0 | not specified | project dashboard | project finance dashboard | 1.0 | 2024-06-13 | 2024-12-20 | 137d | w01: now complete | w01: now complete | w01: now complete | w01: now complete | blue | sideways | yellow | blue | yellow | green | green | green | 0 | 0 | 0.0 | 0.0 | 0.0 | 6.0 | 0.0 | 0.0 | 0.0 | 0.0 | 6.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-02-25 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-01-08 | 2025-01-08 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | completed | eur | it | not specified | not specified | eu | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 2.2044 | not specified | 0.22 | 2024-03-29 | 2024-08-04 | on plan | not specified | 1.0 | on track | 1.0 | 294.0 | 294.0 | 0.0 | 0.0 | 0.0 | 1.0 | 0.0 | 1.0 | previous year | n | 3 | not specified | not specified | not specified | p | 248 | 1.0 | 1.0 | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | 202.0 | not specified | 188.0 | not specified | -137.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | eu capitalisation [it resource] | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 1
e-commerce webshop forward integration | 12352 | creation of online shop for swiss stock products (b2b in switzerland) | karolin koch | karolin koch | project | standalone project | standalone project | bus-eu/it | not specified | it it central eu it-eu | not specified | karolin koch | not specified | sujivan thanabalasingam | markus ellinger | rachael horton-farmer | not specified | growth | dach: commercial - switzerland | it; hr; legal | l3 (planned) | on track | 12352.0 | not specified | project dashboard | project finance dashboard | 0.77 | 2023-09-13 | 2025-12-23 | 595d | w41: project on track for stage l3 implementation (build- supplier) | w41: - build continued (supplier) - content supply (fotos & texts - ongoing) - file transfer sorted - smtp access / mail delivery in progress | w42: - build continued (supplier) - pm on leave | impact: n/a p2g: n'a | green | sideways | red | green | yellow | red | green | green | 0 | 1 | 17.0 | 2.0 | 7.0 | 36.0 | 20.0 | 12.0 | 0.0 | 0.0 | 62.0 | 26.0 | 16.0 | 10.0 | 51305.882352941 | 51305.882352941 | 0.0 | 51305.882352941 | 51305.882352941 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 51305.882352941 | 51305.882352941 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2023-09-13 | 2025-11-28 | 0 | 578d | 2025-10-22 | 2025-10-09 | not specified | 17 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0.0 | not specified | 43610.0 | 43610.0 | 0.0 | 43610.0 | 43610.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 43610.0 | 43610.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | it | not specified | not specified | central eu | implementation / execution | not specified | increase revenue | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0.6523 | not specified | 0.495 | 2023-10-17 | 2024-12-31 | on plan | not specified | 1.0 | on track | 0.934453781512605 | 7.0 | 20.0 | 0.274193548387097 | 0.032258064516129 | 0.112903225806452 | 0.580645161290323 | 0.0 | 1.0 | current year | n | 3 | not specified | not specified | not specified | p | 249 | 1.0 | 1.0 | 1.0 | not specified | not specified | not specified | 2023-09-13 | 2025-11-28 | not specified | not specified |  |  | 2024-08-02 | 2024-12-17 | 2025-01-07 |  | not specified | 0.0 | not specified | -25.0 | not specified | -595.0 | not specified | not specified | not specified | not specified | 2024-10-14 00:00:00 | 2025-10-24 00:00:00 | 2025-12-23 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | -73d | -350d | dates not set | 0.0 | 0.0 | -0.122689075630252 | -0.588235294117647 | 0.0 | not specified | not specified | not specified | not specified | focussed growth | 0.0 | one | not specified | e-commerce webshop forward integration | not specified |  | not specified | not specified | false | stage 3 - implementation | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.77
pmo000249 - acoustic, sound & green al | p-0322 | our high runner products are under price pressure. product lifecycle of stable are almost on the top, & we need to secure our vitality index and business in the future. to be attractive to our customer and end-user we need a new “stable” product with more features. develop new high runner door set in al with acoustic feature as well. panel/front in e.g., 4 different color and 2 wood surface - good if it can bee a click on solution, so you can change appearance and get an aftersales year after year, when woman wants to change. | kira svane kristensen | kira svane kristensen | project | standalone project | standalone project | not specified | kira svane kristensen | r&d europe r&d europe north | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.55 | 2025-03-24 | 2025-12-02 | 182d | week 40 r&d to continue work on prototypes for evaluation. evaluation meeting planned for 10. november. | r&d prototypes in the works. evaluation meeting booked for 10/11. magnets will arrive w44-45 | continue r&d concept development. | no support needed. | green | angle up | red | yellow | red | green | yellow | green | 0 | 0 | 0.0 | 65.0 | 16.0 | 8.0 | 0.0 | 3.0 | 70.0 | 65.0 | 89.0 | 81.0 | 77.0 | 4.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-10-07 | 2025-10-09 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | r&d | interior | npd | north eu | initiation / validation / feasibility | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.868131868131868 | 22.0 | 20.0 | 0.0 | 0.730337078651685 | 0.179775280898876 | 0.0898876404494382 | 0.786516853932584 | 0.213483146067416 | current year | not specified | 3 | not specified | not specified | not specified | p | 251 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | -82.0 | not specified | -159.0 | not specified | -182.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | stage 1 - feasibility | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.55
european peoplepoint payroll interfaces | 57585 | development and implementation of interfaces to provide controlled data supply from the master hr solution (peoplepoint) to kronos for t&a set up for s/l/c and tmf for master payroll data s/l/c. this will automate the process against the authorised payroll calendar to capture approved system data only for processing to meet compliance in payroll processing. | charlotte fox | charlotte fox | project | standalone project | standalone project | it-eu | not specified | it it-eu | not specified | charlotte fox | not specified | sharon delooze | adam painter | rachael horton-farmer | not specified | other | support functions: hr | it; hr | l3 (planned) | on track | 57585.0 | not specified | project dashboard | project finance dashboard | 0.82 | 2024-07-01 | 2025-08-26 | 302d | w42: hypercare - all it deliverables/milestones complete remaining items are with hr to finalise the use of the automation into tmf payroll processing. local teams are prioritised onto hrt and pro wfm for the time being. | w42: hypercare | w42: hypercare | support required: n/a impact: n/a ptg: n/a | green | sideways | red | green | red | red | green | green | 1 | 13 | 0.0 | 0.0 | 6.0 | 12.0 | 6.0 | 4.0 | 0.0 | 0.0 | 18.0 | 6.0 | 4.0 | 2.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2024-07-01 | 2025-04-28 | 0 | 216d | 2025-06-15 | 2025-10-22 | not specified | 27 | not specified | not specified | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 3 | 0 | 2 | 5 | 1.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | it | not specified | not specified | eu | realize value / close / care period | not specified | compliance | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 2024-08-04 | 2024-11-29 | on plan | not specified | 1.0 | on track | 1.0 | 136.0 | 7.0 | 0.0 | 0.0 | 0.333333333333333 | 0.666666666666667 | 0.0 | 1.0 | current year | n | 3 | not specified | not specified | not specified | p | 254 | 1.0 | 1.0 | 1.0 | not specified | not specified | not specified | 2024-07-01 | 2025-04-28 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | -120.0 | not specified | -302.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | bau | 0.0 | one | not specified | european peoplepoint payroll interfaces | not specified |  | not specified | not specified | false | stage 5 - care period | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.82
creation of an online shop template for container business | 14240 | creation of online shop for bos container (b2c in switzerland) | karolin koch | karolin koch | project | standalone project | standalone project | it-eu | not specified | it it central eu it-eu | not specified | karolin koch | not specified | henrik helmer | markus ellinger | rachael horton-farmer | not specified | growth | dach: commercial - germany steel | it | l3 (planned) | on hold | 14240.0 | not specified | project dashboard | project finance dashboard | 0.64 | 2023-09-12 | 2026-02-09 | 630d | w18: project on hold until july project behind track for stage l3 implementation we're currently struggling with very limited business resource capacity to progress with build. negative impact on schedule very likely. | w18: - project set to on hold until july due to lack of business resources | w19: - n/a | impact: n/a p2g: n'a | blue | sideways | red | green | green | red | green | green | 1 | 0 | 8.0 | 2.0 | 24.0 | 22.0 | 29.0 | 27.0 | 0.0 | 0.0 | 56.0 | 34.0 | 30.0 | 4.0 | 42324.7058823528 | 39971.7647058822 | 2352.94117647058 | 42324.7058823528 | 39971.7647058822 | 2352.94117647058 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 42324.7058823528 | 39971.7647058822 | 2352.94117647058 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-28 | 2023-09-12 | 2026-02-09 | 0 | 630d | 2025-04-09 | 2025-05-07 | not specified | 14 | not specified | not specified | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 35976.0 | 33976.0 | 2000.0 | 35976.0 | 33976.0 | 2000.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 35976.0 | 33976.0 | 2000.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | on-hold | eur | it | not specified | not specified | central eu | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0.352 | not specified | 0.11 | 2023-08-11 | 2025-01-01 | on plan | not specified | 1.0 | on track | 0.884126984126984 | 203.0 | 175.0 | 0.142857142857143 | 0.0357142857142857 | 0.428571428571429 | 0.392857142857143 | 0.0 | 1.0 | 2026 | n | 3 | not specified | not specified | not specified | p | 256 | 1.0 | 1.0 | 1.0 | not specified | not specified | not specified | 2023-09-12 | 2026-02-09 | not specified | not specified |  |  | 2024-10-14 | 2025-10-09 | 2025-12-31 | 2026-02-09 | not specified | 0.0 | not specified | 0.0 | not specified | -630.0 | not specified | not specified | not specified | not specified | 2024-10-14 00:00:00 | 2025-10-09 00:00:00 | 2025-12-31 00:00:00 | 2026-02-09 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | 0 | 0 | 0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | creation of an online shop template for container business | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.64
wms & aps upgrade oettingen | 39249 | the warehouse management system (wms) and advanced planning system (aps) were implemented in 2008 in oettingen. now, 15 years later, these systems are outdated and out of support- causing a risk to the business production output. this project is to upgrade both systems to ensure future support | amer basic | karolin koch | project | standalone project | standalone project | it-eu | not specified | it it central eu it-eu | not specified | karolin koch | not specified | markus ellinger | markus ellinger | rachael horton-farmer | not specified | sg&a | support functions: global it - europe | it | l5 (realised) | on track | 39249.0 | not specified | project dashboard | project finance dashboard | 0.98 | 2022-11-01 | 2025-02-10 | 595d | w08: aps & wms: project closed. | w08: - aps & wms: gate 4/5 review approved - project pushed to l4 in wave | w09: n/a | no support needed at this point. | blue | up | red | green | red | green | green | green | 0 | 0 | 0.0 | 0.0 | 3.0 | 17.0 | 3.0 | 3.0 | 0.0 | 0.0 | 20.0 | 3.0 | 3.0 | 0.0 | 194278.823529411 | 0.0 | 194278.823529411 | 98905.3764705879 | 0.0 | 98905.3764705879 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 98905.3764705879 | 0.0 | 98905.3764705879 | 0.0 | 95373.4470588232 | 0.0 | 95373.4470588232 | 0.490910153387794 | 0.0 | 0.490910153387794 | 2025-10-27 | 2022-11-01 | 2024-09-20 | 0 | 494d | 2025-01-20 | 2025-02-21 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 165137.0 | 0.0 | 165137.0 | 84069.57 | 0.0 | 84069.57 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 84069.57 | 0.0 | 84069.57 | 0.0 | 81067.43 | 0.0 | 81067.43 | 0.490910153387793 | 0.0 | 0.490910153387793 | not specified | completed | eur | it | not specified | not specified | central eu | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0.04273962 | 2023-12-10 | 2024-08-31 | on plan | not specified | 1.0 | on track | 1.0 | 282.0 | 250.0 | 0.0 | 0.0 | 0.15 | 0.85 | 0.0 | 1.0 | current year | n | 3 | not specified | not specified | not specified | p | 257 | 1.0 | 1.0 | 1.0 | not specified | not specified | not specified | 2022-11-01 | 2024-09-20 | not specified | not specified | 2023-10-10 | 2023-10-11 | 2023-10-12 | 2024-07-30 | 2024-08-20 | 2024-09-20 | not specified | 0.0 | not specified | -143.0 | not specified | -595.0 | not specified | not specified | 2023-10-10 00:00:00 | 2023-10-11 00:00:00 | 2023-10-12 00:00:00 | 2024-08-13 00:00:00 | 2025-02-10 00:00:00 | 2025-02-10 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0 | 0 | 0 | -174d | -143d | 0.0 | 0.0 | 0.0 | -0.292436974789916 | -0.240336134453782 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | wms & aps upgrade oettingen | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.98
hbw - oettingen | 12650 | implementation of hbw in oe (software, hardware & physical building) | karolin koch | katja kittner | project | standalone project | standalone project | it-eu | not specified | it it central eu it-eu | not specified | karolin koch | not specified | daniel wenz | markus ellinger | rachael horton-farmer | not specified | freight & logistics | dach: manufacturing - germany | it; legal | l2 (validated) | some issues | 12650.0 | not specified | project dashboard | project finance dashboard | 0.14 | 2023-11-01 | 2028-02-25 | 1128d | w37: wms - project on track for it-l3 hbw: n/a | w37: wms - psa & sow software meeting with supplier & legal for final draft hbw: n/a | w38: wms: - distribute final draft psa & sow hbw: n/a | impact: n/a p2g: n/a | green | sideways | #invalid operation | #invalid operation | red | green | yellow | green | 0 | 6 | 31.0 | 58.0 | 154.0 | 72.0 | 38.0 | 50.0 | 126.0 | 126.0 | 315.0 | 243.0 | 241.0 | 2.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-09-23 | 2025-09-16 | not specified | 8 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | it | not specified | not specified | central eu | planning | not specified | cost reduction | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 5.6699038 | not specified | 18.37 | 2023-02-11 | 2026-01-24 | on plan | not specified | 1.0 | on track | 0.461879432624113 | 36.0 | 43.0 | 0.0984126984126984 | 0.184126984126984 | 0.488888888888889 | 0.228571428571429 | 0.4 | 0.6 | 2028 | n | 3 | not specified | not specified | not specified | p | 258 | 1.0 | 1.0 | 1.0 | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | 427.0 | not specified | -974.0 | not specified | -1128.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | improved performance | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.14
warehouse management system - austria | 15217 | introduction of warehousemanagement for spital and several external warehouse locations | karolin koch | karolin koch | project | standalone project | standalone project | it-eu | not specified | it it central eu it-eu | not specified | karolin koch | not specified | dominik marek | markus ellinger | rachael horton-farmer | not specified | manufacturing | dach: manufacturing - austria | it; legal | l3 (planned) | on track | 15217.0 | not specified | project dashboard | project finance dashboard | 0.42 | 2023-03-11 | 2027-09-01 | 1168d | w41: - project approved for implementation - contract review (psa & sow) with preferred vendor underway - cerf approval pending | w41: - final draft of psa & sow rejected by vendor. - cerf presentation open | w42: - pm on leave - distribute amended draft psa - cerf approval week 44 earliest | impact: n/a p2g: n/a | green | angle down | green | green | green | green | green | green | 0 | 0 | 9.0 | 0.0 | 65.0 | 41.0 | 10.0 | 3.0 | 0.0 | 0.0 | 115.0 | 74.0 | 66.0 | 8.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-28 | 2023-03-11 | 2029-05-09 | 0 | 1608d | 2025-10-22 | 2025-10-09 | not specified | 5 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | it | not specified | not specified | central eu | planning | not specified | cost reduction | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0.1056 | not specified | 0.8305 | 2023-12-10 | 2027-08-31 | on plan | not specified | 1.0 | on track | 0.589041095890411 | 7.0 | 20.0 | 0.0782608695652174 | 0.0 | 0.565217391304348 | 0.356521739130435 | 0.0 | 1.0 | 2027 | n | 3 | not specified | not specified | not specified | p | 259 | 1.0 | 1.0 | 1.0 | not specified | not specified | not specified | 2023-03-11 | 2029-05-09 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | 616.0 | not specified | -1168.0 | not specified | not specified | 2023-09-12 00:00:00 | 2023-09-12 00:00:00 | 2025-08-07 00:00:00 | 2026-10-23 00:00:00 | 2027-01-01 00:00:00 | 2027-09-01 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | improved performance | 0.0 | one | not specified | warehouse management system - austria | not specified |  | 0.55 | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.42
titan conversions - aix to linux | 70990 | not specified | cyndi maples | jamal mebane | program | 70990 | 70990: titan conversions - aix to linux | not specified | not specified | it it-eu infrastructure | not specified | jamal mebane | not specified | m.j. vaidya | mike schipper | m.j. vaidya | not specified | other | support functions: global it - infrastructure / service desk | it | l3 (planned) | on hold | not specified | not specified | program dashboard | finance dashboard | 0.556714285714286 | 2024-09-23 | 2026-03-31 | 397d | p-0327 eu - remains on hold. decision to put on hold for six (6 months). p-0272 na - decision to place project on hold. | not specified | not specified | not specified | red | on track | yellow | on track | green | red | yellow | green | 0 | 1 | 21.0 | 46.0 | 30.0 | 96.0 | 21.0 | 23.0 | 50.0 | 50.0 | 193.0 | 97.0 | 93.0 | 4.0 | 1465670.0 | 594406.0 | 871264.0 | 581666.49 | 293294.5 | 288371.99 | not specified | 638706.0 | 280302.0 | 358404.0 | not specified | 1220372.49 | 573596.5 | 646775.99 | not specified | 245297.51 | 20809.5 | 224488.01 | 0.167362032381095 | 0.0350088996409861 | 0.257657851122048 |  | 2024-09-23 | 2026-03-31 | 0 | 397d | 2025-10-28 | 2025-10-29 | not specified | 2 | not specified | not specified | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1.0 | not specified | 1245819.5 | 505245.1 | 740574.4 | 494416.5165 | 249300.325 | 245116.1915 | not specified | 542900.1 | 238256.7 | 304643.4 | not specified | 1037316.6165 | 487557.025 | 549759.5915 | not specified | 208502.8835 | 17688.075 | 190814.8085 | 0.167362032381095 | 0.0350088996409861 | 0.257657851122048 | not specified | on-hold | usd | it | not specified | not specified | not specified | see project details | not specified | not specified | on track | on track | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.72544080604534 | 1.0 | 0.0 | 0.10880829015544 | 0.238341968911917 | 0.155440414507772 | 0.49740932642487 | 0.259067357512953 | 0.740932642487047 | 2026 | not specified | 2 | not specified | not specified | not specified | not specified | 261 | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | [6 empty] | not specified | not specified | not specified | not specified | not specified | -397.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.55671
na titan conversions - aix to linux | p-0272 | n.a. titan is currently hosted through an at&t contract providing both managed aix services and the data center. the underlying architecture is based on aix 7.1 and progress openedge 11.7. progress has dropped support for aix after version 12.4, which will require jw to transition to linux prior to any future database upgrades. this project will transition titan from aix to linux and also transition hosting services from at&t to the n.a. colo data center. business benefits preparing the titan environment for future uplifts operating expense reduction estimated at $1m yearly | cyndi maples | jamal mebane | project | 70990 | 70990: titan conversions - aix to linux | not specified | not specified | it infrastructure | not specified | jamal mebane | not specified | gordon greenland | jeff landry | mj vaidya | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.6 | 2024-09-23 | 2026-03-31 | 397d | project placed on hold per itlt sep 11. looking into potential to extend existing at&t contract at a better rate to minimize spend and risk of delivery window. | not specified | not specified | not specified | red | sideways | red | green | green | red | green | green | 4 | 0 | 21.0 | 2.0 | 24.0 | 85.0 | 21.0 | 23.0 | 0.0 | 0.0 | 132.0 | 47.0 | 46.0 | 1.0 | 1465670.0 | 594406.0 | 871264.0 | 581666.49 | 293294.5 | 288371.99 | 10975.12 | 638706.0 | 280302.0 | 358404.0 | 0.0 | 1220372.49 | 573596.5 | 646775.99 | 10975.12 | 245297.51 | 20809.5 | 224488.01 | 0.167362032381095 | 0.0350088996409861 | 0.257657851122048 | 2025-10-28 | 2024-09-23 | 2026-03-31 | 0 | 397d | 2025-10-28 | 2025-09-16 | not specified | 11 | not specified | not specified | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | on-hold | usd | it | not specified | not specified | not specified | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not planned (l2 to l4) | not specified | not specified | on track | 0.72544080604534 | 1.0 | 43.0 | 0.159090909090909 | 0.0151515151515152 | 0.181818181818182 | 0.643939393939394 | 0.0 | 1.0 | 2026 | n | 3 | not specified | not specified | not specified | p | 146 | 1.0 | 1.0 | not specified | not specified | not specified | not specified | 2025-10-29 | 2026-01-27 | not specified | not specified | 2024-10-03 | 2024-12-11 | 2025-04-03 | 2025-10-09 | 2025-12-11 | 2025-12-11 | not specified | 401.0 | not specified | -63.0 | not specified | -397.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | titan conversion - aix to linux | not specified | 2025-09-17 | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.6
eu titan conversions - aix to linux | p-0327 | migration of eu titan server to a linux platform due to aix no longer being supported | cyndi maples | ben hamnett | project | 70990 | 70990: titan conversions - aix to linux | not specified | not specified | it it-eu infrastructure | not specified | ben hamnett | not specified | gordon greenland | jeff landry | mj vaidya | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.5 | 2024-11-04 | 2025-12-31 | 303d | project on hold - re-assess in six(6) months. cmaples update. | not specified | not specified | not specified | yellow | sideways | red | yellow | red | red | yellow | green | 0 | 1 | 0.0 | 44.0 | 6.0 | 11.0 | 0.0 | 0.0 | 50.0 | 50.0 | 61.0 | 50.0 | 47.0 | 3.0 | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-04-29 | 2025-03-10 | not specified | 4 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | on-hold | usd | it | not specified | not specified | eu | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.851485148514852 | 183.0 | 233.0 | 0.0 | 0.721311475409836 | 0.0983606557377049 | 0.180327868852459 | 0.819672131147541 | 0.180327868852459 | current year | not specified | 3 | not specified | not specified | not specified | p | 260 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | 58.0 | not specified | -188.0 | not specified | -303.0 | not specified | not specified | 2024-11-04 00:00:00 | not specified | not specified | not specified | not specified | 2025-12-31 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | eu titan conversions - aix to linux | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.5
territory expansion leveraging the talon hardware 2.0 platform | 70124 | expand abs/talon service area from the regions physically covered with sales reps to the entire united states. the current strategy limits abs to 17% of the total wholesale hardware market, geographically. by utiliting our dc footprint and ups, we can service the entire domestic market. increasing the size of the market we service from $221m to $1.3b | amy phillips | mike doescher | project | standalone project | standalone project | not specified | not specified | it na/corporate | not specified | amy phillips | adam rummler | adam rummler | mike doescher | kirk kroft | not specified | growth | na - doors & dist: commercial - sales | it | l3 (planned) | on hold | 70124.0 | not specified | project dashboard | project finance dashboard | 0.85 | 2024-12-16 | 2025-10-14 | 217d | wk 35 - rolling out to west coast | it work is complete (done in june) met with jw sales team to showcase functionality and provide them with "leave behinds" - which will roll out the functionality to the west coast started targeted ads with hbs to advertise new functionality | begin close out procedure for the project. money step will not be accomplished until ads reach customers and they begin requesting accounts. | not specified | green | up | green | green | green | green | yellow | green | 0 | 0 | 16.0 | 0.0 | 0.0 | 75.0 | 16.0 | 16.0 | 80.0 | 80.0 | 91.0 | 16.0 | 16.0 | 0.0 | 35000.0 | 10000.0 | 25000.0 | 34194.0 | 5750.0 | 28444.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 34194.0 | 5750.0 | 28444.0 | 0.0 | 806.0 | 4250.0 | -3444.0 | 0.0230285714285714 | 0.425 | -0.13776 | 2025-10-27 | 2024-12-16 | 2025-10-14 | 0 | 217d | 2025-10-16 | 2025-09-10 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 29750.0 | 8500.0 | 21250.0 | 29064.9 | 4887.5 | 24177.4 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 29064.9 | 4887.5 | 24177.4 | 0.0 | 685.1 | 3612.5 | -2927.4 | 0.0 | 0.0 | 0.0 | not specified | active | usd | transformation | not specified | not specified | not specified | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0.21 | not specified | 0.05 | 2024-12-19 | 2025-03-27 | past due for l2 | not specified | 1.0 | on track | 1.0 | 13.0 | 49.0 | 0.175824175824176 | 0.0 | 0.0 | 0.824175824175824 | 0.879120879120879 | 0.120879120879121 | current year | n | 3 | not specified | not specified | not specified | p | 262 | 1.0 | 1.0 | not specified | not specified | not specified | not specified | 2024-12-16 | 2025-10-14 | not specified | not specified | 2024-12-19 | 2024-12-19 | 2025-03-06 | 2025-03-04 | 2025-09-25 | 2025-10-09 | not specified | 0.0 | not specified | 0.0 | not specified | -217.0 | not specified | not specified | 2024-12-19 00:00:00 | 2024-12-19 00:00:00 | 2025-03-06 00:00:00 | 2025-03-04 00:00:00 | 2025-09-25 00:00:00 | 2025-10-09 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | territory expansion leveraging the talon hardware 2.0 platform | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.85
talon hardware 2.0 integration with mmi | 70154 | integrate the recently developed talon 2.0 hardware ordering platform with ponderosa erp so mmi customers can utilize. it currently only works for abs and the turns erp. if customers had the ability to use talon, it would jump start sales and create lasting momentum given the mmi service proposition and dc footprint. | amy phillips | max kane | project | standalone project | standalone project | not specified | not specified | it na/corporate | not specified | max kane | adam rummler | adam rummler | mike doescher | kirk kroft | not specified | growth | na - doors & dist: commercial - sales | it | l3 (planned) | on track | 70154.0 | not specified | project dashboard | project finance dashboard | 0.6 | 2024-12-09 | 2026-02-03 | 302d | wk. 39 steering committee approved new baseline project manager transition to max kane | - reviewed project update with steering committee - noted timeline change due to paradigm/abs priority and resource availability impacts - timeline change is not expected to impact financials. paradigm should still remain within budget and cai will wait until paradigm is ready. | - gain commitment from paradigm to hit 10/10 date for 850 deliverable - get brand filtering design from paradigm to give to costello group - engage costello group in setting up brand filtering | not specified | green | up | red | green | red | green | yellow | green | 0 | 0 | 6.0 | 0.0 | 36.0 | 53.0 | 6.0 | 4.0 | 55.0 | 55.0 | 95.0 | 42.0 | 39.0 | 3.0 | 70000.0 | 35000.0 | 35000.0 | 57246.25 | 23185.0 | 34061.25 | 0.0 | 12331.0 | 11096.0 | 1235.0 | 0.0 | 69577.25 | 34281.0 | 35296.25 | 0.0 | 422.75 | 719.0 | -296.25 | 0.00603928571428571 | 0.0205428571428571 | -0.00846428571428571 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-10-22 | 2025-09-23 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 59500.0 | 29750.0 | 29750.0 | 48659.3125 | 19707.25 | 28952.0625 | 0.0 | 10481.35 | 9431.6 | 1049.75 | 0.0 | 59140.6625 | 29138.85 | 30001.8125 | 0.0 | 359.3375 | 611.15 | -251.8125 | 0.0 | 0.0 | 0.0 | not specified | active | usd | it | not specified | not specified | not specified | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0.05004 | not specified | 0.07 | 2025-08-02 | 2025-07-31 | past due for l2 | not specified | not specified | on track | 0.771523178807947 | 7.0 | 36.0 | 0.0631578947368421 | 0.0 | 0.378947368421053 | 0.557894736842105 | 0.578947368421053 | 0.421052631578947 | 2026 | not specified | 3 | not specified | not specified | not specified | p | 263 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | 23.0 | not specified | -222.0 | not specified | -302.0 | not specified | not specified | 2024-12-19 00:00:00 | 2024-12-19 00:00:00 | 2025-07-10 00:00:00 | 2025-07-08 00:00:00 | 2025-12-04 00:00:00 | 2025-12-18 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | talon hardware 2.0 integration with mmi | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.6
ristretto | 56225 | new window material and manufacturing innovation. | ken hull | ken hull | project | standalone project | standalone project | not specified | amanda jones | not specified | not specified | not specified | jim copeland | ken hull | not specified | not specified | not specified | other | na - windows: commercial - product & pricing | engineering | l2 (validated) | on track | 56225.0 | not specified | project dashboard | project finance dashboard | 0.34 | 2024-11-05 | 2027-11-17 | 792d | working with acell on prototypes | not specified | video and prototypes to be delivered. | not specified | green | up | red | green | red | green | yellow | green | 0 | 0 | 1.0 | 1.0 | 309.0 | 23.0 | 1.0 | 5.0 | 18.0 | 18.0 | 333.0 | 310.0 | 294.0 | 16.0 | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-10-01 | 2025-03-21 | not specified | 7 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | on track | usd | engineering | not specified | not specified | not specified | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 13.624 | not specified | 12.54 | 2026-06-11 | 2027-12-15 | on plan | not specified | 1.0 | on track | 0.32449494949495 | 28.0 | 222.0 | 0.003003003003003 | 0.003003003003003 | 0.927927927927928 | 0.0690690690690691 | 0.0540540540540541 | 0.945945945945946 | 2027 | n | 3 | not specified | not specified | not specified | p | 264 | 1.0 | 1.0 | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified |  |  |  | 2026-05-15 |  |  | not specified | 57.0 | not specified | -874.0 | not specified | -792.0 | not specified | not specified | not specified | not specified | not specified | 2026-07-21 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | ristretto | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.34
expansion of the steel door business in germany | 70298 | project to expand steel door sales in germany | michael nickl | michael nickl | project | standalone project | standalone project | not specified | not specified | not specified | not specified | not specified | michael nickl | michael nickl | not specified | not specified | not specified | growth | dach: commercial - austria steel | not specified | l3 (planned) | on track | 70298.0 | not specified | project dashboard | project finance dashboard | 0.36 | 2024-10-07 | 2027-03-26 | 645d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | sideways | red | green | red | green | yellow | green | 0 | 0 | 0.0 | 2.0 | 55.0 | 108.0 | 3.0 | 13.0 | 120.0 | 120.0 | 165.0 | 57.0 | 46.0 | 11.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-10-07 | 2024-12-04 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | transformation | not specified | not specified | central eu | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 4.7553 | not specified | 0.44 | 2024-11-26 | 2028-01-31 | on plan | not specified | 1.0 | on track | 0.431007751937985 | 22.0 | 329.0 | 0.0 | 0.0121212121212121 | 0.333333333333333 | 0.654545454545455 | 0.727272727272727 | 0.272727272727273 | 2027 | n | 3 | not specified | not specified | not specified | p | 272 | 1.0 | 1.0 | 1.0 | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | 86.0 | not specified | -638.0 | not specified | -645.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | expansion of the steel door business in germany | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.36
telephony program eu | pg-0115 | implementation of back office and contact centre functionality to the uk/swi and germany. plan to continue into the rest of europe | ben bridgewater | ben hamnett | program | pg-0115 | pg-0115: telephony program eu | it-eu | not specified | it it-eu | not specified | erik koekkoek | not specified | not specified | rachael horton - farmer | rachael horton - farmer | laura bourlon | not specified | not specified | not specified | not specified | on track | not specified | not specified | program dashboard | finance dashboard | 0.957213578500707 | 2024-02-25 | 2025-07-21 | 366d | see detailed updates in workstream | see detailed updates in workstream | see detailed updates in workstream | see detailed updates in workstream | yellow | on track | green | on track | red | red | green | green | 3 | 3 | 19.0 | 0.0 | 2.0 | 119.0 | 21.0 | 20.0 | 0.0 | 0.0 | 140.0 | 21.0 | 20.0 | 1.0 | 995137.552941173 | 214052.611764705 | 781084.941176468 | 557277.02352941 | 270168.694117646 | 287108.329411764 | not specified | 212410.211764705 | 0.0 | 212410.211764705 | not specified | 769687.235294115 | 270168.694117646 | 499518.541176469 | not specified | 225450.317647058 | -56116.082352941 | 281566.399999999 | 0.226551914336596 | -0.262160231964962 | 0.360481152761573 |  | 2024-05-06 | 2024-11-29 | 0 | 150d | 2025-08-21 | 2025-10-29 | not specified | 9 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2.0 | not specified | 845866.92 | 181944.72 | 663922.2 | 473685.47 | 229643.39 | 244042.08 | not specified | 180548.68 | 0.0 | 180548.68 | not specified | 654234.15 | 229643.39 | 424590.76 | not specified | 191632.77 | -47698.67 | 239331.44 | 0.226551914336596 | -0.262160231964962 | 0.360481152761574 | not specified | active | eur | it | not specified | not specified | eu | see project details | not specified | increase revenue | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 1.0 | 69.0 | 0.0 | 0.135714285714286 | 0.0 | 0.0142857142857143 | 0.85 | 0.0 | 1.0 | current year | not specified | 2 | not specified | not specified | not specified | pg | 115 | not specified | not specified | not specified | not specified | not specified | 0.0 |  |  | not specified | not specified | [6 empty] | 0 | not specified | not specified | not specified | not specified | -366.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | not specified | 1.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 1.0 | 2.0 | not specified | focussed growth | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.95721
telephony uk [back office & contact centre] | 39769 | implementation of contact center functionality and cloud based telephony. | ben bridgewater | ben hamnett | project | pg-0115 | pg-0115: telephony program eu | it-eu | not specified | it it uk / france / export it-eu | not specified | ben bridgewater | ben bridgewater | jordan tomlinson | adam painter | rachael horton-farmer | not specified | growth | uk: commercial | it | submitted for l5 approval | on track | 39769.0 | not specified | project dashboard | project finance dashboard | 1.0 | 2024-02-25 | 2024-06-28 | 90d | w36: project moved the closed/complete | w36:n/a | w37: n/a | issue/support : awaiting dom to sign off in wave plan to green: | blue | up | red | blue | green | green | green | red | 0 | 0 | 0.0 | 0.0 | 0.0 | 11.0 | 0.0 | 0.0 | 0.0 | 0.0 | 11.0 | 0.0 | 0.0 | 0.0 | 331712.517647058 | 71350.870588235 | 260361.647058823 | 47847.7529411763 | 44060.2941176469 | 3787.4588235294 | 0.0 | 2351.99999999999 | 0.0 | 2351.99999999999 | 0.0 | 50199.7529411763 | 44060.2941176469 | 6139.45882352939 | 0.0 | 281512.764705881 | 27290.5764705881 | 254222.188235293 | 0.848664882177918 | 0.382484141336995 | 0.976419496139756 | 2025-10-27 | 2024-06-06 | 2024-11-29 | 0 | 127d | 2025-01-10 | 2024-12-04 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 281955.64 | 60648.24 | 221307.4 | 40670.59 | 37451.25 | 3219.34 | 0.0 | 1999.2 | 0.0 | 1999.2 | 0.0 | 42669.79 | 37451.25 | 5218.54 | 0.0 | 239285.85 | 23196.99 | 216088.86 | 0.84866488217792 | 0.382484141336995 | 0.976419496139759 | not specified | completed | eur | it | not specified | not specified | uk / france / export | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0.0431211 | not specified | 0.0715418 | 2023-12-20 | 2024-06-14 | on plan | not specified | 1.0 | on track | 1.0 | 292.0 | 329.0 | 0.0 | 0.0 | 0.0 | 1.0 | 0.0 | 1.0 | previous year | n | 3 | not specified | not specified | not specified | p | 273 | 1.0 | 1.0 | 1.0 | not specified | not specified | not specified | 2024-06-06 | 2024-11-29 | not specified | not specified | [6 empty] | not specified | 102.0 | not specified | 154.0 | not specified | -90.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | telephony uk [back office & contact centre] | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 1
telephony ch [back office & contact centre] | 40532 | implementation of contact center functionality and cloud based telephony. | ben bridgewater | ben hamnett | project | pg-0115 | pg-0115: telephony program eu | it-eu | not specified | it it central eu it-eu infrastructure | not specified | ben hamnett | not specified | sujivan thanabalasingam | markus ellinger | rachael horton-farmer | not specified | growth | dach: commercial - switzerland | it | l3 (planned) | on track | 40532.0 | not specified | project dashboard | project finance dashboard | 0.99 | 2024-05-06 | 2025-07-21 | 316d | w43: customs form for logstor pcs complete, awaiting confirmation of postage | w43: customs form complete | w44: pcs to be shipped | not specified | yellow | up | red | green | red | green | green | green | 0 | 0 | 0.0 | 0.0 | 2.0 | 60.0 | 2.0 | 2.0 | 0.0 | 0.0 | 62.0 | 2.0 | 2.0 | 0.0 | 331712.517647058 | 71350.870588235 | 260361.647058823 | 182169.835294117 | 79482.3529411762 | 102687.482352941 | 0.0 | 78704.6588235291 | 0.0 | 78704.6588235291 | 0.0 | 260874.494117646 | 79482.3529411762 | 181392.14117647 | 0.0 | 70838.0235294115 | -8131.48235294115 | 78969.5058823527 | 0.213552458110077 | -0.113964725109913 | 0.303306983860458 | 2025-10-27 | 2024-05-06 | 2024-10-30 | 0 | 128d | 2025-06-20 | 2025-10-24 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 281955.64 | 60648.24 | 221307.4 | 154844.36 | 67560.0 | 87284.36 | 0.0 | 66898.96 | 0.0 | 66898.96 | 0.0 | 221743.32 | 67560.0 | 154183.32 | 0.0 | 60212.32 | -6911.76 | 67124.08 | 0.213552458110077 | -0.113964725109913 | 0.303306983860458 | not specified | active | eur | it | not specified | not specified | central eu | not specified | not specified | increase revenue | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | -0.01334245 | not specified | 0.02774915 | 2023-10-13 | 2024-05-08 | on plan | not specified | 1.0 | on track | 1.0 | 131.0 | 5.0 | 0.0 | 0.0 | 0.032258064516129 | 0.967741935483871 | 0.0 | 1.0 | current year | n | 3 | not specified | not specified | not specified | p | 274 | 1.0 | 1.0 | 1.0 | not specified | not specified | not specified | 2024-05-06 | 2024-10-30 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | -264.0 | not specified | -316.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | focussed growth | 0.0 | one | not specified | telephony ch [back office & contact centre] | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.99
telephony de wood [back office & contact centre] | 40537 | implementation of contact center functionality and cloud based telephony. | ben bridgewater | ben hamnett | project | pg-0115 | pg-0115: telephony program eu | it-eu | not specified | it it central eu it-eu infrastructure | not specified | ben hamnett | not specified | ingo heger | markus ellinger | rachael horton-farmer | not specified | growth | dach: commercial - germany | it | l3 (planned) | on hold | 40537.0 | not specified | project dashboard | project finance dashboard | 0.91 | 2024-05-06 | 2025-06-30 | 301d | w43: dect phones being installed, then gateways; awaiting mittweida porting form. number spoofing request going in to help with testing | w43: user list now complete; headsets on order. personal queue callbacks successfully tested and will go live on monday | w44: establish users for testing, confirm gateway install dates | not specified | yellow | up | red | green | red | red | green | red | 1 | 0 | 19.0 | 0.0 | 0.0 | 48.0 | 19.0 | 18.0 | 0.0 | 0.0 | 67.0 | 19.0 | 18.0 | 1.0 | 331712.517647058 | 71350.870588235 | 260361.647058823 | 327259.435294117 | 146626.047058823 | 180633.388235293 | 0.0 | 131353.552941176 | 0.0 | 131353.552941176 | 0.0 | 458612.988235293 | 146626.047058823 | 311986.94117647 | 0.0 | -126900.470588235 | -75275.176470588 | -51625.2941176469 | -0.38256159727821 | -1.05500011212197 | -0.198283021715496 | 2025-10-27 | 2024-05-06 | 2024-10-30 | 0 | 128d | 2025-08-21 | 2025-10-24 | not specified | 3 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 281955.64 | 60648.24 | 221307.4 | 278170.52 | 124632.14 | 153538.38 | 0.0 | 111650.52 | 0.0 | 111650.52 | 0.0 | 389821.04 | 124632.14 | 265188.9 | 0.0 | -107865.4 | -63983.9 | -43881.5 | -0.38256159727821 | -1.05500011212197 | -0.198283021715496 | not specified | active | eur | it | not specified | not specified | central eu | not specified | not specified | increase revenue | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0.0156662 | not specified | 0.1176461 | 2024-02-22 | 2024-09-23 | on plan | not specified | 1.0 | on track | 1.0 | 69.0 | 5.0 | 0.283582089552239 | 0.0 | 0.0 | 0.716417910447761 | 0.0 | 1.0 | current year | n | 3 | not specified | not specified | not specified | p | 275 | 1.0 | 1.0 | 1.0 | not specified | not specified | not specified | 2024-05-06 | 2024-10-30 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | -243.0 | not specified | -301.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | focussed growth | 0.0 | one | not specified | telephony de wood [back office & contact centre] | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.91
titan source code uplift | pg-0184 | not specified | ben hamnett | ben hamnett | program | pg-0184 | pg-0184: titan source code uplift | it-eu | not specified | it it-eu | not specified | ben hamnett | not specified | not specified | rachael horton - farmer | rachael horton - farmer | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | program dashboard | finance dashboard | 1.0 | 2023-04-12 | 2025-03-20 | 507d | w11: deck presented and approved at eu review board. asked to present at na board for awareness. project complete | w11: closure | not specified | not specified | blue | on track | blue | on track | red | green | green | green | 1 | 0 | 0.0 | 0.0 | 0.0 | 131.0 | 0.0 | 0.0 | 0.0 | 0.0 | 131.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 |  | 2023-08-01 | 2025-02-13 | 0 | 403d | 2025-03-13 | 2025-10-29 | not specified | 1 | not specified | not specified | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | completed | eur | it | not specified | not specified | eu | see project details | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 1.0 | 230.0 | 0.0 | 0.0 | 0.0 | 0.0 | 1.0 | 0.0 | 1.0 | current year | not specified | 2 | not specified | not specified | not specified | pg | 184 | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | [6 empty] | not specified | not specified | not specified | not specified | not specified | -507.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 1
ne titan source code uplift | 33356 | this project aims to align the corporate code with local code in northern europe, and introduce a future-proofed regular update cadence. this enabler will drive other initiatives such as ap automation, true mrp and standard costing | ben hamnett | ben hamnett | project | pg-0184 | pg-0184: titan source code uplift | it-eu | not specified | it it north eu it-eu | not specified | ben hamnett | not specified | martin persson | peter sorensen | rachael horton-farmer | not specified | sg&a | support functions: global it - europe | it; engineering | l4 (executed) | on track | 33356.0 | not specified | project dashboard | project finance dashboard | 1.0 | 2023-04-12 | 2025-03-20 | 507d | w11: closure approved pending presentation at na review board | w11: closure | not specified | not specified | blue | up | red | blue | red | green | green | green | 0 | 0 | 0.0 | 0.0 | 0.0 | 40.0 | 0.0 | 0.0 | 0.0 | 0.0 | 40.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2024-06-06 | 2024-11-29 | 0 | 127d | 2025-03-13 | 2025-03-13 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | completed | eur | it | not specified | not specified | north eu | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0.033 | 2023-10-22 | 2024-11-25 | on plan | not specified | 1.0 | on track | 1.0 | 230.0 | 230.0 | 0.0 | 0.0 | 0.0 | 1.0 | 0.0 | 1.0 | current year | n | 3 | not specified | not specified | not specified | p | 276 | 1.0 | 1.0 | 1.0 | not specified | not specified | not specified | 2024-06-06 | 2024-11-29 | not specified | not specified | [6 empty] | not specified | 421.0 | not specified | -111.0 | not specified | -507.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | ne titan source code uplift | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 1
uk titan source code uplift | 33355 | this project aims to align the corporate code with local code in the uk, and introduce a future-proofed regular update cadence. this enabler will drive other initiatives such as ap automation, true mrp and standard costing | ben hamnett | ben hamnett | project | pg-0184 | pg-0184: titan source code uplift | it-eu | not specified | it it uk / france / export it-eu | not specified | ben hamnett | ben hamnett | emmanuel vaghi | adam painter | rachael horton-farmer | not specified | sg&a | support functions: global it - europe | it; engineering | l4 (executed) | on track | 33355.0 | not specified | project dashboard | project finance dashboard | 1.0 | 2023-08-01 | 2025-03-13 | 423d | w46: hypercare period now complete, 0 issues raised via channel. 1 issue with edi being dealt with by team, this was raised by ray and is being processed as bau. | w46: hypercare period ends | w47: now back to bau. no further updates pending | not specified | blue | up | yellow | blue | yellow | green | green | green | 0 | 0 | 0.0 | 0.0 | 0.0 | 46.0 | 0.0 | 0.0 | 0.0 | 0.0 | 46.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2023-08-01 | 2025-02-13 | 0 | 403d | 2025-03-13 | 2024-12-05 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | completed | eur | it | not specified | not specified | uk / france / export | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0.0715 | 2023-10-22 | 2024-10-19 | on plan | not specified | 1.0 | on track | 1.0 | 230.0 | 328.0 | 0.0 | 0.0 | 0.0 | 1.0 | 0.0 | 1.0 | current year | n | 3 | not specified | not specified | not specified | p | 277 | 1.0 | 1.0 | 1.0 | not specified | not specified | not specified | 2023-08-01 | 2025-02-13 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | -28.0 | not specified | -423.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | uk titan source code uplift | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 1
titan france | 39212 | this project aims to align the corporate code with local code in france, and introduce a future-proofed regular update cadence. this enabler will drive other initiatives such as ap automation, true mrp and standard costing | ben hamnett | ben hamnett | project | pg-0184 | pg-0184: titan source code uplift | it-eu | not specified | it it uk / france / export it-eu | not specified | ben hamnett | ben hamnett | emmanuel vaghi | adam painter | rachael horton-farmer | not specified | sg&a | support functions: global it - europe | it | l4 (executed) | on track | 39212.0 | not specified | project dashboard | project finance dashboard | 1.0 | 2023-08-01 | 2025-03-13 | 423d | french part of project concluded, now bau. no further updates expected from this part of the program | cr accepted for monthly code uplift, now in bau | n/a - project is live | not specified | blue | up | yellow | blue | yellow | green | green | green | 0 | 0 | 0.0 | 0.0 | 0.0 | 45.0 | 0.0 | 0.0 | 0.0 | 0.0 | 45.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2023-08-01 | 2025-02-13 | 0 | 403d | 2025-03-13 | 2024-12-05 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | completed | eur | it | not specified | not specified | uk / france / export | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 2023-10-16 | 2024-07-31 | on plan | not specified | 1.0 | on track | 1.0 | 230.0 | 328.0 | 0.0 | 0.0 | 0.0 | 1.0 | 0.0 | 1.0 | current year | n | 3 | not specified | not specified | not specified | p | 278 | 1.0 | 1.0 | 1.0 | not specified | not specified | not specified | 2023-08-01 | 2025-02-13 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | -28.0 | not specified | -423.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | titan france | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 1
european tender for stiles & rails | 15999 | not specified | mateus hermann | boel sandberg | project | standalone project | standalone project | not specified | boel sandberg | r&d europe r&d europe north | not specified | not specified | boel sandberg | chris bone | not specified | not specified | not specified | sourcing | europe: sourcing (direct & indirect) | engineering | l5 (realised) | on track | 15999.0 | not specified | project dashboard | project finance dashboard | 1.0 | 2023-12-17 | 2025-04-03 | 339d | gate meeting 2-4 | booked and held gate meeting 3/4 | not specified | not specified | blue | up | red | blue | red | green | yellow | green | 0 | 0 | 0.0 | 5.0 | 0.0 | 63.0 | 0.0 | 0.0 | 20.0 | 15.0 | 68.0 | 5.0 | 0.0 | 5.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2023-12-17 | 2024-11-26 | 0 | 247d | 2025-05-22 | 2025-04-03 | not specified | 3 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | completed | eur | r&d | interior | vave | north eu | realize value / close / care period | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0.579700044 | not specified | 0.01144 | 2023-08-11 | 2024-10-25 | on plan | not specified | 1.0 | on track | 1.0 | 160.0 | 209.0 | 0.0 | 0.0735294117647059 | 0.0 | 0.926470588235294 | 0.294117647058824 | 0.705882352941176 | current year | n | 3 | not specified | not specified | 1.0 | p | 280 | 1.0 | 1.0 | 1.0 | not specified | not specified | not specified | 2023-12-17 | 2024-11-26 | not specified | not specified |  | 2024-11-25 | 2024-11-26 |  |  |  | not specified | 0.0 | not specified | -128.0 | not specified | -339.0 | not specified | not specified | not specified | 2025-04-03 00:00:00 | 2025-04-03 00:00:00 | not specified | 2025-04-03 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | -129d | -128d | dates not set | dates not set | 0.0 | -0.380530973451327 | -0.377581120943953 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | stage 5 - care period | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 1
particle board eu standardization/tender | 5322 | not specified | mateus hermann | philipp nothdurft | project | standalone project | standalone project | not specified | philipp nothdurft | r&d europe r&d europe central | not specified | not specified | philipp nothdurft | johannes eiberger | not specified | not specified | not specified | sourcing | europe: sourcing (direct & indirect) | engineering | l3 (planned) | on track | 5322.0 | not specified | project dashboard | project finance dashboard | 0.85 | 2024-01-01 | 2026-02-26 | 564d | new project plan needed as linex slows down the project progress | - | final result 33mm material at + de outstanding emp 22mm material outstanding 18mm results of large scale run | not specified | yellow | angle down | red | red | red | green | yellow | green | 1 | 0 | 4.0 | 4.0 | 3.0 | 49.0 | 0.0 | 5.0 | 18.0 | 18.0 | 60.0 | 11.0 | 4.0 | 7.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-10-28 | 2025-07-11 | not specified | 2 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | r&d | interior | vave | central eu | initiation / validation / feasibility | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 1.874136 | not specified | not specified | 2023-08-11 | 2025-06-06 | on plan | not specified | 1.0 | on track | 0.847517730496454 | 1.0 | 110.0 | 0.0666666666666667 | 0.0666666666666667 | 0.05 | 0.816666666666667 | 0.3 | 0.7 | 2026 | n | 3 | not specified | not specified | 1.0 | p | 281 | 1.0 | 1.0 | 1.0 | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | 366.0 | not specified | -245.0 | not specified | -564.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | stage 1 - feasibility | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.85
infor cpq | pg-0255 | not specified | richard guest | natalie stringfellow | program | pg-0255 | pg-0255: infor cpq | not specified | not specified | it it-eu | not specified | natalie stringfellow | not specified | not specified | not specified | rachael horton - farmer | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | program dashboard | finance dashboard | 0.698028391167192 | 2024-01-02 | 2026-09-07 | 700d | w43: se/no - work has now started on changes required for the customer onboarding process. estimate has also been received back for project pricing changes to support the structural pricing project. uk - work continues on customisations. decision now made on rmi orders and replacement orders. | not specified | w44: se/no - cost review of the project pricing changes required uk - continued titan dev. focus of sf integration | not specified | green | on track | red | on track | red | green | yellow | green | 0 | 0 | 24.0 | 5.0 | 15.0 | 48.0 | 24.0 | 24.0 | 40.0 | 40.0 | 92.0 | 44.0 | 38.0 | 6.0 | 411.764705882351 | 294.117647058823 | 117.647058823529 | 188.235294117646 | 117.647058823529 | 70.5882352941174 | not specified | 47.0588235294116 | 23.5294117647058 | 23.5294117647058 | not specified | 235.294117647058 | 141.176470588235 | 94.1176470588232 | not specified | 176.470588235294 | 152.941176470588 | 23.5294117647058 | 0.42857142857143 | 0.52 | 0.2 |  | 2024-06-06 | 2024-12-03 | 0 | 129d | 2025-10-27 | 2025-10-29 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 350.0 | 250.0 | 100.0 | 160.0 | 100.0 | 60.0 | not specified | 40.0 | 20.0 | 20.0 | not specified | 200.0 | 120.0 | 80.0 | not specified | 150.0 | 130.0 | 20.0 | 0.428571428571429 | 0.52 | 0.2 | not specified | active | eur | it | not specified | not specified | eu | see project details | not specified | not specified | on track | on track | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.681428571428571 | 2.0 | 0.0 | 0.260869565217391 | 0.0543478260869565 | 0.16304347826087 | 0.521739130434783 | 0.434782608695652 | 0.565217391304348 | 2026 | not specified | 2 | not specified | not specified | not specified | not specified | 125 | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | [6 empty] | not specified | not specified | not specified | not specified | not specified | -700.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.69803
cpq - sweden and norway quote system internal & external | 4784 | not specified | richard guest | natalie stringfellow | project | pg-0255 | pg-0255: infor cpq | not specified | not specified | it it north eu it-eu | not specified | nat stringfellow | not specified | lisa sterndalen | peter sorensen | rachael horton-farmer | not specified | growth | nordics: commercial - sweden | it | l3 (planned) | some issues | 4784.0 | not specified | project dashboard | project finance dashboard | 0.65 | 2024-01-02 | 2025-12-19 | 514d | w43: work has now started on changes required for the customer onboarding process. estimate has also been received back for project pricing changes to support the structural pricing project | not specified | w44: cost review of the project pricing changes required | not specified | green | sideways | red | green | red | green | green | green | 0 | 0 | 0.0 | 0.0 | 3.0 | 22.0 | 0.0 | 0.0 | 0.0 | 0.0 | 25.0 | 3.0 | 1.0 | 2.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2024-06-06 | 2024-12-03 | 0 | 129d | 2025-10-27 | 2025-10-27 | not specified | 2 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | it | not specified | not specified | north eu | not specified | not specified | ktlo | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 2.3276 | not specified | 0.2988304 | 2023-08-11 | 2025-03-03 | on plan | not specified | 1.0 | on track | 0.928015564202335 | 2.0 | 2.0 | 0.0 | 0.0 | 0.12 | 0.88 | 0.0 | 1.0 | current year | n | 3 | not specified | not specified | 1.0 | p | 282 | 1.0 | 1.0 | 1.0 | not specified | not specified | not specified | 2024-06-06 | 2024-12-03 | not specified | not specified | [6 empty] | not specified | 156.0 | not specified | -381.0 | not specified | -514.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | focussed growth | 0.0 | one | not specified | cpq - sweden and norway quote system internal & external | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.65
uk open cpq tool | 3539 | not specified | richard guest | natalie stringfellow | project | pg-0255 | pg-0255: infor cpq | not specified | not specified | it it uk / france / export it-eu | not specified | nat stringfellow | not specified | phil boardman | adam painter | rachael horton-farmer | not specified | growth | uk: commercial | it | l1 (identified) | on track | 3539.0 | not specified | project dashboard | project finance dashboard | 0.83 | 2024-04-16 | 2026-09-07 | 625d | 43: work continues on customisations. decision now made on rmi orders and replacement orders. | not specified | w44: continued titan dev. focus of sf integration | not specified | green | sideways | red | green | red | green | yellow | green | 1 | 0 | 0.0 | 0.0 | 12.0 | 17.0 | 0.0 | 0.0 | 2.0 | 2.0 | 29.0 | 12.0 | 8.0 | 4.0 | 411.764705882351 | 294.117647058823 | 117.647058823529 | 188.235294117646 | 117.647058823529 | 70.5882352941174 | 0.0 | 47.0588235294116 | 23.5294117647058 | 23.5294117647058 | 0.0 | 235.294117647058 | 141.176470588235 | 94.1176470588232 | 0.0 | 176.470588235294 | 152.941176470588 | 23.5294117647058 | 0.42857142857143 | 0.52 | 0.2 | 2025-10-27 | 2024-06-06 | 2024-12-03 | 0 | 129d | 2025-10-27 | 2025-10-27 | not specified | 3 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 350.0 | 250.0 | 100.0 | 160.0 | 100.0 | 60.0 | 0.0 | 40.0 | 20.0 | 20.0 | 0.0 | 200.0 | 120.0 | 80.0 | 0.0 | 150.0 | 130.0 | 20.0 | 0.428571428571429 | 0.52 | 0.2 | not specified | active | eur | it | not specified | not specified | uk / france / export | not specified | not specified | increase revenue | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0.1023 | not specified | 0.11 | 2024-01-12 | 2025-03-25 | past due for l2 | not specified | 1.0 | on track | 0.6432 | 2.0 | 2.0 | 0.0 | 0.0 | 0.413793103448276 | 0.586206896551724 | 0.0689655172413793 | 0.931034482758621 | 2026 | n | 3 | not specified | not specified | 1.0 | p | 283 | 1.0 | 1.0 | not specified | not specified | not specified | not specified | 2024-06-06 | 2024-12-03 | not specified | not specified | [6 empty] | not specified | 51.0 | not specified | -643.0 | not specified | -625.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | focussed growth | 0.0 | one | not specified | uk open cpq tool | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.83
france next gen cpq | 67360 | not specified | richard guest | natalie stringfellow | project | pg-0255 | pg-0255: infor cpq | not specified | not specified | it it uk / france / export it-eu | not specified | nat stringfellow | not specified | eric audu | adam painter | rachael horton-farmer | not specified | growth | france: commercial | it | l1 (identified) | on track | 67360.0 | not specified | project dashboard | project finance dashboard | 0.25 | 2024-06-06 | 2024-12-03 | 129d | w27: confirmation france cpq will now start in q1 2026 | not specified | not specified | not specified | green | sideways | red | red | green | green | yellow | green | 0 | 0 | 24.0 | 5.0 | 0.0 | 9.0 | 24.0 | 24.0 | 38.0 | 38.0 | 38.0 | 29.0 | 29.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2024-06-06 | 2024-12-03 | 0 | 129d | 2024-12-06 | 2025-09-25 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | on-hold | eur | it | not specified | not specified | uk / france / export | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not planned (l2 to l4) | not specified | 1.0 | on track | 1.0 | 327.0 | 34.0 | 0.631578947368421 | 0.131578947368421 | 0.0 | 0.236842105263158 | 1.0 | 0.0 | previous year | n | 3 | not specified | not specified | 1.0 | p | 284 | 1.0 | 1.0 | not specified | not specified | not specified | not specified | 2024-06-06 | 2024-12-03 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | 0.0 | not specified | -129.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | france next gen cpq | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.25
focus on direct projects business expansion | 12391 | increase market share in direct project business with steal and wood combined in austria by increasing portfolio (sliding gales, wood products + steel) and by reducing the production costs of steel products through wave projects | michael nickl | michael nickl | project | standalone project | standalone project | not specified | not specified | not specified | not specified | awaiting it pm appointment | not specified | manuel kerschner | markus ellinger | rachael horton-farmer | not specified | growth | dach: commercial - austria steel | engineering; hr | l3 (planned) | on track | 12391.0 | not specified | project dashboard | project finance dashboard | 0.3 | 2024-03-06 | 2027-09-22 | 926d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | sideways | red | green | red | red | yellow | green | 2 | 0 | 0.0 | 3.0 | 46.0 | 14.0 | 6.0 | 8.0 | 13.0 | 13.0 | 63.0 | 49.0 | 38.0 | 11.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-08-26 | 2024-12-09 | not specified | 2 | not specified | not specified | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | transformation | not specified | not specified | eu | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0.7282 | not specified | 0.22 | 2024-09-30 | 2026-01-30 | past due for l3 | not specified | 1.0 | on track | 0.465442764578834 | 64.0 | 324.0 | 0.0 | 0.0476190476190476 | 0.73015873015873 | 0.222222222222222 | 0.206349206349206 | 0.793650793650794 | 2027 | n | 3 | not specified | not specified | not specified | p | 286 | 1.0 | 1.0 | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | 301.0 | not specified | -818.0 | not specified | -926.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | focus on direct projects business expansion | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.3
expansion of domoferm to switzerland | 12305 | expansion of the domoferm steel door business into switzerland. | michael nickl | michael nickl | project | standalone project | standalone project | not specified | not specified | not specified | not specified | it pm not required | michael nickl | daniel walther | markus ellinger | rachael horton-farmer | not specified | growth | dach: commercial - switzerland | hr; it; engineering | l3 (planned) | on track | 12305.0 | not specified | project dashboard | project finance dashboard | 0.49 | 2024-06-03 | 2028-09-15 | 1120d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | sideways | red | green | red | red | yellow | green | 0 | 1 | 0.0 | 9.0 | 90.0 | 36.0 | 0.0 | 11.0 | 132.0 | 132.0 | 135.0 | 99.0 | 60.0 | 39.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2024-06-03 | 2026-02-20 | 0 | 450d | 2025-10-29 | 2024-12-09 | not specified | 1 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | transformation | not specified | not specified | eu | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 1.504275102 | not specified | 0.0 | 2023-10-26 | 2025-07-23 | on plan | not specified | 1.0 | on track | 0.328571428571429 | 0.0 | 324.0 | 0.0 | 0.0666666666666667 | 0.666666666666667 | 0.266666666666667 | 0.977777777777778 | 0.022222222222222 | 2028 | n | 3 | not specified | not specified | not specified | p | 287 | 1.0 | 1.0 | 1.0 | not specified | not specified | not specified | 2024-06-03 | 2026-02-20 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | -938.0 | not specified | -1120.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | expansion of domoferm to switzerland | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.49
doors-system solutions (enabler cpqo) | 12371 | implementation of a cpq solution for simplified order entry and calculation of products from germany and austria | michael nickl | lisa schulze-egberding | project | standalone project | standalone project | not specified | not specified | it it central eu it-eu | not specified | lisa schulze-egberding | michael nickl | thomas staub | markus ellinger | rachael horton-farmer | not specified | growth | dach: commercial - switzerland | it; hr | l3 (planned) | on track | 12371.0 | not specified | project dashboard | project finance dashboard | 0.0 | 2024-05-30 | 2026-04-16 | 491d | wk17: initiation workshops planned; initiation phase has been commissioned | wk17: n/a | wk18: preparation for first workshop | wk17: n/a | green | up | red | red | red | green | yellow | green | 0 | 0 | 0.0 | 76.0 | 49.0 | 9.0 | 2.0 | 0.0 | 132.0 | 132.0 | 134.0 | 125.0 | 122.0 | 3.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-09-30 | 2025-04-28 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | it | not specified | not specified | central eu | not specified | not specified | increase revenue | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 5.343969938 | not specified | 2.309016783 | 2023-11-10 | 2025-08-29 | on plan | not specified | 1.0 | on track | 0.753564154786151 | 29.0 | 184.0 | 0.0 | 0.567164179104478 | 0.365671641791045 | 0.0671641791044776 | 0.985074626865672 | 0.014925373134328 | 2026 | n | 3 | not specified | not specified | not specified | p | 288 | 1.0 | 1.0 | 1.0 | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | 216.0 | not specified | -294.0 | not specified | -491.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | improved performance | 0.0 | one | not specified | doors-system solutions (enabler cpqo) | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0
expansion of dana-wood products to eoffer germany | 61928 | extending current eoffer solution with dana products | lisa schulze-egberding | lisa schulze-egberding | project | standalone project | standalone project | not specified | not specified | it it central eu it-eu | not specified | lisa schulze-egberding | magdalena f�ger | roman w�lferth | markus ellinger | rachael horton-farmer | not specified | growth | dach: commercial - germany | it | l3 (planned) | on track | 61928.0 | not specified | project dashboard | project finance dashboard | 0.0 | 2025-01-01 | 2025-06-26 | 127d | wk17: product modelling ongoing; discussions around project scope/product scope started | wk17: n/a | wk18: analysis of product scope to be modelled and gap between hours already used and remaining | wk17: n/a | green | up | yellow | yellow | green | green | yellow | green | 0 | 0 | 4.0 | 53.0 | 18.0 | 0.0 | 22.0 | 22.0 | 75.0 | 75.0 | 75.0 | 75.0 | 64.0 | 11.0 | 575336.470588233 | 575336.470588233 | 0.0 | 537854.117647057 | 537854.117647057 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 537854.117647057 | 537854.117647057 | 0.0 | 0.0 | 37482.3529411763 | 37482.3529411763 | 0.0 | 0.0651485780187961 | 0.0651485780187961 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-01-27 | 2025-04-28 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 489036.0 | 489036.0 | 0.0 | 457176.0 | 457176.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 457176.0 | 457176.0 | 0.0 | 0.0 | 31860.0 | 31860.0 | 0.0 | 0.0651485780187962 | 0.0651485780187962 | 0.0 | not specified | active | eur | it | not specified | not specified | central eu | not specified | not specified | increase revenue | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0.8535373 | not specified | 0.4411 | 2024-01-10 | 2025-01-05 | past due for l3 | not specified | 1.0 | on track | 1.0 | 275.0 | 184.0 | 0.0533333333333333 | 0.706666666666667 | 0.24 | 0.0 | 1.0 | 0.0 | current year | n | 3 | not specified | not specified | not specified | p | 289 | 1.0 | 1.0 | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | 0.0 | not specified | -127.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | focussed growth | 0.0 | one | not specified | expansion of dana-wood products to eoffer germany | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0
coe spg germany - d365 upgrade / rollout bos & bbe | 72523 | implementation of d365 as erp system for bos (replacement for baan) and bbe (upgrade from axapta 2012) | lisa schulze-egberding | lisa schulze-egberding | project | standalone project | standalone project | not specified | not specified | it it central eu it-eu | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | 72523.0 | not specified | project dashboard | project finance dashboard | 0.0 | 2025-01-01 | 2025-06-26 | 127d | w07: - smartsheet project cancelled - integrated into 31612 (nda) | w07: n/a | w08: n/a | not specified | blue | up | red | red | green | green | yellow | green | 0 | 0 | 6.0 | 53.0 | 16.0 | 0.0 | 22.0 | 22.0 | 75.0 | 75.0 | 75.0 | 75.0 | 75.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-03-11 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-02-13 | 2025-02-17 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | canceled | eur | it | not specified | not specified | central eu | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0.84812651 | not specified | 0.7942 |  |  | not planned (l2 to l4) | not specified | 1.0 | on track | 1.0 | 258.0 | 254.0 | 0.08 | 0.706666666666667 | 0.213333333333333 | 0.0 | 1.0 | 0.0 | current year | n | 3 | not specified | not specified | not specified | p | 290 | 1.0 | 1.0 | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | 0.0 | not specified | -127.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | coe spg germany - d365 upgrade / rollout bos & bbe | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0
agile transformation - global it | 73737 | not specified | roman blekher | tamara johnson | project | standalone project | standalone project | not specified | not specified | it na/corporate | not specified | tamara johnson | not specified | jorge eleta gomez de segura | terry davis | tyce deal | not specified | not specified | support functions: global it - north america | it | l1 (identified) | on track | 73737.0 | not specified | project dashboard | project finance dashboard | 0.99 | 2025-01-01 | 2025-06-12 | 117d | safe training underway. agile coaching on-going with pilot pods | safe agilist and safe scrum master training completed. safe popm (product owner/product manager) training kicked off. | safe practitioner training | no support needed | blue | sideways | green | green | green | green | green | green | 0 | 0 | 0.0 | 0.0 | 1.0 | 10.0 | 1.0 | 1.0 | 0.0 | 0.0 | 11.0 | 1.0 | 1.0 | 0.0 | 0.0 | not specified | not specified | 452630.0 | 0.0 | 452630.0 | 415130.0 | 158333.333333333 | 0.0 | 158333.333333333 | 0.0 | 610963.333333333 | 0.0 | 610963.333333333 | 415130.0 | -610963.333333333 | 0.0 | -610963.333333333 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-05-28 | 2025-10-16 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 384735.5 | 0.0 | 384735.5 | 352860.5 | 134583.333333333 | 0.0 | 134583.333333333 | 0.0 | 519318.833333333 | 0.0 | 519318.833333333 | 352860.5 | -519318.833333333 | 0.0 | -519318.833333333 | 0.0 | 0.0 | 0.0 | not specified | completed | usd | it | not specified | not specified | not specified | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | 1.0 | on track | 1.0 | 154.0 | 13.0 | 0.0 | 0.0 | 0.0909090909090909 | 0.909090909090909 | 0.0 | 1.0 | current year | not specified | 3 | not specified | not specified | 1.0 | p | 294 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | 14.0 | not specified | -117.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | agile transformation | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.99
ux6x installation at high heights (ux691) step 1-3 sided frame | p-0149 | not specified | mateus hermann | philipp nothdurft | project | standalone project | standalone project | not specified | philipp nothdurft | r&d europe r&d europe central | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.28 | 2024-11-28 | 2028-03-06 | 853d | feedback ift necessars; internal test in planning; scope discussions ihh & plug and screw; discussion r&d budget | - | internal test planning of external test (waiting feedback ift) discussion sales/pm project scope discussion r&d - r&d test budget | - | red | down | red | green | red | red | green | green | 2 | 0 | 0.0 | 0.0 | 41.0 | 2.0 | 0.0 | 8.0 | 0.0 | 0.0 | 43.0 | 41.0 | 32.0 | 9.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2024-11-28 | 2026-05-01 | 0 | 372d | 2025-10-22 | 2025-10-22 | not specified | 2 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | r&d | steel | npd | central eu | implementation / execution | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.281359906213365 | 7.0 | 7.0 | 0.0 | 0.0 | 0.953488372093023 | 0.0465116279069767 | 0.0 | 1.0 | 2028 | not specified | 3 | not specified | not specified | 1.0 | p | 230 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2024-11-28 | 2026-05-01 | not specified | not specified |  |  | 2025-08-13 |  | 2026-05-01 | 2026-05-01 | not specified | 0.0 | not specified | -675.0 | not specified | -853.0 | not specified | not specified | not specified | not specified | 2027-02-12 00:00:00 | not specified | 2027-10-22 00:00:00 | 2028-03-06 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | -548d | -539d | -675d | 0.0 | 0.0 | -0.642438452520516 | -0.631887456037515 | -0.791324736225088 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | stage 3 - implementation | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.28
pmo000032,36 sound protec & security entr door | p-0277 | pmo000032-4 sound protection doors 42 db de - definitive solution sound proof. pmo000036-2 security entrance door for ux6xx (rc3) ei30 single leaf (step 1) de | not specified | philipp nothdurft | project | standalone project | standalone project | not specified | philipp nothdurft | r&d europe r&d europe central | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.29 | 2024-11-29 | 2027-02-15 | 577d | waiting to recieve certificate from dibt | not specified | documents are forwarded to dibt on 22.10.2025 | not specified | yellow | angle down | red | green | red | yellow | green | green | 1 | 0 | 0.0 | 1.0 | 17.0 | 2.0 | 0.0 | 2.0 | 0.0 | 0.0 | 20.0 | 18.0 | 18.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2024-11-29 | 2025-09-15 | 0 | 207d | 2025-10-22 | 2025-10-22 | not specified | 1 | 1.0 | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | r&d | steel | npd | central eu | implementation / execution | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.41421143847487 | 7.0 | 7.0 | 0.0 | 0.05 | 0.85 | 0.1 | 0.0 | 1.0 | 2027 | not specified | 3 | not specified | not specified | 1.0 | p | 246 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2024-11-29 | 2025-09-15 | not specified | not specified |  |  |  |  | 2025-09-15 | 2025-02-20 | not specified | 0.0 | not specified | -518.0 | not specified | -577.0 | not specified | not specified | not specified | not specified | not specified | not specified | 2027-02-15 00:00:00 | 2026-09-02 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | -518d | -559d | 0.0 | 0.0 | 0.0 | -0.897746967071057 | -0.968804159445407 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | pmo000032,36 sound protec & security entr door | not specified |  | not specified | not specified | false | stage 3 - implementation | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.29
pmo000771 product implementation ch | p-0343 | project 1 domoferm portfolio | andrás fejes | andrás fejes | project | standalone project | standalone project | not specified | andrás fejes | r&d europe r&d europe central | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.67 | 2025-01-23 | 2025-12-04 | 226d | standard steel frames: r&d ready waiting for pm to define assortment. ux431 configuration into ax and iss ready. ux6xx configuration iss waits for ch fittings to be finalised. | technical information sent out to stakeholders on ch products. ux431 ready | ux6xx finalisation product data sheet for sales and marketing | not specified | green | sideways | green | green | green | green | green | green | 0 | 1 | 0.0 | 0.0 | 8.0 | 31.0 | 0.0 | 0.0 | 0.0 | 0.0 | 39.0 | 8.0 | 3.0 | 5.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-23 | 2025-12-04 | 0 | 226d | 2025-10-22 | 2025-10-10 | not specified | 1 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | r&d | steel | npd | central eu | commercialization / go-live | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.884955752212389 | 7.0 | 19.0 | 0.0 | 0.0 | 0.205128205128205 | 0.794871794871795 | 0.0 | 1.0 | current year | not specified | 3 | not specified | not specified | not specified | p | 295 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-01-23 | 2025-12-04 | not specified | not specified | 2025-05-23 |  |  |  | 2025-12-04 |  | not specified | 0.0 | not specified | 0.0 | not specified | -226.0 | not specified | not specified | 2025-05-23 00:00:00 | not specified | not specified | not specified | 2025-12-04 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0 | dates not set | dates not set | 0 | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | stage 4 - commercialization | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.67
pmo000769 hardware and assortment harmonization | p-0384 | not specified | andrás fejes | andrás fejes | project | standalone project | standalone project | not specified | andrás fejes | r&d europe r&d europe central | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.88 | 2024-09-01 | 2025-12-05 | 330d | wp 1: eco replacement step 3 ongoing; wp 2: ch locks portfolio (eco, glutz) implemented, fittings are under implementation wp 3: anylsis resulted that there shouldn't be any more actions in this project | eco stp. 2: articles' implementation done eco stp. 3: 3x systems' analysis started by r&d ch portfolio: technical info sheet (technische mitteilung) sent out, implementation partially done door closers analysis finished | finish eco step3 analysis by r&d follow up implementation of ch products | not specified | green | sideways | green | green | green | green | green | green | 0 | 1 | 0.0 | 0.0 | 18.0 | 62.0 | 0.0 | 2.0 | 0.0 | 0.0 | 80.0 | 18.0 | 13.0 | 5.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2024-09-01 | 2025-12-12 | 0 | 335d | 2025-10-22 | 2025-10-22 | not specified | 1 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | r&d | steel | npd | central eu | commercialization / go-live | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.918181818181818 | 7.0 | 7.0 | 0.0 | 0.0 | 0.225 | 0.775 | 0.0 | 1.0 | current year | not specified | 3 | not specified | not specified | 1.0 | p | 334 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2024-09-01 | 2025-12-12 | not specified | not specified | 2025-05-23 |  |  |  | 2025-12-04 |  | not specified | 0.0 | not specified | 7.0 | not specified | -330.0 | not specified | not specified | 2025-05-23 00:00:00 | not specified | not specified | not specified | 2025-12-04 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0 | dates not set | dates not set | 0 | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | stage 4 - commercialization | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.88
pmo000538: lf531 | p-0408 | reduce size reinforcement part and reduction density inlay | philipp nothdurft | philipp nothdurft | project | standalone project | standalone project | not specified | philipp nothdurft | r&d europe r&d europe central | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.06 | 2026-01-22 | 2026-12-10 | 231d | ift will start working on certification mid dec. beginning january | - | no actions planned until dibt certification is available | not specified | green | sideways | red | yellow | red | green | yellow | green | 0 | 0 | 0.0 | 5.0 | 25.0 | 0.0 | 0.0 | 1.0 | 7.0 | 2.0 | 30.0 | 30.0 | 28.0 | 2.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-10-22 | 2025-10-22 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | r&d | not specified | not specified | central eu | implementation / execution | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.0 | 7.0 | 7.0 | 0.0 | 0.166666666666667 | 0.833333333333333 | 0.0 | 0.233333333333333 | 0.766666666666667 | 2026 | not specified | 3 | not specified | not specified | not specified | p | 356 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | -386.0 | not specified | -532.0 | not specified | -231.0 | not specified | not specified | not specified | not specified | 2026-09-03 00:00:00 | not specified | 2026-12-10 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | 2025-02-21 00:00:00 | false | stage 3 - implementation | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.06
cover counter plate from the 64mm line | 54860 | the investment in the 64mm line is intended to meet customer requirements and reduce production costs. | georg schmid | georg schmid | project | standalone project | standalone project | not specified | not specified | not specified | not specified | not specified | not specified | herbert staringer | not specified | not specified | not specified | manufacturing | dach: manufacturing - austria steel | not specified | l3 (planned) | on track | 54860.0 | not specified | project dashboard | project finance dashboard | 0.0 | 2025-01-01 | 2025-06-26 | 127d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | sideways | green | green | green | green | yellow | green | 0 | 0 | 0.0 | 0.0 | 22.0 | 0.0 | 22.0 | 22.0 | 22.0 | 22.0 | 22.0 | 22.0 | 22.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2024-12-12 | 2024-12-12 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | jem | not specified | not specified | central eu | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0.1188 | not specified | 0.165 | 2023-10-11 | 2025-03-31 | on plan | not specified | 1.0 | on track | 1.0 | 321.0 | 321.0 | 0.0 | 0.0 | 1.0 | 0.0 | 1.0 | 0.0 | current year | n | 3 | not specified | not specified | not specified | p | 298 | 1.0 | 1.0 | 1.0 | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | 0.0 | not specified | -127.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | cover counter plate from the 64mm line | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0
venice pav | pg-0349 | not specified | jonathan funk | jonathan funk | program | pg-0349 | pg-0349: venice pav | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | program dashboard | finance dashboard | 0.144056206088993 | 2024-09-16 | 2029-10-09 | 1322d | add the high level status of the program in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | on track | red | on track | red | yellow | yellow | red | 0 | 0 | 89.0 | 20.0 | 299.0 | 76.0 | 97.0 | 91.0 | 346.0 | 341.0 | 483.0 | 407.0 | 366.0 | 41.0 | 3646852.0 | 3618102.0 | 28750.0 | 1940242.0 | 1940242.0 | 0.0 | not specified | 1240160.0 | 1240160.0 | 0.0 | not specified | 3180402.0 | 3180402.0 | 0.0 | not specified | 466450.0 | 437700.0 | 28750.0 | 0.127904834087043 | 0.120975030554694 | 1 |  | 2024-12-06 | 2026-01-13 | 0 | 288d | 2025-10-27 | 2025-10-29 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 3099824.2 | 3075386.7 | 24437.5 | 1649205.7 | 1649205.7 | 0.0 | not specified | 1054136.0 | 1054136.0 | 0.0 | not specified | 2703341.7 | 2703341.7 | 0.0 | not specified | 396482.5 | 372045.0 | 24437.5 | 0.127904834087043 | 0.120975030554694 | 1.0 | not specified | active | usd | transformation | not specified | not specified | not specified | see project details | not specified | not specified | on track | on track | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.221633888048412 | 2.0 | 0.0 | 0.184265010351967 | 0.041407867494824 | 0.619047619047619 | 0.157349896480331 | 0.716356107660455 | 0.283643892339545 | 2029 | not specified | 2 | not specified | not specified | not specified | not specified | 302 | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | [6 empty] | not specified | not specified | not specified | not specified | not specified | -1322.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.14406
pav b/w & b/b expansion | 71532 | not specified | jonathan funk | jonathan funk | project | pg-0349 | pg-0349: venice pav | not specified | not specified | na it | not specified | not specified | not specified | silvia jones | not specified | not specified | not specified | not specified | na - windows: commercial - product & pricing | engineering | l1 (identified) | on hold | 71532.0 | not specified | project dashboard | project finance dashboard | 0.08 | 2024-09-16 | 2026-09-11 | 520d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | sideways | red | red | red | green | yellow | green | 0 | 0 | 3.0 | 1.0 | 13.0 | 3.0 | 12.0 | 13.0 | 20.0 | 20.0 | 20.0 | 17.0 | 16.0 | 1.0 | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-05-21 | 2025-02-26 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | on-hold | usd | transformation | not specified | not specified | not specified | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not planned (l2 to l4) | not specified | 1.0 | on track | 0.563461538461539 | 161.0 | 245.0 | 0.15 | 0.05 | 0.65 | 0.15 | 1.0 | 0.0 | 2026 | n | 3 | not specified | not specified | 1.0 | p | 301 | 1.0 | 1.0 | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | 107.0 | not specified | -442.0 | not specified | -520.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | 1) b/w & b/b expansion (windows and patio doors) - pav | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.08
next gen pav | 71533 | not specified | jonathan funk | jonathan funk | project | pg-0349 | pg-0349: venice pav | not specified | not specified | na it | not specified | not specified | jon funk | noy boriboune | not specified | not specified | not specified | not specified | na - windows: commercial - product & pricing | engineering | l1 (identified) | on track | 71533.0 | not specified | project dashboard | project finance dashboard | 0.12 | 2024-11-04 | 2029-10-09 | 1287d | 5/19/25: engineering working on casement/awning designs and needs direction on max sizes to determine loading on the interlock. asd | not specified | thermal analysis of casement/awning designs | alignment on voc/scope | yellow | angle down | red | green | red | yellow | yellow | green | 4 | 0 | 80.0 | 19.0 | 266.0 | 67.0 | 79.0 | 74.0 | 294.0 | 289.0 | 431.0 | 364.0 | 330.0 | 34.0 | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-10-27 | 2025-07-03 | not specified | 5 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | usd | transformation | not specified | not specified | not specified | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not planned (l2 to l4) | not specified | 1.0 | on track | 0.2004662004662 | 2.0 | 118.0 | 0.185614849187935 | 0.0440835266821346 | 0.617169373549884 | 0.155452436194896 | 0.682134570765661 | 0.317865429234339 | 2029 | n | 3 | not specified | not specified | 1.0 | p | 299 | 1.0 | 1.0 | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | 58.0 | not specified | -1566.0 | not specified | -1287.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | 2) redesign pav line | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.12
pav equipment replacement | 69457 | not specified | jonathan funk | jonathan funk | project | pg-0349 | pg-0349: venice pav | not specified | not specified | not specified | not specified | not specified | kenneth patek | kenneth patek | not specified | not specified | not specified | manufacturing | na - windows: manufacturing - vinyl & vpi | not specified | l1 (identified) | on track | 69457.0 | not specified | project dashboard | project finance dashboard | 0.34 | 2024-12-06 | 2026-03-10 | 328d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | sideways | red | green | red | green | yellow | green | 0 | 0 | 6.0 | 0.0 | 20.0 | 6.0 | 6.0 | 4.0 | 32.0 | 32.0 | 32.0 | 26.0 | 20.0 | 6.0 | 3646852.0 | 3618102.0 | 28750.0 | 1940242.0 | 1940242.0 | 0.0 | 0.0 | 1240160.0 | 1240160.0 | 0.0 | 0.0 | 3180402.0 | 3180402.0 | 0.0 | 0.0 | 466450.0 | 437700.0 | 28750.0 | 0.127904834087043 | 0.120975030554694 | 1 | 2025-10-27 | 2024-12-06 | 2026-01-13 | 0 | 288d | 2025-06-16 | 2025-01-21 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 3099824.2 | 3075386.7 | 24437.5 | 1649205.7 | 1649205.7 | 0.0 | 0.0 | 1054136.0 | 1054136.0 | 0.0 | 0.0 | 2703341.7 | 2703341.7 | 0.0 | 0.0 | 396482.5 | 372045.0 | 24437.5 | 0.0 | 0.0 | 0.0 | not specified | active | usd | transformation | not specified | not specified | not specified | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 3.5 | 2024-12-24 | 2025-12-30 | past due for l3 | not specified | 1.0 | on track | 0.713414634146341 | 135.0 | 281.0 | 0.1875 | 0.0 | 0.625 | 0.1875 | 1.0 | 0.0 | 2026 | n | 3 | not specified | not specified | 1.0 | p | 331 | 1.0 | 1.0 | not specified | not specified | not specified | not specified | 2024-12-06 | 2026-01-13 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | -56.0 | not specified | -328.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | pav equipment replacement | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.34
project spider | p-0350 | project spider | ryan russel | ryan russel | project | standalone project | standalone project | not specified | not specified | not specified | not specified | ryan russel | not specified | brian cox | terry davis | tyce deal | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.85 | 2024-12-26 | 2025-05-02 | 92d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | sideways | yellow | yellow | green | green | yellow | green | 0 | 4 | 6.0 | 29.0 | 5.0 | 68.0 | 10.0 | 4.0 | 56.0 | 41.0 | 108.0 | 40.0 | 4.0 | 36.0 | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-04-03 | 2024-12-17 | not specified | 6 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | usd | it | not specified | not specified | not specified | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 1.0 | 209.0 | 316.0 | 0.0555555555555556 | 0.268518518518519 | 0.0462962962962963 | 0.62962962962963 | 0.518518518518519 | 0.481481481481481 | current year | not specified | 3 | not specified | not specified | not specified | p | 303 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | 6.0 | not specified | 55.0 | not specified | -92.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | project spider | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.85
jw ssc test project | p-0373 | test project template for liz depuy and beth gesner to learn the tool | liz depuy | liz depuy | project | standalone project | standalone project | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.0 | 2025-01-01 | 2025-06-26 | 127d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | sideways | green | green | green | green | yellow | green | 0 | 0 | 0.0 | 0.0 | 22.0 | 0.0 | 22.0 | 22.0 | 22.0 | 22.0 | 22.0 | 22.0 | 22.0 | 0.0 | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2024-12-18 | 2024-12-18 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | usd | other | not specified | not specified | not specified | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | 1.0 | not specified | on track | 1.0 | 315.0 | 315.0 | 0.0 | 0.0 | 1.0 | 0.0 | 1.0 | 0.0 | current year | not specified | 3 | not specified | not specified | not specified | p | 304 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | 0.0 | not specified | -127.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | jw ssc test project | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0
distribution marketing projects | p-0374 | not specified | victoria haugen | victoria haugen | project | standalone project | standalone project | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | not specified |  |  | not specified | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | sideways | yellow | yellow | schedule not set | green | yellow | green | 0 | 0 | 0.0 | 27.0 | 0.0 | 0.0 | 0.0 | 0.0 | 27.0 | 26.0 | 1.0 | 1.0 | 0.0 | 1.0 | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-01-14 | 2024-12-18 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | usd | marketing | not specified | not specified | not specified | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.0 | 288.0 | 315.0 | 0.0 | 27.0 | 0.0 | 0.0 | 27.0 | -26.0 | not specified | not specified | 3 | not specified | not specified | 1.0 | p | 305 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | not specified | not specified | not specified | not specified | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | distribution marketing projects | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified
type48 and typ65 fire and smoke protection doors installed in timber walls | 12293 | not specified | andrás fejes | andrás fejes | project | standalone project | standalone project | not specified | andrás fejes | r&d europe r&d europe central | not specified | not specified | andr�s fejes | frank drews | not specified | not specified | not specified | growth | dach: commercial - germany | engineering | l3 (planned) | on track | 12293.0 | not specified | project dashboard | project finance dashboard | 0.29 | 2024-12-16 | 2028-01-21 | 810d | pre-testings agreed with ibs and ift, tests purchased. ift can give a testing date earliest in febr. -> delay in project testing samples' production ongoing | pre-testings were ordered | production of samples for internal and external tests in f30-a walls internal test on 18. nov., ibs test on 12.12.2025 ift test only in february 2026 production of sample for the external wooden wall test (no internal test possible) | not specified | yellow | angle down | yellow | green | yellow | green | yellow | green | 5 | 1 | 0.0 | 0.0 | 56.0 | 25.0 | 0.0 | 1.0 | 2.0 | 2.0 | 81.0 | 56.0 | 55.0 | 1.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2024-12-16 | 2028-01-14 | 0 | 805d | 2025-10-22 | 2025-10-22 | not specified | 6 | not specified | not specified | 1 | 0 | 1 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | r&d | technical | npd | central eu | development | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | 1.0 | on track | 0.281481481481482 | 7.0 | 7.0 | 0.0 | 0.0 | 0.691358024691358 | 0.308641975308642 | 0.0246913580246914 | 0.975308641975309 | 2028 | not specified | 3 | not specified | not specified | 1.0 | p | 306 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2024-12-16 | 2028-01-14 | not specified | not specified | 2025-10-02 | 2026-03-19 | 2026-12-17 |  | 2028-01-14 | 2028-01-14 | not specified | 0.0 | not specified | -7.0 | not specified | -810.0 | not specified | not specified | 2025-10-02 00:00:00 | 2026-03-26 00:00:00 | 2027-01-04 00:00:00 | not specified | 2028-01-21 00:00:00 | 2028-01-21 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0 | -7d | -18d | -7d | -7d | 0.0 | -0.00864197530864198 | -0.0222222222222222 | -0.00864197530864198 | -0.00864197530864198 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | stage 2 - development | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.29
french portfolio | pg-0352 | french portfolio of r&d projects | marine cardon | marine cardon | program | pg-0352 | pg-0352: french portfolio | not specified | marine cardon | r&d europe r&d europe france r&d europe uk / france | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | program dashboard | finance dashboard | 0.60448097412481 | 2023-07-03 | 2026-07-20 | 796d | add the high level status of the program in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | on track | yellow | on track | green | red | yellow | green | 0 | 0 | 19.0 | 299.0 | 346.0 | 306.0 | 74.0 | 68.0 | 329.0 | 62.0 | 969.0 | 663.0 | 605.0 | 58.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 |  | 2023-07-03 | 2026-11-19 | 0 | 884d | 2025-10-24 | 2025-10-29 | not specified | 0 | not specified | not specified | 0 | 1 | 0 | 0 | 0 | 6 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | r&d | not specified | not specified | uk / france | see project details | not specified | not specified | on track | on track | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.763819095477387 | 5.0 | 0.0 | 0.0196078431372549 | 0.308565531475748 | 0.357069143446852 | 0.315789473684211 | 0.33952528379773 | 0.66047471620227 | 2026 | not specified | 2 | not specified | not specified | not specified | not specified | 319 | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | [6 empty] | not specified | not specified | not specified | not specified | not specified | -796.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.60448
pmo000232 fire seal - mann mcgowan | p-0353 | pmo000232 fire seal - mann mcgowan supplier | marine cardon | marine cardon | project | pg-0352 | pg-0352: french portfolio | not specified | marine cardon | r&d europe r&d europe france r&d europe uk / france | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 1.0 | 2023-07-17 | 2025-07-31 | 534d | the project is completed now, just a problem of packaging was highlight and will be in charge for victor in procurement team to solved it | gate 5 was made in august 2025 | need to make a final check if savings fit with what was planned | not specified | on track | on track | red | blue | red | green | green | green | 0 | 0 | 0.0 | 0.0 | 0.0 | 25.0 | 0.0 | 0.0 | 0.0 | 0.0 | 25.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2023-07-17 | 2025-04-18 | 0 | 460d | 2025-07-31 | 2025-08-07 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | completed | eur | r&d | technical | vave | uk / france | realize value / close / care period | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 1.0 | 90.0 | 83.0 | 0.0 | 0.0 | 0.0 | 1.0 | 0.0 | 1.0 | current year | not specified | 3 | not specified | not specified | not specified | p | 307 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2023-07-17 | 2025-04-18 | not specified | not specified | 2023-07-17 | 2024-01-15 | 2024-11-25 |  | 2025-01-27 |  | not specified | 0.0 | not specified | -104.0 | not specified | -534.0 | not specified | not specified | 2023-07-17 00:00:00 | 2024-01-15 00:00:00 | 2024-11-25 00:00:00 | not specified | 2025-01-27 00:00:00 | 2025-07-31 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0 | 0 | 0 | 0 | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | stage 5 - care period | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 1
pmo000525 bulgary cr3-en1627 steel | 64523 | pmo000525 bulgary range cr3 - en1627 - steel frames | marine cardon | marine cardon | project | pg-0352 | pg-0352: french portfolio | not specified | marine cardon | r&d europe r&d europe france r&d europe uk / france | not specified | not specified | not specified | aurelien lamothe | not specified | not specified | not specified | npi / npd | france: commercial | not specified | l5 (realised) | on track | 64523.0 | not specified | project dashboard | project finance dashboard | 0.0 | 2025-07-01 | 2025-07-01 | 1d | a problematic of cost price has been already identify that the reason it impacts sales. this point will be follow by damien for next steps | gate 5 completed in july 2025 | not specified | not specified | green | sideways | red | yellow | red | green | yellow | green | 0 | 0 | 0.0 | 11.0 | 0.0 | 1.0 | 0.0 | 0.0 | 11.0 | 1.0 | 12.0 | 11.0 | 11.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-08-05 | 2025-08-07 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | r&d | technical | npd | uk / france | realize value / close / care period | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | 1.0 | on track | 1.0 | 85.0 | 83.0 | 0.0 | 0.916666666666667 | 0.0 | 0.0833333333333333 | 0.916666666666667 | 0.083333333333333 | current year | not specified | 3 | not specified | not specified | not specified | p | 309 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | -181.0 | not specified | -5.0 | not specified | -1.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 2025-07-01 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | stage 5 - care period | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0
pmo000713 rewriting fire classif rep | p-0359 | pmo000713 rewriting of fire classification reports | marine cardon | marine cardon | project | pg-0352 | pg-0352: french portfolio | not specified | marine cardon | r&d europe r&d europe france r&d europe uk / france | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.5 | 2024-09-02 | 2025-12-15 | 336d | this project is specific to the r&d department. | gate 1 in sept 2024 | plan to be ready for the gate 4 on the 15th of december | not specified | green | sideways | red | green | red | green | green | green | 0 | 0 | 0.0 | 0.0 | 1.0 | 1.0 | 0.0 | 0.0 | 0.0 | 0.0 | 2.0 | 1.0 | 1.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-07-31 | 2025-05-13 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | r&d | technical | sustaining | uk / france | development | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.901785714285714 | 90.0 | 169.0 | 0.0 | 0.0 | 0.5 | 0.5 | 0.0 | 1.0 | current year | not specified | 3 | not specified | not specified | not specified | p | 310 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | 121.0 | not specified | -172.0 | not specified | -336.0 | not specified | not specified | 2024-09-02 00:00:00 | not specified | not specified | not specified | 2025-12-15 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | stage 2 - development | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.5
pmo000660 new decor range door set | 12800 | pmo000660 new decorative range door set for residential business | marine cardon | marine cardon | project | pg-0352 | pg-0352: french portfolio | not specified | marine cardon | r&d europe r&d europe france r&d europe uk / france | not specified | emmanuel vaghi | not specified | frederich l�helguen | adam painter | rachael horton-farmer | not specified | not specified | france: commercial | it; engineering | l2 (validated) | on hold | 12800.0 | not specified | project dashboard | project finance dashboard | 1.0 | 2024-11-03 | 2025-05-09 | 135d | the project runs its stage 2 - development. | gate 1 approved on the 30 april | some test are planned during week 21 at ussel, damien will lead it. we are waiting for some samples from the supplier to approve final details | not specified | green | up | yellow | blue | green | yellow | yellow | green | 5 | 0 | 1.0 | 15.0 | 97.0 | 62.0 | 14.0 | 15.0 | 30.0 | 21.0 | 175.0 | 113.0 | 100.0 | 13.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2024-11-03 | 2026-11-19 | 0 | 534d | 2025-10-15 | 2025-05-13 | not specified | 5 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | r&d | interior | npd | uk / france | development | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | 1.0 | on track | 1.0 | 14.0 | 169.0 | 0.00571428571428571 | 0.0857142857142857 | 0.554285714285714 | 0.354285714285714 | 0.171428571428571 | 0.828571428571429 | current year | not specified | 3 | not specified | not specified | not specified | p | 311 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2024-11-03 | 2026-11-19 | not specified | not specified | 2025-04-30 | 2025-07-08 | 2025-09-16 |  | 2025-11-28 | 2026-11-19 | not specified | 0.0 | not specified | 559.0 | not specified | -135.0 | not specified | not specified | 2025-04-30 00:00:00 | 2025-10-02 00:00:00 | 2025-11-27 00:00:00 | not specified | 2026-02-11 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0 | -86d | -72d | -75d | dates not set | 0.0 | -0.637037037037037 | -0.533333333333333 | -0.555555555555556 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | stage 2 - development | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 1
pmo000775 - end of work frame deco range set | 12801 | end of work frame for residential business and decorative doors | marine cardon | marine cardon | project | pg-0352 | pg-0352: french portfolio | not specified | marine cardon | r&d europe r&d europe france r&d europe uk / france | not specified | emmanuel vaghi | not specified | damien kovac | not specified | not specified | not specified | not specified | france: commercial | engineering; it | l1 (identified) | on hold | 12801.0 | not specified | project dashboard | project finance dashboard | 0.0 | 2024-12-06 | 2025-09-29 | 212d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | sideways | red | yellow | red | green | yellow | green | 0 | 0 | 0.0 | 6.0 | 1.0 | 1.0 | 1.0 | 1.0 | 6.0 | 0.0 | 8.0 | 7.0 | 3.0 | 4.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-08-07 | 2025-04-08 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | r&d | interior | npd | uk / france | initiation / validation / feasibility | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | 1.0 | on track | 1.0 | 83.0 | 204.0 | 0.0 | 0.75 | 0.125 | 0.125 | 0.75 | 0.25 | current year | not specified | 3 | not specified | not specified | not specified | p | 313 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | 26.0 | not specified | -95.0 | not specified | -212.0 | not specified | not specified | 2025-09-29 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | stage 1 - feasibility | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0
pmo000792 panels from 2,9 to 2,8 | p-0363 | pmo000792 panels from 2,9 to 2,8 | marine cardon | marine cardon | project | pg-0352 | pg-0352: french portfolio | not specified | marine cardon | r&d europe r&d europe france r&d europe uk / france | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.0 |  |  | #invalid data type | the project has been relaunched in the end of july to create item and allowed supply to make order | not specified | the go live planned to be in middle of october need to aligned the real date compare to the stocks | not specified | green | sideways | yellow | yellow | schedule not set | green | yellow | green | 0 | 0 | 2.0 | 10.0 | 15.0 | 11.0 | 8.0 | 7.0 | 10.0 | 0.0 | 38.0 | 27.0 | 26.0 | 1.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-02-24 | 2025-05-05 | 0 | 51d | 2025-10-01 | 2025-08-07 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | r&d | interior | vave | uk / france | implementation / execution | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.0 | 28.0 | 83.0 | 0.0526315789473684 | 0.263157894736842 | 0.394736842105263 | 0.289473684210526 | 0.263157894736842 | 0.736842105263158 | not specified | not specified | 3 | not specified | not specified | not specified | p | 314 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-02-24 | 2025-05-05 | not specified | not specified | [6 empty] | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 2025-06-30 00:00:00 | not specified | not specified | not specified | 2025-10-29 00:00:00 | 2026-10-20 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | stage 3 - implementation | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0
pmo000788 new laminated range 2025 | 71945 | pmo000788 new laminated range 2025 | marine cardon | marine cardon | project | pg-0352 | pg-0352: french portfolio | not specified | marine cardon | r&d europe r&d europe france r&d europe uk / france | not specified | not specified | not specified | damien kovac | not specified | not specified | not specified | not specified | france: commercial | it | l1 (identified) | on track | 71945.0 | not specified | project dashboard | project finance dashboard | 0.47 | 2024-11-12 | 2025-09-08 | 215d | project in care period - stage 5 until 8 of september | not specified | quality test made during the first month of commercialization , indicators & kpi | not specified | green | sideways | red | green | yellow | red | yellow | green | 2 | 0 | 0.0 | 2.0 | 3.0 | 28.0 | 5.0 | 5.0 | 2.0 | 2.0 | 33.0 | 5.0 | 5.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2024-11-12 | 2025-08-18 | 0 | 200d | 2025-06-24 | 2025-05-13 | not specified | 2 | not specified | not specified | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | r&d | multiple | npd | uk / france | realize value / close / care period | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | 1.0 | on track | 1.0 | 127.0 | 169.0 | 0.0 | 0.0606060606060606 | 0.0909090909090909 | 0.848484848484849 | 0.0606060606060606 | 0.93939393939394 | current year | not specified | 3 | not specified | not specified | not specified | p | 320 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2024-11-12 | 2025-08-18 | not specified | not specified | 2024-11-12 | 2024-11-25 | 2025-01-27 |  | 2025-02-26 | 2025-03-24 | not specified | 0.0 | not specified | -21.0 | not specified | -215.0 | not specified | not specified | 2024-11-12 00:00:00 | 2024-11-25 00:00:00 | 2025-01-27 00:00:00 | not specified | 2025-02-26 00:00:00 | 2025-09-08 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0 | 0 | 0 | 0 | -168d | 0.0 | 0.0 | 0.0 | 0.0 | -0.781395348837209 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | stage 5 - care period | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.47
pmo000648 express delivery lamin doors | 12787 | pmo000648 express delivery for laminated doors | marine cardon | marine cardon | project | pg-0352 | pg-0352: french portfolio | not specified | marine cardon | r&d europe r&d europe france r&d europe uk / france | not specified | not specified | not specified | damien kovac | not specified | not specified | not specified | growth | france: commercial | engineering | l4 (executed) | on track | 12787.0 | not specified | project dashboard | project finance dashboard | 0.8 | 2023-09-12 | 2025-09-23 | 531d | the project takes so much more time than expected, a lot of resources from the pricing to build a file with all price reported for premium offer | finalization of the configurator file | gate 4 planned on the 15th of september approval of the brochure to relaunch printing as prices have changed | 01/09 approval required from the clt france we need to approve the last version of the file before testing in real its usage, specially to check protection of datas as it's not public prices involved. | yellow | sideways | red | green | red | green | yellow | green | 0 | 0 | 0.0 | 8.0 | 16.0 | 26.0 | 15.0 | 13.0 | 9.0 | 1.0 | 49.0 | 23.0 | 20.0 | 3.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2023-09-12 | 2025-03-26 | 0 | 402d | 2025-08-07 | 2025-08-07 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | r&d | multiple | npd | uk / france | implementation / execution | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | 1.0 | on track | 1.0 | 83.0 | 83.0 | 0.0 | 0.163265306122449 | 0.326530612244898 | 0.530612244897959 | 0.183673469387755 | 0.816326530612245 | current year | not specified | 3 | not specified | not specified | not specified | p | 323 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2023-09-12 | 2025-03-26 | not specified | not specified | 2023-09-12 | 2023-09-29 | 2024-11-12 |  | 2025-02-24 |  | not specified | 0.0 | not specified | -181.0 | not specified | -531.0 | not specified | not specified | 2023-09-12 00:00:00 | 2023-09-29 00:00:00 | 2024-11-12 00:00:00 | not specified | 2025-09-23 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0 | 0 | 0 | -211d | dates not set | 0.0 | 0.0 | 0.0 | -0.397363465160075 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | stage 3 - implementation | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.8
pmo000688 bascule tech+ lca monobloc | 64423 | pmo000688 bascule tech+ lca en monobloc | marine cardon | marine cardon | project | pg-0352 | pg-0352: french portfolio | not specified | marine cardon | r&d europe r&d europe france r&d europe uk / france | not specified | not specified | not specified | aurelien lamothe | not specified | not specified | not specified | npi / npd | france: commercial | engineering | l1 (identified) | on track | 64423.0 | not specified | project dashboard | project finance dashboard | 0.99 | 2024-10-28 | 2025-09-04 | 224d | some problematic has been highlight during production in concerns principally section 217 but it need to determine if there is other problem with other question | not specified | need to plan a date to realize all the tests needed with operational team and methods department | not specified | green | angle down | red | green | red | green | yellow | green | 0 | 0 | 0.0 | 8.0 | 1.0 | 62.0 | 1.0 | 1.0 | 9.0 | 1.0 | 71.0 | 9.0 | 9.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2024-10-28 | 2025-04-18 | 0 | 125d | 2025-08-07 | 2025-08-07 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | r&d | interior | npd | uk / france | commercialization / go-live | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | 1.0 | on track | 1.0 | 83.0 | 83.0 | 0.0 | 0.112676056338028 | 0.0140845070422535 | 0.873239436619718 | 0.126760563380282 | 0.873239436619718 | current year | not specified | 3 | not specified | not specified | not specified | p | 324 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2024-10-28 | 2025-04-18 | not specified | not specified | 2024-10-28 | 2024-10-28 | 2025-02-24 |  | 2025-04-15 |  | not specified | 0.0 | not specified | -139.0 | not specified | -224.0 | not specified | not specified | 2024-10-28 00:00:00 | 2024-10-28 00:00:00 | 2025-04-30 00:00:00 | not specified | 2025-05-28 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0 | 0 | -65d | -43d | dates not set | 0.0 | 0.0 | -0.290178571428571 | -0.191964285714286 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | stage 4 - commercialization | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.99
pmo000385 stiffeners lvl vs lsl alt | 62795 | pmo000385 stiffeners lvl vs lsl alternative (insulation & flat entrance door) | marine cardon | marine cardon | project | pg-0352 | pg-0352: french portfolio | not specified | marine cardon | r&d europe r&d europe france r&d europe uk / france | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | 62795.0 | not specified | project dashboard | project finance dashboard | 0.16 | 2025-06-02 | 2026-07-20 | 296d | the project failed some test of stability so the need is to go back on stage 1. but for now as priority has been decided the project need to be put on hold | not specified | need to check if r&d department could support this project by their side if they have resources avalaible | not specified | on track | on track | red | green | red | red | yellow | green | 1 | 0 | 5.0 | 0.0 | 108.0 | 21.0 | 6.0 | 5.0 | 1.0 | 1.0 | 134.0 | 113.0 | 107.0 | 6.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-10-24 | 2025-08-07 | not specified | 1 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | on-hold | eur | r&d | interior | vave | uk / france | initiation / validation / feasibility | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 2024-10-21 | 2025-07-28 | on plan | not specified | 1.0 | on track | 0.364864864864865 | 5.0 | 83.0 | 0.0373134328358209 | 0.0 | 0.805970149253731 | 0.156716417910448 | 0.00746268656716418 | 0.992537313432836 | 2026 | n | 3 | not specified | not specified | not specified | p | 271 | 1.0 | 1.0 | 1.0 | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | -152.0 | not specified | -389.0 | not specified | -296.0 | not specified | not specified | 2025-12-08 00:00:00 | 2026-03-23 00:00:00 | 2026-06-11 00:00:00 | not specified | 2026-07-20 00:00:00 | 2027-07-09 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | stage 1 - feasibility | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.16
pmo000501 npi-hp-acoustic high perf | 12797 | pmo000501 npi-hp-acoustic high performance | marine cardon | marine cardon | project | pg-0352 | pg-0352: french portfolio | not specified | marine cardon | r&d europe r&d europe france r&d europe uk / france | not specified | it pm not required | not specified | aurelien lamothe | adam painter | rachael horton - farmer | not specified | growth | france: commercial | engineering; it | l3 (planned) | cancelled | 12797.0 | not specified | project dashboard | project finance dashboard | 0.45 | 2023-07-03 | 2026-04-21 | 732d | project hold > aucune ressource ne travail sur le projet cette semaine s17 | réalisation des essais endurance en labo >> terminé | rédaction des rapports >> en cours | lack of ressources in bm department | red | down | red | green | red | red | yellow | green | 1 | 0 | 4.0 | 8.0 | 73.0 | 25.0 | 10.0 | 8.0 | 10.0 | 2.0 | 110.0 | 85.0 | 78.0 | 7.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2023-07-03 | 2025-12-01 | 0 | 631d | 2025-10-15 | 2025-08-07 | true | 1 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | on-hold | eur | r&d | technical | npd | uk / france | implementation / execution | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 2024-05-01 | 2025-12-11 | cancelled | not specified | 1.0 | on track | 0.830601092896175 | 14.0 | 83.0 | 0.0363636363636364 | 0.0727272727272727 | 0.663636363636364 | 0.227272727272727 | 0.0909090909090909 | 0.909090909090909 | 2026 | n | 3 | not specified | not specified | not specified | p | 279 | 1.0 | 1.0 | 1.0 | not specified | not specified | not specified | 2023-07-03 | 2025-12-01 | not specified | not specified | 2023-07-03 | 2024-06-24 | 2025-07-01 |  | 2025-12-01 |  | not specified | 0.0 | not specified | -141.0 | not specified | -732.0 | not specified | not specified | 2023-07-03 00:00:00 | 2024-06-24 00:00:00 | 2026-02-23 00:00:00 | not specified | 2026-04-21 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0 | 0 | -237d | -141d | dates not set | 0.0 | 0.0 | -0.323770491803279 | -0.192622950819672 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | stage 3 - implementation | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.45
pmo000933 - double acting enforcement plate | p-0507 | renforcement plate for double actiong door. quality improvement for business protection and development | marine cardon | marine cardon | project | pg-0352 | pg-0352: french portfolio | not specified | marine cardon | r&d europe r&d europe france r&d europe uk / france | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 1.0 | 2025-08-28 | 2025-09-26 | 22d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | sideways | red | blue | red | green | yellow | green | 0 | 0 | 3.0 | 99.0 | 23.0 | 41.0 | 5.0 | 6.0 | 108.0 | 22.0 | 166.0 | 125.0 | 109.0 | 16.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-07-01 | 2025-09-02 | 0 | 46d | 2025-10-08 | 2025-08-06 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | r&d | not specified | not specified | uk / france | ideation | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 1.0 | 21.0 | 84.0 | 0.0180722891566265 | 0.596385542168675 | 0.13855421686747 | 0.246987951807229 | 0.650602409638554 | 0.349397590361446 | current year | not specified | 3 | not specified | not specified | not specified | p | 451 | not specified | not specified | not specified | not specified | not specified | not specified | 2025-07-01 | 2025-09-02 | not specified | not specified | [6 empty] | not specified | -58.0 | not specified | -24.0 | not specified | -22.0 | not specified | not specified | 2025-11-17 00:00:00 | not specified | not specified | not specified | 2026-01-19 00:00:00 | 2027-01-08 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | 2025-08-06 00:00:00 | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 1
pmo000950 tech lca monobloc profil m&u | p-0520 | single-piece tech+ lca door frames. removal of extensions (existing offer) to improve product quality. | marine cardon | marine cardon | project | pg-0352 | pg-0352: french portfolio | not specified | marine cardon | r&d europe r&d europe france r&d europe uk / france | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.05 | 2025-09-22 | 2025-11-25 | 47d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | sideways | yellow | yellow | yellow | green | yellow | green | 0 | 0 | 4.0 | 132.0 | 8.0 | 2.0 | 9.0 | 7.0 | 133.0 | 11.0 | 146.0 | 144.0 | 136.0 | 8.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-07-01 | 2025-09-02 | 0 | 46d | 2025-10-10 | 2025-09-11 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | r&d | not specified | not specified | uk / france | ideation | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.595744680851064 | 19.0 | 48.0 | 0.0273972602739726 | 0.904109589041096 | 0.0547945205479452 | 0.0136986301369863 | 0.910958904109589 | 0.089041095890411 | current year | not specified | 3 | not specified | not specified | not specified | p | 464 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-07-01 | 2025-09-02 | not specified | not specified | [6 empty] | not specified | -83.0 | not specified | -84.0 | not specified | -47.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | 2025-09-11 00:00:00 | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.05
quoting modernization -jw widow & doors cpq, pim and ordering system | 72664 | to create a digital storefront and cpq tool that our customers can use to place stock and special orders (updated version of qql). the tool will be the first step to building a foundation needed to expand the use of a cpq engine and storefront integration for future growth opportunities and improved customer experience that will differentiate our business. | amy phillips | amy phillips | project | standalone project | standalone project | not specified | not specified | it na it na/corporate | not specified | amy phillips | not specified | marshal livingstone | terry davis | tyce deal | not specified | pricing | na - doors & dist: commercial - sales | it; engineering | l2 (validated) | on hold | 72664.0 | not specified | project dashboard | project finance dashboard | 0.03 | 2025-01-06 | 2026-12-11 | 505d | project on hold | it leadership discussions | - awaiting feedback from it leadership regarding if any data or preparation work can be accomplished prior to tmo approving project. | not specified | yellow | sideways | red | red | red | red | yellow | green | 1 | 0 | 28.0 | 2.0 | 50.0 | 28.0 | 63.0 | 62.0 | 60.0 | 60.0 | 108.0 | 80.0 | 78.0 | 2.0 | 0.0 | not specified | not specified | 3546805.0 | 3413802.0 | 133003.0 | 0.0 | 3087000.0 | 0.0 | 3087000.0 | 0.0 | 6633805.0 | 3413802.0 | 3220003.0 | 0.0 | -6633805.0 | -3413802.0 | -3220003.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-04-07 | 2025-04-07 | not specified | 1 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 3014784.25 | 2901731.7 | 113052.55 | 0.0 | 2623950.0 | 0.0 | 2623950.0 | 0.0 | 5638734.25 | 2901731.7 | 2737002.55 | 0.0 | -5638734.25 | -2901731.7 | -2737002.55 | 0.0 | 0.0 | 0.0 | not specified | on-hold | usd | it | not specified | not specified | not specified | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0.694 | 2025-10-01 | 2025-12-31 | on plan | not specified | 1.0 | on track | 0.421782178217822 | 205.0 | 205.0 | 0.259259259259259 | 0.0185185185185185 | 0.462962962962963 | 0.259259259259259 | 0.555555555555556 | 0.444444444444444 | 2026 | n | 3 | not specified | not specified | not specified | p | 325 | 1.0 | 1.0 | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | -5.0 | not specified | -533.0 | not specified | -505.0 | not specified | not specified | 2025-01-23 00:00:00 | 2025-01-23 00:00:00 | 2025-01-23 00:00:00 | 2025-01-22 00:00:00 | 2025-12-18 00:00:00 | 2025-12-18 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | quoting modernization -jw widow & doors cpq, pim and ordering system | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.03
ci strategy europe 2025 | p-0376 | project plan for rollout of european ci strategy 2025 | ashley gibbs | ashley gibbs | project | standalone project | standalone project | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.0 | 2025-04-22 | 2025-04-22 | 1d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | sideways | green | green | green | green | yellow | green | 0 | 0 | 17.0 | 37.0 | 5.0 | 9.0 | 22.0 | 19.0 | 55.0 | 55.0 | 63.0 | 54.0 | 54.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-03-10 | 2025-01-08 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | jem | not specified | not specified | eu | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 1.0 | 233.0 | 294.0 | 0.26984126984127 | 0.587301587301587 | 0.0793650793650794 | 0.142857142857143 | 0.873015873015873 | 0.126984126984127 | current year | not specified | 3 | not specified | not specified | not specified | p | 326 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | -111.0 | not specified | 65.0 | not specified | -1.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | ci strategy europe 2025 | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0
kingfisher | 69742 | network initiative | andrea chitti | andrea chitti | project | standalone project | standalone project | not specified | not specified | not specified | not specified | not specified | andrea chitti | andrea chitti | not specified | not specified | not specified | footprint | na - bridge project | engineering | l4 (executed) | on track | 69742.0 | not specified | project dashboard | project finance dashboard | 0.63 | 2024-12-07 | 2026-02-10 | 307d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | sideways | red | green | red | green | yellow | green | 0 | 0 | 88.0 | 1.0 | 46.0 | 98.0 | 12.0 | 124.0 | 70.0 | 70.0 | 233.0 | 135.0 | 1.0 | 134.0 | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2024-12-07 | 2025-11-15 | 0 | 245d | 2025-08-27 | 2025-01-08 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | usd | transformation | not specified | not specified | not specified | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | 1.0 | on track | 0.758957654723127 | 63.0 | 294.0 | 0.377682403433476 | 0.00429184549356223 | 0.197424892703863 | 0.420600858369099 | 0.300429184549356 | 0.699570815450644 | 2026 | not specified | 3 | not specified | not specified | not specified | p | 327 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2024-12-07 | 2025-11-15 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | -87.0 | not specified | -307.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | kingfisher | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.63
austria cost performance | p-0378 | in this program, the cost performance improvements for both austrian plants (domoferm kg & spital am pyhrn) are mapped. from the definition, measurement & analysis phase, projects are additionally generated where we want to generate a resource mapping. | georg schmid | georg schmid | project | standalone project | standalone project | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.0 | 2025-01-01 | 2025-06-26 | 127d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | sideways | red | red | green | green | yellow | green | 0 | 0 | 19.0 | 0.0 | 3.0 | 0.0 | 22.0 | 22.0 | 22.0 | 22.0 | 22.0 | 22.0 | 22.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-05-22 | 2025-01-13 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | jem | not specified | not specified | central eu | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 1.0 | 160.0 | 289.0 | 0.863636363636364 | 0.0 | 0.136363636363636 | 0.0 | 1.0 | 0.0 | current year | not specified | 3 | not specified | not specified | not specified | p | 328 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | 0.0 | not specified | -127.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | austria cost performance | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0
global onestream enhancement | p-0379 | not specified | christina hoy | christina hoy | project | standalone project | standalone project | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.95 | 2024-08-01 | 2025-11-07 | 332d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | sideways | red | green | red | green | yellow | green | 0 | 0 | 13.0 | 7.0 | 6.0 | 392.0 | 20.0 | 20.0 | 44.0 | 44.0 | 418.0 | 26.0 | 20.0 | 6.0 | 1165000.0 | 932000.0 | 233000.0 | 1095950.0 | 1095950.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 1095950.0 | 1095950.0 | 0.0 | 0.0 | 69050.0 | -163950.0 | 233000.0 | 0.0592703862660944 | -0.175912017167382 | 1 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-10-14 | 2025-01-13 | not specified | 23 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 990250.0 | 792200.0 | 198050.0 | 931557.5 | 931557.5 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 931557.5 | 931557.5 | 0.0 | 0.0 | 58692.5 | -139357.5 | 198050.0 | 0.0 | 0.0 | 0.0 | not specified | active | usd | finance | not specified | not specified | not specified | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.978915662650602 | 15.0 | 289.0 | 0.0311004784688995 | 0.0167464114832536 | 0.0143540669856459 | 0.937799043062201 | 0.105263157894737 | 0.894736842105263 | current year | not specified | 3 | not specified | not specified | 1.0 | p | 329 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | 153.0 | not specified | -134.0 | not specified | -332.0 | not specified | not specified | not specified | 2024-11-15 00:00:00 | 2025-01-17 00:00:00 | 2025-07-28 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | global onestream enhancement | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.95
ax2012 and baan migration to ax d365 (spg) | 31612 | not specified | lisa schulze-egberding | lisa schulze-egberding | project | standalone project | standalone project | not specified | not specified | it it central eu it-eu | not specified | lisa schulze-egberding | not specified | michael schwaiger | markus ellinger | rachael horton-farmer | not specified | sg&a | support functions: global it - europe | it | l2 (validated) | on track | 31612.0 | not specified | project dashboard | project finance dashboard | 0.0 | 2025-01-01 | 2025-06-26 | 127d | wk17: new offer proposing different phasing received; steerco scheduled to discuss status, timeline and next steps | wk17: n/a | wk18: preparation of steerco | wk17: n/a | green | angle up | red | red | green | green | yellow | green | 0 | 0 | 6.0 | 54.0 | 15.0 | 0.0 | 22.0 | 22.0 | 75.0 | 75.0 | 75.0 | 75.0 | 75.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-02-17 | 2025-04-28 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | it | not specified | not specified | eu | not specified | not specified | increase revenue | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0.2189 | not specified | 1.794 | 2023-10-16 | 2026-01-31 | on plan | not specified | 1.0 | on track | 1.0 | 254.0 | 184.0 | 0.08 | 0.72 | 0.2 | 0.0 | 1.0 | 0.0 | current year | n | 3 | not specified | not specified | 1.0 | p | 330 | 1.0 | 1.0 | 1.0 | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | 0.0 | not specified | -127.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | improved performance | 0.0 | one | not specified | ax2012 migration to ax d365 (spg) | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0
it site support model standardization | 74126 | establish a standard model for site support that defines the hw, applications, process, and documentation. establish a standard security review process for the plants to identify and eliminate gaps. establish a location to host knowledge base, sops, and support documents for all plants. incorporate existing technologies into roadmaps and future spend planning. | cyndi maples | jeff landry | project | standalone project | standalone project | not specified | not specified | it infrastructure | not specified | cyndi maples | cyndi maples | gordon greenland | kirk kroft | m.j. vaidya | not specified | sg&a | support functions: global it - infrastructure / service desk | it | submitted for l2 approval | on track | 74126.0 | not specified | project dashboard | project finance dashboard | 0.17 | 2025-01-23 | 2025-09-24 | 175d | smartsheet schedule 'red' as project was not re-baselined after original creation. cyndi requested re-baseline via smartsheet help, 2/21. itlt-l2 gate review, approved schedule itlt-l3 team kickoff | not specified | itlt-l3 team kickoff | not specified | blue | sideways | red | green | green | red | green | green | 2 | 0 | 0.0 | 0.0 | 48.0 | 13.0 | 48.0 | 48.0 | 0.0 | 0.0 | 61.0 | 48.0 | 48.0 | 0.0 | 202172.0 | 0.0 | 202172.0 | 198655.81 | 0.0 | 198655.81 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 198655.81 | 0.0 | 198655.81 | 0.0 | 3516.19 | 0.0 | 3516.19 | 0.0173920720970263 | 0.0 | 0.0173920720970263 | 2025-10-27 | 2025-01-23 | 2025-09-24 | 0 | 175d | 2025-03-06 | 2025-09-18 | not specified | 4 | not specified | not specified | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 171846.2 | 0.0 | 171846.2 | 168857.4385 | 0.0 | 168857.4385 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 168857.4385 | 0.0 | 168857.4385 | 0.0 | 2988.7615 | 0.0 | 2988.7615 | 0.0 | 0.0 | 0.0 | not specified | canceled | usd | it | not specified | not specified | not specified | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not planned (l2 to l4) | not specified | 1.0 | on track | 1.0 | 237.0 | 41.0 | 0.0 | 0.0 | 0.786885245901639 | 0.213114754098361 | 0.0 | 1.0 | current year | n | 3 | not specified | not specified | not specified | p | 332 | 1.0 | 1.0 | not specified | not specified | not specified | not specified | 2025-01-23 | 2025-09-24 | not specified | not specified | 2025-01-23 | 2025-02-20 | 2025-04-24 | 2025-08-28 | 2025-09-11 | 2025-09-11 | not specified | 0.0 | not specified | 0.0 | not specified | -175.0 | not specified | not specified | 2025-01-23 00:00:00 | 2025-02-20 00:00:00 | 2025-04-24 00:00:00 | 2025-08-28 00:00:00 | 2025-09-11 00:00:00 | 2025-09-11 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | it site support model standardization | not specified | 2025-09-18 | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.17
pmo000835 - packaging unification - germany - oettingen | p-0382 | germany packaging unification oettingen moving from current suppliers for strategic packaging suppliers. | adam keri | adam keri | project | standalone project | standalone project | not specified | not specified | r&d europe r&d europe central r&d europe packaging | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.45 | 2024-11-04 | 2025-09-25 | 234d | delivered samples have been 90% tested | 5 items approval process, apart from ecm is closed | ecm will be written, not approved samples will be replaced from supplier with more suitable ones | lately the local teams seems to be focused on the proejct | yellow | sideways | red | green | red | green | yellow | green | 0 | 0 | 7.0 | 2.0 | 46.0 | 28.0 | 55.0 | 50.0 | 62.0 | 62.0 | 83.0 | 55.0 | 50.0 | 5.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2024-11-04 | 2025-06-10 | 0 | 157d | 2025-05-23 | 2025-05-15 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | r&d | multiple | vave | central eu | implementation / execution | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 1.0 | 159.0 | 167.0 | 0.0843373493975904 | 0.0240963855421687 | 0.55421686746988 | 0.337349397590361 | 0.746987951807229 | 0.253012048192771 | current year | not specified | 3 | not specified | not specified | not specified | p | 333 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2024-11-04 | 2025-06-10 | not specified | not specified | 2025-01-28 | 2025-04-22 |  |  | 2025-06-10 | 2025-06-10 | not specified | 0.0 | not specified | -107.0 | not specified | -234.0 | not specified | not specified | 2025-01-28 00:00:00 | 2025-08-07 00:00:00 | not specified | not specified | 2025-09-25 00:00:00 | 2025-09-25 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0 | -107d | dates not set | -107d | -107d | 0.0 | -0.457264957264957 | 0.0 | -0.457264957264957 | -0.457264957264957 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | stage 3 - implementation | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.45
us timekeeping and na payroll enhancements | p-0385 | enhance payroll systems | christina andert | christina andert | project | standalone project | standalone project | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.91 | 2025-01-06 | 2025-08-15 | 160d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | sideways | red | green | red | green | yellow | green | 0 | 0 | 21.0 | 5.0 | 0.0 | 239.0 | 21.0 | 21.0 | 82.0 | 79.0 | 265.0 | 26.0 | 21.0 | 5.0 | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-09-03 | 2025-01-31 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | usd | finance | not specified | not specified | not specified | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 1.0 | 56.0 | 271.0 | 0.0792452830188679 | 0.0188679245283019 | 0.0 | 0.90188679245283 | 0.309433962264151 | 0.690566037735849 | current year | not specified | 3 | not specified | not specified | not specified | p | 335 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | -5.0 | not specified | -50.0 | not specified | -160.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | us timekeeping and na payroll enhancements | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.91
edi strategy germany | 33347 | not specified | lisa schulze-egberding | lisa schulze-egberding | project | standalone project | standalone project | not specified | not specified | it it central eu it-eu | not specified | lisa schulze-egberding | not specified | markus ellinger | markus ellinger | rachael horton-farmer | not specified | other | support functions: global it - europe | it | l3 (planned) | on track | 33347.0 | not specified | project dashboard | project finance dashboard | 0.0 | 2025-01-01 | 2025-06-26 | 127d | wk17: kick-off with pks to discuss project approach; azure devops board created; ongoing discussions with softzoll about contracting | wk17: n/a | wk18: preparation of azure devops board | wk17: n/a | green | angle up | red | red | green | green | yellow | green | 0 | 0 | 6.0 | 54.0 | 15.0 | 0.0 | 22.0 | 22.0 | 75.0 | 75.0 | 75.0 | 75.0 | 75.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-02-20 | 2025-04-28 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | it | not specified | not specified | eu | not specified | not specified | increase revenue | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0.11 | 2025-05-02 | 2026-05-01 | due soon for l3 | not specified | 1.0 | on track | 1.0 | 251.0 | 184.0 | 0.08 | 0.72 | 0.2 | 0.0 | 1.0 | 0.0 | current year | n | 3 | not specified | not specified | 1.0 | p | 338 | 1.0 | 1.0 | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | 0.0 | not specified | -127.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | focussed growth | 0.0 | one | not specified | edi strategy germany | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0
pmo000857 - packaging unif. brilon | p-0389 | germany packaging unification brilon moving from current suppliers for strategic packaging suppliers. | adam keri | adam keri | project | standalone project | standalone project | not specified | not specified | r&d europe r&d europe central r&d europe packaging | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.71 | 2024-11-04 | 2025-06-23 | 166d | approval process closed, commercial discussions ongoing | all samples have been approved by the site | commercial negotiations shall finish soon, first orders to be placed @zeus | no | green | up | red | red | green | green | yellow | green | 0 | 0 | 32.0 | 0.0 | 0.0 | 51.0 | 32.0 | 9.0 | 62.0 | 62.0 | 83.0 | 32.0 | 9.0 | 23.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2024-11-04 | 2025-06-23 | 0 | 166d | 2025-09-15 | 2025-05-15 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | r&d | multiple | vave | central eu | implementation / execution | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 1.0 | 44.0 | 167.0 | 0.385542168674699 | 0.0 | 0.0 | 0.614457831325301 | 0.746987951807229 | 0.253012048192771 | current year | not specified | 3 | not specified | not specified | not specified | p | 339 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2024-11-04 | 2025-06-23 | not specified | not specified | 2025-01-28 | 2025-04-10 |  |  | 2025-05-28 | 2025-06-23 | not specified | 0.0 | not specified | 0.0 | not specified | -166.0 | not specified | not specified | 2025-01-28 00:00:00 | 2025-04-10 00:00:00 | not specified | not specified | 2025-05-28 00:00:00 | 2025-06-23 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0 | 0 | dates not set | 0 | 0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | stage 3 - implementation | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.71
pmo000858 - packaging unif. mittweida | p-0390 | germany packaging unification mittweida moving from current suppliers for strategic packaging suppliers. | adam keri | adam keri | project | standalone project | standalone project | not specified | not specified | r&d europe r&d europe central r&d europe packaging | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.0 | 2024-11-04 | 2025-07-18 | 185d | quote from zeus until 23.05. | samples @zeus to complete datasheets and quote | quotation | escalation @zeus has happend | red | angle down | red | red | green | green | yellow | green | 0 | 0 | 31.0 | 8.0 | 44.0 | 4.0 | 83.0 | 78.0 | 66.0 | 66.0 | 87.0 | 83.0 | 78.0 | 5.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2024-11-04 | 2025-07-18 | 0 | 185d | 2025-05-23 | 2025-05-15 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | r&d | multiple | vave | central eu | development | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 1.0 | 159.0 | 167.0 | 0.35632183908046 | 0.0919540229885058 | 0.505747126436782 | 0.0459770114942529 | 0.758620689655172 | 0.241379310344828 | current year | not specified | 3 | not specified | not specified | not specified | p | 340 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2024-11-04 | 2025-07-18 | not specified | not specified | 2025-04-18 | 2025-05-30 |  |  | 2025-07-18 | 2025-07-18 | not specified | 0.0 | not specified | 0.0 | not specified | -185.0 | not specified | not specified | 2025-04-18 00:00:00 | 2025-05-30 00:00:00 | not specified | not specified | 2025-07-18 00:00:00 | 2025-07-18 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0 | 0 | dates not set | 0 | 0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | stage 2 - development | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0
pmo000859 - packaging unif. emsdetten | p-0391 | germany packaging unification emsdetten moving from current suppliers for strategic packaging suppliers. | adam keri | adam keri | project | standalone project | standalone project | not specified | not specified | r&d europe r&d europe central r&d europe packaging | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.0 | 2024-11-04 | 2025-08-12 | 202d | quotation until 23.05. | no major improvment this month | quotation | situation has been escalated @zeus | red | angle down | red | red | green | green | yellow | green | 0 | 0 | 24.0 | 0.0 | 52.0 | 11.0 | 76.0 | 76.0 | 66.0 | 66.0 | 87.0 | 76.0 | 76.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2024-11-04 | 2025-08-12 | 0 | 202d | 2025-05-23 | 2025-05-15 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | r&d | multiple | vave | central eu | development | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 1.0 | 159.0 | 167.0 | 0.275862068965517 | 0.0 | 0.597701149425287 | 0.126436781609195 | 0.758620689655172 | 0.241379310344828 | current year | not specified | 3 | not specified | not specified | not specified | p | 341 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2024-11-04 | 2025-08-12 | not specified | not specified | 2025-04-29 | 2025-06-24 |  |  | 2025-08-12 | 2025-08-12 | not specified | 0.0 | not specified | 0.0 | not specified | -202.0 | not specified | not specified | 2025-04-29 00:00:00 | 2025-06-24 00:00:00 | not specified | not specified | 2025-08-12 00:00:00 | 2025-08-12 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0 | 0 | dates not set | 0 | 0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | stage 2 - development | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0
pmo000860 - packaging unif. lenti | p-0392 | dach+ packaging unification lenti moving from current suppliers for strategic packaging suppliers. | adam keri | adam keri | project | standalone project | standalone project | not specified | not specified | r&d europe r&d europe central r&d europe packaging | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.0 | 2024-11-04 | 2025-06-02 | 151d | 1st batch os samples have been tested, approved and then approval was withdrawn from higher management | samples partially approved | lenti defines the dates when the prolonged test can be initiated, zeus prepares a quote for the materials until 16.05. | escalation lenti manangement is ongoing | yellow | angle down | red | red | green | green | yellow | green | 0 | 0 | 60.0 | 3.0 | 0.0 | 19.0 | 59.0 | 50.0 | 61.0 | 61.0 | 82.0 | 63.0 | 49.0 | 14.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2024-11-04 | 2025-06-02 | 0 | 151d | 2025-10-13 | 2025-05-15 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | r&d | multiple | vave | central eu | implementation / execution | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 1.0 | 16.0 | 167.0 | 0.731707317073171 | 0.0365853658536585 | 0.0 | 0.231707317073171 | 0.74390243902439 | 0.25609756097561 | current year | not specified | 3 | not specified | not specified | not specified | p | 342 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2024-11-04 | 2025-06-02 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | 0.0 | not specified | -151.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | stage 3 - implementation | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0
implementation of tpm (total productive maintenance) | p-0393 | implementation of tpm at jeld-wen austria (spital, gänserndorf) | markus stockhammer | markus stockhammer | project | standalone project | standalone project | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.0 | 2025-01-01 | 2025-06-26 | 127d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | sideways | red | red | green | green | yellow | green | 0 | 0 | 7.0 | 1.0 | 14.0 | 0.0 | 22.0 | 22.0 | 22.0 | 22.0 | 22.0 | 22.0 | 22.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-03-04 | 2025-02-12 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | transformation | not specified | not specified | eu | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 1.0 | 239.0 | 259.0 | 0.318181818181818 | 0.0454545454545455 | 0.636363636363636 | 0.0 | 1.0 | 0.0 | current year | not specified | 3 | not specified | not specified | not specified | p | 343 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | 0.0 | not specified | -127.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | implementation of tpm (total productive maintenance) | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0
kantenlackierung | 15158 | lackstraße für kantenlackierung - optimierung der durchläufe | jürgen steinberger | jürgen steinberger | project | standalone project | standalone project | not specified | not specified | not specified | not specified | awaiting it pm appointment | not specified | j�rgen steinberger | markus ellinger | rachael horton-farmer | not specified | manufacturing | dach: manufacturing - austria | it | l3 (planned) | some issues | 15158.0 | not specified | project dashboard | project finance dashboard | 0.0 | 2025-01-01 | 2025-06-26 | 127d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | sideways | red | red | green | green | yellow | green | 0 | 0 | 6.0 | 53.0 | 16.0 | 0.0 | 22.0 | 22.0 | 75.0 | 75.0 | 75.0 | 75.0 | 75.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-02-13 | 2025-02-13 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | other | not specified | not specified | eu | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0.2112 | not specified | 1.1 | 2023-12-10 | 2026-06-02 | on plan | not specified | 1.0 | on track | 1.0 | 258.0 | 258.0 | 0.08 | 0.706666666666667 | 0.213333333333333 | 0.0 | 1.0 | 0.0 | current year | n | 3 | not specified | not specified | not specified | p | 344 | 1.0 | 1.0 | 1.0 | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | 0.0 | not specified | -127.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | kantenlackierung | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0
installation team | 12398 | building an installation team to fix claims, set up exhibitions, assembly of small projects, cooperation with dana. this allows us to improve customer service, get more orders and reduce costs, | barbara toth | barbara toth | project | standalone project | standalone project | not specified | not specified | not specified | not specified | not specified | barbara toth | stefan franz mayer | not specified | not specified | not specified | sg&a | dach: commercial - austria steel | hr | l3 (planned) | on track | 12398.0 | not specified | project dashboard | project finance dashboard | 0.0 | 2025-01-01 | 2025-06-26 | 127d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | sideways | red | red | green | green | yellow | green | 0 | 0 | 6.0 | 1.0 | 15.0 | 0.0 | 22.0 | 22.0 | 22.0 | 22.0 | 22.0 | 22.0 | 22.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-02-17 | 2025-02-17 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | transformation | not specified | not specified | eu | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0.69564 | not specified | 0.022 | 2024-02-27 | 2025-07-31 | on plan | not specified | 1.0 | on track | 1.0 | 254.0 | 254.0 | 0.272727272727273 | 0.0454545454545455 | 0.681818181818182 | 0.0 | 1.0 | 0.0 | current year | n | 3 | not specified | not specified | not specified | p | 345 | 1.0 | 1.0 | 1.0 | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | 0.0 | not specified | -127.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | installation team | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0
pmo000499 - multigenius concealed door closer | p-0397 | concealed door closer eco shulte ei 30 (das) validated for fire and nfs | marine cardon | marine cardon | project | standalone project | standalone project | not specified | marine cardon | r&d europe r&d europe france r&d europe uk / france | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.46 | 2024-02-26 | 2026-01-28 | 503d | final phase of industrialization, need to finish implementation of tools for operators and need to plan pre serie test | not specified | need to approved and integrate price in titan finalization of the brochure and website gate 3 p lanned of the 29 of september | not specified | yellow | angle up | red | green | red | green | yellow | green | 0 | 0 | 0.0 | 8.0 | 28.0 | 52.0 | 0.0 | 0.0 | 9.0 | 1.0 | 88.0 | 36.0 | 28.0 | 8.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2024-02-26 | 2025-08-13 | 0 | 383d | 2025-10-24 | 2025-08-07 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | r&d | not specified | not specified | uk / france | implementation / execution | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.870775347912525 | 5.0 | 83.0 | 0.0 | 0.0909090909090909 | 0.318181818181818 | 0.590909090909091 | 0.102272727272727 | 0.897727272727273 | 2026 | not specified | 3 | not specified | not specified | not specified | p | 346 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2024-02-26 | 2025-08-13 | not specified | not specified | 2024-02-26 | 2024-02-26 | 2025-05-01 |  | 2025-08-11 |  | not specified | 0.0 | not specified | -168.0 | not specified | -503.0 | not specified | not specified | 2024-02-26 00:00:00 | 2024-02-26 00:00:00 | 2025-11-19 00:00:00 | not specified | 2026-01-28 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0 | 0 | -202d | -170d | dates not set | 0.0 | 0.0 | -0.401590457256461 | -0.337972166998012 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | not specified | false | stage 3 - implementation | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.46
bridge program | pg-0398 | network strategy | amanda jones | not specified | program | pg-0398 | pg-0398: bridge program | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | program dashboard | finance dashboard | 0.0 | 2025-01-01 | 2026-03-11 | 311d | add the high level status of the program in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | on track | red | on track | red | green | yellow | green | 0 | 0 | 319.0 | 809.0 | 1301.0 | 322.0 | 56.0 | 1684.0 | 967.0 | 346.0 | 2743.0 | 2421.0 | 48.0 | 2373.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 |  | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-10-22 | 2025-10-29 | not specified | 2 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | usd | transformation | not specified | not specified | not specified | see project details | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | 1.0 | not specified | on track | 0.694533762057878 | 7.0 | 0.0 | 0.116296026248633 | 0.294932555596063 | 0.474298213634707 | 0.117389719285454 | 0.352533722201969 | 0.647466277798031 | 2026 | not specified | 2 | not specified | not specified | not specified | pg | 398 | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | [6 empty] | not specified | not specified | not specified | not specified | not specified | -311.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | 2025-02-18 00:00:00 | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0
template | p-0399 | not specified | ryan johnson | ryan johnson | project | pg-0398 | pg-0398: bridge program | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | not specified | 2025-04-18 | 2025-10-23 | 135d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | sideways | red | red | yellow | green | yellow | green | 0 | 0 | 91.0 | 154.0 | 90.0 | 0.0 | 0.0 | 185.0 | 154.0 | 16.0 | 334.0 | 334.0 | 0.0 | 334.0 | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-05-23 | 2025-02-19 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | usd | transformation | not specified | not specified | not specified | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | 1.0 | not specified | on track | 1.0 | 159.0 | 252.0 | 0.272455089820359 | 0.461077844311377 | 0.269461077844311 | 0.0 | 0.461077844311377 | 0.538922155688623 | current year | not specified | 3 | not specified | not specified | 1.0 | p | 347 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | -107.0 | not specified | -119.0 | not specified | -135.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | project a | not specified |  | not specified | 2025-02-19 00:00:00 | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified
sulphur springs | p-0400 | not specified | ryan johnson | ryan johnson | project | pg-0398 | pg-0398: bridge program | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | not specified | 2025-01-24 | 2025-11-06 | 205d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | sideways | red | yellow | red | green | yellow | green | 0 | 0 | 34.0 | 92.0 | 149.0 | 0.0 | 0.0 | 189.0 | 94.0 | 10.0 | 275.0 | 275.0 | 0.0 | 275.0 | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-04-04 | 2025-02-19 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | usd | transformation | not specified | not specified | not specified | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | 1.0 | not specified | on track | 0.970731707317073 | 208.0 | 252.0 | 0.123636363636364 | 0.334545454545455 | 0.541818181818182 | 0.0 | 0.341818181818182 | 0.658181818181818 | current year | not specified | 3 | not specified | not specified | 1.0 | p | 348 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | -23.0 | not specified | -133.0 | not specified | -205.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | project b | not specified |  | not specified | 2025-02-19 00:00:00 | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified
ligonier | p-0401 | not specified | ryan johnson | ryan johnson | project | pg-0398 | pg-0398: bridge program | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | not specified | 2025-07-01 | 2026-03-11 | 182d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | sideways | red | yellow | red | green | yellow | green | 0 | 0 | 0.0 | 79.0 | 195.0 | 0.0 | 0.0 | 195.0 | 84.0 | 11.0 | 274.0 | 274.0 | 0.0 | 274.0 | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-05-22 | 2025-02-19 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | usd | transformation | not specified | not specified | not specified | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | 1.0 | not specified | on track | 0.478021978021978 | 160.0 | 252.0 | 0.0 | 0.288321167883212 | 0.711678832116788 | 0.0 | 0.306569343065693 | 0.693430656934307 | 2026 | not specified | 3 | not specified | not specified | 1.0 | p | 349 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | -181.0 | not specified | -258.0 | not specified | -182.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | project c | not specified |  | not specified | 2025-02-19 00:00:00 | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified
chiloquin | p-0402 | not specified | ryan johnson | ryan johnson | project | pg-0398 | pg-0398: bridge program | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | not specified |  |  | #invalid data type | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | sideways | yellow | yellow | schedule not set | green | yellow | green | 0 | 0 | 62.0 | 62.0 | 82.0 | 322.0 | 10.0 | 138.0 | 197.0 | 188.0 | 526.0 | 204.0 | 2.0 | 202.0 | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-10-22 | 2025-02-19 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | usd | transformation | not specified | not specified | not specified | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | 1.0 | not specified | on track | 0.0 | 7.0 | 252.0 | 0.11787072243346 | 0.11787072243346 | 0.155893536121673 | 0.612167300380228 | 0.374524714828897 | 0.625475285171103 | not specified | not specified | 3 | not specified | not specified | 1.0 | p | 350 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | project d | not specified |  | not specified | 2025-02-19 00:00:00 | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified
grinnell | p-0403 | not specified | ryan johnson | ryan johnson | project | pg-0398 | pg-0398: bridge program | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | not specified |  |  | #invalid data type | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | sideways | yellow | yellow | schedule not set | green | yellow | green | 0 | 0 | 110.0 | 149.0 | 70.0 | 0.0 | 0.0 | 186.0 | 148.0 | 10.0 | 329.0 | 329.0 | 0.0 | 329.0 | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-06-10 | 2025-02-19 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | usd | transformation | not specified | not specified | not specified | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | 1.0 | not specified | on track | 0.0 | 141.0 | 252.0 | 0.334346504559271 | 0.452887537993921 | 0.212765957446809 | 0.0 | 0.449848024316109 | 0.550151975683891 | not specified | not specified | 3 | not specified | not specified | 1.0 | p | 351 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | project e | not specified |  | not specified | 2025-02-19 00:00:00 | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified
venice | p-0404 | not specified | ryan johnson | ryan johnson | project | pg-0398 | pg-0398: bridge program | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | not specified |  |  | #invalid data type | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | sideways | yellow | yellow | schedule not set | green | yellow | green | 0 | 0 | 0.0 | 12.0 | 182.0 | 0.0 | 0.0 | 182.0 | 21.0 | 15.0 | 192.0 | 192.0 | 0.0 | 192.0 | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-03-10 | 2025-02-19 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | usd | transformation | not specified | not specified | not specified | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | 1.0 | not specified | on track | 0.0 | 233.0 | 252.0 | 0.0 | 0.0625 | 0.947916666666667 | 0.0 | 0.109375 | 0.890625 | not specified | not specified | 3 | not specified | not specified | 1.0 | p | 352 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | project f | not specified |  | not specified | 2025-02-19 00:00:00 | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified
ringtown | p-0405 | not specified | ryan johnson | ryan johnson | project | pg-0398 | pg-0398: bridge program | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.0 | 2025-01-01 | 2025-06-26 | 127d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | sideways | green | green | green | green | yellow | green | 0 | 0 | 0.0 | 41.0 | 186.0 | 0.0 | 1.0 | 186.0 | 46.0 | 10.0 | 224.0 | 224.0 | 1.0 | 223.0 | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-03-10 | 2025-02-19 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | usd | transformation | not specified | not specified | not specified | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | 1.0 | not specified | on track | 1.0 | 233.0 | 252.0 | 0.0 | 0.183035714285714 | 0.830357142857143 | 0.0 | 0.205357142857143 | 0.794642857142857 | current year | not specified | 3 | not specified | not specified | 1.0 | p | 353 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | 0.0 | not specified | -127.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | project g | not specified |  | not specified | 2025-02-19 00:00:00 | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0
se site | p-0406 | not specified | ryan johnson | ryan johnson | project | pg-0398 | pg-0398: bridge program | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.0 | 2025-01-01 | 2025-06-26 | 127d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | sideways | green | green | green | green | yellow | green | 0 | 0 | 4.0 | 118.0 | 154.0 | 0.0 | 1.0 | 186.0 | 98.0 | 29.0 | 276.0 | 276.0 | 1.0 | 275.0 | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-03-25 | 2025-02-19 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | usd | transformation | not specified | not specified | not specified | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | 1.0 | not specified | on track | 1.0 | 218.0 | 252.0 | 0.0144927536231884 | 0.427536231884058 | 0.557971014492754 | 0.0 | 0.355072463768116 | 0.644927536231884 | current year | not specified | 3 | not specified | not specified | 1.0 | p | 354 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | 0.0 | not specified | -127.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | project h | not specified |  | not specified | 2025-02-19 00:00:00 | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0
coral springs | p-0419 | not specified | ryan johnson | ryan johnson | project | pg-0398 | pg-0398: bridge program | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.0 | 2025-01-01 | 2025-06-26 | 127d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | sideways | red | red | green | green | yellow | green | 0 | 0 | 7.0 | 1.0 | 14.0 | 0.0 | 22.0 | 22.0 | 22.0 | 22.0 | 22.0 | 22.0 | 22.0 | 0.0 | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-03-05 | 2025-02-28 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | usd | transformation | not specified | not specified | not specified | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | 1.0 | not specified | on track | 1.0 | 238.0 | 243.0 | 0.318181818181818 | 0.0454545454545455 | 0.636363636363636 | 0.0 | 1.0 | 0.0 | current year | not specified | 3 | not specified | not specified | 1.0 | p | 367 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | 0.0 | not specified | -127.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | coral springs | not specified |  | not specified | 2025-02-28 00:00:00 | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0
ludlow | p-0420 | not specified | ryan johnson | ryan johnson | project | pg-0398 | pg-0398: bridge program | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | not specified | 2025-04-21 | 2026-01-20 | 197d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | sideways | red | yellow | red | green | yellow | green | 0 | 0 | 4.0 | 100.0 | 165.0 | 0.0 | 0.0 | 193.0 | 81.0 | 13.0 | 269.0 | 269.0 | 0.0 | 269.0 | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-06-10 | 2025-02-28 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | usd | transformation | not specified | not specified | not specified | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | 1.0 | not specified | on track | 0.700507614213198 | 141.0 | 243.0 | 0.0148698884758364 | 0.371747211895911 | 0.613382899628253 | 0.0 | 0.301115241635688 | 0.698884758364312 | 2026 | not specified | 3 | not specified | not specified | 1.0 | p | 368 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | -110.0 | not specified | -208.0 | not specified | -197.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | ludlow | not specified |  | not specified | 2025-02-28 00:00:00 | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified
grand rapids | p-0421 | not specified | ryan johnson | ryan johnson | project | pg-0398 | pg-0398: bridge program | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.0 | 2025-01-01 | 2025-06-26 | 127d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | sideways | red | red | green | green | yellow | green | 0 | 0 | 7.0 | 1.0 | 14.0 | 0.0 | 22.0 | 22.0 | 22.0 | 22.0 | 22.0 | 22.0 | 22.0 | 0.0 | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-03-05 | 2025-02-28 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | usd | transformation | not specified | not specified | not specified | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | 1.0 | not specified | on track | 1.0 | 238.0 | 243.0 | 0.318181818181818 | 0.0454545454545455 | 0.636363636363636 | 0.0 | 1.0 | 0.0 | current year | not specified | 3 | not specified | not specified | 1.0 | p | 369 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | 0.0 | not specified | -127.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | grand rapids | not specified |  | not specified | 2025-02-28 00:00:00 | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0
quarterly tax provision | p-0407 | quarterly tax provision process tracker | joel wiggins | joel wiggins | project | standalone project | standalone project | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.77 | 2025-05-15 | 2025-08-15 | 67d | test | etr pending stock comp | test | test | green | down | red | red | red | green | green | green | 0 | 0 | 19.0 | 0.0 | 0.0 | 25.0 | 16.0 | 9.0 | 0.0 | 0.0 | 44.0 | 19.0 | 6.0 | 13.0 | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-09-15 | 2025-06-30 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | usd | finance | not specified | not specified | global | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 1.0 | 44.0 | 121.0 | 0.431818181818182 | 0.0 | 0.0 | 0.568181818181818 | 0.0 | 1.0 | current year | not specified | 3 | not specified | not specified | not specified | p | 355 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-03-07 | 2025-05-12 | not specified | not specified | [6 empty] | not specified | -69.0 | not specified | -95.0 | not specified | -67.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | quarterly tax provision | not specified |  | not specified | 2025-02-21 00:00:00 | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.77
calibration machine for core layer production | p-0417 | replacement of an old calibration machine and improvements to safety | christoph gösweiner | christoph gösweiner | project | standalone project | standalone project | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 1.0 | 2025-01-21 | 2025-06-06 | 99d | assembly in progress | machine on site and extraction ready | commissioning of the machine | if support is needed, check the support needed flag and provide detail. | green | sideways | green | blue | green | green | yellow | green | 0 | 0 | 0.0 | 0.0 | 3.0 | 30.0 | 0.0 | 3.0 | 33.0 | 33.0 | 33.0 | 3.0 | 0.0 | 3.0 | 158823.529411764 | 147058.823529411 | 11764.7058823529 | 105882.352941176 | 105882.352941176 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 105882.352941176 | 105882.352941176 | 0.0 | 0.0 | 52941.1764705881 | 41176.4705882352 | 11764.7058823529 | 0.333333333333334 | 0.280000000000001 | 1 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-08-29 | 2025-03-28 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 135000.0 | 125000.0 | 10000.0 | 90000.0 | 90000.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 90000.0 | 90000.0 | 0.0 | 0.0 | 45000.0 | 35000.0 | 10000.0 | 0.333333333333333 | 0.28 | 1.0 | not specified | active | eur | other | not specified | not specified | eu | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 1.0 | 61.0 | 215.0 | 0.0 | 0.0 | 0.0909090909090909 | 0.909090909090909 | 1.0 | 0.0 | current year | not specified | 3 | not specified | not specified | not specified | p | 365 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | -20.0 | not specified | 20.0 | not specified | -99.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | calibration machine for core layer production | not specified |  | not specified | 2025-02-24 00:00:00 | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 1
test training | p-0418 | not specified | marine cardon | marine cardon | project | standalone project | standalone project | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.49 | 2025-03-01 | 2025-03-12 | 8d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | sideways | red | red | green | green | yellow | green | 0 | 0 | 0.0 | 26.0 | 58.0 | 0.0 | 0.0 | 0.0 | 84.0 | 84.0 | 84.0 | 84.0 | 78.0 | 6.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-10-02 | 2025-02-25 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | r&d | not specified | not specified | uk / france | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 1.0 | 27.0 | 246.0 | 0.0 | 0.30952380952381 | 0.690476190476191 | 0.0 | 1.0 | 0.0 | current year | not specified | 3 | not specified | not specified | 1.0 | p | 366 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | -59.0 | not specified | 106.0 | not specified | -8.0 | not specified | not specified | 2026-02-24 00:00:00 | not specified | 2026-12-16 00:00:00 | not specified | 2027-03-26 00:00:00 | 2027-11-05 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | 2025-02-25 00:00:00 | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.49
dana - people-development | p-0422 | development of qualification matrix / training matrix to build up pillars / knowledge carriers and relieve the existing ones | georg schmid | bernhard maierhofer | project | standalone project | standalone project | not specified | not specified | at-strategy | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.0 | 2025-01-02 | 2028-05-18 | 881d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | sideways | red | red | red | green | yellow | red | 0 | 0 | 8.0 | 0.0 | 14.0 | 0.0 | 8.0 | 9.0 | 22.0 | 22.0 | 22.0 | 22.0 | 22.0 | 0.0 | 12.9411764705882 | 11.7647058823529 | 1.17647058823529 | 17.6470588235294 | 0.0 | 17.6470588235294 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 17.6470588235294 | 0.0 | 17.6470588235294 | 0.0 | -4.70588235294116 | 11.7647058823529 | -16.4705882352941 | -0.363636363636363 | 1.0 | -14 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-04-14 | 2025-03-10 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 11.0 | 10.0 | 1.0 | 15.0 | 0.0 | 15.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 15.0 | 0.0 | 15.0 | 0.0 | -4.0 | 10.0 | -14.0 | -0.363636363636364 | 1.0 | -14.0 | not specified | active | eur | other | not specified | not specified | eu | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.244040862656073 | 198.0 | 233.0 | 0.363636363636364 | 0.0 | 0.636363636363636 | 0.0 | 1.0 | 0.0 | 2028 | not specified | 3 | not specified | not specified | not specified | p | 370 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | -1.0 | not specified | -1057.0 | not specified | -881.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | dana - people-development | not specified |  | not specified | 2025-03-10 00:00:00 | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0
dana - safety | p-0423 | introduction & improvement/harmonization of safety standards | georg schmid | bernhard maierhofer | project | standalone project | standalone project | not specified | not specified | at-strategy | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.0 | 2025-01-01 | 2025-06-26 | 127d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | sideways | red | red | green | green | yellow | green | 0 | 0 | 12.0 | 0.0 | 10.0 | 0.0 | 22.0 | 22.0 | 22.0 | 22.0 | 22.0 | 22.0 | 22.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-03-24 | 2025-03-10 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | other | not specified | not specified | eu | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 1.0 | 219.0 | 233.0 | 0.545454545454545 | 0.0 | 0.454545454545455 | 0.0 | 1.0 | 0.0 | current year | not specified | 3 | not specified | not specified | not specified | p | 371 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | 0.0 | not specified | -127.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | dana - safety | not specified |  | not specified | 2025-03-10 00:00:00 | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0
dana - quality-compliance | p-0424 | development of quality standards / sustainable processes | georg schmid | bernhard maierhofer | project | standalone project | standalone project | not specified | not specified | at-strategy | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.0 | 2025-01-01 | 2025-06-26 | 127d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | sideways | red | red | green | green | yellow | green | 0 | 0 | 12.0 | 0.0 | 10.0 | 0.0 | 22.0 | 22.0 | 22.0 | 22.0 | 22.0 | 22.0 | 22.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-03-24 | 2025-03-10 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | other | not specified | not specified | eu | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 1.0 | 219.0 | 233.0 | 0.545454545454545 | 0.0 | 0.454545454545455 | 0.0 | 1.0 | 0.0 | current year | not specified | 3 | not specified | not specified | not specified | p | 372 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | 0.0 | not specified | -127.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | dana - quality-compliance | not specified |  | not specified | 2025-03-10 00:00:00 | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0
dana - otif | p-0425 | improving delivery performance internally and to suppliers | georg schmid | bernhard maierhofer | project | standalone project | standalone project | not specified | not specified | at-strategy | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.0 | 2025-01-01 | 2025-06-26 | 127d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | sideways | red | red | green | green | yellow | green | 0 | 0 | 12.0 | 0.0 | 10.0 | 0.0 | 22.0 | 22.0 | 22.0 | 22.0 | 22.0 | 22.0 | 22.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-03-24 | 2025-03-10 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | other | not specified | not specified | eu | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 1.0 | 219.0 | 233.0 | 0.545454545454545 | 0.0 | 0.454545454545455 | 0.0 | 1.0 | 0.0 | current year | not specified | 3 | not specified | not specified | not specified | p | 374 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | 0.0 | not specified | -127.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | dana - otif | not specified |  | not specified | 2025-03-10 00:00:00 | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0
dana - cost performance | p-0426 | reduction of manufacturing costs & automation roadmap incl. tpm harmonization | georg schmid | bernhard maierhofer | project | standalone project | standalone project | not specified | not specified | at-strategy | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.0 | 2025-01-01 | 2025-06-26 | 127d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | sideways | red | red | green | green | yellow | green | 0 | 0 | 15.0 | 0.0 | 7.0 | 0.0 | 22.0 | 22.0 | 22.0 | 22.0 | 22.0 | 22.0 | 22.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-04-14 | 2025-03-10 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | other | not specified | not specified | eu | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 1.0 | 198.0 | 233.0 | 0.681818181818182 | 0.0 | 0.318181818181818 | 0.0 | 1.0 | 0.0 | current year | not specified | 3 | not specified | not specified | not specified | p | 375 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | 0.0 | not specified | -127.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | dana - cost performance | not specified |  | not specified | 2025-03-10 00:00:00 | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0
dana - ease of doing business | p-0427 | interface optimization in configurators / erp systems / improvement of sg&a costs | georg schmid | bernhard maierhofer | project | standalone project | standalone project | not specified | not specified | at-strategy | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.0 | 2025-01-01 | 2025-06-26 | 127d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | sideways | red | red | green | green | yellow | green | 0 | 0 | 12.0 | 0.0 | 10.0 | 0.0 | 22.0 | 22.0 | 22.0 | 22.0 | 22.0 | 22.0 | 22.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-03-24 | 2025-03-10 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | other | not specified | not specified | eu | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 1.0 | 219.0 | 233.0 | 0.545454545454545 | 0.0 | 0.454545454545455 | 0.0 | 1.0 | 0.0 | current year | not specified | 3 | not specified | not specified | not specified | p | 376 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | 0.0 | not specified | -127.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | dana - ease of doing business | not specified |  | not specified | 2025-03-10 00:00:00 | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0
dana - innovation | p-0428 | new product developments & marketing | georg schmid | bernhard maierhofer | project | standalone project | standalone project | not specified | not specified | at-strategy | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.0 | 2025-01-01 | 2025-06-26 | 127d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | sideways | red | red | green | green | yellow | green | 0 | 0 | 12.0 | 0.0 | 10.0 | 0.0 | 22.0 | 22.0 | 22.0 | 22.0 | 22.0 | 22.0 | 22.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-03-10 | 2025-03-10 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | other | not specified | not specified | eu | not specified | not specified | not specified | on track | on track | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 1.0 | 233.0 | 233.0 | 0.545454545454545 | 0.0 | 0.454545454545455 | 0.0 | 1.0 | 0.0 | current year | not specified | 3 | not specified | not specified | not specified | not specified | 377 | not specified | not specified | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | 0.0 | not specified | -127.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | dana - innovation | not specified |  | not specified | 2025-03-10 00:00:00 | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0
domoferm - people-development | p-0429 | development of qualification matrix / training matrix to build up pillars / knowledge carriers and relieve the existing ones | georg schmid | georg schmid | project | standalone project | standalone project | not specified | not specified | at-strategy | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.0 | 2025-01-01 | 2025-06-26 | 127d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | sideways | red | red | green | green | yellow | green | 0 | 0 | 9.0 | 0.0 | 13.0 | 0.0 | 22.0 | 22.0 | 22.0 | 22.0 | 22.0 | 22.0 | 22.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-03-10 | 2025-03-10 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | other | not specified | not specified | eu | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 1.0 | 233.0 | 233.0 | 0.409090909090909 | 0.0 | 0.590909090909091 | 0.0 | 1.0 | 0.0 | current year | not specified | 3 | not specified | not specified | not specified | p | 378 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | 0.0 | not specified | -127.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | domoferm - people-development | not specified |  | not specified | 2025-03-10 00:00:00 | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0
domoferm - safety | p-0430 | introduction & improvement/harmonization of safety standards | georg schmid | georg schmid | project | standalone project | standalone project | not specified | not specified | at-strategy | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.0 | 2025-01-01 | 2025-06-26 | 127d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | sideways | red | red | green | green | yellow | green | 0 | 0 | 9.0 | 0.0 | 13.0 | 0.0 | 22.0 | 22.0 | 22.0 | 22.0 | 22.0 | 22.0 | 22.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-03-10 | 2025-03-10 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | other | not specified | not specified | eu | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 1.0 | 233.0 | 233.0 | 0.409090909090909 | 0.0 | 0.590909090909091 | 0.0 | 1.0 | 0.0 | current year | not specified | 3 | not specified | not specified | not specified | p | 379 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | 0.0 | not specified | -127.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | domoferm - safety | not specified |  | not specified | 2025-03-10 00:00:00 | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0
domoferm - quality-compliance | p-0431 | development of quality standards / sustainable processes | georg schmid | georg schmid | project | standalone project | standalone project | not specified | not specified | at-strategy | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.0 | 2025-01-01 | 2025-06-26 | 127d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | sideways | red | red | green | green | yellow | green | 0 | 0 | 9.0 | 0.0 | 13.0 | 0.0 | 22.0 | 22.0 | 22.0 | 22.0 | 22.0 | 22.0 | 22.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-03-10 | 2025-03-10 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | other | not specified | not specified | eu | not specified | not specified | not specified | on track | on track | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 1.0 | 233.0 | 233.0 | 0.409090909090909 | 0.0 | 0.590909090909091 | 0.0 | 1.0 | 0.0 | current year | not specified | 3 | not specified | not specified | not specified | not specified | 380 | not specified | not specified | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | 0.0 | not specified | -127.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | domoferm - quality-compliance | not specified |  | not specified | 2025-03-10 00:00:00 | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0
domoferm - otif | p-0432 | improving delivery performance internally and to suppliers | georg schmid | georg schmid | project | standalone project | standalone project | not specified | not specified | at-strategy | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.0 | 2025-01-01 | 2025-06-26 | 127d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | sideways | red | red | green | green | yellow | green | 0 | 0 | 9.0 | 0.0 | 13.0 | 0.0 | 22.0 | 22.0 | 22.0 | 22.0 | 22.0 | 22.0 | 22.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-03-10 | 2025-03-10 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | other | not specified | not specified | eu | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 1.0 | 233.0 | 233.0 | 0.409090909090909 | 0.0 | 0.590909090909091 | 0.0 | 1.0 | 0.0 | current year | not specified | 3 | not specified | not specified | not specified | p | 381 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | 0.0 | not specified | -127.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | domoferm - otif | not specified |  | not specified | 2025-03-10 00:00:00 | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0
domoferm - cost performance | p-0433 | reduction of manufacturing costs & automation roadmap incl. tpm harmonization | georg schmid | georg schmid | project | standalone project | standalone project | not specified | not specified | at-strategy | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.0 | 2025-01-01 | 2025-06-26 | 127d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | sideways | red | red | green | red | yellow | green | 1 | 0 | 22.0 | 0.0 | 0.0 | 0.0 | 22.0 | 22.0 | 22.0 | 22.0 | 22.0 | 22.0 | 22.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-07-07 | 2025-03-10 | not specified | 1 | 1.0 | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | other | not specified | not specified | eu | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 1.0 | 114.0 | 233.0 | 1.0 | 0.0 | 0.0 | 0.0 | 1.0 | 0.0 | current year | not specified | 3 | not specified | not specified | not specified | p | 382 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | 0.0 | not specified | -127.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | domoferm - cost performance | not specified |  | not specified | 2025-03-10 00:00:00 | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0
domoferm - ease of doing business | p-0434 | interface optimization in configurators / erp systems / improvement of sg&a costs | georg schmid | georg schmid | project | standalone project | standalone project | not specified | not specified | at-strategy | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.0 | 2025-01-01 | 2025-06-26 | 127d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | sideways | red | red | green | green | yellow | green | 0 | 0 | 9.0 | 0.0 | 13.0 | 0.0 | 22.0 | 22.0 | 22.0 | 22.0 | 22.0 | 22.0 | 22.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-03-10 | 2025-03-10 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | other | not specified | not specified | eu | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 1.0 | 233.0 | 233.0 | 0.409090909090909 | 0.0 | 0.590909090909091 | 0.0 | 1.0 | 0.0 | current year | not specified | 3 | not specified | not specified | not specified | p | 383 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | 0.0 | not specified | -127.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | domoferm - ease of doing business | not specified |  | not specified | 2025-03-10 00:00:00 | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0
domoferm - innovation | p-0435 | new product developments & marketing | georg schmid | georg schmid | project | standalone project | standalone project | not specified | not specified | at-strategy | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.0 | 2025-01-01 | 2025-06-26 | 127d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | sideways | red | red | green | green | yellow | green | 0 | 0 | 9.0 | 0.0 | 13.0 | 0.0 | 22.0 | 22.0 | 22.0 | 22.0 | 22.0 | 22.0 | 22.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-03-10 | 2025-03-10 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | other | not specified | not specified | eu | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 1.0 | 233.0 | 233.0 | 0.409090909090909 | 0.0 | 0.590909090909091 | 0.0 | 1.0 | 0.0 | current year | not specified | 3 | not specified | not specified | not specified | p | 384 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | 0.0 | not specified | -127.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | domoferm - innovation | not specified |  | not specified | 2025-03-10 00:00:00 | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0
digital product data transformation | 69785 | single source of truth for product data via new business processes and singl cad/pdm/plm solution | adam painter | adam painter | project | standalone project | standalone project | not specified | not specified | it it-eu | not specified | not specified | not specified | glyn hauser | not specified | not specified | not specified | not specified | uk: commercial | it | submitted for l1 approval | on track | 69785.0 | not specified | project dashboard | project finance dashboard | 0.0 | 2025-01-01 | 2025-06-26 | 127d | reporting starts when project enters stage l3 | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | sideways | red | red | green | green | yellow | green | 0 | 0 | 12.0 | 54.0 | 9.0 | 0.0 | 22.0 | 22.0 | 75.0 | 50.0 | 75.0 | 75.0 | 75.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-03-27 | 2025-03-17 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | it | not specified | not specified | eu | not specified | not specified | compliance | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not planned (l2 to l4) | not specified | 1.0 | on track | 1.0 | 216.0 | 226.0 | 0.16 | 0.72 | 0.12 | 0.0 | 1.0 | 0.0 | current year | n | 3 | not specified | not specified | not specified | p | 385 | 1.0 | 1.0 | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | 0.0 | not specified | -127.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | improved performance | 0.0 | one | not specified | digital product data transformation | not specified |  | not specified | 2025-03-10 00:00:00 | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0
eu basware deployment (sap cfin locations) | 72724 | deploy basware for locations in eu currently on sap cfin (delta scope to current project) | adam painter | adam painter | project | standalone project | standalone project | not specified | not specified | it it-eu | not specified | not specified | not specified | not specified | adam painter | rachael horton - farmer | not specified | not specified | not specified | not specified | not specified | on track | 72724.0 | not specified | project dashboard | project finance dashboard | 0.0 | 2025-09-05 | 2025-09-26 | 16d | reporting starts when project enters stage l3 | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | sideways | red | yellow | red | green | yellow | green | 0 | 0 | 4.0 | 168.0 | 0.0 | 0.0 | 4.0 | 4.0 | 172.0 | 76.0 | 172.0 | 172.0 | 65.0 | 107.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-09-29 | 2025-03-17 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | it | not specified | not specified | eu | not specified | not specified | ktlo | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | 1.0 | on track | 1.0 | 30.0 | 226.0 | 0.0232558139534884 | 0.976744186046512 | 0.0 | 0.0 | 1.0 | 0.0 | current year | n | 3 | not specified | not specified | not specified | p | 386 | 1.0 | 1.0 | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | -247.0 | not specified | -92.0 | not specified | -16.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | focussed growth | 0.0 | one | not specified | eu basware deployment (sap cfin locations) | not specified |  | not specified | 2025-03-10 00:00:00 | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0
edi rakvere | 70507 | not specified | amer basic | amer basic | project | standalone project | standalone project | not specified | not specified | it it-eu | not specified | amer basic | not specified | artur sevtsuk | peter sørensen | peter sørensen | not specified | not specified | not specified | not specified | not specified | on track | 70507.0 | not specified | project dashboard | project finance dashboard | 0.0 | 2025-01-01 | 2025-06-26 | 127d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | blue | sideways | red | red | green | green | yellow | green | 0 | 0 | 22.0 | 53.0 | 0.0 | 0.0 | 22.0 | 22.0 | 75.0 | 50.0 | 75.0 | 75.0 | 75.0 | 0.0 | 0.0 | 0.0 | 0.0 | 16465.094117647 | 16465.094117647 | 0.0 | 0.0 | 54122.9294117645 | 54122.9294117645 | 0.0 | 0.0 | 70588.0235294115 | 70588.0235294115 | 0.0 | 0.0 | -70588.0235294115 | -70588.0235294115 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-07-21 | 2025-09-16 | not specified | 1 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 13995.33 | 13995.33 | 0.0 | 0.0 | 46004.49 | 46004.49 | 0.0 | 0.0 | 59999.82 | 59999.82 | 0.0 | 0.0 | -59999.82 | -59999.82 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | completed | eur | it | not specified | not specified | eu | ideation | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | 1.0 | 1.0 | on track | 1.0 | 100.0 | 43.0 | 0.293333333333333 | 0.706666666666667 | 0.0 | 0.0 | 1.0 | 0.0 | current year | n | 3 | not specified | not specified | 1.0 | p | 387 | 1.0 | 1.0 | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | 0.0 | not specified | -127.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | edi rakvere | not specified |  | not specified | 2025-03-14 00:00:00 | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0
pmo000724 - remove lipping liners glazed fds | p-0439 | remove lipping liners from glazed fds in penrith | hamish white | glyn hauser | project | standalone project | standalone project | not specified | not specified | r&d europe uk r&d europe uk / france | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.51 | 2025-03-01 | 2025-11-14 | 185d | - fpc audit to be completed in august - planned certificate update late nov - customer feedback due mid-nov - g3-4 delayed due to certificate issue date | - fpc audit to be completed in august - planned certificate update late nov - customer feedback due mid-nov - g3-4 delayed due to certificate issue date | - fpc audit to be completed in august - planned certificate update late nov - customer feedback due mid-nov - g3-4 delayed due to certificate issue date | not specified | green | sideways | yellow | yellow | yellow | green | yellow | green | 0 | 0 | 1.0 | 16.0 | 6.0 | 39.0 | 1.0 | 11.0 | 12.0 | 12.0 | 62.0 | 23.0 | 18.0 | 5.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-29 | 2025-03-01 | 2025-11-06 | 0 | 179d | 2025-10-29 | 2025-10-29 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | r&d | interior | npd | uk / france | development | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.935135135135135 | 0.0 | 0.0 | 0.0161290322580645 | 0.258064516129032 | 0.0967741935483871 | 0.629032258064516 | 0.193548387096774 | 0.806451612903226 | current year | not specified | 3 | not specified | not specified | not specified | p | 388 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-03-01 | 2025-11-06 | not specified | not specified | 2025-07-10 | 2025-07-10 | 2025-11-06 |  | 2025-11-06 |  | not specified | 0.0 | not specified | -8.0 | not specified | -185.0 | not specified | not specified | 2025-07-10 00:00:00 | 2025-07-10 00:00:00 | 2025-11-06 00:00:00 | not specified | 2025-11-06 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0 | 0 | 0 | 0 | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | 2025-03-19 00:00:00 | false | stage 2 - development | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.51
pmo000208 - extra trimmable door | p-0440 | increase size of stiles to allow additional trimming | mark hartley | scott mcbride | project | standalone project | standalone project | not specified | scott mcbride | r&d europe uk r&d europe uk / france | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.99 | 2024-03-01 | 2025-06-05 | 330d | gates 1-4 passed 29th may | not specified | not specified | not specified | green | up | yellow | green | yellow | green | yellow | green | 0 | 0 | 0.0 | 5.0 | 0.0 | 59.0 | 0.0 | 0.0 | 5.0 | 5.0 | 64.0 | 5.0 | 5.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-06-03 | 2025-06-03 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | completed | eur | r&d | interior | npd | uk / france | realize value / close / care period | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 1.0 | 148.0 | 148.0 | 0.0 | 0.078125 | 0.0 | 0.921875 | 0.078125 | 0.921875 | current year | not specified | 3 | not specified | not specified | not specified | p | 389 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | 306.0 | not specified | 21.0 | not specified | -330.0 | not specified | not specified | 2025-05-29 00:00:00 | 2025-05-29 00:00:00 | 2025-05-29 00:00:00 | not specified | 2025-05-29 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | 2025-03-19 00:00:00 | false | stage 5 - care period | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.99
pmo000728 - bridgemere moulded range | 64707 | introduction of a new range of moulded doors for howdens joinery in the uk. | mark hartley | scott mcbride | project | standalone project | standalone project | not specified | scott mcbride | r&d europe uk r&d europe uk / france | not specified | it pm not required | not specified | ross hawkings | adam painter | rachael horton-farmer | not specified | npi / npd | uk: commercial | engineering; it | l2 (validated) | on hold | 64707.0 | not specified | project dashboard | project finance dashboard | 0.99 | 2024-03-01 | 2025-04-17 | 295d | - passed gate 17th april | - passed gate 17th april | - actions around the 10k skins | not specified | green | sideways | yellow | green | yellow | green | yellow | green | 0 | 0 | 0.0 | 5.0 | 0.0 | 64.0 | 0.0 | 0.0 | 69.0 | 69.0 | 69.0 | 5.0 | 5.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-06-03 | 2025-06-25 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | completed | eur | r&d | interior | npd | uk / france | realize value / close / care period | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | 1.0 | on track | 1.0 | 148.0 | 126.0 | 0.0 | 0.072463768115942 | 0.0 | 0.927536231884058 | 1.0 | 0.0 | current year | not specified | 3 | not specified | not specified | not specified | p | 390 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | 306.0 | not specified | 70.0 | not specified | -295.0 | not specified | not specified | 2025-04-17 00:00:00 | 2025-04-17 00:00:00 | 2025-04-17 00:00:00 | not specified | 2025-04-17 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | 2025-03-19 00:00:00 | false | stage 5 - care period | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.99
pmo000344-1 - swedoor range 3 - el560 electronic lock | p-0442 | re-introduction/testing of the el560 lock to get it back into certification | olar vallimaa | scott mcbride | project | standalone project | standalone project | not specified | scott mcbride | r&d europe north r&d europe uk r&d europe uk / france | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.0 | 2025-01-23 | 2026-04-30 | 331d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | sideways | red | yellow | red | green | yellow | green | 0 | 0 | 25.0 | 6.0 | 61.0 | 0.0 | 49.0 | 54.0 | 92.0 | 92.0 | 92.0 | 92.0 | 88.0 | 4.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-05-23 | 2025-06-03 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | completed | eur | r&d | interior | npd | north eu | initiation / validation / feasibility | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.604229607250755 | 159.0 | 148.0 | 0.271739130434783 | 0.0652173913043478 | 0.66304347826087 | 0.0 | 1.0 | 0.0 | 2026 | not specified | 3 | not specified | not specified | not specified | p | 391 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | -22.0 | not specified | -308.0 | not specified | -331.0 | not specified | not specified | 2025-05-27 00:00:00 | 2025-09-02 00:00:00 | 2026-03-12 00:00:00 | not specified | 2026-04-30 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | 2025-03-20 00:00:00 | false | stage 1 - feasibility | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0
pmo000448-3 - oak lite doorkits | p-0443 | development of a doorkit solution using the oak lite skin/door | mark hartley | scott mcbride | project | standalone project | standalone project | not specified | scott mcbride | r&d europe uk r&d europe uk / france | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.12 | 2025-04-17 | 2026-04-21 | 264d | - latest trial in sheffield on edge-bander was very successful - gives a great finish - plan to complete another trial (25th july) using a larger batch of oak lite doors (manufactured and varnished in penrith then edge-banded in sheffield) | - latest trial in sheffield on edge-bander was very successful - gives a great finish | - plan to complete another trial using a larger batch of oak lite doors (manufactured and varnished in penrith then edge-banded in sheffield) | not specified | green | angle up | red | green | red | green | yellow | green | 0 | 0 | 0.0 | 12.0 | 50.0 | 8.0 | 0.0 | 9.0 | 54.0 | 54.0 | 70.0 | 62.0 | 52.0 | 10.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-10-07 | 2025-07-17 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | completed | eur | r&d | interior | npd | uk / france | initiation / validation / feasibility | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.53030303030303 | 22.0 | 104.0 | 0.0 | 0.171428571428571 | 0.714285714285714 | 0.114285714285714 | 0.771428571428572 | 0.228571428571428 | 2026 | not specified | 3 | not specified | not specified | not specified | p | 392 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | -106.0 | not specified | -299.0 | not specified | -264.0 | not specified | not specified | 2025-12-18 00:00:00 | 2026-01-13 00:00:00 | 2026-03-03 00:00:00 | not specified | 2026-04-21 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | 2025-03-20 00:00:00 | false | stage 1 - feasibility | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.12
pmo000666 - omnitec lock systems & salto ælements fusion | p-0444 | implement omnictec lock systems and salto ælements fusion into a selection of our hp doors. | kira svane kristensen | kira svane kristensen | project | standalone project | standalone project | not specified | kira svane kristensen | r&d europe | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.64 | 2025-04-09 | 2025-06-10 | 45d | week 21 assortment alignment still ongoing with stc. stc will have discussion with legal to get a conclusion. decision to pause project for two weeks until a discussion have been reached. | project paused until assortment discussion is done. | new stc meeting booked for 3. june. | need support from stc on how to move forward with project regarding assortment (compliance cases on products), and timeline misalignment between r&d and pm. | yellow | down | red | yellow | green | red | yellow | green | 4 | 0 | 1.0 | 45.0 | 0.0 | 19.0 | 1.0 | 0.0 | 45.0 | 5.0 | 65.0 | 46.0 | 41.0 | 5.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-07-01 | 2025-09-02 | 0 | 46d | 2025-07-23 | 2025-05-23 | true | 4 | not specified | not specified | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | on-hold | eur | r&d | not specified | not specified | eu | initiation / validation / feasibility | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 1.0 | 98.0 | 159.0 | 0.0153846153846154 | 0.692307692307692 | 0.0 | 0.292307692307692 | 0.692307692307692 | 0.307692307692308 | current year | not specified | 3 | not specified | not specified | not specified | p | 393 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-07-01 | 2025-09-02 | not specified | not specified | [6 empty] | not specified | 83.0 | not specified | 84.0 | not specified | -45.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | 2025-04-07 00:00:00 | false | stage 1 - feasibility | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.64
daily resources | p-0445 | not specified | marine cardon | marine cardon | project | standalone project | standalone project | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.0 | 2025-01-01 | 2025-06-26 | 127d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | sideways | red | red | green | green | green | green | 0 | 0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d |  | 2025-04-08 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | other | not specified | not specified | eu | ideation | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 1.0 | not specified | 204.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 1.0 | current year | not specified | 3 | not specified | not specified | 1.0 | p | 394 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | 0.0 | not specified | -127.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | 2025-04-08 00:00:00 | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0
pmo0000836 ed 2.0 wave 2 | 75078 | exterior door strategy hierarchy 2.0 tactical projects phase 1 with deadline april 2026 to fit the commerical plan | boel sandberg | boel sandberg | project | standalone project | standalone project | not specified | boel sandberg | r&d europe r&d europe north | not specified | not specified | boel sandberg | erik lundgren | not specified | not specified | not specified | manufacturing | nordics: manufacturing - latvia | engineering | l3 (planned) | on track | 75078.0 | not specified | project dashboard | project finance dashboard | 0.5 | 2025-03-16 | 2026-04-24 | 290d | project moved to stage 3 after gate 2 approval | gate 2 approval | external testing | not specified | green | angle up | red | green | yellow | red | yellow | green | 7 | 0 | 23.0 | 21.0 | 79.0 | 109.0 | 23.0 | 80.0 | 49.0 | 40.0 | 232.0 | 123.0 | 25.0 | 98.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-03-16 | 2026-03-17 | 0 | 262d | 2025-10-17 | 2025-09-22 | not specified | 9 | 1.0 | not specified | 0 | 1 | 2 | 1 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | r&d | not specified | not specified | north eu | implementation / execution | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not planned (l2 to l4) | not specified | 1.0 | on track | 0.562068965517241 | 12.0 | 37.0 | 0.0991379310344828 | 0.0905172413793104 | 0.34051724137931 | 0.469827586206897 | 0.211206896551724 | 0.788793103448276 | 2026 | n | 3 | not specified | not specified | not specified | p | 395 | 1.0 | 1.0 | not specified | not specified | not specified | not specified | 2025-03-16 | 2026-03-17 | not specified | not specified | 2025-05-22 | 2025-08-18 | 2025-11-14 |  | 2026-03-17 |  | not specified | 0.0 | not specified | -38.0 | not specified | -290.0 | not specified | not specified | 2025-05-22 00:00:00 | 2025-09-18 00:00:00 | 2026-01-02 00:00:00 | not specified | 2026-04-24 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0 | -31d | -49d | -38d | dates not set | 0.0 | -0.106896551724138 | -0.168965517241379 | -0.131034482758621 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | 2025-04-09 00:00:00 | false | stage 3 - implementation | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.5
pmo0000839 ed 2.0 wave 3 | 75079 | exterior door strategy hierarchy 2.0 tactical projects phase 2 with longer time plan to implement operational savings | boel sandberg | boel sandberg | project | standalone project | standalone project | not specified | boel sandberg | r&d europe r&d europe north | not specified | not specified | boel sandberg | erik lundgren | not specified | not specified | not specified | manufacturing | nordics: manufacturing - latvia | engineering | l3 (planned) | on track | 75079.0 | not specified | project dashboard | project finance dashboard | 0.26 | 2025-03-10 | 2027-01-20 | 488d | stage 2 establish detailed sample planning for all doors required to do test in wave 3 | gate 1 approval | not specified | not specified | green | sideways | red | red | red | red | yellow | green | 6 | 0 | 13.0 | 1.0 | 53.0 | 26.0 | 2.0 | 64.0 | 59.0 | 59.0 | 93.0 | 67.0 | 0.0 | 67.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-07-01 | 2025-09-02 | 0 | 46d | 2025-10-27 | 2025-06-16 | not specified | 20 | not specified | not specified | 0 | 0 | 2 | 0 | 2 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | r&d | not specified | not specified | north eu | development | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not planned (l2 to l4) | not specified | 1.0 | on track | 0.344262295081967 | 2.0 | 135.0 | 0.139784946236559 | 0.010752688172043 | 0.56989247311828 | 0.279569892473118 | 0.634408602150538 | 0.365591397849462 | 2027 | n | 3 | not specified | not specified | not specified | p | 396 | 1.0 | 1.0 | not specified | not specified | not specified | not specified | 2025-07-01 | 2025-09-02 | not specified | not specified | [6 empty] | not specified | 113.0 | not specified | -505.0 | not specified | -488.0 | not specified | not specified | 2025-06-12 00:00:00 | not specified | not specified | not specified | 2026-12-23 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | 2025-04-09 00:00:00 | false | stage 2 - development | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.26
zeiterfassung wfm | p-0451 | not specified | lara engemann | lara engemann | project | standalone project | standalone project | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.0 | 2025-01-01 | 2025-06-26 | 127d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | sideways | red | red | green | green | yellow | green | 0 | 0 | 15.0 | 1.0 | 6.0 | 0.0 | 22.0 | 22.0 | 22.0 | 22.0 | 22.0 | 22.0 | 22.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-04-17 | 2025-04-17 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | transformation | not specified | not specified | eu | ideation | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 1.0 | 195.0 | 195.0 | 0.681818181818182 | 0.0454545454545455 | 0.272727272727273 | 0.0 | 1.0 | 0.0 | current year | not specified | 3 | not specified | not specified | 1.0 | p | 400 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | 0.0 | not specified | -127.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | zeiterfassung wfm | not specified |  | not specified | 2025-04-17 00:00:00 | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0
pmo000761 extension of wall connections | p-0452 | not specified | andrás fejes | andrás fejes | project | standalone project | standalone project | not specified | andrás fejes | r&d europe r&d europe central | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.2 | 2025-04-07 | 2026-01-08 | 199d | michael fabschitz had to take over from gerald -> he is overloaded now, priority of this topic has to be discussed with jürgen | - | market req. analysis by mf | i need discussion with jürgen, how mf should prioritize this topic in his todo list | yellow | angle down | red | green | red | green | green | green | 0 | 2 | 0.0 | 0.0 | 11.0 | 8.0 | 0.0 | 0.0 | 0.0 | 0.0 | 19.0 | 11.0 | 10.0 | 1.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-04-07 | 2025-12-04 | 0 | 174d | 2025-10-22 | 2025-10-22 | true | 2 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | r&d | steel | vave | central eu | commercialization / go-live | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.743718592964824 | 7.0 | 7.0 | 0.0 | 0.0 | 0.578947368421053 | 0.421052631578947 | 0.0 | 1.0 | 2026 | not specified | 3 | not specified | not specified | 1.0 | p | 401 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-04-07 | 2025-12-04 | not specified | not specified | 2025-05-23 |  |  |  | 2025-12-04 |  | not specified | 0.0 | not specified | -35.0 | not specified | -199.0 | not specified | not specified | 2025-05-23 00:00:00 | not specified | not specified | not specified | 2025-12-02 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0 | dates not set | dates not set | 2d | dates not set | 0.0 | 0.0 | 0.0 | 0.0100502512562814 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | 2025-04-29 00:00:00 | false | stage 4 - commercialization | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.2
pluto | p-0455 | warehouse strategy | sam graves | sam graves | project | standalone project | standalone project | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.33 | 2025-01-01 | 2025-12-15 | 249d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | sideways | red | red | red | green | yellow | green | 0 | 0 | 78.0 | 8.0 | 45.0 | 14.0 | 29.0 | 120.0 | 116.0 | 114.0 | 145.0 | 131.0 | 23.0 | 108.0 | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-09-02 | 2025-05-14 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | usd | transformation | not specified | not specified | not specified | ideation | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.867469879518072 | 57.0 | 168.0 | 0.537931034482759 | 0.0551724137931035 | 0.310344827586207 | 0.096551724137931 | 0.8 | 0.2 | current year | not specified | 3 | not specified | not specified | not specified | p | 404 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | -172.0 | not specified | -249.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | pluto | not specified |  | not specified | 2025-05-14 00:00:00 | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.33
supply chain planning technology | 75265 | implement minimum viable product ibp for sap to replace the current titan based plants supply planning process and tools | ryan russel | chris long | project | standalone project | standalone project | not specified | not specified | it na/corporate | not specified | chris long | chris long | steve cooney | christian suarez | kirk kroft | not specified | supply chain | na - ops: supply chain | it | l3 (planned) | on track | 75265.0 | not specified | project dashboard | project finance dashboard | 0.61 | 2025-05-07 | 2026-01-28 | 191d | it gate l3 was passed on 3/15. we are pending final tmo l2 approval and moving directly to l3 tmo approval. we are finalizing cerf and sow documentation for quick execution | not specified | l2 approval, finalize and socialize cerf and sow. complete wave l3 items (kpi, impacts, milestones & risks | no support needed | green | sideways | red | green | red | red | yellow | yellow | 2 | 0 | 0.0 | 53.0 | 35.0 | 7.0 | 6.0 | 9.0 | 95.0 | 95.0 | 95.0 | 88.0 | 71.0 | 17.0 | 520139.0 | 385183.0 | 134956.0 | 180974.0 | 133515.0 | 47459.0 | 32640.0 | 353184.0 | 278828.0 | 74356.0 | 51200.0 | 534158.0 | 412343.0 | 121815.0 | 83840.0 | -14019.0 | -27160.0 | 13141.0 | -0.0269524107978829 | -0.0705119384811895 | 0.0973724769554522 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-10-16 | 2025-09-16 | not specified | 3 | not specified | not specified | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 442118.15 | 327405.55 | 114712.6 | 153827.9 | 113487.75 | 40340.15 | 27744.0 | 300206.4 | 237003.8 | 63202.6 | 43520.0 | 454034.3 | 350491.55 | 103542.75 | 71264.0 | -11916.15 | -23086.0 | 11169.85 | 0.0 | 0.0 | 0.0 | not specified | active | usd | it | not specified | not specified | not specified | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 2025-05-30 | 2025-09-09 | on plan | not specified | 1.0 | on track | 0.659685863874346 | 13.0 | 43.0 | 0.0 | 0.557894736842105 | 0.368421052631579 | 0.0736842105263158 | 1.0 | 0.0 | 2026 | n | 3 | not specified | not specified | not specified | p | 405 | 1.0 | 1.0 | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | -126.0 | not specified | -216.0 | not specified | -191.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | supply chain planning technology | not specified |  | not specified | 2025-05-14 00:00:00 | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.61
pmo000896 - new bathroom doors with pvc edges | p-0458 | change bathroom door type 1 & wetroom door type 2 from alu edges to pvc. reduce assortment in type 1. project to secure all documentation to be changed and implement new construction . | kira svane kristensen | kira svane kristensen | project | standalone project | standalone project | not specified | kira svane kristensen | r&d europe r&d europe north | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.98 | 2025-06-11 | 2025-10-10 | 88d | week 40 launch week. websites and m&f updated for launch. | websites and m&f updated. photographer have recieved doors. | sustainability. scenery pictures. | no support needed. | green | up | red | green | red | red | yellow | green | 4 | 1 | 1.0 | 1.0 | 1.0 | 60.0 | 2.0 | 1.0 | 1.0 | 0.0 | 63.0 | 3.0 | 1.0 | 2.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-06-11 | 2025-09-25 | 0 | 77d | 2025-10-07 | 2025-10-03 | not specified | 5 | not specified | not specified | 2 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | r&d | interior | npd | north eu | realize value / close / care period | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 1.0 | 22.0 | 26.0 | 0.0158730158730159 | 0.0158730158730159 | 0.0158730158730159 | 0.952380952380952 | 0.0158730158730159 | 0.984126984126984 | current year | not specified | 3 | not specified | not specified | not specified | p | 406 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-06-11 | 2025-09-25 | not specified | not specified | 2025-08-14 |  | 2025-09-25 |  | 2025-09-25 |  | not specified | 0.0 | not specified | -15.0 | not specified | -88.0 | not specified | not specified | 2025-08-14 00:00:00 | not specified | 2025-09-25 00:00:00 | not specified | 2025-09-25 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0 | dates not set | 0 | 0 | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | 2025-05-28 00:00:00 | false | stage 5 - care period | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.98
pmo000737 - high security steel door rc4 for scandinavia | p-0459 | get rc4 doors from tammer approved in our product certifications and implemented into the business erp systems. | kira svane kristensen | kira svane kristensen | project | standalone project | standalone project | not specified | kira svane kristensen | r&d europe r&d europe north | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.96 | 2025-06-11 | 2025-10-13 | 89d | week 41 implementation completed, except for labels at tammer. postponement of gate and launch due to labels. | erp update done. erp sent for verification mounting instructions | labels clarification with tammer. gate 3+4 - expected 16/10. | no support needed. | green | angle up | red | green | yellow | red | green | green | 2 | 0 | 3.0 | 1.0 | 4.0 | 45.0 | 8.0 | 3.0 | 0.0 | 0.0 | 53.0 | 8.0 | 3.0 | 5.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-06-11 | 2025-10-03 | 0 | 83d | 2025-10-09 | 2025-10-09 | not specified | 3 | not specified | not specified | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | r&d | steel | npd | north eu | implementation / execution | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 1.0 | 20.0 | 20.0 | 0.0566037735849057 | 0.0188679245283019 | 0.0754716981132076 | 0.849056603773585 | 0.0 | 1.0 | current year | not specified | 3 | not specified | not specified | not specified | p | 407 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-06-11 | 2025-10-03 | not specified | not specified | 2025-07-03 |  | 2025-09-25 |  | 2025-09-25 |  | not specified | 0.0 | not specified | -10.0 | not specified | -89.0 | not specified | not specified | 2025-07-03 00:00:00 | not specified | 2025-10-09 00:00:00 | not specified | 2025-10-09 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0 | dates not set | -14d | -14d | dates not set | 0.0 | 0.0 | -0.157303370786517 | -0.157303370786517 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | 2025-05-28 00:00:00 | false | stage 3 - implementation | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.96
automation after trim saw operations - garland | 13644 | automated downstack, paint, and wrap | casey haynes | casey haynes | project | standalone project | standalone project | not specified | not specified | not specified | not specified | not specified | not specified | casey haynes | not specified | not specified | not specified | manufacturing | na - doors & dist.: manufacturing - south central | engineering | l3 (planned) | on hold | 13644.0 | not specified | project dashboard | project finance dashboard | 0.71 | 2024-06-06 | 2026-01-26 | 428d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | sideways | red | green | red | red | green | green | 5 | 0 | 2.0 | 1.0 | 75.0 | 53.0 | 13.0 | 10.0 | 0.0 | 0.0 | 131.0 | 78.0 | 75.0 | 3.0 | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-09-02 | 2025-05-28 | not specified | 39 | not specified | not specified | 0 | 1 | 2 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | usd | engineering | not specified | not specified | not specified | ideation | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 2.822856 | not specified | 7.537 | 2025-01-21 | 2026-10-07 | on plan | not specified | 1.0 | on track | 0.852803738317757 | 57.0 | 154.0 | 0.0152671755725191 | 0.00763358778625954 | 0.572519083969466 | 0.404580152671756 | 0.0 | 1.0 | 2026 | n | 3 | not specified | not specified | not specified | p | 408 | 1.0 | 1.0 | 1.0 | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | 209.0 | not specified | -214.0 | not specified | -428.0 | not specified | not specified | not specified | not specified | not specified | 2026-01-12 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | automation after trim saw operations - garland | not specified |  | not specified | 2025-05-28 00:00:00 | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.71
pmo000889 - red oak thresholds | p-0461 | project scope is to evaluate the opportunity for changing the current threshold standard in ne changed to red oak, and ensure implementation if feasible. there is a indication of a €500k saving on vs. the current white oak which is the main objective for wanting to start the project now. important focus areas to investigate: is a special treatment to get the appearance of white oak needed? if so what is the cost and complexity of implementation. implementation to market requires a smooth transition with a 1:1 appearance to avoid having to recall, or accepting customer sending back, their current inventory. additionally what is the number of suppliers we will be working with and a decision for changing from beech to red oak in dk. | kira svane kristensen | kira svane kristensen | project | standalone project | standalone project | not specified | kira svane kristensen | r&d europe r&d europe north | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.39 | 2025-06-04 | 2025-12-10 | 136d | week 41 decision to take evalution meeting of thresholds on 11/11. discussions with sherwin on recipe and grimslöv and leigola on getting 100pcs orders. | sherwin will have recipe ready 14/10. after that startup 100pcs orders. leigola to begin 100pcs order. | 100pcs batches. evaluation meeting | no support needed. | green | angle up | red | green | yellow | red | green | green | 3 | 0 | 0.0 | 0.0 | 24.0 | 19.0 | 0.0 | 3.0 | 0.0 | 0.0 | 43.0 | 24.0 | 23.0 | 1.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-06-04 | 2025-12-04 | 0 | 132d | 2025-10-09 | 2025-10-09 | not specified | 3 | not specified | not specified | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | r&d | interior | vave | north eu | development | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.779411764705882 | 20.0 | 20.0 | 0.0 | 0.0 | 0.558139534883721 | 0.441860465116279 | 0.0 | 1.0 | current year | not specified | 3 | not specified | not specified | not specified | p | 409 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-06-04 | 2025-12-04 | not specified | not specified | 2025-06-26 | 2025-10-09 | 2025-12-04 |  | 2025-12-04 |  | not specified | 0.0 | not specified | -6.0 | not specified | -136.0 | not specified | not specified | 2025-06-26 00:00:00 | 2025-11-19 00:00:00 | 2025-12-04 00:00:00 | not specified | 2025-12-04 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0 | -41d | 0 | 0 | dates not set | 0.0 | -0.301470588235294 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | 2025-06-04 00:00:00 | false | stage 2 - development | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.39
pmo000642 - become a licenced door processor | pg-0463 | become a licenced door processor | richard bertram | scott mcbride | program | pg-0463 | pg-0463: pmo000642 - become a licenced door processor | not specified | scott mcbride | r&d europe r&d europe uk r&d europe uk / france | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | program dashboard | finance dashboard | 0.637594840667678 | 2024-05-06 | 2025-12-23 | 427d | add the high level status of the program in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | on track | red | on track | green | green | yellow | green | 0 | 0 | 105.0 | 64.0 | 50.0 | 253.0 | 114.0 | 35.0 | 191.0 | 191.0 | 464.0 | 211.0 | 91.0 | 120.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 |  | 2024-05-06 | 2025-12-23 | 0 | 427d | 2025-10-23 | 2025-10-29 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 2 | 0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | r&d | interior | npd | uk | see project details | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.908665105386417 | 6.0 | 0.0 | 0.226293103448276 | 0.137931034482759 | 0.107758620689655 | 0.545258620689655 | 0.411637931034483 | 0.588362068965517 | current year | not specified | 2 | not specified | not specified | not specified | pg | 463 | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | [6 empty] | not specified | not specified | not specified | not specified | not specified | -427.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | 2025-06-10 00:00:00 | false | not specified | 1.0 | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.63759
pmo000642 - ldp - 3 - pmo | p-0462 | become a licenced door processor | lisa ward | scott mcbride | project | pg-0463 | pg-0463: pmo000642 - become a licenced door processor | not specified | scott mcbride | r&d europe r&d europe uk r&d europe uk / france | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.39 | 2024-05-06 | 2025-12-12 | 420d | - updating the project based on tollgate deliverables - adding proof of deliverables to activities - compiling gate doc - plan is to go to gate 20th nov | - updating the project based on tollgate deliverables - adding proof of deliverables to activities - compiling gate doc - plan is to go to gate 20th nov | - compiling gate doc - plan is to go to gate 20th nov | not specified | yellow | angle up | red | yellow | red | green | yellow | green | 0 | 0 | 0.0 | 32.0 | 14.0 | 23.0 | 5.0 | 6.0 | 69.0 | 69.0 | 69.0 | 46.0 | 40.0 | 6.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-29 | 2024-05-06 | 2025-10-03 | 0 | 370d | 2025-10-07 | 2025-10-29 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | r&d | interior | npd | uk / france | commercialization / go-live | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.923809523809524 | 22.0 | 0.0 | 0.0 | 0.463768115942029 | 0.202898550724638 | 0.333333333333333 | 1.0 | 0.0 | current year | not specified | 3 | not specified | not specified | not specified | p | 410 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2024-05-06 | 2025-10-03 | not specified | not specified |  | 2025-10-03 |  |  |  |  | not specified | 0.0 | not specified | -70.0 | not specified | -420.0 | not specified | not specified | not specified | 2025-11-07 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | -35d | dates not set | dates not set | dates not set | 0.0 | -0.0833333333333333 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | 2025-06-04 00:00:00 | false | stage 4 - commercialization | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.39
pmo000642 - ldp - 1 - design and development | p-0464 | become a licenced door processor - design and development | tony pell | tony pell | project | pg-0463 | pg-0463: pmo000642 - become a licenced door processor | not specified | not specified | r&d europe r&d europe uk r&d europe uk / france | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.99 | 2025-06-09 | 2025-11-19 | 118d | deliver p1 - 2 design and development rules completed and handed over to ops for pre-production testing. deliver p3 - 4 design and development rules completed and handed over to titan team to allow set up complete in titan. design and development sits at 99% completion. - effectively 100% but 1% left to cover any queries raised following launch | specification guides issued ands circulated - ongoing revisions will be issued. document control process in place | resolve any issues fed back form sales and ops now we are live with the specification guide drawings and cnc programmes etc await detail of new smoke fire and security foa required to confirm what hardware and other specification amends we need to make to our existing range offer in process of setting up etc. await further news from halspan regarding trada response to latest test results. | not specified | green | up | red | green | red | yellow | yellow | green | 3 | 0 | 1.0 | 0.0 | 4.0 | 63.0 | 1.0 | 0.0 | 7.0 | 7.0 | 68.0 | 5.0 | 0.0 | 5.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-06-09 | 2025-11-03 | 0 | 106d | 2025-10-23 | 2025-10-23 | not specified | 3 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | r&d | interior | npd | uk | commercialization / go-live | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.872881355932203 | 6.0 | 6.0 | 0.0147058823529412 | 0.0 | 0.0588235294117647 | 0.926470588235294 | 0.102941176470588 | 0.897058823529412 | current year | not specified | 3 | not specified | not specified | not specified | p | 411 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-06-09 | 2025-11-03 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | -16.0 | not specified | -118.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | 2025-06-10 00:00:00 | false | stage 4 - commercialization | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.99
pmo000642 - ldp - 5 - estimating, scheduling and commercial | p-0468 | pmo000642 - ldp - estimating, scheduling and commercial | phil boardman | phil boardman | project | pg-0463 | pg-0463: pmo000642 - become a licenced door processor | not specified | not specified | r&d europe r&d europe uk r&d europe uk / france | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.74 | 2025-06-08 | 2025-12-23 | 142d | 1 - further review or functional review including external sales, completed create a clear post and pre order function inline with target markets and growth 1 - delivery confirmation package waiting for follow up with pm on o&m manual & technical drawings 2 - training phase phase 1-4 titan 3 - visibility of the full specification document to support estimating and sales." | 1 - further review or functional review including external sales, completed create a clear post and pre order function inline with target markets and growth | 1 - delivery confirmation package waiting for follow up with pm on o&m manual & technical drawings 2 - training phase phase 1-4 titan 3 - visibility of the full specification document to support estimating and sales. | not specified | green | on track | red | green | green | red | yellow | green | 1 | 0 | 5.0 | 0.0 | 5.0 | 20.0 | 5.0 | 3.0 | 5.0 | 5.0 | 30.0 | 10.0 | 3.0 | 7.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-06-08 | 2025-12-23 | 0 | 142d | 2025-10-22 | 2025-10-02 | not specified | 1 | not specified | not specified | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | r&d | interior | npd | uk | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.725352112676056 | 7.0 | 27.0 | 0.166666666666667 | 0.0 | 0.166666666666667 | 0.666666666666667 | 0.166666666666667 | 0.833333333333333 | current year | not specified | 3 | not specified | not specified | not specified | p | 415 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-06-08 | 2025-12-23 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | 0.0 | not specified | -142.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | 2025-06-10 00:00:00 | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.74
pmo000642 - ldp - 2 - titan set-up | p-0469 | pmo000642 - ldp - titan set-up | tony pell | tony pell | project | pg-0463 | pg-0463: pmo000642 - become a licenced door processor | not specified | not specified | r&d europe r&d europe uk r&d europe uk / france | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 1.0 | 2025-06-09 | 2025-10-15 | 93d | deliver p1 - 2 set up at 100% deliver p3 - 4 set up at 100% overall project sits at 100% completion. | final items set up. new extension question added. new sill option added. launched to live | ongoing feedback from sales and ops reviewed and changes implemented as required | not specified | green | up | red | blue | red | green | yellow | green | 0 | 0 | 0.0 | 0.0 | 0.0 | 50.0 | 0.0 | 0.0 | 6.0 | 6.0 | 50.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-06-09 | 2025-09-29 | 0 | 81d | 2025-10-23 | 2025-10-23 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | r&d | interior | npd | uk | commercialization / go-live | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 1.0 | 6.0 | 6.0 | 0.0 | 0.0 | 0.0 | 1.0 | 0.12 | 0.88 | current year | not specified | 3 | not specified | not specified | not specified | p | 416 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-06-09 | 2025-09-29 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | -16.0 | not specified | -93.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | 2025-06-10 00:00:00 | false | stage 4 - commercialization | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 1
pmo000642 - ldp - 7 - marketing | p-0470 | pmo000642 - ldp - marketing | lisa ward | lisa ward | project | pg-0463 | pg-0463: pmo000642 - become a licenced door processor | not specified | not specified | r&d europe r&d europe uk r&d europe uk / france | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.82 | 2025-06-16 | 2025-10-31 | 100d | ongoing progress. | samples labels signed off. awaiting costs and timings. marketing working through briefs, awaiting timings. 3rd party supplier checklist meeting with quality. a/w timings and costs for samples bags. | 3rd party supplier checklist meeting with purchasing.. veneer photography monday. sample process to be documented and items set up in titan. | not specified | yellow | sideways | red | green | red | green | yellow | green | 0 | 1 | 3.0 | 0.0 | 8.0 | 3.0 | 7.0 | 0.0 | 13.0 | 13.0 | 14.0 | 11.0 | 0.0 | 11.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-06-16 | 2025-10-01 | 0 | 78d | 2025-10-13 | 2025-10-02 | not specified | 1 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | r&d | interior | npd | uk | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.98 | 16.0 | 27.0 | 0.214285714285714 | 0.0 | 0.571428571428571 | 0.214285714285714 | 0.928571428571429 | 0.071428571428571 | current year | not specified | 3 | not specified | not specified | not specified | p | 417 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-06-16 | 2025-10-01 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | -30.0 | not specified | -100.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | 2025-06-10 00:00:00 | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.82
pmo000642 - ldp - 8 - product costs, data and pricing control | p-0471 | pmo000642 - ldp - product costs, data and pricing control | keith murgatroyd | keith murgatroyd | project | pg-0463 | pg-0463: pmo000642 - become a licenced door processor | not specified | not specified | r&d europe r&d europe uk r&d europe uk / france | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.28 | 2025-06-16 | 2025-12-23 | 137d | product offer full componentry list cost build-up list for each componentry data progress tracker ratify all material costs inc all vendors set-up and maintained by procurementl. moqs sales visibility pricing cost model, vendor and selling price monthly review - who & when pipeline cocpq requires updating in line with prodcut offer p1 to 4 june 25. ldp calulator working correctly. trained out to sales & estimating pb pbd titan list price drivers | arranged scoping session with tp & cb to walk through current cost calculator components and update and confirm the correct materials and costs - 2 hours session with more to come as progress is made current pricing calculator updated to include costs of glass & glazing - further updates to follow once information confirmed current titan vendor items & costs downloaded - this may change as and when new items are set up and confirmed | schedule further working sessions with tp & cb to update the data with a view to building a list price driver database also progress being made with infor on cpq phase 2 development including integration with titan to automate attribution of items once selected in cpq then to pull costs from titan to allow understanding of quote margins on cpq and loa approval process being developed in cpq to eventually replace the salesforce process once developed initial salesforce reports on quotes indicated as won where an loa approval is and is not present - discussion tomorrow on how to develop this and how to progress with checking quotes won / orders placed on an ongoing basis | work with tp and others | green | sideways | red | red | green | green | yellow | green | 0 | 0 | 8.0 | 0.0 | 4.0 | 1.0 | 9.0 | 0.0 | 13.0 | 13.0 | 13.0 | 12.0 | 0.0 | 12.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-06-16 | 2025-12-23 | 0 | 137d | 2025-10-10 | 2025-07-17 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | r&d | interior | npd | uk | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.715328467153285 | 19.0 | 104.0 | 0.615384615384615 | 0.0 | 0.307692307692308 | 0.0769230769230769 | 1.0 | 0.0 | current year | not specified | 3 | not specified | not specified | not specified | p | 418 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-06-16 | 2025-12-23 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | 0.0 | not specified | -137.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | 2025-06-10 00:00:00 | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.28
pmo000642 - ldp - 6 - external sales specification | p-0472 | pmo000642 - ldp - external sales specification | philip berry | philip berry | project | pg-0463 | pg-0463: pmo000642 - become a licenced door processor | not specified | not specified | r&d europe r&d europe uk r&d europe uk / france | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.65 | 2025-06-16 | 2025-12-15 | 131d | product offer standard offer complete. p1 & 2 training this week 2nd october at assa abloy showroom. sales visibility dashboard established. action required to calibrate input and accuracy. pby pbd pricing loa control in place. discounts in place. new vetting process put in place. need to align prices on both pricings tools. pipeline control new areas live on salesforce pipeline visible with strategy to define accurately. account plans being developed. specification guide in progress with tony pell | further training yet to be booked. tony pell discussion for p5 priority completed with actions on an excel template. sales visibility - plotting and forecasting for q4 & q1 2026 up to date. pricing - loa process complete. new cpq discounts in place. orders to be placed to be requoted on revision 9 of the excel template. pipeline control - meeting with phil boardman on wednesday to run through reports. specification guide - in progress with tony pell. | next training tbc - either assa abloy foundations course for specification or visit a commercial door factory. sales visibility - ongoing - new estimator starting so quotations can be completed. pricing - as previous keeping new orders to the correct dm. pipeline control - moving forward with phil boardman meeting on accounts. specification guide - need tony pell to run through with the team. | phil boardman and tony pell | green | angle up | red | red | green | green | yellow | green | 0 | 0 | 10.0 | 0.0 | 6.0 | 3.0 | 9.0 | 0.0 | 19.0 | 19.0 | 19.0 | 16.0 | 2.0 | 14.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-06-16 | 2025-12-15 | 0 | 131d | 2025-10-20 | 2025-10-20 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | completed | eur | r&d | interior | npd | uk | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.748091603053435 | 9.0 | 9.0 | 0.526315789473684 | 0.0 | 0.315789473684211 | 0.157894736842105 | 1.0 | 0.0 | current year | not specified | 3 | not specified | not specified | not specified | p | 419 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-06-16 | 2025-12-15 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | 0.0 | not specified | -131.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | 2025-06-10 00:00:00 | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.65
pmo000642 - ldp - 9 - objectives and timelines | p-0473 | pmo000642 - ldp - objectives and timelines | richard bertram | richard bertram | project | pg-0463 | pg-0463: pmo000642 - become a licenced door processor | not specified | not specified | r&d europe r&d europe uk r&d europe uk / france | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.93 | 2025-06-16 | 2025-10-31 | 100d | sales to fill last quarter. pipeline required. build a leadership mindset focused on accountability, coaching, and consistency. increase engagement, ownership, and cross-functional collaboration. align structures, systems, and behaviours to support cultural shift and in order to achieve what is required. agree on an operating model for running commercial door sets. develop a business readiness plan and develop a project plan to ensure that jw uk are ready to “launch” (sales, product, systems, operations, supply chain and marketing are all ready). a targeted culture transformation is required to create a sustainable foundation for operational excellence, business recovery, and long-term growth. | lhg at £170k in manufacture. wembley park c34k. farrons ldp c20k. highbury london access control construction c203k. process flow completed. structures and systems completed ready for objective meeting as high level status started sample process / samples for approval for sales. developed 5th october h/o presentation for circulation. | p 1 to 3 ops fmea review. p3 to 4 fmea. business planning modules. org structures now, y26, 5m & 10m. samples manufacture. process flow & objectives rollout. feedback presentation to co-rordinate | skills cover hang and glaze / cnc ops. set for 500 sets week without kaval. | green | angle up | green | green | green | green | yellow | green | 0 | 0 | 0.0 | 0.0 | 9.0 | 13.0 | 0.0 | 0.0 | 1.0 | 1.0 | 22.0 | 9.0 | 0.0 | 9.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-06-16 | 2025-10-31 | 0 | 100d | 2025-10-21 | 2025-10-21 | not specified | 0 | 1.0 | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | completed | eur | r&d | interior | npd | uk | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.98 | 8.0 | 8.0 | 0.0 | 0.0 | 0.409090909090909 | 0.590909090909091 | 0.0454545454545455 | 0.954545454545455 | current year | not specified | 3 | not specified | not specified | not specified | p | 420 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-06-16 | 2025-10-31 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | 0.0 | not specified | -100.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | 2025-06-10 00:00:00 | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.93
pmo000642 - ldp - 4 - supply chain & manufacture (qa & otif) | p-0476 | pmo000642 - ldp - 4 - supply chain & manufacture (qa & otif) | russell hurst | chris williams | project | pg-0463 | pg-0463: pmo000642 - become a licenced door processor | not specified | not specified | r&d europe r&d europe uk r&d europe uk / france | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.82 | 2025-06-16 | 2025-09-30 | 77d | overall project health still in red and the dash is showing no change at 82% despite progressing another 12 sets on the p1-p2 trial open actions still showing as 77 as we start to complete the p1-p2 trials, work is now being undertaken to progress p3-p4 the resulting actions from the p1-p2 fmea now stands at over 600 sub workstream as follows. supply chain - 92% sourcing - 98% inventory - 77% production planning - 90% manufacturing - 72% qa,sop's and training - 52% | po's raised for p3-p4 non stocked items p3-p4 orders currently being scheduled. just waiting for review from production then we'll feedback to tony another 12 sets of the trial due to complete over the weekend | complete the scheduling and planning phase of p3-p4 spotlight the tenoning, glazing and assembly processes as the first areas to complete the fmea action plan meeting booked with ray friday morning to finish creating the capacity planning tool split down by ldp, internal and external sets | r&d attendance at fmea daily meeting for the next 2 weeks to provide quicker resolution to queries (alejadro attended, thankyou) sales guidance on stock profile for hardware and sundry items (still required) please, please, please can someone align our handing orientation with the rest of the industry | yellow | sideways | red | red | green | green | yellow | green | 3 | 2 | 78.0 | 32.0 | 0.0 | 77.0 | 78.0 | 26.0 | 58.0 | 58.0 | 179.0 | 102.0 | 46.0 | 56.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-06-16 | 2025-09-30 | 0 | 77d | 2025-10-09 | 2025-10-09 | not specified | 7 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | r&d | interior | npd | uk | planning | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 1.0 | 20.0 | 20.0 | 0.435754189944134 | 0.17877094972067 | 0.0 | 0.430167597765363 | 0.324022346368715 | 0.675977653631285 | current year | not specified | 3 | not specified | not specified | not specified | p | 423 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-06-16 | 2025-09-30 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | 0.0 | not specified | -77.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | 2025-06-11 00:00:00 | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.82
pmo000891 - oakfield and dordogne obscure glass | p-0465 | pmo000891 - oakfield and dordogne obscure glass | ross hawkings | scott mcbride | project | standalone project | standalone project | not specified | scott mcbride | r&d europe r&d europe uk r&d europe uk / france | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.67 | 2025-06-09 | 2025-12-08 | 131d | - launch date wk 47 (17th nov) - glass on order, due 20th october - delayed until 14th nov. - alice informing customer delivery will be 5th december - plan to go to gate 3 & 4 once handover has been completed - updated prices need to be confirmed | - glass on order, due 20th october - delayed until 14th nov. - alice informing customer delivery will be 5th december | - glass on order, due 20th october - delayed until 14th nov. - alice informing customer delivery will be 5th december - plan to go to gate 3 & 4 once handover has been completed | not specified | green | sideways | red | green | red | green | yellow | green | 1 | 0 | 1.0 | 7.0 | 19.0 | 41.0 | 6.0 | 5.0 | 8.0 | 8.0 | 68.0 | 27.0 | 22.0 | 5.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-29 | 2025-06-09 | 2025-10-24 | 0 | 100d | 2025-10-07 | 2025-10-29 | not specified | 2 | not specified | not specified | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | r&d | interior | npd | uk | implementation / execution | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.786259541984733 | 22.0 | 0.0 | 0.0147058823529412 | 0.102941176470588 | 0.279411764705882 | 0.602941176470588 | 0.117647058823529 | 0.882352941176471 | current year | not specified | 3 | not specified | not specified | not specified | p | 412 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-06-09 | 2025-10-24 | not specified | not specified | 2025-08-07 | 2025-08-07 | 2025-10-13 |  | 2025-10-24 |  | not specified | 0.0 | not specified | -45.0 | not specified | -131.0 | not specified | not specified | 2025-08-07 00:00:00 | 2025-08-07 00:00:00 | 2025-11-25 00:00:00 | not specified | 2025-12-08 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0 | 0 | -43d | -45d | dates not set | 0.0 | 0.0 | -0.32824427480916 | -0.343511450381679 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | 2025-06-10 00:00:00 | false | stage 3 - implementation | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.67
pmo000892 - oakfield 35mm fd30 and atherton 2 light clear glazed | p-0466 | pmo000892 - oakfield 35mm fd30 and atherton 2 light clear glazed | ross hawkings | scott mcbride | project | standalone project | standalone project | not specified | scott mcbride | r&d europe r&d europe uk r&d europe uk / france | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.64 | 2025-06-09 | 2026-01-29 | 169d | - passed gate 07/08 | - passed gate 07/08 | not specified | not specified | green | up | red | green | red | green | green | green | 0 | 0 | 0.0 | 0.0 | 5.0 | 47.0 | 1.0 | 1.0 | 0.0 | 0.0 | 52.0 | 5.0 | 5.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-06-09 | 2025-08-08 | 0 | 45d | 2025-08-13 | 2025-08-27 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | completed | eur | r&d | interior | npd | uk | realize value / close / care period | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.609467455621302 | 77.0 | 63.0 | 0.0 | 0.0 | 0.0961538461538462 | 0.903846153846154 | 0.0 | 1.0 | 2026 | not specified | 3 | not specified | not specified | not specified | p | 413 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-06-09 | 2025-08-08 | not specified | not specified | 2025-08-07 | 2025-08-07 | 2025-08-07 |  | 2025-08-07 |  | not specified | 0.0 | not specified | -174.0 | not specified | -169.0 | not specified | not specified | 2025-08-07 00:00:00 | 2025-08-07 00:00:00 | 2025-08-07 00:00:00 | not specified | 2025-08-07 00:00:00 | 2026-01-29 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0 | 0 | 0 | 0 | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | 2025-06-10 00:00:00 | false | stage 5 - care period | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.64
pmo000893 - 2'2" roi range extension - 44mm fd30 | p-0467 | pmo000893 - 2'2" roi range extension - 44mm fd30 | ross hawkings | scott mcbride | project | standalone project | standalone project | not specified | scott mcbride | r&d europe r&d europe uk r&d europe uk / france | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.16 | 2025-06-09 | 2025-08-29 | 60d | - awaiting customer feedback on whether on the timeline of the project and if it's progressing | - awaiting customer feedback on whether on the timeline of the project and if it's progressing | - awaiting customer feedback on whether on the timeline of the project and if it's progressing | not specified | green | sideways | red | red | red | green | yellow | green | 2 | 0 | 35.0 | 7.0 | 0.0 | 12.0 | 35.0 | 32.0 | 7.0 | 0.0 | 54.0 | 42.0 | 39.0 | 3.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-06-09 | 2025-08-08 | 0 | 45d | 2025-09-10 | 2025-07-23 | not specified | 2 | not specified | not specified | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | on-hold | eur | r&d | interior | npd | uk | initiation / validation / feasibility | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 1.0 | 49.0 | 98.0 | 0.648148148148148 | 0.12962962962963 | 0.0 | 0.222222222222222 | 0.12962962962963 | 0.87037037037037 | current year | not specified | 3 | not specified | not specified | not specified | p | 414 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-06-09 | 2025-08-08 | not specified | not specified |  | 2025-07-11 | 2025-07-25 |  | 2025-08-08 |  | not specified | 0.0 | not specified | -21.0 | not specified | -60.0 | not specified | not specified | not specified | 2025-07-25 00:00:00 | 2025-07-25 00:00:00 | not specified | 2025-08-08 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | -14d | 0 | 0 | dates not set | 0.0 | -0.233333333333333 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | 2025-06-10 00:00:00 | false | stage 1 - feasibility | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.16
pmo000886 - uk en test program | pg-0480 | pmo000886 - uk en test program | glyn hauser | scott mcbride | program | pg-0480 | pg-0480: pmo000886 - uk en test program | not specified | scott mcbride | r&d europe r&d europe uk r&d europe uk / france | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | program dashboard | finance dashboard | 0.11 | 2024-12-22 | 2027-07-30 | 680d | - working in partnership with a fire house and several key suppliers to start our initial benchmark tests - the first round of these tests will be carried out over 3 days at united kingdom testing & certification (uktc) in east kilbride at the end of july 2025 - uktc audit in sheffield to be completed 7th & 10th july - samples being produced for tests at the end of july | - tests booked 28th-31st july - uktc audit in sheffield booked 7th & 10th july - project created in smartsheets | - produce samples for audit (7th & 10th july) - cnc programming and machining trials to ensure all new hardware machining is set up and correct prior to the audit date - cpa to be completed - weekly team meetings | - support for audit to ensure it goes smoothly | green | on track | green | on track | green | green | yellow | green | 0 | 0 | 10.0 | 5.0 | 77.0 | 21.0 | 10.0 | 15.0 | 40.0 | 40.0 | 113.0 | 92.0 | 88.0 | 4.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 |  | 2024-12-22 | 2027-07-30 | 0 | 680d | 2025-10-29 | 2025-10-29 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | r&d | interior | npd | uk | see project details | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.327941176470588 | 0.0 | 0.0 | 0.0884955752212389 | 0.0442477876106195 | 0.68141592920354 | 0.185840707964602 | 0.353982300884956 | 0.646017699115044 | 2027 | not specified | 2 | not specified | not specified | not specified | pg | 480 | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | [6 empty] | not specified | not specified | not specified | not specified | not specified | -680.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | 2025-06-12 00:00:00 | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.11
pmo000886 - uk en test program cf160 - en1643-1 | p-0481 | pmo000886 - uk en test program cf160 - en1643-1 | glyn hauser | scott mcbride | project | pg-0480 | pg-0480: pmo000886 - uk en test program | not specified | scott mcbride | r&d europe r&d europe uk r&d europe uk / france | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.11 | 2024-12-22 | 2027-07-30 | 680d | - initial round of testing passed - change in uk business priorities means that budget for remaining tests has been deferred to 2026 - will still push for completing gate 0-1 in august - need a discussion with pm and commercial around when we will transition over to en as this will feed into required marketing activity | - initial round of testing passed - will still push for completing gate 0-1 in august | - confirm business case - complete gate 1 actions with a view to going to gate in august - need a discussion with pm and commercial around when we will transition over to en as this will feed into required marketing activity | - need a discussion with pm and commercial around when we will transition over to en as this will feed into required marketing activity | yellow | angle down | yellow | green | green | green | yellow | green | 0 | 0 | 10.0 | 5.0 | 77.0 | 21.0 | 10.0 | 15.0 | 40.0 | 40.0 | 113.0 | 92.0 | 88.0 | 4.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2024-12-22 | 2027-07-30 | 0 | 680d | 2025-10-29 | 2025-08-05 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | r&d | interior | npd | uk | initiation / validation / feasibility | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.327941176470588 | 0.0 | 85.0 | 0.0884955752212389 | 0.0442477876106195 | 0.68141592920354 | 0.185840707964602 | 0.353982300884956 | 0.646017699115044 | 2027 | not specified | 3 | not specified | not specified | not specified | p | 427 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2024-12-22 | 2027-07-30 | not specified | not specified | 2025-08-14 | 2026-06-04 | 2026-12-03 |  | 2027-02-01 | 2027-07-30 | not specified | 0.0 | not specified | 0.0 | not specified | -680.0 | not specified | not specified | 2025-11-13 00:00:00 | 2026-06-04 00:00:00 | 2026-12-03 00:00:00 | not specified | 2027-02-01 00:00:00 | 2027-07-30 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | -91d | 0 | 0 | 0 | 0 | -0.133823529411765 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | 2025-06-12 00:00:00 | false | stage 1 - feasibility | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.11
kontron | 00000 | server migration | karolin koch | karolin koch | project | standalone project | standalone project | not specified | not specified | it it central eu it-eu | not specified | karolin koch | not specified | not specified | not specified | rachael horton - farmer | not specified | not specified | not specified | not specified | not specified | on track | 0.0 | not specified | project dashboard | project finance dashboard | 0.52 | 2025-07-01 | 2025-12-29 | 130d | on track | not specified | not specified | not specified | on track | on track | red | red | yellow | red | green | green | 1 | 2 | 34.0 | 1.0 | 15.0 | 91.0 | 37.0 | 30.0 | 0.0 | 0.0 | 141.0 | 50.0 | 38.0 | 12.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-10-22 |  | #invalid value | 21 | not specified | not specified | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | on track | eur | it | not specified | not specified | central eu | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | 1.0 | on track | 0.669230769230769 | 7.0 | on track | 0.24113475177305 | 0.00709219858156028 | 0.106382978723404 | 0.645390070921986 | 0.0 | 1.0 | current year | n | 3 | not specified | not specified | not specified | p | 428 | not specified | 1.0 | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | -181.0 | not specified | -186.0 | not specified | -130.0 | not specified | not specified | 2025-07-01 00:00:00 | 2025-09-25 00:00:00 | 2025-09-25 00:00:00 | 2025-07-01 00:00:00 | 2025-11-06 00:00:00 | 2025-07-01 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | kontron | not specified |  | not specified | 2025-06-17 00:00:00 | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.52
**re-alignment of bend product line - product and operational | 57207 | re-align bend products into 1 product line (available in wood/wood or extruded clad/wood), and commercial line (wide stile, wood/wood and extruded clad/wood) | stephen ambrosia | stephen ambrosia | project | standalone project | standalone project | not specified | not specified | not specified | not specified | mike crawford (brm) | stephen ambrosia | cliff birch | kirk kroft | kirk kroft | not specified | growth | na - windows: commercial - product & pricing | engineering; it | l3 (planned) | on track | 57207.0 | not specified | project dashboard | project finance dashboard | 0.37 | 2024-10-01 | 2027-12-31 | 849d | engineering progressing - end date oct '25 data work is in progress - end date dec '25 ame/ops - reviewing equipment requirements. supply chain - monitoring bom's and inventory adjustments. marketing - commercialization plan in review for path to launch. | casement engineering prototype with roto hardware passed evaluation and testing. double hung data book has 7 of 22 cutsheets completed. all new tooling related drawings 100% complete and sent to vendors; parts being quoted. data - casement working in titan and being verified. hgw in progress. | engineering - casement roto hardware investigation. - quote and purchase tooling as finalized. - identify new equipment/tooling needs with ame/ops. - complete dfmea. - double hung data book 14 of 22 cutsheets complete. - complete equipment drawings, wood ext. dh straightline 3d initial model, clad ext. hgw rough 3d model, and wood ext. hgw rough 3d model. | not specified | yellow | sideways | red | green | red | red | yellow | red | 5 | 0 | 50.0 | 47.0 | 192.0 | 220.0 | 50.0 | 49.0 | 324.0 | 323.0 | 509.0 | 289.0 | 187.0 | 102.0 | 3650000.0 | 1900000.0 | 1750000.0 | 0.0 | 0.0 | 0.0 | 0.0 | 101500.0 | 101500.0 | 0.0 | 0.0 | 101500.0 | 101500.0 | 0.0 | 0.0 | 3548500.0 | 1798500.0 | 1750000.0 | 0.972191780821918 | 0.946578947368421 | 1 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-10-28 | 2025-09-22 | not specified | 19 | not specified | not specified | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 3102500.0 | 1615000.0 | 1487500.0 | 0.0 | 0.0 | 0.0 | 0.0 | 86275.0 | 86275.0 | 0.0 | 0.0 | 86275.0 | 86275.0 | 0.0 | 0.0 | 3016225.0 | 1528725.0 | 1487500.0 | 0.0 | 0.0 | 0.0 | not specified | active | usd | transformation | not specified | not specified | not specified | implementation / execution | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 3.379 | not specified | 1.971 | 2024-11-19 | 2026-02-14 | on plan | not specified | 1.0 | on track | 0.332155477031802 | 1.0 | 37.0 | 0.0982318271119843 | 0.0923379174852652 | 0.37721021611002 | 0.432220039292731 | 0.636542239685658 | 0.363457760314342 | 2027 | n | 3 | not specified | not specified | not specified | p | 429 | 1.0 | 1.0 | 1.0 | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | 92.0 | not specified | -918.0 | not specified | -849.0 | not specified | not specified | not specified | not specified | not specified | 2026-02-06 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | **re-alignment of bend product line - product and operational | not specified |  | not specified | 2025-06-17 00:00:00 | false | stage 3 - implementation | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.37
attributor project | 12812 | not specified | marine cardon | marine cardon | project | standalone project | standalone project | not specified | marine cardon | r&d europe r&d europe france r&d europe uk / france | not specified | emmanuel vaghi | emmanuel vaghi | emmanuel vaghi | adam painter | rachael horton-farmer | not specified | sg&a | france: commercial | it | l2 (validated) | on track | 12812.0 | not specified | project dashboard | project finance dashboard | 0.0 | 2026-02-02 | 2026-02-20 | 15d | the project if on hold regarding priority alignement | we have a file with all task needed to be follow or done before the relaunched | active project is planned in february 2026 | not specified | on track | on track | red | green | red | green | yellow | green | 0 | 0 | 0.0 | 52.0 | 128.0 | 10.0 | 0.0 | 0.0 | 58.0 | 8.0 | 190.0 | 180.0 | 168.0 | 12.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-07-01 | 2025-09-02 | 0 | 46d | 2025-10-28 | 2025-08-07 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | on-hold | eur | r&d | not specified | not specified | uk / france | planning | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 1.1e-06 | not specified | 0.0 | 2023-06-10 | 2025-09-15 | past due for l3 | not specified | 1.0 | on track | 0.0 | 1.0 | 83.0 | 0.0 | 0.273684210526316 | 0.673684210526316 | 0.0526315789473684 | 0.305263157894737 | 0.694736842105263 | 2026 | n | 3 | not specified | not specified | 1.0 | p | 430 | 1.0 | 1.0 | not specified | not specified | not specified | not specified | 2025-07-01 | 2025-09-02 | not specified | not specified | [6 empty] | not specified | -216.0 | not specified | -171.0 | not specified | -15.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | 2025-07-07 00:00:00 | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0
contract lifecycle management (clm) - eu | 32789 | eu rollout of docusign and clm repository | ben hamnett | ben hamnett | project | standalone project | standalone project | not specified | not specified | it it-eu | not specified | awaiting it pm appointment | not specified | lisa parrish | adam painter | rachael horton-farmer | not specified | sourcing | support functions: global legal | it; legal | l3 (planned) | on track | 32789.0 | not specified | project dashboard | project finance dashboard | 0.0 | 2025-01-01 | 2025-06-26 | 127d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | sideways | red | red | green | green | yellow | green | 0 | 0 | 22.0 | 53.0 | 0.0 | 0.0 | 22.0 | 22.0 | 75.0 | 75.0 | 75.0 | 75.0 | 75.0 | 0.0 | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-07-07 | 2025-10-16 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | on-hold | usd | it | not specified | not specified | eu | ideation | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | -0.61085 | not specified | 1.37739 | 2025-01-14 | 2026-10-02 | past due for l3 | not specified | 1.0 | on track | 1.0 | 114.0 | 13.0 | 0.293333333333333 | 0.706666666666667 | 0.0 | 0.0 | 1.0 | 0.0 | current year | n | 3 | not specified | not specified | not specified | p | 431 | 1.0 | 1.0 | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | 0.0 | not specified | -127.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | contract lifecycle management (clm) - eu | not specified |  | not specified | 2025-07-07 00:00:00 | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0
new build yule implementation | p-0488 | new build yule implementation | chris miller | chris miller | project | standalone project | standalone project | not specified | not specified | r&d europe r&d europe uk r&d europe uk / france | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.0 | 2025-07-01 | 2025-09-02 | 46d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | sideways | yellow | yellow | green | green | yellow | green | 0 | 0 | 4.0 | 86.0 | 4.0 | 0.0 | 9.0 | 9.0 | 94.0 | 94.0 | 94.0 | 94.0 | 90.0 | 4.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-07-01 | 2025-09-02 | 0 | 46d | 2025-07-16 | 2025-07-17 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | completed | eur | r&d | interior | npd | uk | ideation | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 1.0 | 105.0 | 104.0 | 0.0425531914893617 | 0.914893617021277 | 0.0425531914893617 | 0.0 | 1.0 | 0.0 | current year | not specified | 3 | not specified | not specified | not specified | p | 438 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-07-01 | 2025-09-02 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | 0.0 | not specified | -46.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | 2025-07-08 00:00:00 | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0
pmo000897 - uk yule - cf160 construction unification | p-0484 | pmo000897 - uk yule - cf160 construction unification | ross hawkings | scott mcbride | project | standalone project | standalone project | not specified | scott mcbride | r&d europe r&d europe uk r&d europe uk / france | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.29 | 2025-06-29 | 2026-11-10 | 357d | - launch date tbc - test date mid-nov - if test is successful - certification publication will drive full changeover | - test date mid-nov | - test date mid-nov - if test is successful - certification publication will drive full changeover | not specified | green | sideways | red | yellow | red | green | yellow | green | 0 | 0 | 0.0 | 33.0 | 46.0 | 12.0 | 0.0 | 3.0 | 71.0 | 71.0 | 91.0 | 79.0 | 67.0 | 12.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-29 | 2025-07-01 | 2025-09-02 | 0 | 46d | 2025-10-29 | 2025-10-29 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | r&d | interior | vave | uk | initiation / validation / feasibility | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.246498599439776 | 0.0 | 0.0 | 0.0 | 0.362637362637363 | 0.505494505494506 | 0.131868131868132 | 0.78021978021978 | 0.21978021978022 | 2026 | not specified | 3 | not specified | not specified | not specified | p | 439 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-07-01 | 2025-09-02 | not specified | not specified | [6 empty] | not specified | 2.0 | not specified | -434.0 | not specified | -357.0 | not specified | not specified | 2026-01-20 00:00:00 | 2026-04-28 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | 2025-07-08 00:00:00 | false | stage 1 - feasibility | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.29
pmo000898 - uk yule - lock block size harmonisation | p-0485 | pmo000898 - uk yule - lock block size harmonisation | ross hawkings | scott mcbride | project | standalone project | standalone project | not specified | scott mcbride | r&d europe r&d europe uk r&d europe uk / france | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 1.0 | 2025-07-06 | 2025-08-08 | 25d | passed gates 1-4 7th august | passed gates 1-4 7th august | passed gates 1-4 7th august | not specified | green | sideways | green | blue | green | green | green | green | 0 | 0 | 0.0 | 0.0 | 0.0 | 44.0 | 0.0 | 0.0 | 0.0 | 0.0 | 44.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-07-06 | 2025-08-08 | 0 | 25d | 2025-08-11 | 2025-08-21 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | completed | eur | r&d | interior | vave | uk | realize value / close / care period | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 1.0 | 79.0 | 69.0 | 0.0 | 0.0 | 0.0 | 1.0 | 0.0 | 1.0 | current year | not specified | 3 | not specified | not specified | not specified | p | 440 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-07-06 | 2025-08-08 | not specified | not specified | 2025-08-07 | 2025-08-07 | 2025-08-07 |  | 2025-08-07 | 2025-08-07 | not specified | 0.0 | not specified | 0.0 | not specified | -25.0 | not specified | not specified | 2025-08-07 00:00:00 | 2025-08-07 00:00:00 | 2025-08-07 00:00:00 | not specified | 2025-08-07 00:00:00 | 2025-08-07 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | 2025-07-08 00:00:00 | false | stage 5 - care period | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 1
pmo000899 - uk yule - glazed door construction and range rationalisation | p-0486 | pmo000899 - uk yule - glazed door construction and range rationalisation | ross hawkings | scott mcbride | project | standalone project | standalone project | not specified | scott mcbride | r&d europe r&d europe uk r&d europe uk / france | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.32 | 2025-06-29 | 2026-08-10 | 291d | - drawings completed - conversion date tbc - need to evaluate exposure figures that are a result of the project | - drawings completed - conversion date tbc - need to evaluate exposure figures that are a result of the project | - drawings completed - conversion date tbc - need to evaluate exposure figures that are a result of the project | not specified | green | sideways | red | green | red | green | yellow | green | 0 | 0 | 2.0 | 1.0 | 40.0 | 10.0 | 2.0 | 3.0 | 42.0 | 42.0 | 53.0 | 43.0 | 36.0 | 7.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-29 | 2025-07-01 | 2025-09-02 | 0 | 46d | 2025-10-29 | 2025-10-29 | not specified | 2 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | r&d | interior | vave | uk | initiation / validation / feasibility | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.302405498281787 | 0.0 | 0.0 | 0.0377358490566038 | 0.0188679245283019 | 0.754716981132076 | 0.188679245283019 | 0.792452830188679 | 0.207547169811321 | 2026 | not specified | 3 | not specified | not specified | not specified | p | 441 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-07-01 | 2025-09-02 | not specified | not specified | [6 empty] | not specified | 2.0 | not specified | -342.0 | not specified | -291.0 | not specified | not specified | 2026-01-05 00:00:00 | 2025-12-12 00:00:00 | 2026-01-19 00:00:00 | not specified | 2026-02-16 00:00:00 | 2026-08-10 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | 2025-07-08 00:00:00 | false | stage 1 - feasibility | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.32
pmo000900 - uk yule - bi-fold thickness and size harmonisation | p-0487 | pmo000900 - uk yule - bi-fold thickness and size harmonisation | ross hawkings | scott mcbride | project | standalone project | standalone project | not specified | scott mcbride | r&d europe r&d europe uk r&d europe uk / france | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.0 | 2025-09-02 | 2026-04-01 | 152d | - launch date tbc - samples completed and confirmed that size change will have no impact on their customers ability to install the new bi-fold - awaiting requirements from customer on format of suitability report needed - meeting with b&q planned for w/c 10th november to gain feedback from customer | - samples completed and confirmed that size change will have no impact on their customers ability to install the new bi-fold | - awaiting requirements from customer on format of suitability report needed | not specified | yellow | sideways | red | yellow | red | green | yellow | green | 0 | 0 | 0.0 | 46.0 | 32.0 | 6.0 | 1.0 | 6.0 | 73.0 | 73.0 | 84.0 | 78.0 | 74.0 | 4.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-29 | 2025-07-01 | 2025-09-02 | 0 | 46d | 2025-10-07 | 2025-10-29 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | r&d | interior | vave | uk | initiation / validation / feasibility | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.276315789473684 | 22.0 | 0.0 | 0.0 | 0.547619047619048 | 0.380952380952381 | 0.0714285714285714 | 0.869047619047619 | 0.130952380952381 | 2026 | not specified | 3 | not specified | not specified | not specified | p | 442 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-07-01 | 2025-09-02 | not specified | not specified | [6 empty] | not specified | -63.0 | not specified | -211.0 | not specified | -152.0 | not specified | not specified | 2025-12-12 00:00:00 | 2026-03-31 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | 2025-07-08 00:00:00 | false | stage 1 - feasibility | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0
espresso 2.0 | pg-0497 | not specified | jim copeland | jim copeland | program | pg-0497 | pg-0497: espresso 2.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | program dashboard | finance dashboard | 0.171787307882995 | 2025-07-01 | 2028-08-31 | 828d | key focus areas: 1.0 • staining process improvement: follow up with ken and mike to finalize and implement a solution for improving the staining process to better bring out the graining in grinnell. (@ken hull, @mike lotko) • thd samples 1.5 • die redundancy and enhancement: initiate the process to get a second die made for the two panel arch top, ensuring redundancy and more pronounced graining for finishing. (@ken hull, @mike lotko) • traditional channel die change process: establish a working team and develop a plan to shorten the die changeover time for supporting seven skus in the traditional channel, moving from shifts to minutes. (@jim copeland, @mike lotko adam, justin) • assessment of dies: assess the dies produced for acceptability, decide on replacement for any cracked dies, and initiate the supply chain process for ordering replacements if needed. (@mike lotko @ken hull) • glazed units die timeline: follow up with larry after tomorrow’s meeting to obtain and communicate a timeline for the die required to confirm the glazed unit design. (@mike lotko) • design lock for glazed business focus • market pricing research: complete research with sales and marketing to establish market pricing for the traditional channel and communicate findings to the team. (@matt goodman) • base coat application costing: determine the cost and margin impact of applying a base coat to all doors before entering the traditional channel and decide on the number of colors to offer. (paul, ken, matt) 2.0 • raw materials sourcing and testing: obtain samples of raw materials (foam, resin, catalysts), test with dino in italy and north america, and ensure multiple sources are available to avoid single-source risk. | key focus areas: 1.0 • staining process improvement: follow up with ken and mike to finalize and implement a solution for improving the staining process to better bring out the graining in grinnell. (@ken hull, @mike lotko) • thd samples 1.5 • die redundancy and enhancement: initiate the process to get a second die made for the two panel arch top, ensuring redundancy and more pronounced graining for finishing. (@ken hull, @mike lotko) • traditional channel die change process: establish a working team and develop a plan to shorten the die changeover time for supporting seven skus in the traditional channel, moving from shifts to minutes. (@jim copeland, @mike lotko adam, justin) • assessment of dies: assess the dies produced for acceptability, decide on replacement for any cracked dies, and initiate the supply chain process for ordering replacements if needed. (@mike lotko @ken hull) • glazed units die timeline: follow up with larry after tomorrow’s meeting to obtain and communicate a timeline for the die required to confirm the glazed unit design. (@mike lotko) • design lock for glazed business focus • market pricing research: complete research with sales and marketing to establish market pricing for the traditional channel and communicate findings to the team. (@matt goodman) • base coat application costing: determine the cost and margin impact of applying a base coat to all doors before entering the traditional channel and decide on the number of colors to offer. (paul, ken, matt) 2.0 • raw materials sourcing and testing: obtain samples of raw materials (foam, resin, catalysts), test with dino in italy and north america, and ensure multiple sources are available to avoid single-source risk. | not specified | not specified | yellow | on track | green | on track | red | red | yellow | red | 2 | 0 | 0.0 | 0.0 | 1221.0 | 248.0 | 1.0 | 1.0 | 4.0 | 4.0 | 1469.0 | 1221.0 | 1214.0 | 7.0 | 19363000.0 | 19313000.0 | 50000.0 | 0.0 | 0.0 | 0.0 | not specified | 19363000.0 | 14313000.0 | 5050000.0 | not specified | 19363000.0 | 14313000.0 | 5050000.0 | not specified | 0.0 | 5000000.0 | -5000000.0 | 0.0 | 0.258892973644695 | -100 |  | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-10-27 | 2025-10-29 | not specified | 4 | 1.0 | not specified | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 16458550.0 | 16416050.0 | 42500.0 | 0.0 | 0.0 | 0.0 | not specified | 16458550.0 | 12166050.0 | 4292500.0 | not specified | 16458550.0 | 12166050.0 | 4292500.0 | not specified | 0.0 | 4250000.0 | -4250000.0 | 0.0 | 0.258892973644695 | -100.0 | not specified | on track | usd | engineering | not specified | not specified | not specified | see project details | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.105072463768116 | 2.0 | 0.0 | 0.0 | 0.0 | 0.831177671885637 | 0.168822328114364 | 0.00272294077603812 | 0.997277059223962 | 2028 | not specified | 2 | not specified | not specified | not specified | pg | 497 | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | [6 empty] | not specified | not specified | not specified | not specified | not specified | -828.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | 2025-07-08 00:00:00 | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.17179
espresso 2.0 foam manufacture in house | p-0495 | not specified | jim copeland | jim copeland | project | pg-0497 | pg-0497: espresso 2.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.18 | 2025-07-08 | 2027-12-08 | 632d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | sideways | red | green | red | red | green | green | 2 | 0 | 0.0 | 0.0 | 201.0 | 42.0 | 0.0 | 0.0 | 0.0 | 0.0 | 243.0 | 201.0 | 201.0 | 0.0 | 3000000.0 | 3000000.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 3000000.0 | 3000000.0 | 0.0 | 0.0 | 3000000.0 | 3000000.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-10-03 | 2025-07-07 | not specified | 16 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 2550000.0 | 2550000.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 2550000.0 | 2550000.0 | 0.0 | 0.0 | 2550000.0 | 2550000.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | usd | engineering | not specified | not specified | not specified | ideation | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.129746835443038 | 26.0 | 114.0 | 0.0 | 0.0 | 0.827160493827161 | 0.17283950617284 | 0.0 | 1.0 | 2027 | not specified | 3 | not specified | not specified | 1.0 | p | 432 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | -188.0 | not specified | -895.0 | not specified | -632.0 | not specified | not specified | not specified | not specified | not specified | 2027-12-01 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | espresso 2.0 foam manufacture in house | not specified |  | not specified | 2025-07-07 00:00:00 | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.18
espresso 2.0 high speed mfg | p-0496 | not specified | jim copeland | jim copeland | project | pg-0497 | pg-0497: espresso 2.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.1 | 2025-07-15 | 2028-05-25 | 748d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | sideways | red | green | red | green | green | green | 0 | 0 | 0.0 | 0.0 | 199.0 | 42.0 | 0.0 | 0.0 | 0.0 | 0.0 | 241.0 | 199.0 | 199.0 | 0.0 | 7010000.0 | 7010000.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 7010000.0 | 7010000.0 | 0.0 | 0.0 | 7010000.0 | 7010000.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-10-27 | 2025-07-07 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 5958500.0 | 5958500.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 5958500.0 | 5958500.0 | 0.0 | 0.0 | 5958500.0 | 5958500.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | usd | engineering | not specified | not specified | not specified | ideation | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.102941176470588 | 2.0 | 114.0 | 0.0 | 0.0 | 0.825726141078838 | 0.174273858921162 | 0.0 | 1.0 | 2028 | not specified | 3 | not specified | not specified | 1.0 | p | 433 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | -195.0 | not specified | -1064.0 | not specified | -748.0 | not specified | not specified | not specified | not specified | not specified | 2028-05-18 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | espresso 2.0 high speed mfg | not specified |  | not specified | 2025-07-07 00:00:00 | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.1
espresso 2.0 amc mfg in house | p-0491 | not specified | jim copeland | jim copeland | project | pg-0497 | pg-0497: espresso 2.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.08 | 2025-07-08 | 2028-08-31 | 823d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | sideways | red | green | red | green | green | green | 0 | 0 | 0.0 | 0.0 | 206.0 | 36.0 | 0.0 | 0.0 | 0.0 | 0.0 | 242.0 | 206.0 | 200.0 | 6.0 | 2000000.0 | 2000000.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 2000000.0 | 2000000.0 | 0.0 | 0.0 | 2000000.0 | 2000000.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-10-03 | 2025-07-08 | not specified | 2 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 1700000.0 | 1700000.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 1700000.0 | 1700000.0 | 0.0 | 0.0 | 1700000.0 | 1700000.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | usd | engineering | not specified | not specified | not specified | ideation | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.0996354799513973 | 26.0 | 113.0 | 0.0 | 0.0 | 0.851239669421488 | 0.148760330578512 | 0.0 | 1.0 | 2028 | not specified | 3 | not specified | not specified | 1.0 | p | 434 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | -188.0 | not specified | -1162.0 | not specified | -823.0 | not specified | not specified | not specified | not specified | not specified | 2027-07-16 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | espresso 2.0 amc mfg in house | not specified |  | not specified | 2025-07-08 00:00:00 | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.08
espresso die mfg | p-0492 | not specified | jim copeland | jim copeland | project | pg-0497 | pg-0497: espresso 2.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.29 | 2025-07-01 | 2027-11-24 | 627d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | sideways | red | green | red | green | yellow | green | 0 | 0 | 0.0 | 0.0 | 207.0 | 44.0 | 0.0 | 0.0 | 3.0 | 3.0 | 251.0 | 207.0 | 206.0 | 1.0 | 2053000.0 | 2053000.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 2053000.0 | 2053000.0 | 0.0 | 0.0 | 2053000.0 | 2053000.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-10-03 | 2025-07-08 | not specified | 1 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 1745050.0 | 1745050.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 1745050.0 | 1745050.0 | 0.0 | 0.0 | 1745050.0 | 1745050.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | usd | engineering | not specified | not specified | not specified | ideation | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.138755980861244 | 26.0 | 113.0 | 0.0 | 0.0 | 0.824701195219124 | 0.175298804780877 | 0.0119521912350598 | 0.98804780876494 | 2027 | not specified | 3 | not specified | not specified | 1.0 | p | 435 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | -181.0 | not specified | -881.0 | not specified | -627.0 | not specified | not specified | not specified | not specified | not specified | 2027-09-09 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | espresso die mfg | not specified |  | not specified | 2025-07-08 00:00:00 | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.29
espresso 2.0 enhanced finishing | p-0493 | not specified | jim copeland | jim copeland | project | pg-0497 | pg-0497: espresso 2.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.25 | 2025-07-08 | 2027-09-15 | 572d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | sideways | red | green | red | red | yellow | green | 2 | 0 | 0.0 | 0.0 | 206.0 | 42.0 | 1.0 | 1.0 | 1.0 | 1.0 | 248.0 | 206.0 | 206.0 | 0.0 | 50000.0 | not specified | 50000.0 | 0.0 | 0.0 | 0.0 | 0.0 | 50000.0 | 0.0 | 50000.0 | 0.0 | 50000.0 | 0.0 | 50000.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-10-03 | 2025-07-08 | not specified | 15 | not specified | not specified | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 42500.0 | 0.0 | 42500.0 | 0.0 | 0.0 | 0.0 | 0.0 | 42500.0 | 0.0 | 42500.0 | 0.0 | 42500.0 | 0.0 | 42500.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | usd | engineering | not specified | not specified | not specified | ideation | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.143356643356643 | 26.0 | 113.0 | 0.0 | 0.0 | 0.830645161290323 | 0.169354838709677 | 0.00403225806451613 | 0.995967741935484 | 2027 | not specified | 3 | not specified | not specified | 1.0 | p | 436 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | -188.0 | not specified | -811.0 | not specified | -572.0 | not specified | not specified | not specified | not specified | not specified | 2027-09-08 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | espresso 2.0 enhanced finishing | not specified |  | not specified | 2025-07-08 00:00:00 | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.25
espresso 2.0 full systems mfg in house | p-0494 | not specified | jim copeland | jim copeland | project | pg-0497 | pg-0497: espresso 2.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.18 | 2025-07-08 | 2027-12-08 | 632d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | sideways | red | green | red | green | green | green | 0 | 0 | 0.0 | 0.0 | 202.0 | 42.0 | 0.0 | 0.0 | 0.0 | 0.0 | 244.0 | 202.0 | 202.0 | 0.0 | 250000.0 | 250000.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 250000.0 | 250000.0 | 0.0 | 0.0 | 250000.0 | 250000.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-10-03 | 2025-07-08 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 212500.0 | 212500.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 212500.0 | 212500.0 | 0.0 | 0.0 | 212500.0 | 212500.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | usd | engineering | not specified | not specified | not specified | ideation | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.129746835443038 | 26.0 | 113.0 | 0.0 | 0.0 | 0.827868852459016 | 0.172131147540984 | 0.0 | 1.0 | 2027 | not specified | 3 | not specified | not specified | 1.0 | p | 437 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | -188.0 | not specified | -895.0 | not specified | -632.0 | not specified | not specified | not specified | not specified | not specified | 2027-12-01 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | espresso 2.0 full systems mfg in house | not specified |  | not specified | 2025-07-08 00:00:00 | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.18
ukg wallet | p-0498 | earned wage access | christina andert | christina andert | project | standalone project | standalone project | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | not specified |  |  | #invalid data type | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | sideways | yellow | yellow | schedule not set | yellow | yellow | green | 1 | 0 | 0.0 | 107.0 | 0.0 | 0.0 | 0.0 | 0.0 | 107.0 | 11.0 | 107.0 | 107.0 | 0.0 | 107.0 | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-07-11 | 2025-07-11 | not specified | 4 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | usd | finance | not specified | not specified | not specified | ideation | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.0 | 110.0 | 110.0 | 0.0 | 1.0 | 0.0 | 0.0 | 1.0 | 0.0 | not specified | not specified | 3 | not specified | not specified | not specified | p | 443 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | ukg wallet | not specified |  | not specified | 2025-07-11 00:00:00 | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified
ukg oneview connect | p-0499 | not specified | christina andert | christina andert | project | standalone project | standalone project | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.22 | 2024-03-01 | 2025-09-22 | 407d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | sideways | red | yellow | red | green | yellow | green | 0 | 0 | 13.0 | 17.0 | 27.0 | 46.0 | 49.0 | 49.0 | 13.0 | 5.0 | 103.0 | 57.0 | 49.0 | 8.0 | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-09-03 | 2025-07-11 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | usd | finance | not specified | not specified | not specified | ideation | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 1.0 | 56.0 | 110.0 | 0.12621359223301 | 0.16504854368932 | 0.262135922330097 | 0.446601941747573 | 0.12621359223301 | 0.87378640776699 | current year | not specified | 3 | not specified | not specified | 1.0 | p | 444 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | 306.0 | not specified | -88.0 | not specified | -407.0 | not specified | not specified | not specified | not specified | not specified | 2025-07-31 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | ukg oneview connect | not specified |  | not specified | 2025-07-11 00:00:00 | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.22
ukg non recurring pay | p-0500 | not specified | christina andert | christina andert | project | standalone project | standalone project | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | not specified |  |  | #invalid data type | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | sideways | yellow | yellow | schedule not set | green | yellow | green | 0 | 0 | 0.0 | 107.0 | 0.0 | 0.0 | 0.0 | 0.0 | 107.0 | 11.0 | 107.0 | 107.0 | 0.0 | 107.0 | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-07-11 | 2025-07-11 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | usd | finance | not specified | not specified | not specified | ideation | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.0 | 110.0 | 110.0 | 0.0 | 1.0 | 0.0 | 0.0 | 1.0 | 0.0 | not specified | not specified | 3 | not specified | not specified | 1.0 | p | 445 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | ukg non recurring pay | not specified |  | not specified | 2025-07-11 00:00:00 | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified
sap sf to ukg pro pay integration hosting | p-0501 | transitioning python code to jw network. | christina andert | christina andert | project | standalone project | standalone project | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | not specified |  |  | #invalid data type | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | sideways | yellow | yellow | schedule not set | green | yellow | green | 0 | 0 | 0.0 | 107.0 | 0.0 | 0.0 | 0.0 | 0.0 | 107.0 | 11.0 | 107.0 | 107.0 | 0.0 | 107.0 | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-07-11 | 2025-07-11 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | usd | finance | not specified | not specified | not specified | ideation | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.0 | 110.0 | 110.0 | 0.0 | 1.0 | 0.0 | 0.0 | 1.0 | 0.0 | not specified | not specified | 3 | not specified | not specified | not specified | p | 446 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | sap sf to ukg pro pay integration hosting | not specified |  | not specified | 2025-07-11 00:00:00 | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified
pmo000906 - lhg tooting lock & handle | p-0502 | pmo000906 - lhg tooting lock & handle | phil boardman | scott mcbride | project | standalone project | standalone project | not specified | scott mcbride | r&d europe r&d europe uk r&d europe uk / france | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.73 | 2025-07-23 | 2025-11-21 | 88d | - launch date 24th october - deliveries on-track - compiling gate 3-4 doc | - launch date 24th october - deliveries on-track - compiling gate 3-4 doc | - launch date 24th october - deliveries on-track - compiling gate 3-4 doc | not specified | yellow | angle up | red | green | red | red | yellow | green | 1 | 0 | 0.0 | 7.0 | 12.0 | 38.0 | 0.0 | 3.0 | 6.0 | 6.0 | 57.0 | 19.0 | 15.0 | 4.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-29 | 2025-07-01 | 2025-09-02 | 0 | 46d | 2025-10-29 | 2025-10-29 | not specified | 1 | not specified | not specified | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | r&d | interior | npd | uk | implementation / execution | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.806818181818182 | 0.0 | 0.0 | 0.0 | 0.12280701754386 | 0.210526315789474 | 0.666666666666667 | 0.105263157894737 | 0.894736842105263 | current year | not specified | 3 | not specified | not specified | not specified | p | 447 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-07-01 | 2025-09-02 | not specified | not specified | [6 empty] | not specified | -22.0 | not specified | -80.0 | not specified | -88.0 | not specified | not specified | 2025-08-28 00:00:00 | 2025-08-28 00:00:00 | 2025-11-21 00:00:00 | not specified | 2025-11-21 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | 2025-07-23 00:00:00 | false | stage 3 - implementation | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.73
eudr - deforestation regulation | 70102 | the eu deforestation regulation (eudr) is a significant initiative aimed at minimizing the eu’s contribution to global deforestation and forest degradation. note: jorgen knudsen is project manager for the project. guillaume worringer project sponsor | jorgen knudsen | jorgen knudsen | program | 70102 | 70102: eudr - deforestation regulation | not specified | not specified | it it-eu | not specified | not specified | not specified | j�rgen knudsen | rachael horton-farmer | rachael horton-farmer | not specified | supply chain | europe: sourcing (direct & indirect) | it | l1 (identified) | on hold | 70102.0 | not specified | program dashboard | finance dashboard | 0.359513274336283 | 2025-01-01 | 2026-03-31 | 325d | add the high level status of the program in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | on track | red | on track | red | green | yellow | green | 0 | 0 | 9.0 | 10.0 | 61.0 | 186.0 | 11.0 | 20.0 | 101.0 | 101.0 | 266.0 | 80.0 | 67.0 | 13.0 | 0.0 | 0.0 | 0.0 | 132798.823529411 | 0.0 | 132798.823529411 | not specified | 0.0 | 0.0 | 0.0 | not specified | 132798.823529411 | 0.0 | 132798.823529411 | not specified | -132798.823529411 | 0.0 | -132798.823529411 | 0.0 | 0.0 | 0 |  | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-10-21 | 2025-10-29 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 112879.0 | 0.0 | 112879.0 | not specified | 0.0 | 0.0 | 0.0 | not specified | 112879.0 | 0.0 | 112879.0 | not specified | -112879.0 | 0.0 | -112879.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | it | not specified | not specified | eu | see project details | not specified | compliance | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | 1.0 | on track | 0.664615384615385 | 8.0 | 0.0 | 0.0338345864661654 | 0.037593984962406 | 0.229323308270677 | 0.699248120300752 | 0.379699248120301 | 0.620300751879699 | 2026 | not specified | 2 | not specified | not specified | not specified | pg | 503 | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | [6 empty] | not specified | not specified | not specified | not specified | not specified | -325.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | improved performance | 0.0 | one | not specified | not specified | not specified |  | not specified | 2025-07-28 00:00:00 | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.35951
business workstream - eudr - deforestation regulation | p-0289 | the eu deforestation regulation (eudr) is a significant initiative aimed at minimizing the eu’s contribution to global deforestation and forest degradation. note: jorgen knudsen is project manager for the project. guillaume worringer project sponsor | jorgen knudsen | jorgen knudsen | project | 70102 | 70102: eudr - deforestation regulation | not specified | not specified | not specified | not specified | not specified | not specified | j�rgen knudsen | rachael horton-farmer | rachael horton-farmer | not specified | supply chain | europe: sourcing (direct & indirect) | it | l1 (identified) | on hold | not specified | not specified | project dashboard | project finance dashboard | 0.0 | 2025-01-01 | 2025-06-26 | 127d | on track | not specified | not specified | not specified | on track | on track | red | red | green | green | yellow | green | 0 | 0 | 9.0 | 10.0 | 17.0 | 122.0 | 11.0 | 11.0 | 12.0 | 12.0 | 158.0 | 36.0 | 25.0 | 11.0 | 0.0 | 0.0 | 0.0 | 132798.823529411 | 0.0 | 132798.823529411 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 132798.823529411 | 0.0 | 132798.823529411 | 0.0 | -132798.823529411 | 0.0 | -132798.823529411 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-10-21 |  | #invalid value | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 112879.0 | 0.0 | 112879.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 112879.0 | 0.0 | 112879.0 | 0.0 | -112879.0 | 0.0 | -112879.0 | 0.0 | 0.0 | 0.0 | not specified | on track | eur | it | not specified | not specified | eu | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not planned (l2 to l4) | not specified | not specified | on track | 1.0 | 8.0 | on track | 0.0569620253164557 | 0.0632911392405063 | 0.107594936708861 | 0.772151898734177 | 0.0759493670886076 | 0.924050632911393 | current year | n | 3 | not specified | not specified | not specified | p | 163 | 1.0 | 1.0 | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | 0.0 | not specified | -127.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | eudr - deforestation regulation | not specified |  | not specified | not specified | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0
it workstream - eudr - deforestation regulation | p-0504 | the eu deforestation regulation (eudr) is a significant initiative aimed at minimizing the eu’s contribution to global deforestation and forest degradation. note: jorgen knudsen is project manager for the project. guillaume worringer project sponsor | jorgen knudsen | amer basic | project | 70102 | 70102: eudr - deforestation regulation | not specified | not specified | it it-eu | not specified | amer basic | not specified | j�rgen knudsen | rachael horton-farmer | rachael horton-farmer | not specified | supply chain | europe: sourcing (direct & indirect) | it | l1 (identified) | on hold | not specified | not specified | project dashboard | project finance dashboard | 0.5 | 2025-01-01 | 2026-03-31 | 325d | w38: osapiens implementation is ongoing to ensure that the tool is live to be used before regulation deadline. key challenge is still to understand what impact eudr will have on the supply chain and how we can automate the process through enhanced erp functionality and setup of middleware/integration platform. detailed solution discussion ongoing with major erps and solution architect team supporting in the decision to select the right integration partner. | not specified | w39: super user flow test of dds process (capturing inbound dds numbers and generation of outbound dds) | ptg: resources in the core project team are thin and support need from local business units to ensure compliance before deadline. | green | sideways | red | green | red | green | yellow | green | 0 | 0 | 0.0 | 0.0 | 44.0 | 64.0 | 0.0 | 9.0 | 89.0 | 89.0 | 108.0 | 44.0 | 42.0 | 2.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-10-21 | 2025-10-14 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | it | not specified | not specified | eu | ideation | not specified | compliance | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.664615384615385 | 8.0 | 15.0 | 0.0 | 0.0 | 0.407407407407407 | 0.592592592592593 | 0.824074074074074 | 0.175925925925926 | 2026 | not specified | 3 | not specified | not specified | not specified | p | 448 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | -278.0 | not specified | -325.0 | not specified | not specified | 2025-01-01 00:00:00 | 2025-01-27 00:00:00 | 2025-04-14 00:00:00 | 2025-04-14 00:00:00 | 2026-03-31 00:00:00 | 2026-03-31 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | improved performance | 0.0 | one | not specified | it workstream - eudr - deforestation regulation | not specified |  | not specified | 2025-07-28 00:00:00 | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.5
inventory control 2.0 | 75834 | not specified | william leslie | william leslie | project | standalone project | standalone project | not specified | not specified | not specified | not specified | chris long | will leslie | emily cochrane | christian suarez | gaurav ahlawat | not specified | supply chain | na - ops: supply chain | it | l3 (planned) | on track | 75834.0 | not specified | project dashboard | project finance dashboard | 0.23 | 2025-06-20 | 2026-07-31 | 291d | on track | not specified | not specified | not specified | on track | on track | red | green | red | green | yellow | green | 0 | 0 | 24.0 | 2.0 | 187.0 | 66.0 | 50.0 | 62.0 | 279.0 | 279.0 | 279.0 | 213.0 | 208.0 | 5.0 | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-09-30 |  | #invalid value | 3 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | on track | usd | transformation | not specified | not specified | not specified | not specified | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | 0.16067 | not specified | 1.053277 | 2025-07-18 | 2027-03-31 | past due for l3 | not specified | 1.0 | on track | 0.323024054982818 | 29.0 | on track | 0.0860215053763441 | 0.00716845878136201 | 0.670250896057348 | 0.236559139784946 | 1.0 | 0.0 | 2026 | n | 3 | not specified | not specified | 1.0 | p | 449 | 1.0 | 1.0 | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | -170.0 | not specified | -400.0 | not specified | -291.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | inventory control 2.0 | not specified |  | not specified | 2025-07-31 00:00:00 | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.23
pmo000923 - taylor wimpey extra trim doorkits / datapins | p-0508 | pmo000923 - taylor wimpey extra trim doorkits / datapins | ross hawkings | scott mcbride | project | standalone project | standalone project | not specified | scott mcbride | r&d europe r&d europe uk r&d europe uk / france | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.99 | 2025-08-11 | 2026-04-06 | 171d | - passed gate 0-4 23rd october | - passed gate 0-4 23rd october | - passed gate 0-4 23rd october | not specified | green | sideways | red | green | red | green | yellow | green | 0 | 0 | 2.0 | 0.0 | 7.0 | 42.0 | 4.0 | 4.0 | 2.0 | 2.0 | 51.0 | 9.0 | 9.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-29 | 2025-07-01 | 2025-09-02 | 0 | 46d | 2025-10-09 | 2025-10-29 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | r&d | interior | npd | uk | realize value / close / care period | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.339181286549708 | 20.0 | 0.0 | 0.0392156862745098 | 0.0 | 0.137254901960784 | 0.823529411764706 | 0.0392156862745098 | 0.96078431372549 | 2026 | not specified | 3 | not specified | not specified | not specified | p | 452 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-07-01 | 2025-09-02 | not specified | not specified | [6 empty] | not specified | -41.0 | not specified | -216.0 | not specified | -171.0 | not specified | not specified | 2025-10-09 00:00:00 | 2025-10-09 00:00:00 | 2025-10-08 00:00:00 | not specified | 2025-10-08 00:00:00 | 2026-04-06 00:00:00 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | 2025-08-11 00:00:00 | false | stage 5 - care period | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.99
customer experience agile pod | p-0509 | continuous improvement agile planning for work in support of the customer experience teams | sheri schrier | sheri schrier | project | standalone project | standalone project | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.0 | 2025-01-01 | 2025-06-26 | 127d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | sideways | red | red | green | green | yellow | green | 0 | 0 | 22.0 | 0.0 | 0.0 | 0.0 | 22.0 | 22.0 | 22.0 | 22.0 | 22.0 | 22.0 | 22.0 | 0.0 | 0.0 | not specified | not specified | 159000.0 | 102000.0 | 57000.0 | 0.0 | 106000.0 | 68000.0 | 38000.0 | 0.0 | 265000.0 | 170000.0 | 95000.0 | 0.0 | -265000.0 | -170000.0 | -95000.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-08-15 | 2025-08-15 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 135150.0 | 86700.0 | 48450.0 | 0.0 | 90100.0 | 57800.0 | 32300.0 | 0.0 | 225250.0 | 144500.0 | 80750.0 | 0.0 | -225250.0 | -144500.0 | -80750.0 | 0.0 | 0.0 | 0.0 | not specified | active | usd | it | not specified | not specified | not specified | ideation | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 1.0 | 75.0 | 75.0 | 1.0 | 0.0 | 0.0 | 0.0 | 1.0 | 0.0 | current year | not specified | 3 | not specified | not specified | not specified | p | 453 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | 0.0 | not specified | -127.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | customer experience agile pod | not specified |  | not specified | 2025-08-15 00:00:00 | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0
interior molded/flush spec alignment | 74524 | not specified | william leslie | william leslie | project | standalone project | standalone project | not specified | not specified | not specified | not specified | not specified | will leslie | kayce hunt | not specified | not specified | not specified | other | na - doors & dist: commercial - product & pricing | not specified | submitted for l2 approval | on track | 74524.0 | not specified | project dashboard | project finance dashboard | 0.52 | 2025-07-07 | 2025-12-05 | 110d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | sideways | red | red | red | green | yellow | green | 0 | 0 | 28.0 | 4.0 | 2.0 | 13.0 | 28.0 | 27.0 | 47.0 | 47.0 | 47.0 | 34.0 | 27.0 | 7.0 | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-10-28 | 2025-08-18 | not specified | 5 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | usd | transformation | not specified | not specified | not specified | ideation | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not planned (l2 to l4) | not specified | 1.0 | on track | 0.754545454545455 | 1.0 | 72.0 | 0.595744680851064 | 0.0851063829787234 | 0.0425531914893617 | 0.276595744680851 | 1.0 | 0.0 | current year | n | 3 | not specified | not specified | 1.0 | p | 454 | 1.0 | 1.0 | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | -187.0 | not specified | -162.0 | not specified | -110.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | interior molded/flush spec alignment | not specified |  | not specified | 2025-08-18 00:00:00 | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.52
sda project | p-0511 | currently, the windows and doors product lines lack a unified, efficient, and transparent system for managing sales processes, approvals, customer interactions, and reporting. information is often fragmented across emails and disparate platforms, leading to inconsistent data, inefficient approvals, limited visibility into performance, and difficulty in tracking critical metrics like sda impact, quote expirations, and win/loss outcomes. | amanda jones | amanda jones | project | standalone project | standalone project | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.02 | 2025-08-11 | 2026-02-24 | 142d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | sideways | red | red | red | green | yellow | green | 0 | 0 | 6.0 | 0.0 | 16.0 | 2.0 | 7.0 | 8.0 | 23.0 | 23.0 | 24.0 | 22.0 | 22.0 | 0.0 | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-10-09 | 2025-08-19 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | usd | transformation | not specified | not specified | not specified | ideation | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.408450704225352 | 20.0 | 71.0 | 0.25 | 0.0 | 0.666666666666667 | 0.0833333333333333 | 0.958333333333333 | 0.041666666666667 | 2026 | not specified | 3 | not specified | not specified | not specified | p | 455 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | -222.0 | not specified | -243.0 | not specified | -142.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | sda project | not specified |  | not specified | 2025-08-19 00:00:00 | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.02
it cost optimization | p-0512 | deloitte review of it costs and opportunities | garrett farmer | garrett farmer | project | standalone project | standalone project | not specified | not specified | it | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.0 | 2025-01-01 | 2025-06-26 | 127d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | sideways | red | red | green | green | yellow | green | 0 | 0 | 22.0 | 53.0 | 0.0 | 0.0 | 22.0 | 22.0 | 75.0 | 75.0 | 75.0 | 75.0 | 75.0 | 0.0 | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-08-21 | 2025-08-21 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | usd | it | not specified | not specified | global | ideation | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 1.0 | 69.0 | 69.0 | 0.293333333333333 | 0.706666666666667 | 0.0 | 0.0 | 1.0 | 0.0 | current year | not specified | 3 | not specified | not specified | not specified | p | 456 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | 0.0 | not specified | -127.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | it cost optimization | not specified |  | not specified | 2025-08-21 00:00:00 | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0
pmo000707 - eu platform - european platform harmonization uk | p-0513 | pmo000707 - eu platform - european platform harmonization uk | glyn hauser | scott mcbride | project | standalone project | standalone project | not specified | scott mcbride | r&d europe r&d europe uk r&d europe uk / france | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.0 | 2025-07-01 | 2025-09-02 | 46d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | sideways | red | red | green | green | yellow | green | 0 | 0 | 9.0 | 85.0 | 0.0 | 0.0 | 9.0 | 9.0 | 94.0 | 94.0 | 94.0 | 94.0 | 90.0 | 4.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-07-01 | 2025-09-02 | 0 | 46d | 2025-09-08 | 2025-09-08 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | r&d | interior | vave | uk | ideation | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 1.0 | 51.0 | 51.0 | 0.0957446808510638 | 0.904255319148936 | 0.0 | 0.0 | 1.0 | 0.0 | current year | not specified | 3 | not specified | not specified | not specified | p | 457 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-07-01 | 2025-09-02 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | 0.0 | not specified | -46.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | 2025-09-08 00:00:00 | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0
pmo000913 - fed lite 80mm frame | p-0514 | pmo000913 - fed lite 80mm frame | tony pell | scott mcbride | project | standalone project | standalone project | not specified | scott mcbride | r&d europe r&d europe uk r&d europe uk / france | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.0 | 2025-07-01 | 2025-09-02 | 46d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | sideways | red | red | green | green | yellow | green | 0 | 0 | 9.0 | 85.0 | 0.0 | 0.0 | 9.0 | 9.0 | 94.0 | 94.0 | 94.0 | 94.0 | 90.0 | 4.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-07-01 | 2025-09-02 | 0 | 46d | 2025-09-08 | 2025-09-08 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | r&d | interior | npd | uk | ideation | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 1.0 | 51.0 | 51.0 | 0.0957446808510638 | 0.904255319148936 | 0.0 | 0.0 | 1.0 | 0.0 | current year | not specified | 3 | not specified | not specified | not specified | p | 458 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-07-01 | 2025-09-02 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | 0.0 | not specified | -46.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | 2025-09-08 00:00:00 | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0
pmo000929 - howdens - new moulded range introductions - 3p shaker and 1p reeded | p-0515 | pmo000929 - howdens - new moulded range introductions - 3p shaker and 1p reeded | ross hawkings | scott mcbride | project | standalone project | standalone project | not specified | scott mcbride | r&d europe r&d europe uk r&d europe uk / france | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.0 | 2025-07-01 | 2025-09-02 | 46d | - launch date wk 50 2026 (tbc) - confirmation required on who will pay for tooling (jw or howdens) - awaiting feedback from customer before being able to start the project | - confirmation required on who will pay for tooling (jw or howdens) - awaiting feedback from customer before being able to start the project | - confirmation required on who will pay for tooling (jw or howdens) - awaiting feedback from customer before being able to start the project | not specified | green | sideways | red | red | green | green | yellow | green | 0 | 0 | 9.0 | 85.0 | 0.0 | 0.0 | 9.0 | 9.0 | 94.0 | 94.0 | 94.0 | 94.0 | 90.0 | 4.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-07-01 | 2025-09-02 | 0 | 46d | 2025-09-08 | 2025-10-29 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | r&d | interior | npd | uk | initiation / validation / feasibility | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 1.0 | 51.0 | 0.0 | 0.0957446808510638 | 0.904255319148936 | 0.0 | 0.0 | 1.0 | 0.0 | current year | not specified | 3 | not specified | not specified | not specified | p | 459 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-07-01 | 2025-09-02 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | 0.0 | not specified | -46.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | 2025-09-08 00:00:00 | false | stage 1 - feasibility | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0
pmo000930 - howdens - new refreshed foil door range | p-0516 | pmo000930 - howdens - new refreshed foil door range | ross hawkings | scott mcbride | project | standalone project | standalone project | not specified | scott mcbride | r&d europe r&d europe uk r&d europe uk / france | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.0 | 2025-07-01 | 2025-09-02 | 46d | - launch date wk 25 2026 - challenge is to deliver sooner (in progress) - spec being defined (standard or increased trim) - commercials being presented to customer for both options - walnut lipping solution/stain option being investigated | - challenge is to deliver sooner (in progress) - spec being defined (standard or increased trim) - commercials being presented to customer for both options - walnut lipping solution/stain option being investigated | - challenge is to deliver sooner (in progress) - spec being defined (standard or increased trim) - commercials being presented to customer for both options - walnut lipping solution/stain option being investigated | not specified | green | sideways | red | red | green | green | yellow | green | 0 | 0 | 9.0 | 85.0 | 0.0 | 0.0 | 9.0 | 9.0 | 94.0 | 94.0 | 94.0 | 94.0 | 90.0 | 4.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-07-01 | 2025-09-02 | 0 | 46d | 2025-09-08 | 2025-10-29 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | r&d | interior | npd | uk | initiation / validation / feasibility | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 1.0 | 51.0 | 0.0 | 0.0957446808510638 | 0.904255319148936 | 0.0 | 0.0 | 1.0 | 0.0 | current year | not specified | 3 | not specified | not specified | not specified | p | 460 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-07-01 | 2025-09-02 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | 0.0 | not specified | -46.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | 2025-09-08 00:00:00 | false | stage 1 - feasibility | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0
pmo000931 - howdens - new "oak lite" moulded range | p-0517 | pmo000931 - howdens - new "oak lite" moulded range | ross hawkings | scott mcbride | project | standalone project | standalone project | not specified | scott mcbride | r&d europe r&d europe uk r&d europe uk / france | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.0 | 2025-07-01 | 2025-09-02 | 46d | - launch date tbc - samples of ladder style due end of nov - samples to be shown to customer for feedback once received | - samples of ladder style due end of nov - samples to be shown to customer for feedback once received | - samples of ladder style due end of nov - samples to be shown to customer for feedback once received | not specified | green | sideways | red | red | green | green | yellow | green | 0 | 0 | 9.0 | 85.0 | 0.0 | 0.0 | 9.0 | 9.0 | 94.0 | 94.0 | 94.0 | 94.0 | 90.0 | 4.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-07-01 | 2025-09-02 | 0 | 46d | 2025-09-08 | 2025-10-29 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | r&d | interior | npd | uk | initiation / validation / feasibility | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 1.0 | 51.0 | 0.0 | 0.0957446808510638 | 0.904255319148936 | 0.0 | 0.0 | 1.0 | 0.0 | current year | not specified | 3 | not specified | not specified | not specified | p | 461 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-07-01 | 2025-09-02 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | 0.0 | not specified | -46.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | 2025-09-08 00:00:00 | false | stage 1 - feasibility | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0
pmo000932 - howdens - new flush reeded decor range | p-0518 | pmo000932 - howdens - new flush reeded decor range | ross hawkings | scott mcbride | project | standalone project | standalone project | not specified | scott mcbride | r&d europe r&d europe uk r&d europe uk / france | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.0 | 2025-07-01 | 2025-09-02 | 46d | - launch date tbc - schattdecor option being investigated to be shown to customers for feedback | - schattdecor option being investigated to be shown to customers for feedback | - schattdecor option being investigated to be shown to customers for feedback | not specified | green | sideways | red | red | green | green | yellow | green | 0 | 0 | 9.0 | 85.0 | 0.0 | 0.0 | 9.0 | 9.0 | 94.0 | 94.0 | 94.0 | 94.0 | 90.0 | 4.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-07-01 | 2025-09-02 | 0 | 46d | 2025-09-08 | 2025-10-29 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | r&d | interior | npd | uk | initiation / validation / feasibility | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 1.0 | 51.0 | 0.0 | 0.0957446808510638 | 0.904255319148936 | 0.0 | 0.0 | 1.0 | 0.0 | current year | not specified | 3 | not specified | not specified | not specified | p | 462 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-07-01 | 2025-09-02 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | 0.0 | not specified | -46.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | 2025-09-08 00:00:00 | false | stage 1 - feasibility | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0
stick paper core | p-0519 | stick paper core to replace eps foam core | james zhang | james zhang | project | standalone project | standalone project | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.0 | 2025-01-01 | 2025-06-26 | 127d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | sideways | red | red | green | green | yellow | green | 0 | 0 | 22.0 | 53.0 | 0.0 | 0.0 | 22.0 | 22.0 | 75.0 | 75.0 | 75.0 | 75.0 | 75.0 | 0.0 | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-09-09 | 2025-09-09 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | usd | other | not specified | not specified | not specified | ideation | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 1.0 | 50.0 | 50.0 | 0.293333333333333 | 0.706666666666667 | 0.0 | 0.0 | 1.0 | 0.0 | current year | not specified | 3 | not specified | not specified | not specified | p | 463 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | 0.0 | not specified | -127.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | stick paper core | not specified |  | not specified | 2025-09-09 00:00:00 | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0
retail catalogs 2025 | p-0521 | not specified | rohit ramakrishna | rohit ramakrishna | project | standalone project | standalone project | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.0 | 2025-01-01 | 2025-06-26 | 127d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | sideways | red | red | green | green | yellow | green | 0 | 0 | 22.0 | 0.0 | 0.0 | 0.0 | 22.0 | 22.0 | 22.0 | 22.0 | 22.0 | 22.0 | 22.0 | 0.0 | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-09-17 | 2025-09-17 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | usd | it | not specified | not specified | not specified | ideation | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 1.0 | 42.0 | 42.0 | 1.0 | 0.0 | 0.0 | 0.0 | 1.0 | 0.0 | current year | not specified | 3 | not specified | not specified | 1.0 | p | 465 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | 0.0 | not specified | -127.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | retail catalogs 2025 | not specified |  | not specified | 2025-09-17 00:00:00 | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0
retail catalogs 2026 | p-0522 | not specified | rohit ramakrishna | rohit ramakrishna | project | standalone project | standalone project | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.0 | 2025-01-01 | 2025-06-26 | 127d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | sideways | red | red | green | green | yellow | green | 0 | 0 | 22.0 | 0.0 | 0.0 | 0.0 | 22.0 | 22.0 | 22.0 | 22.0 | 22.0 | 22.0 | 22.0 | 0.0 | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-09-17 | 2025-09-17 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | usd | it | not specified | not specified | not specified | ideation | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 1.0 | 42.0 | 42.0 | 1.0 | 0.0 | 0.0 | 0.0 | 1.0 | 0.0 | current year | not specified | 3 | not specified | not specified | 1.0 | p | 466 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | 0.0 | not specified | -127.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | retail catalogs 2026 | not specified |  | not specified | 2025-09-17 00:00:00 | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0
solidworks upgrade | p-0523 | we are currently using solidworks 2020, which is no longer supported and has performance issues, including frequent slowdowns. this project aims to upgrade to a supported version to improve stability, speed, and ensure continued vendor support. | kaia simson | kaia simson | project | standalone project | standalone project | not specified | not specified | it it-eu | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.28 | 2025-09-30 | 2025-12-01 | 45d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | sideways | red | green | red | green | yellow | green | 0 | 0 | 2.0 | 1.0 | 17.0 | 12.0 | 2.0 | 3.0 | 2.0 | 1.0 | 32.0 | 20.0 | 19.0 | 1.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-10-28 | 2025-09-26 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | it | not specified | not specified | eu | ideation | not specified | reduce risk | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.488888888888889 | 1.0 | 33.0 | 0.0625 | 0.03125 | 0.53125 | 0.375 | 0.0625 | 0.9375 | current year | not specified | 3 | not specified | not specified | not specified | p | 467 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | -272.0 | not specified | -158.0 | not specified | -45.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | bau | 0.0 | one | not specified | solidworks upgrade | not specified |  | not specified | 2025-09-26 12:39:51 | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.28
pmo000991 - packaging unification - austria - dana | p-0524 | it is a vave initiative, part of packaging unification project already launched in uk and denmark. currently ongoing in germany and now starting in austria | vera pissaia | vera pissaia | project | standalone project | standalone project | not specified | vera pissaia | r&d europe r&d europe central | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.03 | 2025-09-25 | 2025-11-13 | 36d | datasheets development ongoing documentation provided by the factories was not enough to execute the task | part of the datasheets have been received waiting feedback from remaining 4 suppliers (kellner&kunze, brangs&heinrichs, antalis and wellpappe forchheim) follow up sent to them yesterday, expected to have all documentation on 29/10 g1 date to be locked by 03/10 | datasheets to be completed by 31/10 quoting to start 03/10 - this week we need confirmation if anthony will be the responsible person for quoting in this project or we thomas pfaffel (?) | not specified | green | sideways | red | yellow | red | green | yellow | green | 0 | 0 | 11.0 | 73.0 | 1.0 | 2.0 | 2.0 | 10.0 | 75.0 | 66.0 | 87.0 | 85.0 | 1.0 | 84.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-07-01 | 2025-09-02 | 0 | 46d | 2025-10-28 | 2025-10-28 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | r&d | multiple | vave | central eu | ideation | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 0.694444444444444 | 1.0 | 1.0 | 0.126436781609195 | 0.839080459770115 | 0.0114942528735632 | 0.0229885057471264 | 0.862068965517241 | 0.137931034482759 | current year | not specified | 3 | not specified | not specified | not specified | p | 468 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-07-01 | 2025-09-02 | not specified | not specified | 2025-01-28 | 2025-04-10 |  |  | 2025-05-28 | 2025-06-23 | not specified | -86.0 | not specified | -72.0 | not specified | -36.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | 2025-10-08 00:00:00 | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.03
pmo000992 - packaging unification - austria - domoferm | p-0525 | it is a vave initiative, part of packaging unification project already launched in uk and denmark. currently ongoing in germany and now starting in austria | vera pissaia | vera pissaia | project | standalone project | standalone project | not specified | vera pissaia | r&d europe r&d europe central | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.0 | 2025-07-01 | 2025-09-02 | 46d | datasheets under development a list of questions has been sent to the factory for clarification, waiting feedback | expecting to receive the list from the factory by 29/10 datasheets to be concluded by 31/10 g1 date to be locked by 03/10 | quoting to start from 03/11 - confirmation required if anthony will be quoting or thomas pfaffel (?) | not specified | green | sideways | red | red | green | green | yellow | green | 0 | 0 | 69.0 | 88.0 | 0.0 | 19.0 | 68.0 | 59.0 | 155.0 | 155.0 | 176.0 | 157.0 | 139.0 | 18.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-07-01 | 2025-09-02 | 0 | 46d | 2025-10-23 | 2025-10-28 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | r&d | multiple | vave | central eu | ideation | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 1.0 | 6.0 | 1.0 | 0.392045454545455 | 0.5 | 0.0 | 0.107954545454545 | 0.880681818181818 | 0.119318181818182 | current year | not specified | 3 | not specified | not specified | not specified | p | 469 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-07-01 | 2025-09-02 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | 0.0 | not specified | -46.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | 2025-10-08 00:00:00 | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0
project lego | 71534 | entry wood hybrid product line | jonathan funk | not specified | project | standalone project | standalone project | not specified | not specified | not specified | not specified | not specified | stephen ambrosia | cliff birch | not specified | not specified | not specified | npi / npd | na - windows: commercial - product & pricing | engineering | l1 (identified) | on track | 71534.0 | not specified | project dashboard | project finance dashboard | 0.0 | 2025-01-01 | 2025-06-26 | 127d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | sideways | red | red | green | green | yellow | green | 0 | 0 | 22.0 | 0.0 | 0.0 | 0.0 | 22.0 | 22.0 | 22.0 | 22.0 | 22.0 | 22.0 | 22.0 | 0.0 | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-10-15 | 2025-10-15 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | usd | transformation | not specified | not specified | not specified | ideation | not specified | increase revenue | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not planned (l2 to l4) | not specified | 1.0 | on track | 1.0 | 14.0 | 14.0 | 1.0 | 0.0 | 0.0 | 0.0 | 1.0 | 0.0 | current year | n | 3 | not specified | not specified | not specified | p | 470 | 1.0 | 1.0 | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | 0.0 | not specified | -127.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | project lego | not specified |  | not specified | 2025-10-15 00:00:00 | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0
interior door late stage configuration - autoline maximization | 76360 | the hypothesis of this project, is that by utilizing our autolines to make untrimmed doors, we will achieve cost out and better delivery in our molded door category. the financials for this will be worked through and submitted in this project, before moving to l2. | jim copeland | not specified | project | standalone project | standalone project | not specified | not specified | not specified | not specified | not specified | jim copeland | kayce hunt | not specified | not specified | not specified | not specified | na - doors & dist: commercial - product & pricing | not specified | l0 (idea) | on track | 76360.0 | not specified | project dashboard | project finance dashboard | 0.0 | 2025-10-16 | 2026-04-15 | 130d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | sideways | yellow | green | yellow | green | yellow | green | 0 | 0 | 3.0 | 0.0 | 19.0 | 0.0 | 3.0 | 4.0 | 22.0 | 22.0 | 22.0 | 22.0 | 22.0 | 0.0 | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-10-28 | 2025-10-15 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | usd | transformation | not specified | not specified | not specified | ideation | not specified | cost reduction | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not planned (l2 to l4) | 1.0 | 1.0 | on track | 0.0769230769230769 | 1.0 | 14.0 | 0.136363636363636 | 0.0 | 0.863636363636364 | 0.0 | 1.0 | 0.0 | 2026 | n | 3 | not specified | not specified | not specified | p | 471 | 1.0 | 1.0 | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | -288.0 | not specified | -293.0 | not specified | -130.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | interior door late stage configuration - autoline maximization | not specified |  | not specified | 2025-10-15 00:00:00 | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0
flat panel - center of excellence - production on pur lines | 76391 | use pur lines in grinnell and pataskala to intercompany support door plants with hollow core flat panel doors | william leslie | not specified | project | standalone project | standalone project | not specified | not specified | not specified | not specified | not specified | will leslie | chris romanello | not specified | not specified | not specified | manufacturing | na - doors & dist: commercial - product & pricing | not specified | l1 (identified) | on track | 76391.0 | not specified | project dashboard | project finance dashboard | 0.52 | 2025-10-02 | 2026-01-09 | 72d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | sideways | red | green | red | green | yellow | green | 0 | 0 | 2.0 | 12.0 | 81.0 | 158.0 | 2.0 | 14.0 | 253.0 | 253.0 | 253.0 | 95.0 | 95.0 | 0.0 | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-27 | 2025-01-01 | 2025-06-26 | 0 | 127d | 2025-10-28 | 2025-10-21 | not specified | 1 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | usd | transformation | not specified | not specified | not specified | ideation | not specified | cost reduction | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not planned (l2 to l4) | not specified | 1.0 | on track | 0.277777777777778 | 1.0 | 8.0 | 0.00790513833992095 | 0.0474308300395257 | 0.320158102766798 | 0.624505928853755 | 1.0 | 0.0 | 2026 | n | 3 | not specified | not specified | not specified | p | 472 | 1.0 | 1.0 | not specified | not specified | not specified | not specified | 2025-01-01 | 2025-06-26 | not specified | not specified | [6 empty] | not specified | -274.0 | not specified | -197.0 | not specified | -72.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | flat panel - center of excellence - production on pur lines | not specified |  | not specified | 2025-10-21 00:00:00 | false | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0.52
smartsheet improvements pmo eu | p-0529 | initiative to update current dashboards, documentation management and resource management tool implementation for eu | vera pissaia | vera pissaia | project | standalone project | standalone project | not specified | vera pissaia | r&d europe | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | on track | not specified | not specified | project dashboard | project finance dashboard | 0.0 | 2025-07-01 | 2025-09-02 | 46d | add the high level status of the project in rows below. | summarize the accomplishments for the week. | provide a look ahead to upcoming milestones and activities. | if support is needed, check the support needed flag and provide detail. | green | sideways | red | red | green | green | yellow | green | 0 | 0 | 9.0 | 85.0 | 0.0 | 0.0 | 9.0 | 9.0 | 94.0 | 94.0 | 94.0 | 94.0 | 90.0 | 4.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0 | 2025-10-28 | 2025-07-01 | 2025-09-02 | 0 | 46d | 2025-10-28 | 2025-10-28 | not specified | 0 | not specified | not specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | not specified | 0.0 | not specified | not specified | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | active | eur | r&d | multiple | sustaining | eu | ideation | not specified | not specified | on track | approved | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  | not specified | not specified | not specified | on track | 1.0 | 1.0 | 1.0 | 0.0957446808510638 | 0.904255319148936 | 0.0 | 0.0 | 1.0 | 0.0 | current year | not specified | 3 | not specified | not specified | not specified | p | 473 | 1.0 | not specified | not specified | not specified | not specified | not specified | 2025-07-01 | 2025-09-02 | not specified | not specified | [6 empty] | not specified | 0.0 | not specified | 0.0 | not specified | -46.0 | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | not specified | dates not set | dates not set | dates not set | dates not set | dates not set | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | not specified | not specified | not specified | not specified | not specified | 0.0 | one | not specified | not specified | not specified |  | not specified | 2025-10-28 00:00:00 | true | not specified | not specified | not specified | not specified | not specified | not specified | not specified |  |  |  | 0