## Sheet1
# | Name | Stage | Weekly status | IT Project Manager | Initiative Owner | Accountable Workstream | Interdependencies | IT implementation complexity | Total overall IT Costs (Expense + Capex, recurring and one-time) | Estimated Start Date of IT Work | Estimated End Date of IT Work | L4 forecast date | Estimated Start Date of IT Work_to_Interdependencies_days
1846 | canada controls | l3 (planned) | on hold | cyndi maples | richard chin | na - windows: manufacturing - canada | it | medium | not specified | 2023-10-11 | 2025-06-05 | 2025-07-17
2089 | [st. apollinaire] remove installation sheet on finish products | l1 (identified) | on hold | not specified | stephane berthiaume | na - windows: manufacturing - canada | it | not specified | not specified |  |  | 2024-05-28
2791 | upgrade phone system - outgoing voicemail for employee info | l0 (idea) | on track | jeff landry | sam mccoy | na - doors & dist.: manufacturing - northeast | it | not specified | 0.2
3533 | [uk; 2023 idea; enabler] - life tracking | l1 (identified) | on hold | not specified | joanne norton | uk: commercial | it | not specified | not specified |  |  | 2023-12-29
3537 | [uk; 2023 idea; volume] - uk fire door inspection & after-care service | l3 (planned) | on track | adam painter | andrew clements | uk: commercial | legal; it | medium | not specified | 2024-02-26 | 2024-12-31 | 2025-09-01
3539 | #bud24 [uk; 2023 idea; volume] - uk open cpq tool (fpp) | l1 (identified) | on track | nat stringfellow | phil boardman | uk: commercial | it | large | 0.1353 | 2024-04-16 | 2025-04-30 | 2025-11-28
3541 | uk - live chat customer service (enabler) | l3 (planned) | on hold | not specified | philip beickler | uk: commercial | it | medium | not specified | 2024-08-01 | 2026-06-01 | 2025-03-03
3554 | [uk; 2023 idea; enabler] - automate e-mail marketing | l1 (identified) | on hold | not specified | richard guest | uk: commercial | it | not specified | not specified
3563 | uk - ecomm increase for customers sheffield | l3 (planned) | on hold | not specified | clair edwards | uk: commercial | it | small | not specified | 2023-10-06 | 2023-12-30 | 2024-01-02
3593 | [uk; 2023 idea; volume] - enter market for steel doors & frames uk | l3 (planned) | on hold | it pm not required | lisa ward | uk: commercial | engineering; it | large | not specified | 2026-12-31 | 2026-12-31 | 2025-01-31
4575 | [uk, ideation session 2023] e2e it system integration (automation) | l1 (identified) | on hold | not specified | emily mosley | uk: manufacturing | it | not specified | not specified
4581 | [uk, ideation session 2023] fg inventory optimisation | l1 (identified) | on hold | not specified | emily mosley | europe: freight & logistics | it | not specified | not specified
4597 | [uk, ideation session 2023], enabler - reduce paperuse through automation (automation) sheffield | l1 (identified) | on hold | not specified | russel hurst | uk: manufacturing | it; engineering | not specified | not specified
4605 | [uk, ideation session 2023] implement vmi | l0 (idea) | on hold | not specified | ben hall-evans | europe: sourcing (direct & indirect) | it; legal | not specified | not specified
4731 | [no; 2023 ideas; enabler]-digitalization of customer service: vra #addhc | l3 (planned) | on track | richard guest | jenny lewton | nordics: commercial - norway | it | medium | 0.05527503666666667 | 2024-03-18 | 2025-03-26 | 2025-09-30
4784 | * [sw; 2023 ideas; ]-cpq - sweden and norway quote system internal & external pmo live prj eu - #bud24 #addhc | l3 (planned) | some issues | nat stringfellow | lisa sterndalen | nordics: commercial - sweden | it | large | 0.7546 | 2023-12-01 | 2025-05-02 | 2025-10-31
4868 | [dk; 2023 idea; enabler] - cost + on all products (specially commercial products) | l2 (validated) | on hold | not specified | harjinder malhi | europe: spend control tower | it | not specified | not specified |  |  | 2024-01-01
5112 | test #training kw | l1 (identified) | on track | not specified | kim wright | training 001 | hr; it; legal; engineering | not specified | not specified
5308 | [europe, ideation session 2023] item level data availability (indirect) | l1 (identified) | on hold | not specified | kristiina klemm | europe: sourcing (direct & indirect) | it | not specified | not specified
5310 | [europe, ideation session 2023] item master standartization | l2 (validated) | on hold | not specified | ivan kozatsenko | europe: sourcing (direct & indirect) | it | small | not specified |  |  | 2024-06-30
5312 | [europe, ideation session 2023] ui clarification for data input | l2 (validated) | on hold | not specified | ivan kozatsenko | europe: sourcing (direct & indirect) | it | small | not specified | 2023-11-02 | 2023-12-29 | 2023-12-29
5314 | [europe, ideation session 2023] workflows - make them more robust and fast | l2 (validated) | on hold | not specified | ivan kozatsenko | europe: sourcing (direct & indirect) | it | small | not specified |  |  | 2024-07-31
5320 | spital: skins - laminate sheets standardization for dana #efficiency | l3 (planned) | on track | it pm not required | thomas ecker | dach: manufacturing - austria | it | small | 0.0 | 2025-04-30 | 2025-11-30 | 2025-12-31
5488 | [europe, ideation session 2023] s&op software tools/systems (not for demand forecasting)(s&op - enabler) | l1 (identified) | on hold | not specified | paul middleton | europe: freight & logistics | it | not specified | not specified
5589 | switch to lower cost provider to reduce price on product #training | l2 (validated) | on track | not specified | stephanie wen | training 001 | it; engineering | not specified | 0.0 |  |  | 2023-10-27
11824 | create a out of production training center/program | l0 (idea) | on hold | not specified | david jones | na - doors & dist.: manufacturing - network | hr; legal; engineering; it | not specified | not specified
11864 | *#bud24 howdens oak lite npi | submitted for l4 approval | on track | it pm not required | ross hawkings | uk: commercial | it; engineering | small | not specified | 2024-09-02 | 2024-10-18 | 2025-06-02
11901 | **[vpi spokane] - project harmoney west in-house lamination | l3 (planned) | on track | jeff landry | john neill (jw) | na - windows: manufacturing - vinyl & vpi | it | small | 0.0 | 2024-06-01 | 2025-03-06 | 2025-08-16
12120 | use 3rd-party fulfillment networks | l1 (identified) | on hold | not specified | nick seagers | [to be deleted] na - doors & dist.: doors retail sales | it | not specified | not specified
12128 | create pro ecommerce site for traditional customers | l1 (identified) | on hold | jon gies | nick seagers | na - ops: customer service | it | medium | not specified | 2023-10-23 | 2024-03-31 | 2024-06-15
12141 | parts business (warranty/consumer/dealers/ecommerce) | l1 (identified) | on hold | sheri schrier | tim chu | na - ops: customer service | it | medium | not specified |  |  | 2025-03-04
12278 | [de; idea 2023; process] - (track & trace)/kundenportal | l3 (planned) | on track | it pm not required | joanna turnbull | dach: commercial - germany | it; hr | medium | 0.013145000000000004 | 2024-01-22 | 2026-01-30 | 2026-10-01
12304 | [de; fpp; enabler] - technology upgrade for eoffer - camos 365 | l1 (identified) | on hold | not specified | martin ott | dach: commercial - germany | it | not specified | not specified
12305 | **[de; fpp; efficiency] - expansion of domoferm to switzerland #addhc #wavenotbudgeted | l3 (planned) | on track | it pm not required | daniel walther | dach: commercial - switzerland | hr; it; engineering | medium | 0.0 | 2024-06-03 | 2026-01-16 | 2026-07-02
12344 | [ch; idea 2023; efficiency] - basware | l1 (identified) | on track | awaiting it pm appointment | wouter broek | dach: commercial - switzerland | it | medium | not specified |  |  | 2024-12-31
12352 | [ch; idea 2023; efficiency] - e-commerce webshop (stock products) forward integration #wavenotbudgeted | l3 (planned) | on track | karolin koch | sujivan thanabalasingam | dach: commercial - switzerland | it; hr; legal | small | 0.055000000000043986 | 2024-03-11 | 2025-11-17 | 2025-11-17
12359 | [ch; idea 2023; efficiency] - order quality | l3 (planned) | on hold | karolin koch | sujivan thanabalasingam | dach: commercial - switzerland | it | medium | not specified | 2024-04-01 | 2024-05-31 | 2024-12-31
12366 | [ch; idea 2023; volume] - steelcontainer for switzerland | l2 (validated) | on hold | markus ellinger | philipp schär | dach: commercial - switzerland | hr; it | small | not specified |  |  | 2024-12-31
12371 | **[ch; idea 2023; efficiency] - doors-system solutions (enabler cpqo) #addhc #wavenotbudgeted | l3 (planned) | on track | lisa schulze-egberding | thomas staub | dach: commercial - switzerland | it; hr | large | 1.8960356249999986 |  |  | 2025-08-29
12374 | [at; idea 2023; efficiency] - service partner portal | l3 (planned) | on track | karolin koch | gertraud scheuchel | dach: commercial - austria | it | medium | 0.10395000000000003 | 2024-08-19 | 2025-12-19 | 2025-11-28
12380 | [at; idea 2023; volume] - fixglazing into configurator - cpq (at p1) | l3 (planned) | on hold | karolin koch | paul weissbach | dach: commercial - austria steel | engineering; it | medium | not specified | 2024-01-01 | 2024-12-31 | 2025-03-31
12394 | [at; idea 2023; volume] - high-end (dana) showroom expansion (at p2) | l2 (validated) | on hold | it pm not required | gertraud scheuchel | dach: commercial - austria | it; legal | small | not specified | 2025-04-01 | 2025-06-30 | 2025-08-01
12403 | [at; idea 2023; growth] - know-how building - cpq - process optimazition (enabler for 12391) | l3 (planned) | on hold | it pm not required | jurge beyer-reiter | dach: commercial - austria steel | engineering; it | small | not specified | 2024-01-15 | 2025-11-30 | 2027-04-01
12404 | [at; idea 2023; growth] - end customer configurator (direct report & b2b) (at p2) | l3 (planned) | on track | karolin koch | christoph eibl | dach: commercial - austria | it | medium | 0.1359622 | 2024-08-01 | 2027-01-18 | 2027-01-15
12562 | [france, ideation session 2023] it risk management | l1 (identified) | on hold | not specified | jérôme raynouard | support functions: global it - europe | it | not specified | not specified
12569 | product lifecycle management | l2 (validated) | on hold | it pm not required | aurelien lamothe | france: commercial | it; engineering | small | not specified | 2024-01-15 | 2024-04-19 | 2024-06-28
12615 | bremgarten: cnc frames production capacity upgrade - add second bmb #strategy #bud24 #bud25 #growth #brownfield | l1 (identified) | on track | it pm not required | michaela vahle | dach: manufacturing - switzerland | it; legal | small | 0.04253920000000001 | 2023-11-01 | 2024-11-30 | 2028-07-01
12635 | [germany, ideation session 2023] automation of bbe (steel) (automation, swivel bending) first machine | l2 (validated) | on hold | it pm not required | dennis schröder | dach: manufacturing - germany steel | it | small | not specified | 2024-03-04 | 2024-12-31 | 2025-05-31
12636 | [germany, ideation session 2023] automated swivel bending bos (steel) (automation) | l3 (planned) | on track | it pm not required | boris wewer | dach: manufacturing - germany steel | it | small | 0.027500000000000004 | 2024-03-04 | 2025-05-16 | 2025-07-01
12640 | [austria, ideation session 2023] include laser in customized frames process (steel) (throughput) | l2 (validated) | on hold | awaiting it pm appointment | ahmet ali topakkaya | dach: manufacturing - austria steel | it | large | not specified |  |  | 2025-02-14
12650 | germany supply chain: hbw e2e automation oettingen #strategy #addhc #bigrock | l2 (validated) | some issues | karolin koch | daniel wenz | dach: manufacturing - germany | it; legal | large | 2.838055 | 2023-11-01 | 2028-05-14 | 2028-07-18
12653 | oettingen: mila2.0 core production line #strategy #bigrock #sustaining #efficiency #growth | l3 (planned) | on track | it pm not required | matthias stimpfle | dach: manufacturing - germany | engineering; it | small | not specified | 2025-09-29 | 2025-12-23 | 2027-10-01
12676 | [germany, ideation session 2023] automated production line for customized frames bos (steel) (automation) | l3 (planned) | some issues | awaiting it pm appointment | boris wewer | dach: manufacturing - germany steel | it | small | 0.09900000000000002 | 2025-01-01 | 2026-04-30 | 2026-07-01
12685 | spital: new folding line and laminate line (automation) #strategy #bigrock #efficiency #sustaining | l2 (validated) | on track | it pm not required | bernhard maierhofer | dach: manufacturing - austria | engineering; legal; it | large | 0.23251459000000002 | 2027-03-01 | 2029-09-30 | 2029-12-02
12690 | [austria, ideation session 2023] tmf re-evaluation-replacement (payroll) | l1 (identified) | on track | not specified | katharina böhm | support functions: hr | hr; it; legal | not specified | not specified
12696 | [austria, ideation session 2023] refurbishment hage 2 | l3 (planned) | on track | it pm not required | ahmet ali topakkaya | dach: manufacturing - austria steel | it | medium | 0.0 | 2024-09-30 | 2025-02-17 | 2026-03-31
12707 | [europe, ideation session 2023] automate sales and financial reporting | submitted for l1 approval | on track | graham whetton | dalbir dubb | europe: spend control tower | it | large | not specified
12710 | #addhc [europe, ideation session 2023] audit software license usage | l3 (planned) | on hold | rachael horton-farmer | rachael horton-farmer | support functions: global it - europe | it | medium | not specified | 2024-01-01 | 2024-07-31 | 2024-12-31
12742 | [europe, ideation session 2023] standardize broadband agreements | l0 (idea) | on hold | not specified | rachael horton-farmer | support functions: global it - europe | it | not specified | not specified
12743 | [europe, ideation session 2023] review and optimize it service vendors | l0 (idea) | on hold | not specified | rachael horton-farmer | support functions: global it - europe | it | not specified | not specified
12762 | #addhc [europe, ideation session 2023] enabler - enabler - establish a dedicated master data team | l2 (validated) | on track | graham whetton | graham whetton | support functions: global it - europe | it | large | 0.6204000000000001 | 2024-11-01 | 2024-12-31 | 2025-04-01
12780 | [fr; 2023 ideas] -ar process improvement - overdue invoices | l3 (planned) | on hold | emmanuel vaghi | audrey penelle | france: manufacturing | it; legal | small | not specified | 2024-02-29 | 2024-09-30 | 2024-10-04
12785 | enabler : improve customer support through delivery tracker | l2 (validated) | on track | it pm not required | lilian ragazzi | france: commercial | it | medium | not specified | 2024-06-03 | 2024-07-05 | 2024-07-15
12793 | new product: steel doors for collective buildings | l2 (validated) | on hold | emmanuel vaghi | angela bullock | france: commercial | engineering; it | medium | not specified | 2024-11-30 | 2025-01-22 | 2025-02-26
12796 | pod : new product duritop (german range) | l2 (validated) | on hold | emmanuel vaghi | anne renon | france: commercial | it | small | not specified | 2024-02-01 | 2024-02-29 | 2024-03-08
12798 | [fr; 2023 ideas; growth]-new product: moisture-resistant doors for humid environments | l1 (identified) | on hold | not specified | peter gibb | france: commercial | engineering; it | not specified | not specified
12800 | pod : offre puerta vales | l2 (validated) | on hold | emmanuel vaghi | frederich l’helguen | france: commercial | it; engineering | medium | not specified | 2024-08-30 | 2024-12-03 | 2025-01-14
12801 | gh : huisserie fin de chantier gamme déco | l1 (identified) | on hold | emmanuel vaghi | damien kovac | france: commercial | engineering; it | small | not specified |  |  | 2024-06-21
12812 | #bud24 enabler npd initiatives - product structure & attributer uplift - door slab & transom generic [po-imp-pim_phase1] | l2 (validated) | on track | emmanuel vaghi | emmanuel vaghi | france: commercial | it | medium | 0.0 | 2024-12-02 | 2025-01-04 | 2025-09-15
13035 | ar automation | l0 (idea) | on hold | not specified | stan johnson | support functions: finance | it | not specified | not specified
13036 | otc automation | l0 (idea) | on hold | not specified | stan johnson | support functions: finance | it | not specified | not specified
13037 | automate expense reporting | l0 (idea) | on hold | not specified | melanie baker | support functions: finance | it | not specified | not specified
13039 | global shared services | l0 (idea) | on track | not specified | michael leon | support functions: finance | it | not specified | not specified
13040 | collections workflow system | l0 (idea) | on hold | not specified | stan johnson | support functions: finance | it | not specified | not specified
13041 | integrate bswift monthly insurance charges | l0 (idea) | on hold | not specified | mona moisa | support functions: finance | it; hr | not specified | not specified
13042 | bs reconciliation sytem (automation) | l0 (idea) | on track | not specified | michael leon | support functions: finance | it | not specified | not specified
13043 | desktop rpa (ex uipath) | l0 (idea) | on hold | not specified | andrew larkins | support functions: finance | it | not specified | not specified
13053 | leverage one stream for more automation/standard work | l1 (identified) | on hold | not specified | kimberly yagla | support functions: finance | it | not specified | not specified
13069 | na titan standard cost | l3 (planned) | on hold | cyndi maples | florence kennedy ward | support functions: finance | it | medium | not specified | 2023-01-23 | 2027-02-18 | 2027-10-28
13078 | gl wands removal | l1 (identified) | on hold | not specified | tracy melsness | support functions: finance | it | not specified | not specified
13079 | simplify ppe process | l1 (identified) | on hold | not specified | tracy melsness | support functions: finance | it | not specified | not specified
13080 | purchase req matrix workflow | l1 (identified) | on hold | not specified | alex moss | support functions: finance | it | not specified | not specified
13090 | collections tool | l1 (identified) | on hold | not specified | anne carter | support functions: finance | it | not specified | not specified
13092 | rpa | l1 (identified) | on hold | not specified | elena wallace | support functions: finance | it | not specified | not specified
13173 | increase price realization via list price adjustment #training | l2 (validated) | on track | not specified | rainer frerichs | training 001 | it; engineering | not specified | not specified |  |  | 2024-01-12
13202 | simplification of european it landscape | l1 (identified) | on hold | not specified | rachael horton-farmer | support functions: global it - europe | it | not specified | not specified
13203 | *uk ed - composite door (inc fire) and swedoor uk spec | l3 (planned) | on hold | amer basic | tony pell | uk: commercial | it; engineering; hr; legal | large | not specified | 2024-04-01 | 2025-08-29 | 2025-03-10
13375 | sap/cfin viability | l0 (idea) | on hold | not specified | michael leon | support functions: finance | it | not specified | not specified
13376 | tier1 erp | l0 (idea) | on hold | not specified | michael leon | support functions: finance | it | not specified | not specified
13378 | europe ssc - eu basware implementation | l1 (identified) | on hold | not specified | anne carter | support functions: finance | it | not specified | not specified
13379 | cfin treasury module integration | l0 (idea) | on hold | not specified | mona moisa | support functions: finance | it | not specified | not specified
13380 | finish out sap cfin rollout | l0 (idea) | on hold | not specified | michael leon | support functions: finance | it | not specified | not specified
13382 | risk management information system (rmis) | l3 (planned) | on track | fabio rivera | kelly beegle | support functions: global legal | it | medium | 0.590623 | 2022-12-01 | 2025-09-12 | 2025-11-10
13385 | maximize onestream reporting capabilities | l1 (identified) | on hold | not specified | kimberly yagla | support functions: finance | it | not specified | not specified
13386 | cost center vs profit center | l1 (identified) | on hold | not specified | tracy melsness | support functions: finance | it | not specified | not specified
13391 | contract management dashboard | l0 (idea) | on hold | not specified | sam lee | support functions: finance | it | not specified | not specified
13394 | globally streamline data sharing with audit (pwc & ey) | l1 (identified) | on hold | not specified | george snyder | support functions: finance | it | not specified | not specified
13395 | streamline data sharing within finance | l1 (identified) | on hold | not specified | benjamin martinez | support functions: finance | it | not specified | not specified
13401 | basware ic approval flow improvement | l1 (identified) | on hold | not specified | elena wallace | support functions: finance | it | not specified | not specified
13403 | snow tickets | l0 (idea) | on hold | not specified | mike crawford (r2r) | support functions: finance | it | not specified | not specified
13405 | efficiency increase for sox | l1 (identified) | on hold | not specified | eszter lamara-maloviczki | support functions: finance | it | not specified | not specified
13406 | incoming document handling | l1 (identified) | on hold | not specified | anne carter | support functions: finance | it | not specified | not specified
13407 | docucenter | l1 (identified) | on hold | not specified | anne carter | support functions: finance | it | not specified | not specified
13664 | thd gcc design builder launch | submitted for l2 approval | on track | not specified | colleen creese | na - doors & dist: commercial - sales | it | medium | 0.25 | 2024-11-29 | 2025-03-29 | 2025-12-31
13744 | **[enabler] demand-driven planning and execution | l3 (planned) | on hold | heath webster | steve cooney | na - ops: supply chain | it | large | not specified | 2025-04-01 | 2026-03-03 | 2026-06-26
13751 | buyer / planner workbench | l3 (planned) | on hold | fabio rivera | emily cochrane | na - ops: supply chain | it | medium | not specified | 2025-04-15 | 2026-03-17 | 2027-01-19
13845 | [rantoul] remove paperwork from assembly areas. | l1 (identified) | on hold | not specified | bill brinkoetter | na - windows: manufacturing - premium & components | it | not specified | not specified
13847 | [rantoul] fix/replace the preflush. need a backflush. | l1 (identified) | on hold | not specified | bill brinkoetter | na - windows: manufacturing - premium & components | it | not specified | not specified
13855 | [rantoul] automated clear to build platform/ all parts in building to build unit. | l0 (idea) | on hold | not specified | kris anderson | na - windows: manufacturing - premium & components | it | not specified | not specified
13875 | [rantoul] - pps | l1 (identified) | on hold | not specified | steve satterlee | na - windows: manufacturing - premium & components | it | not specified | not specified
13880 | [rantoul] - titan enhancements | l1 (identified) | on hold | not specified | bill brinkoetter | na - windows: manufacturing - premium & components | it | not specified | not specified
13891 | [rantoul] scan confirmation | l0 (idea) | on hold | not specified | brittany pomrenke | na - windows: manufacturing - premium & components | it | not specified | not specified
13908 | [grinnell doors] foam fill interior doors vs solid core materials | l0 (idea) | on hold | not specified | troy dillon | na - doors & dist.: manufacturing - midwest & steel | engineering; it | not specified | not specified
13909 | [grinnell doors] foam fill steel door slabs like fiberglass | l0 (idea) | on hold | not specified | troy dillon | na - doors & dist.: manufacturing - midwest & steel | it; engineering | not specified | not specified
13922 | [grinnell doors] steel production level load | l1 (identified) | on hold | not specified | troy dillon | na - doors & dist.: manufacturing - midwest & steel | it | not specified | not specified |  |  | 2025-06-30
13993 | [ringtown] move local barcode server to cloud based solution | l1 (identified) | on track | jeff landry | joshua yeager | na - windows: manufacturing - vinyl & vpi | it | not specified | not specified |  |  | 2026-04-30
13995 | [ringtown] allow ptm access to domain password reset and unlock | l1 (identified) | on track | ryan russel | joshua yeager | na - windows: manufacturing - vinyl & vpi | it | not specified | not specified |  |  | 2026-04-30
13998 | [ringtown] add wirelss coverage to blue building | l1 (identified) | on hold | not specified | joshua yeager | na - windows: manufacturing - vinyl & vpi | it | not specified | not specified
13999 | [ringtown] add serial scanning into shopfloor shipping | l1 (identified) | on track | not specified | joshua yeager | na - windows: manufacturing - vinyl & vpi | it | not specified | not specified
14001 | [ringtown] add telemetry system to pits | l1 (identified) | on hold | not specified | joshua yeager | na - windows: manufacturing - vinyl & vpi | it | not specified | not specified
14002 | [ringtown] add rfid to ppe machines | l0 (idea) | on hold | not specified | joshua yeager | na - windows: manufacturing - vinyl & vpi | it | not specified | not specified
14027 | [ringtown] - scan inventory continously (racking module) | l1 (identified) | on hold | not specified | joshua yeager | na - windows: manufacturing - vinyl & vpi | it | not specified | not specified
14092 | product photography in-house studio | l0 (idea) | on hold | not specified | james vandenbulcke | [to be deleted] na - doors & dist.: doors retail sales | it | not specified | not specified
14118 | move acquired companies to unified accounting system | l0 (idea) | on hold | not specified | michael leon | support functions: finance | it | not specified | not specified
14119 | fixed asset data sharing | l1 (identified) | on hold | not specified | beth gesner | support functions: finance | it | not specified | not specified
14172 | implement new t&a system to replace old as400 | submitted for l3 approval | on track | awaiting it pm appointment | barbara mayer | support functions: hr | it | small | 0.09570000000000001 |  |  | 2025-08-31
14201 | [europe, ideation session 2023] european category reporting (sku rationalisation enabler) | l2 (validated) | on hold | graham whetton | angela bullock | europe: product rationalisation | it | medium | not specified |  |  | 2024-12-20
14202 | [europe, ideation session 2023] european discontinuation process (enabler) | l3 (planned) | on hold | graham whetton | angela bullock | europe: commercial rationalisation | it | small | not specified |  |  | 2024-12-20
14233 | [europe, ideation session 2023] sku heatmap analysis | l1 (identified) | on hold | not specified | graham whetton | europe: product rationalisation | it | not specified | not specified
14237 | [europe, ideation session 2023] product definition cleanup | l0 (idea) | on hold | not specified | stefan gazsi | europe: product rationalisation | it | not specified | not specified
14238 | [europe, ideation session 2023] master data clean-up (enabler) | l1 (identified) | on hold | not specified | stefan gazsi | europe: product rationalisation | it | not specified | not specified
14240 | [europe, ideation session 2023] creation of an online shop template for containerbusiness | l3 (planned) | on hold | karolin koch | henrik helmer | dach: commercial - germany steel | it | medium | not specified | 2024-01-08 | 2025-12-30 | 2025-05-09
14269 | [europe, ideation session 2023] discontinue bought-in asia doors at sheffield | l0 (idea) | on hold | not specified | russell birchley | europe: product rationalisation | legal; it | not specified | not specified
14499 | enabler - new phone system for dk sales | l0 (idea) | on hold | not specified | henrik rechnagel pedersen | support functions: global it - europe | it | not specified | not specified
14525 | diversified transport sales strategy | l0 (idea) | on hold | not specified | chris miller | europe: freight & logistics | legal; it | not specified | not specified
14546 | [europe, ideation session 2023] track & trace delivery system | l0 (idea) | on hold | not specified | ian ross | europe: freight & logistics | it | not specified | not specified
14554 | [europe, ideation session 2023] faster load planning | l1 (identified) | on hold | not specified | ian ross | europe: freight & logistics | it | not specified | not specified
14566 | [europe, ideation session 2023] terminal operation improvement | l1 (identified) | on hold | taivo kinsiveer | joel vanhatalo | europe: freight & logistics | it | medium | not specified | 2023-09-01 | 2023-10-15 | 2025-12-31
14656 | [europe, ideation session 2023] autonomous forklift implementation | l0 (idea) | on hold | not specified | chris harcombe | europe: freight & logistics | it; engineering; hr | not specified | not specified
14700 | [europe, ideation session 2023] document integration for efficiency | l0 (idea) | on hold | not specified | markus ellinger | europe: freight & logistics | it | not specified | not specified
14714 | [europe, ideation session 2023] reduced picking costs | l0 (idea) | on hold | not specified | michael prinz | europe: freight & logistics | engineering; it | not specified | not specified
15158 | spital: new edgeband laquering #efficiency | l3 (planned) | some issues | awaiting it pm appointment | jürgen steinberger | dach: manufacturing - austria | it | medium | not specified | 2025-11-17 | 2026-09-25 | 2026-10-09
15217 | austria supply chain: warehouse management system | l3 (planned) | on track | karolin koch | dominik marek | dach: manufacturing - austria | it; legal | medium | 0.4537192000000001 | 2024-06-05 | 2027-01-20 | 2027-08-31
15319 | productmap steel doors | l0 (idea) | on hold | not specified | jurge beyer-reiter | dach: commercial - germany steel | engineering; it; legal | not specified | not specified
15321 | robotic forklift loading at shipping | l1 (identified) | on hold | not specified | royce alexander | na - doors & dist.: manufacturing - midwest & steel | it | not specified | not specified
15351 | kissimmee - require orders of full pallets for prehang from retail customers | l0 (idea) | on hold | not specified | travis smith | na - doors & dist.: manufacturing - southeast / michigan | it | not specified | not specified
15378 | turns - list price override hold code | l0 (idea) | on hold | not specified | mike doescher | [to be deleted] na - doors & dist.: doors channel strategy | it | not specified | not specified
15408 | utilize a two tier distribution system | l1 (identified) | on hold | not specified | noora mcgee | na - ops: freight / logistics | it; hr | not specified | not specified
15415 | [enabler] create a single customer all inclusive data descriptor | l0 (idea) | on hold | kurt dimos | sid hines | na - ops: customer service | it | large | not specified
15503 | harmonizing configurator (germany and austria) spg - cpq | l1 (identified) | on hold | not specified | jurge beyer-reiter | dach: commercial - austria steel | it; engineering | not specified | not specified
15727 | review of titan items #s deactivate/remove unnecessary duplicates | l1 (identified) | on hold | not specified | stephanie jordan | na - doors & dist.: manufacturing - south central | it | not specified | not specified
15739 | warranty cost reduction | l0 (idea) | on hold | not specified | bradley humphrey | na - doors & dist.: manufacturing - south central | it; engineering | not specified | not specified
15836 | [enabler] plan for every part initiative | l3 (planned) | on hold | ryan russel | josh bui | na - ops: supply chain | it | medium | not specified | 2024-04-07 | 2024-10-31 | 2025-01-04
16000 | archival / document management system (dms) | l0 (idea) | on hold | not specified | rachael horton-farmer | support functions: global it - europe | legal; it | not specified | not specified
16061 | european shared services | l3 (planned) | some issues | meridith fix | anne carter | support functions: finance | it; hr | large | 4.880353499999999 | 2024-06-11 | 2026-06-05 | 2028-04-24
16068 | purchase requisition form (sap ip) workflow tool | l2 (validated) | on track | jens schjott | endre hornyak | support functions: finance | it | medium | not specified | 2023-10-12 | 2023-11-03 | 2024-01-24
16104 | wave bud #24cost optimisation 2-shell frames domoferm gänserndorf | l3 (planned) | on track | it pm not required | gerhard aichinger | dach: manufacturing - austria steel | it | small | 0.0 | 2025-11-12 | 2025-12-05 | 2025-12-15
16185 | [vpi] 531 - 591 intersection redesign - v2 | l3 (planned) | on track | ty pearsall | grant leavell | na - windows: quality | engineering; it | medium | 0.0 | 2025-02-22 | 2025-07-31 | 2025-07-11
16188 | [vpi] 511 internal narrow bar bracket | l1 (identified) | on hold | not specified | benjamin bissell | na - windows: manufacturing - vinyl & vpi | engineering; it | not specified | not specified |  |  | 2024-03-12
16298 | critical event management: mass notifications phase i | l3 (planned) | on track | meridith fix | rocco procopio | support functions: eh&s | hr; legal; it | small | 0.17623400000000006 | 2023-12-27 | 2024-05-31 | 2025-05-08
16312 | employee relief fund / standard for employee fundraising | l2 (validated) | some issues | julie bridges | melissa farrington | support functions: c&c | hr; it; legal | small | 0.073328 | 2023-11-01 | 2024-06-28 | 2024-09-03
16315 | consolidate and assign ownership of external corporate (jeld-wen, inc.) communications channels and content strategy | l1 (identified) | on track | not specified | caryn klebba | support functions: communications | it; hr; legal | not specified | not specified
16318 | my jeld-wen intranet overhaul for all employees to encompass sharepoint, cmd, jw connect, hr portal (#enabler) | l3 (planned) | on hold | julie bridges | sarah whitmire | support functions: communications | it; hr; legal | large | not specified | 2024-01-01 | 2024-05-31 | 2025-01-31
16319 | explore options for improved real-time and video translations at large events / videos #enabler | l2 (validated) | on track | michael schwaiger | gaynor campbell | support functions: communications | it | small | 0.1 | 2024-01-16 | 2024-01-31 | 2024-03-12
16327 | comms role clarity | l3 (planned) | on hold | sue murphy | sarah whitmire | support functions: communications | it | small | not specified | 2023-12-01 | 2023-12-15 | 2024-01-31
16329 | corporate website | l1 (identified) | on track | not specified | caryn klebba | support functions: communications | it | not specified | not specified
22368 | supply chain financing - na | l1 (identified) | on hold | not specified | brian luke | support functions: working capital | it | not specified | not specified
22377 | create easy nwc vs ebitda calculation for payment terms vs pricing | l1 (identified) | on hold | not specified | brian luke | support functions: working capital | it | not specified | not specified
22578 | **[validated offline] special order program rebuild including catalog, displays and retail commercial actions- windows portion | l3 (planned) | on track | mike crawford (brm) | divya kapoor | na - windows: commercial - product & pricing | it | medium | 0.061 | 2024-10-01 | 2025-10-28 | 2026-07-31
22712 | develop global knowledge base - enabler | l1 (identified) | on track | not specified | andrew hoel | na - ops: customer service | it | not specified | not specified
23021 | [mt vernon] window serialization | l1 (identified) | on hold | not specified | floyd chamberlain | na - windows: manufacturing - vinyl & vpi | it | not specified | not specified |  |  | 2024-01-31
23071 | interior prehung retail packaging standardization | l3 (planned) | on track | ryan russel | greg hughes | na - doors & dist: commercial - product & pricing | it; engineering | small | 0.149071 | 2024-01-01 | 2024-05-31 | 2025-09-30
23237 | centralize invoicing (and credit memos) | l1 (identified) | on track | not specified | stan johnson | support functions: working capital | it | not specified | not specified
23241 | global system standardization | l0 (idea) | on track | not specified | mike crawford (r2r) | support functions: working capital | it | not specified | not specified
23242 | o2c reconstruction | l0 (idea) | on track | not specified | stan johnson | support functions: working capital | it | not specified | not specified
23245 | ease of payment | l1 (identified) | on hold | not specified | brian luke | support functions: working capital | it | not specified | not specified
23998 | infrastructure - legacy windows server os upgrades | l3 (planned) | on track | brad duffey | gordon greenland | support functions: global it - infrastructure / service desk | it | large | 0.03244025 | 2024-01-09 | 2025-03-31 | 2025-06-27
24050 | machine prep coordinated and streamlined | l0 (idea) | on hold | not specified | deby cigler | na - doors & dist.: manufacturing - west | it | not specified | not specified
31612 | #wavenotbudgeted - pmo live prj eu - enabler: ax2012 and baan migration to ax d365 (spg) | l2 (validated) | on track | lisa schulze-egberding | michael schwaiger | support functions: global it - europe | it | medium | 1.7160000000000002 | 2024-02-12 | 2026-06-30 | 2026-01-31
31670 | **inside sales / quote lead nurture | l2 (validated) | on track | jeff stetson | loree shano | na - windows: commercial - sales | hr; it | small | 0.0 |  |  | 2024-12-16
31804 | [example] increase operating uptime | l2 (validated) | on hold | adam painter | julien loo | training 001 | engineering; it | small | not specified |  |  | 2024-01-31
32069 | [dist-net] merge edi vans | l3 (planned) | on hold | max kane | mike doescher | support functions: global it - north america | it | medium | not specified | 2024-06-21 | 2024-06-27 | 2025-01-31
32070 | [dist-net] uc phones across all abs/mmi sites with an integrated call center | l0 (idea) | on hold | not specified | james micka | na - doors & dist.: manufacturing - west | it | not specified | not specified
32074 | [sacm] it training for maint | l0 (idea) | on hold | not specified | chris mcleod | na - doors & dist.: manufacturing - west | it | not specified | not specified
32084 | [dist-net] journal upload | l1 (identified) | on hold | not specified | karen king | na - doors & dist.: manufacturing - west | it | not specified | not specified
32085 | [dist-net] non-cash settlement of ic balances | l0 (idea) | on hold | not specified | john slusser | na - doors & dist.: manufacturing - south central | it | not specified | not specified
32144 | enterprise it testing coe application & support team | l0 (idea) | on hold | not specified | dan stroup | support functions: global it - north america | it | not specified | not specified
32789 | contract lifecycle management (clm) - additional phases (eur and na) | l3 (planned) | on track | awaiting it pm appointment | lisa parrish | support functions: global legal | it; legal | medium | 0.753187 | 2025-06-23 | 2025-11-15 | 2026-02-10
32794 | lead information governance (ig) initiative; implementing policies, processes, and related tools | l3 (planned) | on track | not specified | danielle darling | support functions: global legal | it | large | 0.8039999999999998 | 2024-03-31 | 2025-06-30 | 2026-08-31
32795 | identify a document management system | l2 (validated) | on hold | mike crawford (r2r) | danielle darling | support functions: global legal | it | medium | not specified | 2024-11-01 | 2024-12-31 | 2025-02-28
32797 | automate invention disclosure form (idf) process | l3 (planned) | on hold | chris hill | jan morton | support functions: global legal | it | medium | not specified | 2024-01-08 | 2024-08-13 | 2024-08-15
32858 | automation of titan deployment | l2 (validated) | on hold | not specified | sailaja kandala | support functions: global it - north america | it | medium | not specified |  |  | 2024-03-30
32859 | automation of qql deployments | l1 (identified) | on hold | jamal mebane | sailaja kandala | support functions: global it - infrastructure / service desk | it | large | not specified
32860 | automation of grc (tool replacement) and audit data collection and review | l2 (validated) | on hold | jamal mebane | sailaja kandala | support functions: global it - infrastructure / service desk | it | large | not specified | 2024-01-09 | 2024-02-24 | 2024-03-23
32862 | qql solution and hosting review | l3 (planned) | on hold | jamal mebane | sailaja kandala | support functions: global it - infrastructure / service desk | it | medium | not specified | 2024-04-02 | 2024-04-13 | 2024-04-16
32863 | titan cloud hosting and dr redesign | l3 (planned) | on hold | jamal mebane | sailaja kandala | support functions: global it - infrastructure / service desk | it | medium | not specified | 2023-08-01 | 2024-12-24 | 2025-09-02
32867 | evaluate uc communications for professional track workers | l3 (planned) | some issues | jamal mebane | gordon greenland | support functions: global it - infrastructure / service desk | it | medium | 0.21488000000000002 | 2024-08-27 | 2024-11-09 | 2025-10-03
32870 | cybersecurity - cyberark to microsoft epm migration | l3 (planned) | on hold | brad duffey | miles romello | support functions: global it - cyber | it | large | not specified | 2024-03-04 | 2024-08-27 | 2024-08-27
32872 | cybersecurity - transition from okta to microsoft | l3 (planned) | on track | brad duffey | m.j. vaidya | support functions: global it - cyber | it | large | 0.12806499999999998 | 2023-10-17 | 2025-08-30 | 2025-08-29
32876 | eliminate non-voip phone costs | l3 (planned) | some issues | jamal mebane | m.j. vaidya | support functions: global it - infrastructure / service desk | it | medium | 0.011170999999999999 |  |  | 2025-09-05
32877 | implement standard operating model between it, advanced engineering, and ptms | l1 (identified) | on hold | not specified | christian suarez | support functions: global it - north america | it | not specified | not specified
32883 | customer experience - centralized software license management | l3 (planned) | on hold | not specified | ravi ramaraj | support functions: global it - infrastructure / service desk | it | small | not specified | 2024-06-25 | 2024-07-30 | 2024-07-12
33119 | [stayton] warehouse optimization | l1 (identified) | on track | jeff landry | ryan lahoda | na - windows: manufacturing - vinyl & vpi | it | not specified | not specified |  |  | 2025-06-27
33321 | solidworks upgrade | l1 (identified) | on hold | adam painter | glyn hauser | support functions: r&d | it | not specified | not specified
33323 | decommission vienna dc to atea | l1 (identified) | on hold | not specified | jens schjott | support functions: global it - europe | it | not specified | not specified
33324 | ax upgrade germany (finance) | l1 (identified) | on hold | not specified | markus ellinger | support functions: global it - europe | it | not specified | not specified
33326 | enabler: ifas erp migration | l1 (identified) | on track | lisa schulze-egberding | markus ellinger | support functions: global it - europe | it | medium | 4.151400000000001 |  |  | 2026-10-31
33328 | single european h&s portal | l1 (identified) | on track | not specified | merit vain | support functions: global it - europe | it | not specified | not specified
33330 | move streamserve in sweden to lasernet and autoform | l1 (identified) | on hold | not specified | peter sorensen | support functions: global it - europe | it | not specified | not specified
33331 | synergy system is outdated and needs upgrade | l1 (identified) | on hold | awaiting it pm appointment | adam painter | support functions: global it - europe | it | not specified | not specified
33332 | ap automation uk | l1 (identified) | on hold | not specified | mark hampton | support functions: finance | it | not specified | not specified
33333 | cyber security risk mitigation old os clients | l1 (identified) | on hold | not specified | jens schjott | support functions: global it - europe | it | not specified | not specified
33334 | #addhc cyber security data security for euc/mobile devices | l3 (planned) | on hold | jens schjott | jens schjott | support functions: global it - europe | it | medium | not specified | 2023-11-01 | 2024-02-14 | 2024-02-14
33336 | enabler: as/400 operating system going out of support | submitted for l4 approval | on track | karolin koch | markus ellinger | support functions: global it - europe | it | small | 0.0 | 2023-11-01 | 2024-03-31 | 2025-09-19
33338 | risk-mitigation: fenocs - upgrade of os and db | l3 (planned) | on hold | ben hamnett | peter sorensen | support functions: global it - europe | it | medium | not specified | 2023-11-15 | 2024-03-01 | 2024-04-26
33339 | enabler - migrate to standardised reporting and analytics toolsets #addhc | l3 (planned) | some issues | ben hamnett | graham whetton | support functions: global it - europe | it | small | 0.25630000000000014 | 2023-12-15 | 2025-07-31 | 2025-07-31
33342 | cost saving and rsik opportunity for eixsting domains - ie dooria, uk, oettingen etc. domains | l1 (identified) | on hold | not specified | jens schjott | support functions: global it - europe | it | not specified | not specified
33343 | dms gänserndorf- in- and outbound with workflows for 3-way matches, automatic invoice verification, legal deposit, etc. | l1 (identified) | on hold | not specified | michael schwaiger | support functions: global it - europe | it; legal | not specified | not specified
33345 | migrate filemaker ch erp solution to strategic erp ms d365 | l1 (identified) | on hold | not specified | markus ellinger | support functions: global it - europe | it | not specified | not specified
33346 | migrate baan bos emsdetten de erp solution to strategic erp ms d365 | l1 (identified) | on hold | not specified | markus ellinger | support functions: global it - europe | it | not specified | not specified
33347 | eoffer edi link integration germany | l3 (planned) | on track | lisa schulze-egberding | markus ellinger | support functions: global it - europe | it | medium | 0.10461317350000002 | 2024-02-19 | 2026-01-12 | 2026-01-05
33349 | migrate ppsl au/hu erp solution to strategic erp ms d365 | l1 (identified) | on hold | not specified | markus ellinger | support functions: global it - europe | it | not specified | not specified
33350 | migrate as400 de erp solution to strategic erp ms d365 | l1 (identified) | on hold | not specified | markus ellinger | support functions: global it - europe | it | not specified | not specified
33351 | migrate ic2000 dk erp solution to strategic erp titan | l1 (identified) | on hold | not specified | peter sorensen | support functions: global it - europe | it | not specified | not specified
33352 | migrate prms se/no erp solution to strategic erp titan | l1 (identified) | on hold | not specified | peter sorensen | support functions: global it - europe | it | not specified | not specified
33353 | migrate xal dk erp solution to strategic erp titan | l1 (identified) | on hold | not specified | peter sorensen | support functions: global it - europe | it | not specified | not specified
33359 | backup of azure devops jeld-wen org | l1 (identified) | on hold | not specified | rachael horton-farmer | support functions: global it - europe | it | not specified | not specified
33360 | minimize sox controls manual work | l1 (identified) | on track | not specified | jens schjott | support functions: global it - europe | it | not specified | not specified
33363 | standardise to calendar months | l1 (identified) | on track | not specified | michael leon | support functions: finance | it | not specified | not specified
33364 | fire extinguish system it room - ussel | l1 (identified) | on hold | not specified | jérôme raynouard | support functions: global it - europe | it | not specified | not specified
33365 | it room waterproofing - eauze | l1 (identified) | on hold | not specified | jérôme raynouard | support functions: global it - europe | it | not specified | not specified
33366 | finance sytem in lenti - upgrade requirements | l3 (planned) | on hold | amer basic | jérôme raynouard | support functions: global it - europe | it | small | not specified | 2023-10-02 | 2023-11-10 | 2023-11-17
33367 | at spital - dc2 has insufficent fire security | l1 (identified) | on hold | karolin koch | sebastian neuhofer | support functions: global it - europe | it | large | not specified |  |  | 2024-05-01
33368 | old clients in production in emsdetten | l1 (identified) | on hold | not specified | sven ortmeier | support functions: global it - europe | it | not specified | not specified
33369 | old hardware servers in oettingen (filenet, wayrts) | l1 (identified) | on hold | amer basic | sven ortmeier | support functions: global it - europe | it | not specified | not specified
33370 | group policies not alligned | l1 (identified) | on track | not specified | jens schjott | support functions: global it - europe | it | not specified | not specified
33371 | telephony system brilon | l1 (identified) | on hold | not specified | sven ortmeier | support functions: global it - europe | it | not specified | not specified
33372 | rakvere server room uses sprinkler extinguishing system that needs to be changed to gas or vacuum based setup | l1 (identified) | on hold | not specified | taivo kinsiveer | support functions: global it - europe | it | not specified | not specified
33373 | aizkraukle facilities using radio signal setup for mpls line | l1 (identified) | on hold | not specified | taivo kinsiveer | support functions: global it - europe | it | not specified | not specified
33374 | atgfs006 - domoferm database (pdm) | l1 (identified) | on hold | karolin koch | sebastian neuhofer | support functions: global it - europe | it | large | not specified
33375 | set up vlan structure for gänserndorf | l1 (identified) | on hold | rachael horton-farmer | sebastian neuhofer | support functions: global it - europe | it | large | not specified
33376 | cisco wifi controller redundancy | l1 (identified) | on track | not specified | fredrik jonasson | support functions: global it - europe | it | not specified | not specified
33377 | failure of service (central firewall logstor) | l1 (identified) | on track | not specified | fredrik jonasson | support functions: global it - europe | it | not specified | not specified
33378 | enabler - standardise data integration platforms and build out coe #addhc | l2 (validated) | on track | it pm not required | graham whetton | support functions: global it - europe | it | medium | 0.44000000000000006 |  |  | 2025-04-01
33514 | global application rationalization & optimization | l0 (idea) | on hold | not specified | dan stroup | support functions: global it - north america | it | not specified | not specified
33520 | sourcing/design/operations & product management (water based strategy) | l1 (identified) | on hold | not specified | lydia fritsch | europe: sourcing (direct & indirect) | engineering; it | not specified | not specified
33793 | pmo live prj eu - interface as400 (jeld-wen) to ax (bbe) for intercompany orders | submitted for l4 approval | on track | it pm not required | ersan gültekin | dach: commercial - germany steel | it | medium | 0.0 | 2023-10-24 | 2025-10-31 | 2025-07-15
34102 | cybersecurity - network segmentation - phase 1 - global sd-wan implementation (na) | l3 (planned) | on track | brad duffey | m.j. vaidya | support functions: global it - cyber | it | large | 1.6892403 | 2024-01-03 | 2025-04-25 | 2025-06-28
36462 | **[enabler] s&oe | l3 (planned) | on track | awaiting it pm appointment | steve cooney | na - ops: supply chain | it | small | not specified |  |  | 2025-03-22
36464 | ibp demand - product lifecycle/new product introduction | l3 (planned) | on hold | awaiting it pm appointment | trina phillips | na - ops: s&op | it | small | not specified | 2025-03-28 | 2025-04-04 | 2025-04-11
37438 | na cfin rollout / ssc & organization | l3 (planned) | on track | meridith fix | stan johnson | support functions: finance | it | medium | 4.692317999999999 | 2023-10-12 | 2024-01-31 | 2026-07-01
37462 | systems - lab data lims | l1 (identified) | on track | not specified | jason kantola | support functions: engineering | it; engineering | not specified | 0.75
37698 | ** [dist-net]warehouse management system - sacramento & rialto | l3 (planned) | some issues | fabio rivera | patrick smith | na - doors & dist.: manufacturing - west | it | large | 2.7639294 | 2025-03-17 | 2025-06-26 | 2025-07-14
37787 | cybersecurity - implement network access control | l3 (planned) | on hold | brad duffey | miles romello | support functions: global it - cyber | it | large | not specified | 2024-05-06 | 2025-03-20 | 2025-03-27
37792 | cybersecurity - 3rd party risk management - contractor access | l1 (identified) | on hold | brad duffey | ravi ramaraj | support functions: global it - cyber | it | not specified | not specified
37796 | cybersecurity - global secure access - (currently on hold) | l0 (idea) | on hold | not specified | ravi ramaraj | support functions: global it - cyber | it | not specified | not specified
37798 | samba upgrade titan servers | l1 (identified) | on hold | not specified | stephen morris | support functions: global it - infrastructure / service desk | it | not specified | not specified
37800 | cybersecurity - passwordless authentication (hello) - (wait until post intune deployment) | l1 (identified) | on hold | brad duffey | ravi ramaraj | support functions: global it - cyber | it | not specified | not specified
37802 | cybersecurity - removable media restriction | l1 (identified) | on hold | brad duffey | brad duffey | support functions: global it - cyber | it | medium | not specified | 2024-05-21 | 2024-12-07 | 2024-12-07
37916 | atgfs010 - qlikview server | l1 (identified) | on hold | karolin koch | sebastian neuhofer | support functions: global it - europe | it | not specified | not specified
38054 | advanced safety | l1 (identified) | on track | not specified | crystal gunn | support functions: eh&s | it; engineering; legal | not specified | 0.0
38055 | automate ehs audit checklist | l1 (identified) | on track | not specified | crystal pollin | support functions: eh&s | it | not specified | not specified
38056 | jw cell phones for all managers | l1 (identified) | on track | not specified | crystal pollin | support functions: eh&s | it | not specified | not specified
38066 | sustainability data ai enhancements | l1 (identified) | on track | not specified | eric rapp | support functions: eh&s | legal; it | not specified | not specified
38073 | engineering and asset management | l2 (validated) | on track | mike crawford (r2r) | rob barnett | support functions: engineering | engineering; it | small | not specified | 2024-06-11 | 2024-07-20 | 2025-09-27
38075 | machinery standardisation | l0 (idea) | on track | not specified | rob barnett | support functions: engineering | engineering; legal; it; hr | not specified | not specified
38130 | lift assist equipment to replace manual loading | l1 (identified) | on track | not specified | rob barnett | support functions: engineering | hr; it; legal; engineering | not specified | not specified
38133 | vr training | l1 (identified) | on track | not specified | lisa luis | support functions: eh&s | it | not specified | not specified
38171 | tablet usage for completing inspections | l0 (idea) | on track | not specified | william morgan | support functions: eh&s | it | not specified | not specified
38533 | *inventory control & cycle counting: windows pilot + remaining sites | l3 (planned) | on hold | chris hill | josh bui | na - ops: supply chain | it | large | not specified | 2025-07-07 | 2026-10-30 | 2027-08-07
38621 | hr systems & processes: implement wifi availability at the plant level | l0 (idea) | on hold | not specified | dani casey | support functions: hr | it | not specified | not specified
38636 | data analytics: data lake integration for peoplepoint and adp to allow automated dashboards | l1 (identified) | on hold | not specified | cassandra benoit | support functions: hr | it | not specified | not specified
38651 | hr systems & process: chatgpt | l0 (idea) | on hold | not specified | dani casey | support functions: hr | it | not specified | not specified
38654 | hr systems & processes: electronic employee files & secure document management solutions | l2 (validated) | on hold | not specified | dani casey | support functions: hr | it | not specified | not specified |  |  | 2024-04-30
38657 | hr systems & processes: onboarding/cross boarding implementation for jw | l1 (identified) | on hold | not specified | sue murphy | support functions: hr | it | not specified | not specified
38659 | compensation: build broad-based incentive plan (enterprise and manufacturing plans) | l1 (identified) | on track | not specified | jason weeks | support functions: hr | legal; it | not specified | not specified |  |  | 2025-01-01
38702 | talent management: succession planning & talent reviews | l2 (validated) | on hold | not specified | shanon wilson | support functions: hr | hr; it | small | not specified |  |  | 2024-07-31
38711 | enablement hr systems & processes: deploy/install ess access tools for bc employees | l0 (idea) | on hold | not specified | sharon delooze | support functions: hr | it | not specified | not specified
38712 | benefits: benefit advocacy center (bac) bot | l0 (idea) | on hold | not specified | karen monroe | support functions: hr | it; legal | not specified | not specified
39284 | erp pps/l upgrade, spital [enablement] | l3 (planned) | some issues | karolin koch | michael tasch | support functions: global it - europe | it | large | 0.021409564000000006 | 2024-02-09 | 2025-11-05 | 2025-12-10
39329 | *ibp supply - develop planning bom's | l2 (validated) | on hold | chad alterio | justin wilcox | na - ops: supply chain | it | medium | not specified |  |  | 2024-12-31
39369 | enabler: eu timekeeping - upgrade to pro wfm | l3 (planned) | on track | olusola ogidi | sharon delooze | support functions: hr | hr; it | large | 1.8523218501854004 | 2025-04-14 | 2025-11-07 | 2026-02-06
39395 | pmo live prj eu [enablement] - legacy windows server os risk- europe | l3 (planned) | on hold | ben hamnett | jens schjott | support functions: global it - europe | it | large | not specified | 2023-10-01 | 2025-03-31 | 2025-05-01
40532 | new contact centre & telephony upgrade (swi fpp) #bud24 #addhc (dependent on 39769 uk) | l3 (planned) | on track | ben hamnett | sujivan thanabalasingam | dach: commercial - switzerland | it | medium | 0.0688512 | 2024-01-05 | 2025-08-29 | 2024-07-26
40537 | #bud24 included: pmo live prj eu new contact centre & telephony upgrade (de fpp) #addhc | l3 (planned) | on hold | ben hamnett | ingo heger | dach: commercial - germany | it | medium | not specified | 2024-01-04 | 2025-09-30 | 2025-09-29
41127 | [enablement / risk reduction] pmo live prj eu - salesforce re-org #addhc | l3 (planned) | on track | richard guest | richard guest | support functions: global it - europe | it | large | 0.022000000000000002 | 2023-07-03 | 2023-09-29 | 2027-12-13
41582 | l2l - corp rollout (windows & doors) | l2 (validated) | on track | fabio rivera | rob barnett | support functions: engineering | it; engineering | small | not specified | 2023-09-05 | 2025-03-27 | 2025-03-29
41605 | cybersecurity - plant machine domain segregation | submitted for l2 approval | on hold | brad duffey | brad duffey | support functions: global it - cyber | it | large | not specified |  |  | 2025-01-27
41606 | cybersecurity - replace firewalls in klamath falls and logstor | l0 (idea) | on hold | not specified | ravi ramaraj | support functions: global it - cyber | it | not specified | not specified
41613 | cybersecurity - phishing | l0 (idea) | on hold | not specified | ravi ramaraj | support functions: global it - cyber | it | not specified | not specified
41620 | cybersecurity - web application gateway | l2 (validated) | on hold | brad duffey | ravi ramaraj | support functions: global it - cyber | it | medium | not specified | 2024-05-07 | 2024-07-31 | 2024-07-31
41625 | cybersecurity - audit dormant and external ad/azure account | l0 (idea) | on hold | not specified | ravi ramaraj | support functions: global it - cyber | it | not specified | not specified
41627 | coral springs wireless expansion | l3 (planned) | on hold | jeff landry | sailaja kandala | support functions: global it - infrastructure / service desk | it | small | not specified | 2024-01-15 | 2024-12-21 | 2025-01-21
41628 | cybersecurity - evaluate microsegmentation | l0 (idea) | on hold | not specified | ravi ramaraj | support functions: global it - cyber | it | not specified | not specified
41636 | cybersecurity - intune implementation | l0 (idea) | on hold | not specified | ravi ramaraj | support functions: global it - cyber | it | not specified | not specified
41640 | cybersecurity - migrate to azure/onedrive/sharepoint for file storage | l0 (idea) | on hold | not specified | ravi ramaraj | support functions: global it - cyber | it | not specified | not specified
41643 | oceanside network and phone upgrade | l3 (planned) | on hold | jamal mebane | gordon greenland | support functions: global it - infrastructure / service desk | it | medium | not specified | 2024-09-23 | 2025-02-15 | 2025-01-31
41705 | automated distribution groups | l0 (idea) | on track | not specified | joel busack | support functions: communications | it | not specified | not specified
41707 | sharepoint site collection | l0 (idea) | on hold | not specified | joel busack | support functions: global it - north america | it | not specified | not specified
43545 | sap single sign on for s4hana | submitted for l2 approval | on hold | jamal mebane | nicholas zeller | support functions: global it - infrastructure / service desk | it | small | not specified | 2023-11-01 | 2024-05-31 | 2024-06-07
46073 | move ibp dw to rides platform | l0 (idea) | on track | not specified | lee patterson | support functions: global it - north america | it | not specified | not specified
46075 | eliminate rpa toolset (blueprism) | l0 (idea) | on track | not specified | rohit ramakrishna | support functions: global it - north america | it | not specified | not specified
46077 | masterforex replacement | l0 (idea) | on hold | not specified | kurt dimos | support functions: global it - north america | it | not specified | not specified
46082 | erp standardization | l0 (idea) | on hold | not specified | kurt dimos | support functions: global it - north america | it | not specified | not specified
46086 | optimize accounting reporting for increased visibility | l0 (idea) | on hold | not specified | katelyn lattimore | support functions: global it - north america | it | not specified | not specified
46089 | bods 4.3 upgrade | l1 (identified) | on hold | not specified | rajasekar muthukrishnan | support functions: global it - north america | it | not specified | not specified
46767 | improved label printing solution | l0 (idea) | on hold | not specified | christian suarez | support functions: global it - north america | it | not specified | not specified
46798 | upgrade turns to run on azure | l0 (idea) | on hold | not specified | mike doescher | support functions: global it - north america | it | not specified | not specified
46818 | enhance servicenow workflows for ease of use by business team | l0 (idea) | on hold | not specified | jaya alakkat | support functions: global it - infrastructure / service desk | it | not specified | not specified
46829 | customer experience - email distribution lists | l0 (idea) | on hold | not specified | terry davis | support functions: global it - infrastructure / service desk | it | not specified | not specified
46832 | customer experience - network and hardware standards in plants | l0 (idea) | on hold | not specified | terry davis | support functions: global it - infrastructure / service desk | it | not specified | not specified
47877 | titan jboss upgrade | l3 (planned) | on hold | jamal mebane | kurt dimos | support functions: global it - north america | it | large | not specified | 2023-08-01 | 2024-03-30 | 2024-09-06
48847 | customer service transformation - austria steel | l3 (planned) | on hold | amer basic | markus weinzierl | dach: commercial - austria steel | it | large | not specified | 2025-03-03 | 2025-06-30 | 2029-06-30
50690 | finance it system harmonization - na | l2 (validated) | on hold | christina andert | stan johnson | support functions: finance | it | medium | not specified |  |  | 2025-09-30
51800 | eliminate progress dev server | l0 (idea) | on hold | not specified | john delgado | support functions: global it - infrastructure / service desk | it | not specified | not specified
51802 | centralize middleware tech | l0 (idea) | on hold | not specified | eric vancurler | support functions: global it - infrastructure / service desk | it | not specified | not specified
51804 | devops / dev secops transformation program from traditional it operating model | l0 (idea) | on hold | not specified | sailaja kandala | support functions: global it - infrastructure / service desk | it | not specified | not specified
51806 | review kubernates to drive improvements on ci/cd | l0 (idea) | on hold | not specified | sailaja kandala | support functions: global it - infrastructure / service desk | it | not specified | not specified
51807 | hybrid value chain architecture model | l0 (idea) | on hold | not specified | sailaja kandala | support functions: global it - infrastructure / service desk | it | not specified | not specified
51809 | customer experience - automated desktop & laptop computer configuration | l1 (identified) | on track | jamal mebane | terry davis | support functions: global it - infrastructure / service desk | it | small | 0.045 |  |  | 2024-01-02
51811 | customer experience - implement chargeback to plants and departments for all software and hardware. | l1 (identified) | on hold | jamal mebane | sailaja kandala | support functions: global it - infrastructure / service desk | it | medium | not specified
51812 | password writeback | l0 (idea) | on hold | not specified | ravi ramaraj | support functions: global it - cyber | it | not specified | not specified
51813 | password self-service reset | l0 (idea) | on hold | not specified | ravi ramaraj | support functions: global it - cyber | it | not specified | not specified
51814 | cybersecurity - hybrid join all computers to aad | l0 (idea) | on hold | not specified | ravi ramaraj | support functions: global it - cyber | it | not specified | not specified
51815 | change azure ad connect to sync on ad guid | l0 (idea) | on hold | not specified | ravi ramaraj | support functions: global it - cyber | it | not specified | not specified
51816 | server & workstation hardening | l0 (idea) | on hold | not specified | terry davis | support functions: global it - infrastructure / service desk | it | not specified | not specified
51817 | non-personal acct mgmt | l0 (idea) | on hold | not specified | ravi ramaraj | support functions: global it - cyber | it | not specified | not specified
51818 | domain registrar consolidation | l0 (idea) | on hold | not specified | terry davis | support functions: global it - infrastructure / service desk | it | not specified | not specified
51820 | configuration scanning using cis and/or tenable | l0 (idea) | on hold | not specified | terry davis | support functions: global it - infrastructure / service desk | it | not specified | not specified
51821 | all jw email only in outlook or owa | l0 (idea) | on hold | not specified | terry davis | support functions: global it - infrastructure / service desk | it | not specified | not specified
51822 | customer experience - certificate management tool | l1 (identified) | on hold | it pm not required | sailaja kandala | support functions: global it - infrastructure / service desk | it | medium | not specified
51825 | customer experience - gpo migration to mecm and/or intune | l0 (idea) | on hold | not specified | terry davis | support functions: global it - infrastructure / service desk | it | not specified | not specified
51826 | user file share migration to onedrive | l0 (idea) | on hold | not specified | terry davis | support functions: global it - infrastructure / service desk | it | not specified | not specified
51828 | utilize group managed service accts | l0 (idea) | on hold | not specified | terry davis | support functions: global it - infrastructure / service desk | it | not specified | not specified
51830 | align usernames across systems | l0 (idea) | on hold | not specified | terry davis | support functions: global it - infrastructure / service desk | it | not specified | not specified
51831 | chat bot for jw users | l0 (idea) | on hold | not specified | terry davis | support functions: global it - infrastructure / service desk | it | not specified | not specified
51833 | customer experience - software and hardware catalog purchases | l1 (identified) | on hold | not specified | terry davis | support functions: global it - infrastructure / service desk | it | not specified | not specified
51835 | remove telnet access for titan and require ssh | l0 (idea) | on hold | not specified | stephen morris | support functions: global it - infrastructure / service desk | it | not specified | not specified
51836 | eliminate file servers at the plant | l0 (idea) | on hold | not specified | stephen morris | support functions: global it - infrastructure / service desk | it | not specified | not specified
51838 | customer experience - automated computer configuration | l1 (identified) | on hold | not specified | terry davis | support functions: global it - infrastructure / service desk | it | not specified | not specified |  |  | 2024-04-30
51839 | vdi for contractor access | l0 (idea) | on hold | not specified | ravi ramaraj | support functions: global it - infrastructure / service desk | it | not specified | not specified
51950 | #bud24 customer document distribution web platform uplift | l0 (idea) | on track | emmanuel vaghi | celine mesureur | france: commercial | it; engineering | small | not specified | 2023-10-23 | 2023-10-28
52146 | [fr; 2023 ideas; pricing]- fr4 - price structure phase 2 (discount) | l1 (identified) | on hold | not specified | eric audu | france: commercial | it | not specified | not specified | 2024-06-01 | 2024-08-10
52211 | customer experience - technology refresh of the charlotte hq training room | l1 (identified) | on track | it pm not required | sailaja kandala | support functions: global it - infrastructure / service desk | it | medium | 0.225 |  |  | 2024-12-28
52356 | security upgrade - workstation update to windows 11 | l3 (planned) | on track | jamal mebane | m.j. vaidya | support functions: global it - infrastructure / service desk | it | small | 0.19817099999999999 | 2024-12-05 | 2024-12-05 | 2025-11-01
54306 | customer experience - lock down the use of non-personal accounts | l0 (idea) | on hold | not specified | ravi ramaraj | support functions: global it - cyber | it | not specified | not specified
54697 | customer experience - jwreportit update or replacement | l0 (idea) | on track | not specified | terry davis | support functions: global it - infrastructure / service desk | it | not specified | not specified
54781 | customer experience - consolidation of mobile device contracts and support for united states | l1 (identified) | on track | not specified | gordon greenland | support functions: global it - infrastructure / service desk | it | small | 0.1 |  |  | 2024-02-29
54837 | b+q new moulded door offering (2 new latvia skins) pmo000459 | l0 (idea) | on hold | not specified | ruth deardon | uk: commercial | it; engineering | not specified | not specified
54838 | readyfit communal top + side light options pmo000565 | l0 (idea) | on hold | not specified | ruth deardon | uk: commercial | it; engineering | not specified | not specified
54839 | secureset fd60 flat entrance door set range pmo000458 | l0 (idea) | on hold | not specified | ruth deardon | uk: commercial | engineering; it | not specified | not specified
54867 | [enabler] supplier enabled innovation | l1 (identified) | on hold | christian suarez | sean scarboro | na - ops sourcing | it; legal; engineering | medium | not specified |  |  | 2024-11-19
55056 | [mount vernon] l2l data base for spare parts | l1 (identified) | on track | not specified | donald marston | na - windows: manufacturing - vinyl & vpi | it | not specified | not specified
55176 | data management | l1 (identified) | on hold | not specified | missy seig | na - windows: manufacturing - premium & components | it | not specified | not specified
55487 | it asset management process and dashboard | l1 (identified) | on hold | it pm not required | sailaja kandala | support functions: global it - infrastructure / service desk | it | medium | not specified
55712 | ax for poland | l1 (identified) | on hold | not specified | jaroslaw norek | uk and france: exports | it | not specified | not specified
55885 | 3d laser machine for hse | l1 (identified) | on hold | markus ellinger | pavel beneš | dach: manufacturing - austria steel | it; legal | small | not specified |  |  | 2025-01-01
56233 | bremgarten: risk mitigation cnc door production #strategy #sustaining #efficiency #bud25 #brownfield | l2 (validated) | on track | awaiting it pm appointment | michaela vahle | dach: manufacturing - switzerland | it; legal | medium | not specified | 2025-10-01 | 2027-01-01 | 2028-01-01
56702 | [dist-net] computer assisted order entry door detail | l1 (identified) | on hold | not specified | curtis randall | na - doors & dist.: manufacturing - west | it | not specified | not specified
57155 | growth zargag region basel - taking over of local pms | l0 (idea) | on hold | not specified | rainer fischer | dach: commercial - switzerland | hr; it | not specified | not specified
57170 | esg data improvements | l2 (validated) | on track | not specified | carolyn payne | support functions: global legal | it | medium | not specified | 2024-06-20 | 2024-08-17 | 2025-03-31
57207 | **re-alignment of bend product line - product and operational | l3 (planned) | on track | mike crawford (brm) | cliff birch | na - windows: commercial - product & pricing | engineering; it | medium | not specified | 2025-10-31 | 2025-12-05 | 2026-02-14
57216 | eu infrastructure consolidation | l1 (identified) | on track | amer basic | jens schjott | support functions: global it - europe | it | medium | not specified | 2024-01-02 | 2024-05-31
57585 | european peoplepoint payroll interfaces | l3 (planned) | on track | charlotte fox | sharon delooze | support functions: hr | it; hr | medium | not specified | 2024-03-01 | 2025-08-22 | 2025-08-01
57805 | cybersecurity - network segmentation - phase 1 - global sd-wan implementation (eu) | l3 (planned) | some issues | ben hamnett | sven ortmeier | support functions: global it - europe | it | large | 0.062645 | 2024-02-27 | 2025-10-31 | 2025-10-10
58156 | european kronos payroll interface | l1 (identified) | on hold | not specified | sharon delooze | support functions: hr | it; hr | not specified | not specified
58231 | matrix pricing capabilities in titan | l0 (idea) | on track | not specified | claudia amaya | support functions: finance | it | not specified | not specified
58313 | us timekeeping | l0 (idea) | on track | not specified | stan johnson | support functions: finance | hr; it | not specified | not specified
58352 | servicenow integration with sap recruiting module | l0 (idea) | on hold | not specified | jaya alakkat | support functions: global it - north america | hr; it | not specified | not specified
58722 | connect karona’s erp (kqa) to mycarrier to pull freight quotes | l2 (validated) | on hold | it pm not required | karl heugel | na - doors & dist.: manufacturing - southeast / michigan | it | small | not specified | 2024-02-01 | 2024-05-31 | 2024-05-31
58826 | doc link application and os upgrade | l1 (identified) | on track | not specified | stephen morris | support functions: global it - cyber | it | not specified | 0.125
58962 | *iris | l3 (planned) | on track | christian suarez | emily cochrane | na - ops: supply chain | it | medium | 0.31097500000000006 | 2024-03-04 | 2025-12-27 | 2025-12-27
58964 | **enabler - project pluto raw material warehousing | l3 (planned) | question for offline discussion | christian suarez | justin wilcox | na - ops: supply chain | it | medium | not specified | 2024-05-28 | 2024-06-15 | 2025-09-27
58991 | improving stock/special information in titan | l0 (idea) | on track | christian suarez | nikki smith | na - ops: s&op | it | small | not specified
59216 | [enabler] ibp demand - visibility to store display demand in ibp | l3 (planned) | on hold | chad alterio | joe ellis | na - ops: s&op | it | medium | not specified | 2024-10-28 | 2024-11-15 | 2024-12-20
60502 | karona system pricing project | submitted for l2 approval | on track | awaiting it pm appointment | meredith aycock | na - doors & dist: commercial - sales | it | medium | not specified |  |  | 2025-08-29
60771 | [de, pm interior wood, 2024] portfolio hardware 2024/25 | l0 (idea) | on hold | not specified | wolfgang oswald | dach: commercial - germany | engineering; it | not specified | not specified | 2024-04-22 | 2024-09-16
61301 | [de; idea 2024; npi] stiba special sizes | l1 (identified) | on hold | not specified | wolfgang oswald | dach: commercial - germany | it; engineering | not specified | not specified
61302 | [de; idea 2023; enabler] online configurator for bauhaus (kilsgaard portfolio) | l0 (idea) | on track | not specified | michel michalik | dach: commercial - germany | it | not specified | not specified
61309 | produce 1200 doors in vpi east to reduce shipping cost. | l1 (identified) | on hold | not specified | garrett logan | na - windows: manufacturing - vinyl & vpi | it; engineering; hr | not specified | not specified
61928 | [geklont von #12376] expansion of dana-wood products to germany | l3 (planned) | on track | lisa schulze-egberding | roman wülferth | dach: commercial - germany | it | medium | 0.0870023 | 2024-09-01 | 2025-12-03 | 2025-11-18
62023 | critical event management - mass notifications phase ii | l1 (identified) | on track | not specified | rocco procopio | support functions: eh&s | it | not specified | not specified
62058 | lightguide ar projection on interior layup lines | l1 (identified) | on track | not specified | coskun cerit | na - doors & dist.: manufacturing - midwest & steel | it | not specified | not specified
62251 | en program scandinavia | l1 (identified) | on track | awaiting it pm appointment | nadezda melnikova | nordics: manufacturing - sweden | engineering; it | small | not specified |  |  | 2032-06-15
63955 | operation otif | l0 (idea) | on hold | not specified | troy fink | na - windows: manufacturing - vinyl & vpi | it | not specified | not specified
64034 | exterior door retail packaging update | l1 (identified) | on track | not specified | julia smith | na - doors & dist: commercial - marketing | it; engineering | not specified | not specified
64035 | packaging graphic number cross-reference system | l1 (identified) | on track | not specified | lindsay tinnell | na - doors & dist: commercial - marketing | engineering; it | not specified | not specified
64395 | cybersecurity - next gen firewall implementation | l3 (planned) | on track | brad duffey | m.j. vaidya | support functions: global it - cyber | it | medium | 0.12692400000000004 | 2024-07-26 | 2025-09-25 | 2025-09-25
64541 | increased use of shipping through abs | l0 (idea) | on track | not specified | jackie clark | na - ops: freight / logistics | it | not specified | not specified
64707 | howdens wk13 2025 npi - bridgemere moulded range | l2 (validated) | on hold | it pm not required | ross hawkings | uk: commercial | engineering; it | small | not specified |  |  | 2025-03-07
64855 | rocklin pva build monitors | l0 (idea) | on track | not specified | cary m moore | na - doors & dist.: manufacturing - west | it | not specified | not specified
65204 | enabler - eu price volume mix report - net sales & direct margin bridge | l2 (validated) | on track | graham whetton | sylvain auriault | europe: spend control tower | it | medium | 0.11000000000000001 | 2024-07-29 | 2025-04-30 | 2024-10-31
65214 | enabler - wall to wall profitability europe - pricing dashboard | l2 (validated) | on track | graham whetton | sylvain auriault | europe: spend control tower | it | large | 0.2706 | 2024-03-13 | 2025-06-30 | 2025-02-28
65414 | transition grand prairie to flush (usdm2) | l1 (identified) | on hold | not specified | nikki smith | na - ops: supply chain | it | not specified | not specified
65415 | transition wedowee from kathy (usdm1) to flush (usdm2) | l1 (identified) | on hold | not specified | nikki smith | na - ops: supply chain | it | not specified | not specified
65416 | transition coral springs from kathy (usdm1) to flush (usdm2) | l1 (identified) | on hold | not specified | nikki smith | na - ops: supply chain | it | not specified | not specified
65557 | [enabler] integration: foundational business data integration with salesforce | l1 (identified) | on track | awaiting it pm appointment | troy conroy | support functions: global it - north america | it | medium | not specified |  |  | 2024-10-04
65638 | automate trim saw processes for improved efficiency | l0 (idea) | on hold | not specified | tom perkins | na - doors & dist.: manufacturing - southeast / michigan | engineering; it | not specified | not specified
65752 | vorne system on layup lines | l0 (idea) | on track | not specified | tom perkins | na - doors & dist.: manufacturing - southeast / michigan | it | not specified | not specified
65753 | material flow from mercantile facility to ave a facility | l0 (idea) | on track | not specified | tom perkins | na - doors & dist.: manufacturing - southeast / michigan | engineering; it | not specified | not specified
66123 | distribution pricing | l1 (identified) | on track | not specified | victoria haugen | na - doors & dist: commercial - product & pricing | it | not specified | not specified
66677 | [germany, ideation session 2023] automated swivel bending bos #2 (steel) (automation) | l1 (identified) | on hold | not specified | boris wewer | dach: manufacturing - germany steel | it | not specified | not specified | 2024-06-03 | 2024-06-28
66882 | replacing aama label with glass bug | l1 (identified) | on track | not specified | chris enzler | na - windows: quality | it; engineering | not specified | not specified
66889 | north american warehousing strategy | l2 (validated) | on track | christian suarez | justin wilcox | na - ops: supply chain | it | medium | 0.45 | 2025-06-17 | 2026-02-09 | 2026-04-27
67358 | special order - retail distribution | submitted for l3 approval | on track | mike crawford (brm) | carmen wagner | na - doors & dist: commercial - sales | it | medium | not specified | 2024-06-05 | 2024-10-15 | 2025-01-11
67360 | france next gen cpq | l1 (identified) | on track | nat stringfellow | eric audu | france: commercial | it | not specified | not specified
67370 | na interim digital storefront for trad doors and distribution | l3 (planned) | on track | amy phillips | victoria haugen | na - doors & dist: commercial - sales | it; engineering | medium | 0.5724370000000001 | 2024-05-29 | 2025-12-31 | 2025-12-31
67406 | sunset old versions of basware in europe | l0 (idea) | on track | not specified | peter sorensen | support functions: global it - europe | it | not specified | not specified
68053 | **[enabler] north star delivery metric | l3 (planned) | on track | chris long | nikki smith | na - ops: supply chain | it | medium | 0.613603 | 2024-07-16 | 2024-10-25 | 2025-03-11
68248 | solve speed problems in r&d north caused by poor internet speed, solidworks upgrade from 2020 to 2024 | l0 (idea) | some issues | not specified | olar vallimaa | support functions: r&d | it; engineering | not specified | not specified
68315 | gh : end-of-job installation frame for technical products (huisserie fin de chantier technique) | l1 (identified) | on track | not specified | damien kovac | france: commercial | engineering; it | not specified | not specified
68615 | cybersecurity - identity and access management | l1 (identified) | on hold | ryan russel | miles romello | support functions: global it - cyber | it | not specified | not specified
68660 | plm sevax - das double action | l1 (identified) | on track | not specified | aurelien lamothe | france: commercial | it; engineering | not specified | not specified
68869 | [geklont von #12635] [germany, ideation session 2023] automation of bbe (steel) (automation, swivel bending) second machine | l1 (identified) | on hold | not specified | dennis schröder | dach: manufacturing - germany steel | it | not specified | not specified
69206 | distribution service/care integration into cx core | l2 (validated) | on hold | jamal mebane | brian gerello | na - doors & dist: commercial - sales | hr; it | medium | not specified | 2024-11-20 | 2024-12-31 | 2025-01-13
69294 | uk - replace synergy document management system/archive | l1 (identified) | on track | kaia simson | adam painter | support functions: global it - europe | it | small | not specified
69295 | ai/machine learning for ehs | l0 (idea) | on track | not specified | crystal pollin | support functions: eh&s | it | not specified | not specified
69343 | germany wood document archival system (filenet migration) | l1 (identified) | on track | not specified | markus ellinger | support functions: global it - europe | it | not specified | not specified
69785 | eu strategy project - digital product data transformation - cad / pdm / plm | submitted for l1 approval | on track | not specified | glyn hauser | uk: commercial | it | not specified | not specified
69854 | enabler - eu timekeeping - standardisation | l3 (planned) | some issues | charlotte fox | sharon delooze | support functions: hr | hr; it | large | 2.189375629709124 | 2025-02-07 | 2026-10-30 | 2027-01-28
69889 | connect teamguru to rides | l0 (idea) | on track | not specified | joel busack | support functions: global it - north america | it | not specified | not specified | 2024-09-04 | 2024-09-04
70040 | project compass - o2c-27 automation | submitted for l3 approval | on track | garrett farmer | elizabeth chaney | support functions: finance | it | medium | 2.5940350000000003 |  |  | 2025-04-11
70078 | bremgarten: cutting / middle layers / edging / molding #strategy #sustaining #efficiency #brownfield | l2 (validated) | on track | awaiting it pm appointment | michaela vahle | dach: manufacturing - switzerland | it; legal | medium | not specified | 2026-11-01 | 2027-01-31 | 2028-05-31
70079 | bremgarten: surface treatment & reconstruction of old production area #strategy #efficiency #brownfield | l2 (validated) | on track | awaiting it pm appointment | michaela vahle | dach: manufacturing - switzerland | it; legal | medium | not specified | 2029-01-01 | 2029-04-30 | 2030-09-30
70102 | eudr - eu deforestation regulation | l1 (identified) | on hold | not specified | jørgen knudsen | europe: sourcing (direct & indirect) | it | not specified | not specified
70123 | digital adoption platform (dap) enterprise training tool | submitted for l2 approval | on track | sheri schrier | mary lou mckeighan | na - ops: customer service | it; hr | small | 0.045 | 2026-04-01 | 2026-09-30 | 2027-01-09
70124 | territory expansion leveraging the talon hardware 2.0 platform | l3 (planned) | on hold | amy phillips | adam rummler | na - doors & dist: commercial - sales | it | small | not specified | 2025-05-27 | 2025-05-30 | 2025-10-17
70154 | talon hardware 2.0 integration with mmi | l3 (planned) | on track | max kane | adam rummler | na - doors & dist: commercial - sales | it | medium | 0.027602 | 2025-07-07 | 2025-11-19 | 2026-01-01
70212 | european digital product passport (dpp) | l1 (identified) | on track | not specified | jørgen knudsen | europe: product rationalisation | it | not specified | not specified
70409 | new product : steel frames for france - sourcing | l1 (identified) | on hold | not specified | damien kovac | france: commercial | engineering; it | not specified | not specified
70460 | customer care case management - enabler | l3 (planned) | on track | sheri schrier | ben brunworth | na - ops: customer service | it | medium | 0.0 | 2025-04-01 | 2025-04-26 | 2025-12-31
70520 | progressive output automation - ussel | l1 (identified) | on hold | not specified | lionel chancel | france: manufacturing | it | not specified | not specified
70523 | enabler: commercial excellence - export pl | submitted for l3 approval | on track | richard guest | thomas rathausky | uk and france: exports | it | medium | not specified | 2025-10-01 | 2026-04-30 | 2026-03-31
70524 | commercial excellence - ch | l3 (planned) | on track | richard guest | philipp schär | dach: commercial - switzerland | it | medium | not specified | 2026-01-01 | 2026-06-30 | 2026-06-30
70525 | commercial excellence - de wood ¦ enabler | l3 (planned) | on track | richard guest | christian wienand | dach: commercial - germany | it | medium | not specified | 2025-06-30 | 2025-07-30 | 2025-12-01
70526 | commercial excellence - de steel ¦ enabler | l3 (planned) | on track | richard guest | christian wienand | dach: commercial - germany steel | it | medium | not specified | 2025-06-30 | 2025-07-30 | 2025-12-29
70527 | commercial excellence - at wood | l3 (planned) | on track | richard guest | markus weinzierl | dach: commercial - austria | it | medium | not specified | 2024-10-31 | 2025-01-31 | 2025-12-22
70528 | commercial excellence - at steel | l3 (planned) | on track | richard guest | markus weinzierl | dach: commercial - austria steel | it | medium | not specified | 2024-10-31 | 2025-01-31 | 2025-12-22
70693 | enabler: commercial excellence - export hu | submitted for l3 approval | on track | richard guest | thomas rathausky | uk and france: exports | it | medium | not specified | 2025-10-01 | 2025-12-31 | 2026-02-27
70711 | enabler: commercial excellence - export hse | submitted for l3 approval | on track | richard guest | thomas rathausky | uk and france: exports | it | medium | not specified | 2026-01-30 | 2026-05-29 | 2025-05-19
70825 | structural pricing denmark | l1 (identified) | on track | not specified | dorthe schou | nordics: commercial - denmark | it | not specified | not specified
70990 | titan conversion - aix to linux | l3 (planned) | on hold | jamal mebane | m.j. vaidya | support functions: global it - infrastructure / service desk | it | medium | not specified | 2024-10-03 | 2025-12-05 | 2025-11-09
71008 | v2 in-house strutting | l3 (planned) | on hold | ty pearsall | tim andren | na - windows: manufacturing - premium & components | it | small | not specified | 2025-03-01 | 2025-03-31 | 2025-06-28
71426 | joseph schedule downloads | l1 (identified) | on track | not specified | dan marlar | na - windows: manufacturing - premium & components | it; engineering | not specified | not specified
71427 | kent schedule downloads | l1 (identified) | on track | not specified | kris anderson | na - windows: manufacturing - premium & components | it; engineering | not specified | not specified
71784 | tis replacement with sap treasury module | l1 (identified) | on track | not specified | tabitha molatore | support functions: finance | it | not specified | 0.21000000000000002 | 2024-10-17 | 2024-11-30
71897 | [st.apollinaire]convert 8500 igus from cardinal to united-budget 2025 | l0 (idea) | on hold | not specified | francois turcotte | na - windows: manufacturing - canada | it | not specified | not specified
71914 | [st.apollinaire] buy triple igu's from united windows - budget 2025 | l0 (idea) | on track | not specified | stephane berthiaume | na - windows: manufacturing - canada | it | not specified | not specified
71945 | fr : new laminated range 2025 | l1 (identified) | on track | not specified | damien kovac | france: commercial | it | not specified | not specified
71958 | frame range : pin lca | l0 (idea) | on track | not specified | damien kovac | france: commercial | it | not specified | not specified
72067 | entra id implementation | l1 (identified) | on track | not specified | jeff stetson | support functions: global it - north america | it | not specified | not specified
72170 | implement new build to stock order process (garland autoline enabler) | l2 (validated) | on track | not specified | nikki smith | na - doors & dist.: manufacturing - south central | it | not specified | not specified |  |  | 2025-04-04
72285 | develop and implement a warranty parts tracking system | l1 (identified) | on track | not specified | dave miller | na - ops: customer service | it | not specified | not specified
72394 | vpi door line labor & warranty reduction through automation phase 1 | l1 (identified) | on track | ty pearsall | pat cozza | na - windows: manufacturing - vinyl & vpi | it | medium | 0.046 | 2025-08-31 | 2026-05-31 | 2026-05-31
72462 | customer service online (track & trace) | l1 (identified) | on track | emmanuel vaghi | celine mesureur | france: commercial | it | small | not specified |  |  | 2026-09-01
72624 | eoffer full order entry system | l1 (identified) | on hold | not specified | martin ott | dach: commercial - germany | it | not specified | not specified
72626 | as/400 roadmap | l1 (identified) | on track | not specified | markus ellinger | support functions: global it - europe | it | not specified | not specified
72664 | **quoting modernization -jw window & doors cpq, pim and ordering system | l2 (validated) | on hold | amy phillips | marshal livingstone | na - doors & dist: commercial - sales | it; engineering | large | not specified | 2024-09-01 | 2025-03-31 | 2025-10-17
72724 | eu basware deployment - current sap cfin locations | submitted for l1 approval | on track | not specified | anne carter | support functions: finance | it | not specified | not specified
73237 | abs seattle kval 990 prehang line | l1 (identified) | on track | not specified | greg leffers | na - doors & dist.: manufacturing - west | engineering; legal; it | not specified | not specified
73240 | **refresh warranty fail codes - enabler | l3 (planned) | on track | sheri schrier | ben brunworth | na - ops: customer service | it | medium | not specified | 2025-03-22 | 2025-04-30 | 2025-06-01
73737 | agile transformation - global it | l1 (identified) | on track | tamara johnson | jorge eleta gomez de segura | support functions: global it - north america | it | large | 0.06
73984 | "costco door" | l0 (idea) | on hold | not specified | matt goodman | na - doors & dist: commercial - product & pricing | engineering; it | not specified | not specified
74068 | price modernization - jw doors & windows | l1 (identified) | on track | not specified | brent schauf | na - doors & dist: commercial - product & pricing | it | not specified | 0.87 |  |  | 2026-05-23
74126 | it site support model standardization | submitted for l2 approval | on track | cyndi maples | gordon greenland | support functions: global it - infrastructure / service desk | it | medium | 0.20217000000000002 | 2025-01-23 | 2025-09-11 | 2025-09-24
74156 | global it contracts cost reduction opportunities (2025 initiatives) | l1 (identified) | on hold | not specified | byron bunte | support functions: global it - north america | it | not specified | not specified | 2025-01-28 | 2025-02-28 | 2025-12-31
74160 | direct set v2 | l1 (identified) | on track | not specified | chase clark | na - windows: commercial - product & pricing | engineering; it | not specified | not specified
74162 | <enabler> digital sales efficiencies and effectiveness enablement of traditional and retail sales | submitted for l2 approval | on track | not specified | daniel howes | na - doors & dist: commercial - sales | it | large | not specified |  |  | 2025-12-31
74211 | <enabler> shiloh platform (retail sales pos analytics) replacement | l3 (planned) | on track | awaiting it pm appointment | keri grandelli | na - doors & dist: commercial - sales | it | medium | 0.26132 | 2025-08-01 | 2025-08-15 | 2025-12-01
74255 | booking system campus oettingen (sales calendar - oettingen, training/seminars, events etc) ¦ enabler | l0 (idea) | on track | not specified | carsten westermann | dach: commercial - germany | it | not specified | not specified
74550 | **traditional credit self-service | l3 (planned) | on track | sheri schrier | andrew hoel | na - ops: customer service | it | medium | not specified | 2025-04-01 | 2025-04-15 | 2025-07-15
74551 | warranty ai functionality | l1 (identified) | on track | not specified | andrew hoel | na - ops: customer service | it | not specified | not specified
74554 | salesforce plant training--enabler project empower with salesforce | submitted for l4 approval | on track | sheri schrier | nancy poradish | na - ops: customer service | it | small | not specified | 2025-02-24 | 2025-03-24 | 2025-05-30
74987 | <enabler> customer single source of truth | l2 (validated) | on track | awaiting it pm appointment | daniel howes | na - doors & dist: commercial - sales | it | medium | not specified |  |  | 2026-04-01
74997 | lowe's rithum integration | l0 (idea) | on track | mike crawford (brm) | nick seagers | na - doors & dist: commercial - sales | it | not specified | not specified
75057 | [lcd] lacantina: ddmrp app integration | l3 (planned) | on track | ty pearsall | michael chickene | na - ops: supply chain | it | small | 0.0 | 2025-04-15 | 2025-06-28 | 2025-10-31
75262 | evaluate line item detail on incoming edi | l1 (identified) | on track | mike crawford (brm) | nick seagers | support functions: global it - north america | it | not specified | not specified
75263 | project aspen - chiloquin | l3 (planned) | on track | fabio rivera | erin berardi | na - bridge project | it; hr; legal; engineering | medium | not specified | 2025-06-02 | 2025-06-30 | 2025-06-30
75265 | **{enabler}-supply chain planning technology | l3 (planned) | on track | chris long | steve cooney | na - ops: supply chain | it | medium | 0.534878 | 2025-09-05 | 2025-11-06 | 2025-11-20
75313 | **m52 - lacantina geo expansion | l1 (identified) | on track | awaiting it pm appointment | charles clare | na - doors & dist: commercial - sales | it | medium | not specified |  |  | 2025-12-31
75577 | demand driven production scheduling | l1 (identified) | on track | christian suarez | erin dawson | na - ops: supply chain | it | large | not specified
75708 | fix the broken stock vs specials edi flag | l1 (identified) | on track | not specified | nikki smith | na - ops: supply chain | it | not specified | not specified
75728 | <enabler> sales enablement pod 2h 2025 - foundational crm fixes + analytics enhancements | l2 (validated) | on track | awaiting it pm appointment | daniel howes | na - doors & dist: commercial - sales | it | medium | 0.2 |  |  | 2025-12-31
75733 | <enabler> sales optimization- enterprise territory management & maps | submitted for l3 approval | on track | awaiting it pm appointment | daniel howes | na - windows: commercial - sales | it | medium | 0.4 | 2025-10-01 | 2026-01-01 | 2026-09-30
75742 | <enabler> sales enablement - full jw expansion (abs, mmi, lacantina) | l1 (identified) | on track | not specified | daniel howes | na - doors & dist: commercial - sales | it | not specified | not specified
75778 | eu timekeeping phase iii | l0 (idea) | on track | not specified | sharon delooze | support functions: hr | it; hr | not specified | not specified
75834 | inventory control 2.0 | l3 (planned) | on track | chris long | emily cochrane | na - ops: supply chain | it | medium | 0.850941 | 2025-07-16 | 2026-05-01 | 2027-03-31
75881 | eu - it - sga savings '25 | l1 (identified) | on track | not specified | ben bridgewater | support functions: global it - europe | it | not specified | not specified |  |  | 2025-12-22
76000 | enabler - wms implementation - west distribution - project hydra | l2 (validated) | on track | christian suarez | justin wilcox | na - ops: supply chain | it | medium | 0.23048 | 2025-09-03 | 2025-10-22 | 2025-12-10
76216 | enabler: supply data & analytics improvements | l3 (planned) | on track | chris long | emily cochrane | na - ops: s&op | it | small | 0.184176 | 2025-09-13 | 2025-11-24 | 2025-12-29
76335 | cms upgrade | submitted for l1 approval | on track | not specified | michael larsen | europe: commercial rationalisation | it | not specified | not specified | 2025-11-03 | 2025-11-28
76385 | improve forecast accuracy | l0 (idea) | on track | not specified | abbey bissell | na – ops: delivery & materials | it | not specified | not specified